## Sheet1
APN_ROW Segment | Street # | Street Name | County | Structural Status | Debris Crew | Location in smartsheets | APN Status | Soil Sample | Date Collected | 1st Lab sample received-lab | Soil Sample Results | Recs Notes | Current Sample Event | ExpectedResultsDate | Soil Samples Approved | Soil_Sample Date checks-M | Soil Boring | Boring 1st result received-lab | Soil Boring Results | Soil_Boring Date checks-M | Soil Re-scrape | rescrape 1st recived-lab | Re-scrape Results | Soil_Rescrape Date checks-M | Soil Re-scrape 2 | 2nd rescrape-lab | Re-scrape 2 Results | Soil_Rescrape2 Date checks-M | Soil Rescrape 3 | 3rd rescrape-lab | Re-scrape 3 Results | Soil_Rescrape3 Date checks-M | Field Notes | Tt Recommendation | State Recommendation | State Recommendation | State Rec Details | State Rec Details | DTSC Mercury Site | State Rec Details | State Rec Details | State Rec Date | QC State Recs | Division
110-260-011 | 1805 | 1805 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
001-362-001 | 29723 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Samples Shipped | 2022-04-02 | 05/19/2022 | 2022-04-08 | Re-scrape |  | Rescrape 2 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Re-scrape | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-051-009 | 334 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/25/2022 | 2022-03-07 | Approved | SBs at 110-051-005 (0.06 miles) have lead up to 97 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | 110-051-009 (334 Highway 89) had a foundation left that was not supposed to be and debris had to return to remove it, this changed the size of the structure and now 5 samples are required. The original samples A1-A3 should be replaced the new A1-A5. samples shipped 2/25/22 | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 | ["Soil Passes"] | Northern Division
002-330-003 | 14121 | Highway 70 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-20 | 04/20/2022 | 2022-04-28 | Approved |  | Confirmation |  | 2022-04-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
002-350-001 | 16920 | State Highway 70 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-23 | 05/17/2022 | 2022-03-31 | Approved | Onsite SBs have cobalt up to 48 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Rescrape successful for lead. | Rescrape 2 |  | 2022-05-26 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 |  | Match | 2022-05-17 | 2022-05-25 |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
002-420-002 | 25313 | Highway 70 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-25 | 03/25/2022 | 2022-04-04 | Approved |  | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
002-430-011 | 26520 | Highway 70 | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-080-002 | 32932 | Highway 70 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 03/29/2022 | 2022-03-18 | Soil Boring | Onsite SBs have arsenic up to 140 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-08 | Match | 2022-03-29 | 2022-04-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
005-090-004 | 34076 | Highway 70 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-16 | 03/16/2022 | 2022-03-24 | Approved |  | Confirmation |  | 2022-03-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/25/2022 | ["Soil Passes"] | Northern Division
110-081-012 | 640 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-081-013 | 642 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-081-014 | 644 | Main Street | Plumas | Ready for Final Sign-off | Tree Only Parcels | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
110-082-016 | 645 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 04/12/2022 | 2022-02-08 | Re-scrape | Greenville Zone X FSO SBs at 110-082-001 (375 feet) have lead up to 190 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Rescrape for those higher. | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR Limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
005-041-012 | 260 | Darmer Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 02/16/2022 | 2022-02-03 | Re-scrape |  | Rescrape 1 |  | 2022-02-25 | Match |  |  |  | Match | 2022-02-16 | 2022-02-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
005-041-013 | 314 | Darmer Avenue | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 02/16/2022 | 2022-02-03 | Re-scrape |  | Rescrape 1 |  | 2022-02-25 | Match |  |  |  | Match | 2022-02-16 | 2022-02-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
110-300-034 | 371 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 12/03/2021 | 2021-11-12 | Re-scrape |  | Rescrape 2 |  | 2021-12-14 | Match |  |  |  | Match | 2021-11-17 | 2021-11-24 | Re-scrape | Match | 2021-12-03 | 2021-12-13 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
110-300-036 | 381 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-300-039 | 391 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 02/21/2022 | 2022-03-01 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | road blocked off by tree crew 1/27/22 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
145-040-002 | 10348 | Dixie Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-130-020 | 12922 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-140-002 | 12932 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
110-064-012 | 140 | Church Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 11/20/2021 | 2021-11-30 | Approved | Greenville Zone X Soil borings on adjacent 110-064-018 (60 feet) have lead up to 230 mg/kg. A PPDR limit of 230 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 230 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
005-010-011 | 10100 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/04/2022 | 2022-03-14 | Approved | Onsite SBs have lead up to 180 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
005-020-024 | 11063 | Highway 89 | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
111-160-005 | 14425 | Highway 89 | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-031-002 | 115 | Lake Almanor West Drive | Plumas | Final Sign Off Complete | Ready for FSO | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-031-003 | 117 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-031-004 | 119 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-042-002 | 124 | Lake Almanor West Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-051-003 | 135 | Lake Almanor West Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-051-005 | 139 | Lake Almanor West Drive | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-212-006 | 368 | Lake Almanor West Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
129-372-040 | 459-625 | Lake View Drive | Lassen | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-230-033 | 3547 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 03/21/2022 | 2022-03-08 | Re-scrape |  | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-21 | 2022-03-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
004-330-016 | 5284 | Diamond Mountain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-330-019 | 5284 | Diamond Mountain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-330-020 | 5460 | Lights Creek Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 03/22/2022 | 2022-03-30 | Approved |  | Confirmation |  | 2022-03-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
012-320-003 | 439 | Lilac Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-21 | 12/21/2021 | 2021-12-30 | Approved |  | Confirmation |  | 2022-01-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/03/2022 | ["Soil Passes"] | Northern Division
004-050-029 | 478 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 02/15/2022 | 2022-02-23 | Approved |  | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
004-270-009 | 549 | Williams Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 02/28/2022 | 2022-02-22 | Re-scrape | SBs at 004-270-013 (0.10mi) have arsenic up to 11 mg/kg indicating concentrations at or below the value are likely background or ambient conditions. An error in reporting indicated the highest SB was 9.1 mg/kg, so that B2 would have originally passed. The 12 mg/kg identified during the rescrape is most likely background given the sample prior to rescrape was 9.9 mg/kg and elevated arsenic within the area as supported by nearby onsite SBs. C2 was identified for rescrape due to elevated zinc, as possible indicator of ash. | Rescrape 1 |  | 2022-03-10 | Match |  |  |  | Match | 2022-02-28 | 2022-03-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
011-210-013 | 7117 | Rim Drive | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
012-290-050 | 1388 | Soldier Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/29/2022 | 2022-03-22 | Soil Boring | Onsite SBs have arsenic up to 82 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-08 | Match | 2022-03-29 | 2022-04-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
110-220-044 | 7 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/25/2022 | 2022-03-07 | Approved | SBs from 110-190-004 (0.07 miles) have arsenic up to 480 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
110-352-006 | 150 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
110-352-007 | 152 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 12/02/2021 | 2021-11-29 | Re-scrape |  | Rescrape 1 |  | 2021-12-13 | Match |  |  |  | Match | 2021-12-02 | 2021-12-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
110-352-008 | 154 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
002-480-006 | 6900 | Butterfly Valley-Twain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-210-003 | 32 | Calais Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/25/2022 | 2022-03-07 | Approved | SBs at 110-190-025 (0.12 miles) have arsenic up to 240 mg/kg and mercury up to 3.2 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
110-210-004 | 102 | Calais Drive | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 04/13/2022 | 2022-04-01 | Approved | Greenville Zone X, but also widespread elevated arsenic and mercury. Onsite soil borings have lead up to 3,500 mg/kg, arsenic up to 240 mg/kg, and mercury up to 4.1 mg/kg, supporting all concentrations lower likely represent ambient, legacy, or background conditions. The PPDR limit, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 3,500 mg/kg. | Soil Boring 1 |  | 2022-04-22 | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
110-210-005 | 103 | Calais Drive | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-26 | 04/25/2022 | 2022-04-01 | Re-scrape | Greenville Zone X Nearby soil borings at adjacent 110-210-004 (200 feet) have lead at 120 mg/kg, arsenic at 150 mg/kg, and mercury at 1.7 mg/kg. PPDR limits for each of these metals are proposed accordingly for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentrations likely represent ambient, background, or legacy conditions and not related to the Dixie Fire. Successful rescrape for cadmium. | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
110-210-007 | 105 | Calais Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 04/28/2022 | 2022-03-29 | Re-scrape | SBs at 110-190-025 (0.13 miles) have arsenic up to 240 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Rescrape for lead successful. | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
110-210-008 | 110 | Calais Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 03/21/2022 | 2022-03-29 | Approved | SBs at 110-190-025 (0.19 miles) have arsenic up to 240 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
110-072-006 | 551 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved | Greenville Zone X Soil borings at nearby 110-072-008 (100 feet) have lead up to 170 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 170 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-081-026 | 552 | Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-081-027 | 624 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 01/24/2022 | 2022-02-01 | Approved |  | Confirmation |  | 2022-02-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/03/2022 | ["Soil Passes"] | Northern Division
011-180-013 | 11504 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-281-003 | 7246 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-282-004 | 7265 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-120-004 | 37453 | 28N01 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-31 | Approved |  | Confirmation | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
007-130-006 | 417 | Rain Drop Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-31 | Approved |  | Confirmation | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
007-140-011 | 606 | Rain Drop Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-180-014 | 11484 | Chester Warner Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-281-004 | 7236 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
011-282-003 | 7245 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-061-013 | 204 | Main Street | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-19 | 05/19/2022 | 2022-05-27 | Approved |  | Confirmation | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-120-049 | 207 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 05/03/2022 | 2022-02-18 | Soil Boring | Greenville Zone X In addition to widespread lead, there are also multiple exceedances for arsenic and mercury in the confirmation samples, indicating these constituents may not be fire debris related. PPDR limit will likely be set at 220 mg/kg based on 110-110-001 (400 ft). Onsite SBs have arsenic up to 150 mg/kg and mercury up to 17 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Rescrape successful for single lead exceedance. | Rescrape 1 |  | 2022-05-12 | Match | 2022-04-20 | 2022-04-28 | Re-scrape | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
110-016-005 | 408 | Second Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 03/07/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-17 | Match |  |  |  | Match | 2022-03-07 | 2022-03-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/17/2022 | ["Soil Passes"] | Northern Division
004-230-017 | 5790 | North Arm Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 04/06/2022 | 2022-03-29 | Soil Boring | NOTE: consider rescraping B1 for lead given few exceedances. Onsite SBs have arsenic at 210 mg/kg and lead at 360 mg/kg, supporting all concentrations lower likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-14 | Match | 2022-04-06 | 2022-04-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes regarding lead. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
004-330-013 | 6260 | North Arm Road | Plumas | Ready for Erosion Control | Erosion Control - Haz Tree | Soil Samples Approved | Samples Shipped | 2022-03-18 | 05/20/2022 | 2022-05-09 | Re-scrape |  | Rescrape 1 | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match | 2022-05-20 | 2022-05-31 | Approved | Match |  |  |  | Match |  |  |  | Match | samples amended for other part of parcel that was included per state rep 04/29/22 | [5 empty] | No |  |  |  |  | Northern Division
110-300-003 | 395 | North Highway 89 | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 04/13/2022 | 2022-03-01 | Re-scrape | Onsite SBs have elevated arsenic, lead, and mercury, rescrapes not necessary. | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-13 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-180-012 | 185 | Spirit Springs | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
110-352-035 | 142 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 02/28/2022 | 2022-03-08 | Approved |  | Confirmation |  | 2022-03-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
108-300-024 | 248 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
145-010-005 | 10666 | Dixie Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-04 | 05/04/2022 | 2022-05-12 | Approved |  | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
145-020-003 | 10717 | Dixie Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-26 | 04/26/2022 | 2022-05-03 | Approved |  | Confirmation |  | 2022-05-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
011-210-007 | 7405 | Rim Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/13/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-210-020 | 7416 | Rim Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 11/15/2021 | 2021-11-23 | Approved |  | Confirmation |  | 2021-11-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/24/2021 | ["Soil Passes"] | Northern Division
019-470-460 | 019-470-460 | No address (Hate Mtn. Road) | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 04/08/2022 | 2022-04-18 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
019-690-050 | 019-690-050 | No Address (Ridge Lane) | Siskiyou | Ready for Final Sign-off | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-31 | 05/16/2022 | 2022-04-08 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-16 | 2022-05-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
111-010-005 | 18295 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-03-16 | 05/18/2022 | 2022-03-24 | Re-scrape |  | Rescrape 2 | 05/26/2022 | 2022-05-27 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Re-scrape | Match | 2022-05-18 | 2022-05-26 | Approved | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-154-006 | 434-960 | Third Street | Lassen | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
008-160-004 | 90 | Beckwourth Genesee Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-160-017 | 702 | Beckwourth Genesee Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-160-023 | 2184 | Beckwourth Genesee Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-160-014 | 9700 | Beckwourth Genesee Road | Plumas | No Asbestos Detected | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-360-015 | 745-625 | Doyle Grade Road | Lassen | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
141-360-042 | 745-905 | Doyle Grade Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 02/18/2022 | 2022-02-04 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-18 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
001-160-041 | 1700 | 28N77 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-29 | 03/25/2022 | 2021-12-07 | Re-scrape |  | Rescrape 1 |  | 2022-04-05 | Match |  |  |  | Match | 2022-03-25 | 2022-04-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
011-060-018 | 370 | 29N38 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-07 | 05/07/2022 | 2022-05-13 | Approved |  | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
110-019-001 | 314 | 2nd Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 04/27/2022 | 2021-11-24 | Re-scrape |  | Rescrape 1 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
002-090-015 | 3023 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-016 | 3145 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-020-011 | 920 | 26N24 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-680-010 | 13523 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
002-360-004 | 18550, 18500 | Rich Bar Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Re-scrape Results Rec'd from Lab | HOLD Other | 2022-02-03 | 05/23/2022 | 2022-02-09 | Re-scrape | BKG samples at 002-360-003 have cobalt up to 112 mg/kg and lead at 450 mg/kg, supporting concentrations below likely represent ambient or background conditions. Rescrape recommended for elevated lead at K1. J1 successfully rescraped by DTSC: Antimony: 3.2 mg/kg Lead: 19 mg/kg Mercury: 0.23 mg/kg | Rescrape 1 | 05/31/2022 |  | Match |  |  |  | Match | 2022-05-23 | 2022-06-01 |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
019-670-580 | 13178 | Ridge Lane | Siskiyou | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 05/16/2022 | 2022-04-11 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-16 | 2022-05-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
110-370-005 | 18791 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 03/24/2022 | 2022-04-01 | Approved |  | Confirmation |  | 2022-04-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
007-200-005 | 6800 | Fords Wagon Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-11 | 01/11/2022 | 2022-01-19 | Approved |  | Confirmation |  | 2022-01-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/20/2022 | ["Soil Passes"] | Northern Division
009-460-004 | 424 | Forest Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-230-010 | 236 | Forest Lodge Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 03/09/2022 | 2022-03-07 | Re-scrape |  | Rescrape 1 |  | 2022-03-18 | Match |  |  |  | Match | 2022-03-09 | 2022-03-17 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
145-040-003 | 10316 | Dixie Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-019 | 2062 | Carmen Road | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Boring Results | Ready for Sampling | 2022-05-05 |  | 2022-05-13 | Soil Boring |  | Rescrape 1 |  |  | Match | 2022-05-17 | 2022-05-25 | Re-scrape | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-252-005 | 6954 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-253-001 | 6959 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-24 | 11/24/2021 | 2021-12-06 | Approved |  | Confirmation |  | 2021-12-07 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/07/2021 | ["Soil Passes"] | Northern Division
110-071-005 | 520 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-01 | 12/01/2021 | 2021-12-09 | Approved | Greenville Zone X Soil borings at 110-072-014 (275 feet) have lead up to 370 mg/kg. While onsite soil borings do not have elevated lead results, the widespread pattern of lead in the confirmation samples suggests that concentrations less than 370 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-071-006 | 522 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-01 | 04/13/2022 | 2022-03-09 | Re-scrape | Greenville Zone X Soil borings at nearby 110-072-014 (120 feet) have lead up to 370 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 370 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape for cadmium. | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR Limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
110-071-007 | 528 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2021-11-19 |  | 2021-12-01 | Re-scrape | Greenville Zone X Soil borings at nearby 110-072-014 (150 feet) have lead up to 370 mg/kg. While onsite soil borings do not have elevated lead results, the widespread pattern of lead in the confirmation samples suggests that concentrations less than 370 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 370 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Revised recommendations per CalOES direction. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-072-014 | 529 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-10-30 | 11/18/2021 | 2021-11-05 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead up to 370 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 370 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 370 mg/kg is proposed for the subject APN based on onsite background boring results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for elevated lead. | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2021-11-18 | 2021-11-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-081-020 | 660 | Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-082-010 | 675 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 02/08/2022 | 2022-01-27 | Re-scrape |  | Rescrape 1 |  | 2022-02-17 | Match |  |  |  | Match | 2022-02-08 | 2022-02-16 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
110-082-013 | 687 | Main Street | Plumas | Returned to County | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved | SBs at 110-082-002 (0.17 miles) have lead up to 150 mg/kg, supporting onsite concentrations likely represent background or ambient conditions. Previously recommended for Soil Passes, changed due to updated Greenville Zone X evaluation. This was overcome by events as the APN was returned to County. | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
110-090-014 | 691 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 01/19/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-01-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/29/2022 | ["Soil Passes"] | Northern Division
110-090-015 | 701 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
008-130-001 | 5411 | Genesee Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-130-009 | 5589 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-130-036 | 5673 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-350-034 | 6049 | Genesee Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-001 | 102 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-018 | 106 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-023-014 | 301 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 12/04/2021 | 2021-12-13 | Approved |  | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
110-023-015 | 305 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
110-072-008 | 541 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/07/2022 | 2022-02-15 | Approved | Greenville Zone X Onsite soil borings have elevated lead results to 170 mg/kg; however, soil borings at 110-072-014 (160 feet) have lead up to 370 mg/kg. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 370 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 370 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
008-290-001 | 7926 | Frenchman Boulevard | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
008-290-002 | 8056 | Frenchman Boulevard | Plumas | Pending Soil Sample Results | Pending Soils Results | Re-scrape Results Rec'd from Lab | Samples Shipped | 2022-04-06 | 05/23/2022 | 2022-04-14 | Re-scrape | No nearby SBs | Rescrape 1 | 05/31/2022 |  | Match |  |  |  | Match | 2022-05-23 | 2022-06-01 |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-300-005 | 525 | Pioneer Way | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/06/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
110-010-003 | 321 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-10-30 | 10/30/2021 | 2021-11-05 | Approved | Arsenic is only metal which exceeds health screening levels. The estimated background concentration for arsenic is 27 mg/kg, based on the existing 105 samples. Results from six samples were removed as outliers and are not included in the calculations with results of 250, 220, 210, 120, 57, and 47 mg/kg from two locations. DFP-110-171-003-BKG-038 and DFP-110-172-010-BKG-039. | Confirmation |  | 2021-11-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/08/2021 | ["Soil Passes"] | Northern Division
110-018-001 | 328 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 02/14/2022 | 2022-02-22 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-292-003 | 479 | Greenacre Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 03/03/2022 | 2022-03-11 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-292-007 | No Address (411) | Greenacre Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-070-003 | 9385 | Highway 89 | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2022-03-23 |  | 2022-03-31 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-500-002 | 9806 | Highway 89 | Plumas | Re-scrape Needed | DTSC Hold | Soil Sample Results | Ready for Sampling | 2022-03-31 |  | 2022-04-08 | Re-scrape | Refer A1 to DTSC for elevated mercury. All other rescrapes for arsenic to be conducted by BOP. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
108-071-011 | 121 | Kokane Trail | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-132-011 | 314 | Hamblin Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 04/07/2022 | 2022-02-21 | Re-scrape | Former Zone X Hold. Rescrape recommended because lead exceedances are not widespread. | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-07 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
004-240-003 | 5910 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-250-002 | 5676 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-382-018 | 11 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 02/17/2022 | 2022-01-31 | Re-scrape |  | Rescrape 1 |  | 2022-02-25 | Match |  |  |  | Match | 2022-02-17 | 2022-02-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
011-180-012 | 11518 | Chester Warner Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Samples Shipped | 2021-11-13 | 05/24/2022 | 2021-11-19 | Re-scrape |  | Rescrape 1 | 06/01/2022 |  | Match |  |  |  | Match | 2022-05-24 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-120-019 | 301 | Crescent Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 | ["Soil Passes"] | Northern Division
110-132-044 | 304 | Crescent Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 04/20/2022 | 2021-12-15 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated lead; however, soil borings at 110-131-023 (190 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-04-29 | Match | 2022-03-25 | 2022-04-04 |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
004-240-004 | 5878 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Working with Frank Gutham and Taylor to fix SSF and determine where trees need to be moved for soil sampling to take place. Tree issue resolved 2/23/22 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
145-050-003 | 10003 | Dixie Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 12/10/2021 | 2021-12-20 | Approved |  | Confirmation |  | 2021-12-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/21/2021 | ["Soil Passes"] | Northern Division
145-050-006 | 10008 | Dixie Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-300-011 | 111 | Gretna Green | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/06/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
110-132-012 | 310 | Hamblin Avenue | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/25/2022 | 2022-03-07 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
110-016-004 | 410 | Second Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/02/2022 | 2022-03-09 | Approved |  | Confirmation |  | 2022-03-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
141-154-010 | 434-805 | Second Street | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-19 | 03/31/2022 | 2022-03-25 | Re-scrape | Nearby APNs cleared for arsenic | Rescrape 1 |  | 2022-04-11 | Match |  |  |  | Match | 2022-03-31 | 2022-04-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
011-030-001 | 376 | 30N36 | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-27 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-062-038 | 121 | Ann Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-190-029 | 87 | South Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-200-002 | 75 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 03/15/2022 | 2022-03-07 | Re-scrape | SBs at 110-200-007 (0.1 miles) have arsenic up to 250 mg/kg and mercury up to 5.5 mg/kg, supporting that all onsite concentrations likely represent ambient or background conditions. Successful rescrape for cadmium | Rescrape 1 |  | 2022-03-24 | Match |  |  |  | Match | 2022-03-15 | 2022-03-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
110-200-011 | 85 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved | SBs from 110-190-025 (0.07 miles) have arsenic up to 240 mg/kg and mercury up to 3.2 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-370-001 | 19098 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 03/03/2022 | 2022-01-31 | Re-scrape |  | Rescrape 2 |  | 2022-03-15 | Match |  |  |  | Match | 2022-02-19 | 2022-02-25 | Re-scrape | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-380-017 | 19217 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 04/13/2022 | 2022-03-22 | Re-scrape |  | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
011-222-008 | 7404 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/20/2021 | 2021-11-12 | Re-scrape |  | Rescrape 1 |  | 2021-12-01 | Match |  |  |  | Match | 2021-11-20 | 2021-11-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
011-290-002 | 11164 | Chester Warner Valley Road | Plumas | ROE Received | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-320-001 | 5815 | Hyampom Road | Trinity | Re-scrape Needed | Outer County Rescrape Crew #1 | Soil Sample Results | Samples Shipped | 2022-05-19 | 05/19/2022 | 2022-05-27 | Re-scrape |  | Confirmation | 05/27/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-001 | Tract 37 | Juniper Lake | Lassen | Asbestos Abatement Needed | Crew # 107 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-004 | Lot 28 & 29, Block 67 | Juniper Lake Resort | Lassen | Asbestos Abatement Complete | Crew # 107 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-010 | Tract 41 | Juniper Lake Resort | Lassen | No Asbestos Detected | Access Issues |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-011 | Tract 41 | Juniper Lake Resort | Lassen | Chimney Tip Needed | Access Issues |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-012 | Tract 41 | Juniper Lake Resort | Lassen | No Asbestos Detected | Access Issues |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
109-130-070 | 7609 | Juniper Valley Circle | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-28 | 01/28/2022 | 2022-02-07 | Approved |  | Confirmation |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
110-040-021 | 201 | Kinder Avenue | Plumas | Ready for Soil Sampling | Crew #800 (CAL HAZ LOAD OUT) |  | Ready for Sampling | [5 empty] | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-032-002 | 240 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-10-30 | 12/01/2021 | 2021-11-05 | Re-scrape |  | Rescrape 2 |  | 2021-12-10 | Match |  |  |  | Match | 2021-11-17 | 2021-11-29 | Re-scrape | Match | 2021-12-01 | 2021-12-09 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/10/2021 | ["Soil Passes"] | Northern Division
110-032-029 | 227 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-18 | 12/02/2021 | 2021-11-30 | Re-scrape |  | Rescrape 1 |  | 2021-12-13 | Match |  |  |  | Match | 2021-12-02 | 2021-12-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
110-033-001 | 232 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-230-003 | 240 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-10-29 | 10/29/2021 | 2021-11-04 | Approved | Arsenic and cobalt are the only metals which exceeds health screening levels. The estimated background concentration for arsenic is 27 mg/kg, based on the existing 105 samples. Results from six samples were removed as outliers and are not included in the calculations with results of 250, 220, 210, 120, 57, and 47 mg/kg from two locations. DFP-110-171-003-BKG-038 and DFP-110-172-010-BKG-039. The estimated cobalt background concentration is 30 mg/kg and additional sample results will not likely lower the cobalt level. | Confirmation |  | 2021-11-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/09/2021 | ["Soil Passes"] | Northern Division
001-362-005 | 29581 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 05/02/2022 | 2022-04-07 | Re-scrape |  | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
011-150-008 | 12592 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-241-006 | 7099 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-243-005 | 7076 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 11/17/2021 | 2021-11-29 | Approved |  | Confirmation |  | 2021-11-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/30/2021 | ["Soil Passes"] | Northern Division
011-242-007 | 7091 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/12/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-243-003 | 7106 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-243-002 | 7120 | Harkness Drive | Plumas | Ready for Tree Operations | Tree Only Parcels | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 11/17/2021 | 2021-11-29 | Approved |  | Confirmation |  | 2021-11-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/30/2021 | ["Soil Passes"] | Northern Division
011-270-005 | 4045 | Section Old Red Bluff Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-26 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
016-160-063 | 401 | Drinkwater Ranch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 04/08/2022 | 2022-02-28 | Soil Boring | Onsite SBs have cobalt up to 63 mg/kg and vanadium up to 510 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrapes for other exceedances. | Rescrape 1 |  | 2022-04-21 | Match | 2022-03-10 | 2022-03-18 | Re-scrape | Match | 2022-04-08 | 2022-04-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-016-003 | 412 | 2nd Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved | SBs at 110-019-006 (0.09 miles) have lead up to 200 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
007-190-019 | 7100 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-190-011 | 434-100 | Diamond Mountain Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes","Soil Passes"] | ["Soil Passes","Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes","Soil Passes"] | Northern Division
004-060-020 | 510 | Red Knoll Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/24/2022 | 2022-03-14 | Re-scrape |  | Rescrape 1 |  | 2022-04-04 | Match |  |  |  | Match | 2022-03-24 | 2022-04-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
004-060-027 | 550 | Red Knoll Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/04/2022 | 2022-03-14 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
012-300-001 | 130 | Berry Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-21 |  | 2021-12-30 | Re-scrape | A2-R3 conducted by DTSC for mercury. No other exceedances. Confirmation result for mercury at A2-R3 is 0.017 mg/kg. | Rescrape 3 |  | 2022-04-08 | Match |  |  |  | Match | 2022-01-14 | 2022-01-24 | Re-scrape | Match | 2022-02-04 | 2022-02-11 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | Yes |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
110-062-008 | 120 | Bidwell Avenue | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-015 | 116 | Bidwell Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 05/04/2022 | 2022-02-11 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 190 mg/kg. A PPDR limit of 190 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-16 | Match |  |  |  | Match | 2022-05-04 | 2022-05-12 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
110-062-030 | 125 | Bidwell Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 | 05/13/2022 | 2021-12-17 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 160 mg/kg. A PPDR limit of 160 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 2 |  | 2022-05-25 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-25 | 2022-05-04 | Re-scrape | Match | 2022-05-13 | 2022-05-23 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/25/2022 | ["Soil Passes"] | Northern Division
110-062-031 | 125 | Bidwell Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved |  | Confirmation |  | 2022-02-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/19/2022 | ["Soil Passes"] | Northern Division
011-180-009 | 11586 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 12/07/2021 | 2021-11-18 | Re-scrape |  | Rescrape 1 |  | 2021-12-16 | Match |  |  |  | Match | 2021-12-07 | 2021-12-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/16/2021 | ["Soil Passes"] | Northern Division
110-040-028 | 101 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-161-009 | 146 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
110-162-011 | 147 | Hot Springs Road | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 02/07/2022 | 2021-12-13 | Soil Boring | Onsite SBs have arsenic up to 280 mg/kg, and mercury up to 4 mg/kg, likely represent ambient or background conditions. | Rescrape 1 |  | 2022-02-16 | Match | 2022-01-15 | 2022-01-21 | Re-scrape | Match | 2022-02-07 | 2022-02-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
110-171-017 | 154 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-08 | Approved |  | Confirmation |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
110-172-002 | 155 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 01/17/2022 | 2021-11-23 | Re-scrape | Onsite soil borings have arsenic up to 1300 mg/kg and mercury up to 7 mg/kg. Confirmation soil samples are all lower than soil borings, and thus are likely ambient levels and not related to fire soil debris. | Soil Boring 1 |  | 2022-01-27 | Match | 2022-01-17 | 2022-01-25 | Approved | Match | 2021-12-01 | 2021-12-09 | Soil Boring | Match |  |  |  | Match |  |  |  | Match | 110-190-004 has trees that were placed where an auto burned. Notified state and planning 11/13/21. Planning confirmed asphalt can stay on 11/13. | See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
005-033-001 | 218 | Indian Falls Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 01/13/2022 | 2021-12-16 | Re-scrape | Onsite SBs do not indicate elevated lead | Rescrape 1 |  | 2022-01-26 | Match |  |  |  | Match | 2022-01-13 | 2022-01-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
005-042-006 | 255 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Not Ready for Sampling | 2022-02-03 |  |  | Approved |  |  |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-043-004 | 262 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-016-006 | 406 | Second Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 02/09/2022 | 2021-12-15 | Re-scrape |  | Rescrape 2 |  | 2022-02-19 | Match |  |  |  | Match | 2022-01-25 | 2022-02-03 | Re-scrape | Match | 2022-02-09 | 2022-02-17 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/19/2022 | ["Soil Passes"] | Northern Division
110-017-003 | 407 | Second Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 02/14/2022 | 2022-02-22 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
141-050-048 | 747-525 | Doyle Grade Road | Lassen | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/19/2022 | 2022-02-10 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-19 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
141-220-006 | 434-860 | Doyle Loop | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-28 | 03/28/2022 | 2022-04-05 | Approved |  | Confirmation |  | 2022-04-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/06/2022 | ["Soil Passes"] | Northern Division
110-062-040 | 430 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 04/02/2022 | 2022-02-24 | Re-scrape | Zone X rescrape recommended since lead exceedances are not widespread. Former Zone X Hold | Rescrape 1 |  | 2022-04-13 | Match |  |  |  | Match | 2022-04-02 | 2022-04-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-064-009 | 435 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 04/27/2022 | 2022-02-10 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated lead; however, soil borings on adjacent 110-064-013 (100 feet) have lead up to 630 mg/kg. A PPDR limit of 630 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
110-071-003 | 440 | Main Street | Plumas | Ready for Final Sign-off | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 04/27/2022 | 2022-02-11 | Re-scrape | Greenville Zone X Soil borings at nearby 110-072-014 (375 feet) have elevated lead up to 370 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 2 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Re-scrape | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
110-120-020 | 307 | Crescent Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2022-03-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
110-140-008 | 311 | Crescent Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/23/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2022-03-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
005-035-010 | 290 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 01/27/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
011-252-001 | 7046 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-220-022 | 113 | Round Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/02/2022 | 2022-03-10 | Approved |  | Confirmation |  | 2022-03-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
001-362-027 | 29381 | Highway 89 | Plumas | Re-scrape Needed | DTSC Hold | Soil Sample Results | Updated to Smartsheets | 2021-11-29 |  | 2021-12-07 | Re-scrape | The concentrations at this APN are similar to adjacent 001-362-028, which was identified to have legacy fill. These exceedances could be associated with legacy fill and more information may be available upon DTSC field activities. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
001-362-032 | 29511 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 04/09/2022 | 2022-03-30 | Re-scrape |  | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-09 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
009-330-017 | 3011 | Carmen Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2022-04-27 |  | 2022-05-04 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-24 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-038 | 3390 | Carmen Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-233-002 | 7236 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-037 | 320 | Main Street | Plumas | Re-scrape Needed | DTSC Hold | Soil Sample Results | Ready for Sampling | 2022-03-18 |  | 2022-03-28 | Re-scrape | DTSC Mercury Site Greenville Zone X Nearby soil borings at 110-061-011 (210 feet) have lead up to 250 mg/kg and mercury up to 4.5 mg/kg. A PPDR limit of 250 mg/kg for lead and a PPDR limit of 4.5 for mercury are proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentrations likely represent ambient, background, or legacy conditions. Revised recommendation per CalOES direction. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-063-013 | 325 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 04/26/2022 | 2021-11-30 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 340 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 340 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-05 | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
110-064-020 | 118 | Church Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved | Greenville Zone X Nearby soil borings at 110-131-023 (250 feet) have lead up to 440 mg/kg. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-131-013 | 123 | Church Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-131-020 | 127 | Church Street | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape 2 Results | Ready for Sampling | 2021-11-09 |  | 2021-11-16 | Re-scrape | Greenville Zone X Onsite background soil borings do not have elevated; however, nearby soil borings at 110-064-013 (100 feet) have lead up to 630 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 630 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 3 |  |  | Match |  |  |  | Match | 2021-11-19 | 2021-11-30 | Re-scrape | Match | 2022-04-12 | 2022-04-20 | Re-scrape | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-132-004 | 224 | Grand Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/24/2021 | 2021-11-12 | Re-scrape | Greenville Zone X. Onsite background soil borings do not have elevated lead; however, soil borings at 110-132-026 (80 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2021-11-24 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-292-008 | 411 | Greenacre Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 11/20/2021 | 2021-11-30 | Approved |  | Confirmation |  | 2021-12-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
110-300-007 | 411 | Greenacre Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-034-001 | 205 | Indian Falls Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/17/2022 | 2022-03-10 | Re-scrape |  | Rescrape 1 |  | 2022-03-28 | Match |  |  |  | Match | 2022-03-17 | 2022-03-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
011-241-007 | 7075 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-243-006 | 7060 | Harkness Drive | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
012-320-044 | 149 | Lakewood Drive | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-20 | 12/20/2021 | 2021-12-28 | Approved |  | Confirmation |  | 2022-01-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/03/2022 | ["Soil Passes"] | Northern Division
110-022-003 | 109 | Landon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 11/17/2021 | 2021-11-29 | Approved |  | Confirmation |  | 2021-11-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/30/2021 | ["Soil Passes"] | Northern Division
110-022-004 | 111 | Landon Avenue | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved |  | Confirmation |  | 2022-02-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/19/2022 | ["Soil Passes"] | Northern Division
110-390-005 | 590 | Snowy Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 03/10/2022 | 2022-03-04 | Re-scrape |  | Rescrape 1 |  | 2022-03-21 | Match |  |  |  | Match | 2022-03-10 | 2022-03-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
001-230-009 | 28137 | Highway 89 | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Boring | Ready for Sampling | 2022-05-14 |  | 2022-05-20 | Soil Boring |  | Soil Boring 1 |  |  | Match | 2022-05-25 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-028 | 29331 | Highway 89 | Plumas | Re-scrape Needed | DTSC Hold | Soil Sample Results | Updated to Smartsheets | 2021-11-29 |  | 2021-12-07 | Re-scrape | Field notes indicate legacy fill identified in area. CS results could be legacy fill not readily observable. Reevaluate after first rescrape. A1, A2, A3 referred to DTSC for elevated lead at A3. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Legacy piles on site that were not marked with paint or mentioned in the SUM. Spoke with area lead Katrina and crew will return to mark legacy area. Soils will sample 11/29/21. | [5 empty] | Yes |  |  |  |  | Northern Division
004-050-013 | 399 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 12/04/2021 | 2021-12-13 | Approved |  | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
004-050-031 | 418 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 | 12/09/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
004-050-032 | 438 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 02/15/2022 | 2022-02-23 | Approved |  | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
011-210-010 | 7239 | Rim Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | snow cover 04/12 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
011-210-018 | 7292 | Rim Drive | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-350-026 | 3151 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-350-027 | 3151 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-350-033 | 3151 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-040-015 | 212/214 | Mill Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-23 | 04/20/2022 | 2021-12-03 | Re-scrape | Greenville Zone X Onsite background soil borings do not have exceedances for lead; however, nearby soil borings at 110-051-006 (240 feet) have lead up to 220 mg/kg. A PPDR limit of 220 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Successful rescrape for cadmium. | Rescrape 1 |  | 2022-04-29 | Match |  |  |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
110-061-015 | 113 | Mill Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 04/26/2022 | 2021-12-13 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 300 mg/kg. A PPDR limit of 300 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-05 | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
110-120-010 | 131 | Ayoob Aly | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 03/25/2022 | 2021-12-15 | Approved | Greenville Zone X Onsite soil borings do not have elevated lead; however, nearby background soil borings at 110-120-044 (240 feet) have elevated lead at 270 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 270 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 270 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely present ambient, background, or legacy conditions. | Soil Boring 1 |  | 2022-04-12 | Match | 2022-03-25 | 2022-04-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-120-022 | 139 | Ayoob Aly | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 04/25/2022 | 2022-02-23 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 160 mg/kg; however, nearby background soil borings at 110-063-007 (350 feet) have elevated lead up to 380 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 380 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 380 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentration likely present ambient, background, or legacy conditions. Areas greater than this concentration, in addition to other metals above nearby soil borings, are recommended for rescrapes. | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
001-361-006 | 29524 | Highway 89 | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
001-362-007 | 29535 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-23 | 04/08/2022 | 2022-03-31 | Re-scrape |  | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-08 | 2022-04-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
001-362-023 | 29543 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 03/24/2022 | 2022-04-01 | Approved |  | Confirmation |  | 2022-04-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
002-020-001 | 13375 | Humboldt Road | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
002-050-015 | 8000 | Humbug Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Re-scrape Results Rec'd from Lab | Samples Shipped | 2022-05-07 | 05/23/2022 | 2022-05-13 | Re-scrape |  | Rescrape 1 | 05/31/2022 |  | Match |  |  |  | Match | 2022-05-23 | 2022-06-01 |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-680-030 | 13517 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 04/08/2022 | 2022-02-11 | Re-scrape |  | Rescrape 3 |  | 2022-04-21 | Match |  |  |  | Match | 2022-03-02 | 2022-03-10 | Re-scrape | Match | 2022-03-22 | 2022-03-30 | Re-scrape | Match | 2022-04-08 | 2022-04-18 | Approved | Match | Original field notes indicated 019-580-030, corrected to correct APN of 019-680-030. | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
002-020-002 | 11755 | Humboldt Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-017-005 | 403 | 2nd Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 02/12/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
110-031-012 | 217 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 12/03/2021 | 2021-12-13 | Approved | SBs at 110-051-005 (0.10 miles) have arsenic up to 57 mg/kg, supporting onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
110-032-007 | 220 | Kinder Avenue | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 02/07/2022 | 2021-12-15 | Re-scrape | Greenville Zone X Nearby soil borings at 110-031-017 (280 feet) have lead up to 89 mg/kg. A PPDR limit of 89 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-13 | Match |  |  |  | Match | 2022-02-07 | 2022-02-15 | Approved | Match |  |  |  | Match |  |  |  | Match | APN has part of driveway concrete that needs to be removed. Spoke with Lacey Moore and crew will return Monday (12/6/21) | Soil passes PPDR limit. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
004-050-025 | 358 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-120-005 | 110 | Ayoob Aly | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 03/04/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-120-031 | 117 | Ayoob Aly | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-15 | 04/23/2022 | 2022-01-21 | Re-scrape | Greenville Zone X Nearby background soil borings at 110-120-044 (300 feet) have elevated arsenic up to 42 mg/kg and 110-120-022 (175 feet) have lead up to 160 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 160 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 42 mg/kg for arsenic and 160 mg/kg for lead are proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentration likely present ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-02 | Match |  |  |  | Match | 2022-04-23 | 2022-04-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/02/2022 | ["Soil Passes"] | Northern Division
002-240-004 | 6250 | 25N81 | Plumas | Debris Removal in Progress | Crew # 103 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-280-019 | 11400 | Frenchman Boulevard | Plumas | Ready for Debris Removal | Crew # 302 (Tehama) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-200-009 | 14200 | Frenchman Boulevard | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-26 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-022 | 174 | Frenchman Cove Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
009-330-024 | 309 | Frenchman Cove Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-31 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-340-008 | 112 | Goose Bay View Trail | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-009 | 114 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-014 | 115 | Goose Bay View Trail | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-241-003 | 7155 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/13/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-242-001 | 7170 | Chester Warner Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-400-001 | 725 | Sugarloaf Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
008-410-001 | 827 | Sugarloaf Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-14 | 05/14/2022 | 2022-05-20 | Approved |  | Confirmation |  | 2022-05-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
015-010-030 | 7600 | Summit Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-05-03 | 05/03/2022 | 2022-05-11 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
002-120-019 | 319 | Round Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-064-003 | 401 | South Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-200-012 | 110-200-012 | South Main Street | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-223-007 | 7329 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 | 11/22/2021 | 2021-12-02 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-224-003 | 7332 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-232-006 | 7196 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-233-006 | 7211 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-120-021 | 812 | Round Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-430-001 | 8 | Round Valley Woods Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/02/2022 | 2022-03-09 | Approved | SBs at 110-190-025 (0.04 miles) have arsenic up to 240 mg/kg and mercury up to 3.2 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
110-430-019 | 67 | Round Valley Woods Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/09/2022 | 2022-03-01 | Approved |  | Rescrape 1 |  | 2022-03-18 | Match |  |  |  | Match | 2022-03-09 | 2022-03-17 |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
016-160-016 | 480 | Drinkwater Gulch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 03/15/2022 | 2022-02-11 | Re-scrape | Onsite SBs have cobalt up to 36 mg/kg, supporting cobalt concentrations are likely ambient or background. Note that the grMz cobalt level changed from 35 mg/kg to 29 mg/kg based on additional background sampling, following the activities at this APN. | Soil Boring 1 |  | 2022-03-24 | Match | 2022-03-15 | 2022-03-23 | Approved | Match | 2022-02-28 | 2022-03-08 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
016-160-064 | 581 | Drinkwater Gulch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 04/08/2022 | 2022-02-23 | Soil Boring | Onsite SBs have cobalt up to 60 mg/kg, supporting all onsite levels likely represent ambient or background conditions. Successful rescrape for lead. | Rescrape 1 |  | 2022-04-21 | Match | 2022-03-03 | 2022-03-11 | Re-scrape | Match | 2022-04-08 | 2022-04-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
016-160-075 | 771 | Drinkwater Gulch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/04/2022 | 2022-02-14 | Approved |  | Confirmation |  | 2022-02-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
019-470-450 | 019-470-450 | no address Hate Mtn Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
100-202-120 | 13021 | Norman Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-28 | 01/28/2022 | 2022-02-07 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
100-202-140 | 13109 | Norman Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-18 | 02/04/2022 | 2022-01-26 | Re-scrape | Nearby soil borings do not have elevated arsenic. | Rescrape 1 |  | 2022-02-14 | Match |  |  |  | Match | 2022-02-04 | 2022-02-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
110-010-004 | 317 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-019-003 | 209 | Landon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 02/10/2022 | 2021-11-30 | Re-scrape |  | Rescrape 3 |  | 2022-02-21 | Match |  |  |  | Match | 2021-12-02 | 2021-12-10 | Re-scrape | Match | 2022-01-25 | 2022-02-03 | Re-scrape | Match | 2022-02-10 | 2022-02-18 | Approved | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | Yes |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
141-130-001 | 435-350 | Lassen Drive | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-17 | 03/17/2022 | 2022-03-25 | Approved |  | Confirmation |  | 2022-03-28 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
110-032-032 | 251 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-040-029_GuestHouse | 120 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-040-029_House | 120 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved | Greenville Zone X Soil borings on adjacent 110-061-011 (350 feet) have lead up to 250 mg/kg. A PPDR limit of 250 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 250 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-110-001 | 125 | Main Street | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved | Greenville Zone X Onsite soil borings do not have elevated arsenic and have lead up to 200 mg/kg; however, soil borings at 110-061-013 (200 feet) have arsenic up to 82 mg/kg and lead up to 320 mg/kg. Nearby soil borings at 110-190-025 (800 feet) have arsenic up to 240 mg/kg. The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 320 mg/kg and the PPDR for arsenic for this property is 240 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-190-023 | 835 | Hideaway Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
111-221-001 | 17460 | Highland Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-035-017 | 256 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-043-007 | 273 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/23/2022 | 2022-02-10 | Re-scrape |  | Rescrape 1 |  | 2022-03-03 | Match |  |  |  | Match | 2022-02-23 | 2022-03-02 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
005-054-001 | 175 | Indian Falls Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-130-013 | 12247 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-150-013 | 12510 | Chester Warner Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-040-026 | 115 | Greenville Wolf Creek Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-26 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-040-027 | 128 | Greenville Wolf Creek Road | Plumas | Final Sign Off Complete | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 02/03/2022 | 2022-02-11 | Approved | Former Zone X hold. Background SBs have lead above 80 mg/kg. | Confirmation |  | 2022-03-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
110-051-004 | 318 | Highway 89 | Plumas | Ready for Soil Sampling | Pending Soils Results |  | Ready for Sampling | [5 empty] | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-052-008 | 333 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-02 | 11/17/2021 | 2021-11-10 | Re-scrape | Greenville lead clears rescrape, although not right downtown. | Rescrape 1 |  | 2021-11-30 | Match |  |  |  | Match | 2021-11-17 | 2021-11-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/30/2021 | ["Soil Passes"] | Northern Division
005-382-005 | 9 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-132-006 | 216 | Grand Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved | Greenville Zone X Soil borings at 110-132-026 (40 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-132-008 | 200 | Grand Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved | Greenville Zone X Onsite background soil borings have lead up to 120 mg/kg; however, soil borings at 110-132-026 (130 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on onsite soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-132-010 | 318 | Hamblin Avenue | Plumas | Final Sign Off Complete | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/29/2021 | 2021-11-18 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 100 mg/kg. The pattern of lead in the soil samples suggests that concentrations less than 100 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 100 mg/kg is proposed for the subject APN based on onsite soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-11 | Match |  |  |  | Match | 2021-11-29 | 2021-12-07 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-132-015 | 321 | Hamblin Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 04/07/2022 | 2022-02-15 | Re-scrape | Onsite soil borings do not have elevated lead, but the surface interval does have elevated mercury. Former Zone X hold. Rescrapes previously recommended for lead since exceedances are not widespread. | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-07 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
011-020-014 | 951 | FS RD 5N60B | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-03 | 05/20/2022 | 2022-05-11 | Re-scrape | Soil borings at 011-020-015 (0.25 miles) have cobalt up to 150 mg/kg and nickel up to 2,600 mg/kg. While there are some concentrations of cobalt slightly over 150 mg/kg, the elevated cobalt and nickel signatures are unique to this area and do not have any relationship with debris contamination. All cobalt and nickel concentrations likely represent ambient or background conditions. Rescrape recommended for lead. | Rescrape 1 | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match | 2022-05-20 | 2022-05-31 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
129-300-067 | 459-880 | Garra Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-19 | 04/01/2022 | 2022-03-25 | Re-scrape | Nearby APNs cleared for arsenic. | Rescrape 1 |  | 2022-04-12 | Match |  |  |  | Match | 2022-04-01 | 2022-04-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
129-300-088 | 460-200 | Garra Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 12/03/2021 | 2021-12-13 | Approved |  | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
011-210-015 | 7050 | Rim Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/06/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
019-670-160 | 13714 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 05/17/2022 | 2022-04-11 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
011-150-014 | 12484 | Warner Valley Road | Plumas | Returned to County | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-050-013 | 13905 | Weemasoul Road | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 05/12/2022 | 2022-04-12 | Re-scrape |  | Rescrape 1 |  | 2022-05-24 | Match |  |  |  | Match | 2022-05-12 | 2022-05-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
001-361-005 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Not Ready for Sampling | 2022-03-15 |  | 2022-03-23 | Approved |  |  |  | 2022-03-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-361-005_07 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 03/15/2022 | 2022-03-23 | Approved |  | Confirmation |  | 2022-03-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
001-361-005_08 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 03/15/2022 | 2022-03-23 | Approved |  | Confirmation |  | 2022-03-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
001-361-005_10 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-22 | Approved |  | Confirmation |  | 2022-03-23 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/23/2022 | ["Soil Passes"] | Northern Division
001-361-005_11 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-22 | Approved |  | Confirmation |  | 2022-03-23 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/23/2022 | ["Soil Passes"] | Northern Division
001-361-005_12 | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 04/07/2022 | 2022-03-22 | Re-scrape |  | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-07 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
001-361-005_PumpHouse | 29586 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved to not sample by IMT 04/05/22 | [5 empty] | No |  |  |  |  | Northern Division
001-361-008 | 29588 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 04/07/2022 | 2022-03-14 | Re-scrape |  | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-07 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
001-362-020 | 29591 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 03/21/2022 | 2022-03-29 | Approved |  | Confirmation |  | 2022-03-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
001-362-021 | 29593 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/01/2022 | 2022-04-11 | Approved |  | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-072-027 | 314 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-23 | 11/23/2021 | 2021-12-03 | Approved | Greenville Zone X Nearby soil borings at 110-072-014 (230 feet) have lead up to 370 mg/kg. The PPDR limit, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 370 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-132-026 | 315 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 04/12/2022 | 2022-02-11 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on onsite soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Rescrape recommended for copper. | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-132-027 | 319 | Bush Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-132-039 | 119 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved | Greenville Zone X Soil borings at 110-131-023 (150 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
002-120-014 | 683 | Round Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 04/05/2022 | 2022-03-29 | Soil Boring | Onsite SBs have arsenic up to 380 mg/kg and mercury up to 6.1 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Note elevated levels of lead up to 1,200 mg/kg in SBs. | Soil Boring 1 |  | 2022-04-14 | Match | 2022-04-05 | 2022-04-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
002-120-020 | 701 | Round Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-17 | 03/17/2022 | 2022-03-25 | Approved | Arsenic signature appears to be background. APN straddles the grMz-Pz geologic contact, and Pz has arsenic background of 46 mg/kg. | Confirmation |  | 2022-03-28 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
002-120-022 | 736 | Round Valley Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-222-012 | 7348 | Warner Creek Drive | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-24 | 11/24/2021 | 2021-12-06 | Approved |  | Confirmation |  | 2021-12-07 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/07/2021 | ["Soil Passes"] | Northern Division
011-222-015 | 7378 | Warner Creek Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 11/17/2021 | 2021-11-29 | Approved |  | Confirmation |  | 2021-11-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/30/2021 | ["Soil Passes"] | Northern Division
011-224-004 | 7391 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | no qualifying debris, approved by Pauline to not sample | [5 empty] | No |  |  |  |  | Northern Division
011-233-004 | 7196 | Chester Warner Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-300-009 | 337 | Pioneer Way | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 03/30/2022 | 2022-04-06 | Approved |  | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
110-062-007 | 410 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-08 | Approved |  | Confirmation |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
110-062-029 | 410 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 01/27/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
009-200-013 | 13618 | 24N02 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
145-030-001 | 3641 | 24N08Y | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2021-12-10 |  | 2021-12-20 | Re-scrape | Nearby APNs cleared for arsenic, but these are large APNs, reevaluate after first rescrape | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-24 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-361-002 | 29736 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 03/01/2022 | 2021-12-13 | Re-scrape | APN is located 250 feet from boundary of geologic unit Pm, which has an arsenic background concentration of 8.4 mg/kg. Given the distribution and concentrations of arsenic at the subject locations, these likely represent background conditions within the Pm unit. Successful rescrape for mercury only. | Rescrape 1 |  | 2022-03-11 | Match |  |  |  | Match | 2022-03-01 | 2022-03-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
001-470-019 | 42339 | Highway 89 | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-052-007 | 339 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 01/20/2022 | 2022-01-27 | Approved | Needs new Plumas Q CGS. | Confirmation |  | 2022-01-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/29/2022 | ["Soil Passes"] | Northern Division
111-010-037 | 18092 | Highway 89 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-031-006 | 300 | Indian Falls Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-035-006 | 301 | Indian Falls Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-310-005 | 680 | Dutch Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-02 | 12/02/2021 | 2021-12-10 | Approved |  | Confirmation |  | 2021-12-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
024-030-045 | 6040 | Dutch Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-22 | 02/22/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2022-03-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
108-320-034 | 512 | Eagle Crest Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-320-036 | 508 | Eagle Crest Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-300-003 | 255 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-300-019 | 258 | Osprey Loop | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-270-005 | 576 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-29 | 03/29/2022 | 2022-04-06 | Approved |  | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
004-270-006 | 741 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 02/24/2022 | 2022-02-18 | Re-scrape | SBs at 004-270-013 (0.21 mi) have arsenic up to 11 mg/kg and cobalt up to 34 mg/kg supporting onsite concentrations at or below these values are likely background or ambient. | Rescrape 1 |  | 2022-03-08 | Match |  |  |  | Match | 2022-02-24 | 2022-03-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-280-001 | 2160 | Williams Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-070-010 | 436-005 | Willow Drive | Lassen | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-19 | 05/19/2022 | 2022-05-27 | Approved |  | Confirmation | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-222-006 | 7421 | Warner Creek Drive | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 |  | 2021-12-02 | Approved | Received email from Pauline Totten 12/7 indicating remaining debris is legacy waste, no additional rescrape necessary. | Rescrape 1 |  | 2021-12-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Trailer not scraped. Katrina, area lead, came out and agreed. Trailer will be scraped next few days. property on hold until then. Area Lead Katrina confirmed it was scraped 11/21/21 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/08/2021 | ["Soil Passes"] | Northern Division
011-224-001 | 7445 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-391-001 | 36542 | Highway 70 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-051-006 | 310 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 04/23/2022 | 2022-02-10 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 220 mg/kg, however soil borings at 110-061-015 (420 ft) have lead up to 300 mg/kg. Soil borings at 110-051-005 (50 feet) have arsenic up to 57 mg/kg. A PPDR limit of 300 mg/kg for lead and 57 mg/kg for arsenic are proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-02 | Match |  |  |  | Match | 2022-04-23 | 2022-04-29 | Approved | Match |  |  |  | Match |  |  |  | Match | D1 was sampled as B1 and B2 for 110-051-005. LandGlide and Explorer show that it should be part of 110-051-005. D1 sample will be eliminated from this APN. | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/02/2022 | ["Soil Passes"] | Northern Division
110-051-008 | 340 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-04 | 05/04/2022 | 2022-05-12 | Approved | Greenville Zone X Soil borings at 110-051-006 (450 feet) have elevated lead up to 220 mg/kg. A PPDR limit of 220 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | team unable to sample CalHaz material on site 04/18, 04/19 | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
110-052-001 | 343 | Highway 89 | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 03/11/2022 | 2022-03-04 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 130 mg/kg. A PPDR limit of 130 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-13 | Match |  |  |  | Match | 2022-03-11 | 2022-03-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-291-012 | 430 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 12/10/2021 | 2021-12-20 | Approved |  | Confirmation |  | 2021-12-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/21/2021 | ["Soil Passes"] | Northern Division
110-292-001 | 461 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/23/2022 | 2022-03-15 | Re-scrape |  | Rescrape 1 |  | 2022-04-01 | Match |  |  |  | Match | 2022-03-23 | 2022-03-31 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/01/2022 | ["Soil Passes"] | Northern Division
001-260-002 | 15675 | Vestal Road | Tehama | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-22 | 04/22/2022 | 2022-05-02 | Approved |  | Confirmation |  | 2022-05-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | debris pile 2 on site, state said to sample rest of parcel 04/23 debris pile 2 removed and sampled one more area (E1) 04/26 state deemed legacy, sample E1 removed by lab 04/27 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/03/2022 | ["Soil Passes"] | Northern Division
011-254-002 | 6948 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 04/08/2022 | 2022-04-18 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
011-254-003 | 6960 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-010-001 | 329 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-291-013 | 333 | Kinder Avenue | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-033 | 2035 | Mule Ear Road | Plumas | Ready for Debris Removal | Crew # 114 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-043 | 2317 | Mule Ear Road | Plumas | Ready for Soil Sampling | Plumas Completed |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-035 | 2409 | Mule Ear Road | Plumas | Ready for Debris Removal | Crew # 114 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
016-160-054 | 3595 | Hyampom Road | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-17 | 05/17/2022 | 2022-05-25 | Approved | All APNs in this area have cobalt over the background concentration. The APNs are very spread out, and the closest soil boring is 0.75 miles at 016-160-069 with cobalt up to 56 mg/kg. Given the small single exceedance (32 mg/kg versus 29 mg/kg cleanup goal) and consistent elevated cobalt concentrations in the area, the 32 mg/kg likely represents ambient or background conditions. | Confirmation |  | 2022-05-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
016-160-068 | 1400 | Drinkwater Gulch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-22 | Approved | SBs at 016-160-067 (0.12 miles) have cobalt up to 100 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-23 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/23/2022 | ["Soil Passes"] | Northern Division
111-010-039 | 17978 | Highway 89 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
100-161-170 | 12805 | Martin Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-22 | 02/18/2022 | 2022-01-05 | Re-scrape | Onsite soil borings have arsenic up to 22 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-02 | Match | 2022-02-18 | 2022-02-28 | Approved | Match | 2022-01-10 | 2022-01-18 | Re-scrape | Match | 2022-02-03 | 2022-02-11 | Soil Boring | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
100-161-220 | 12825 | Martin Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 |  | 2021-12-17 | Re-scrape | SBs at 100-161-170 (0.11 miles) have arsenic up to 22 mg/kg, supporting al onsite concentrations likely represent ambient or background conditions. |  |  | 2022-05-17 | Match |  |  |  | Match | 2022-01-10 |  | Approved | Match |  |  |  | Match |  |  |  | Match | large rocks covering DUs B1 and B2 and rescrape wasn't able to be completed. Notified Jason Brodersen 1/10/22 and he notified the IMT on 1/10/22. SBs collected from adjacent APN in February have elevated arsenic which clear this APN. No rescrape necessary. | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/17/2022 | ["Soil Passes"] | Northern Division
108-010-004 | 90 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-021-005 | 109 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-022-001 | 112 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-032-004 | 114 | Lake Almanor West Drive | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-251-002 | 7015 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-252-002 | 7016 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-018 | 2813 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-019 | 2900 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-020 | 3022 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-100-007 | 6215 | Seneca Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-19 | 05/19/2022 | 2022-05-25 | Approved | SBs at 002-110-009 (0.19 miles) have arsenic up to 180 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Per field team: the sampling locations for A and B consists of loose rocks. Difficult to grab soil. Photo emailed to Jason. Bridge property priority per IMT. Samples sent with a 3-dat TAT 05/19. | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
100-161-230 | 13331 | Shasta Vista Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 01/20/2022 | 2022-01-28 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
108-151-002 | 135 | Slim Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-173-004 | 182 | Slim Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-130-008 | 363 | Rain Drop Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 04/08/2022 | 2022-04-18 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
108-340-016 | 111 | Goose Bay View Trail | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-243-004 | 7090 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-210-048 | 1235 | Diamond Mountain Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-410-011 | 1315 | Diamond Mountain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-042-005 | 291 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-042-010 | 327 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-150-025 | 37450 | Round House Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-220-026 | 112 | Round Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-400-021 | 395 | Butterfly Valley Twain Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/06/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
005-400-028 | 435 | Butterfly Valley Twain Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/06/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
110-071-004 | 504 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 04/20/2022 | 2022-03-11 | Re-scrape | Greenville Zone X Soil borings at 110-064-018 (250 feet) have lead up to 230 mg/kg. A PPDR limit of 230 mg/kg is proposed for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 230 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for elevated lead. | Rescrape 1 |  | 2022-04-29 | Match |  |  |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
110-072-032 | 511 | Main Street | Plumas | Ready for Tree Operations | DTSC Hold | Soil Samples Approved | HOLD Other | 2022-03-01 | 04/18/2022 | 2022-03-09 | Re-scrape | Greenville Zone X Soil borings at nearby property 110-072-014 (110 feet) have lead up to 370 mg/kg. The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 370 mg/kg. Confirmation sample results at or below this concentration likely represent ambient, background, or legacy conditions. Refer elevated mercury at D1 to DTSC. | Rescrape 1 |  | 2022-04-27 | Match |  |  |  | Match | 2022-04-18 | 2022-04-26 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Pending mercury rescrape from DTSC |  |  |  |  | Yes |  |  |  | ["Soil Passes"] | Northern Division
110-072-036 | 519 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-26 | 01/26/2022 | 2022-02-03 | Approved | Greenville Zone X Soil borings at adjacent property 110-072-014 (20 feet) have lead up to 370 mg/kg. The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 370 mg/kg. Confirmation sample results at or below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
007-120-003 | 37496 | 28N01 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-16 | 05/16/2022 | 2022-05-24 | Approved |  | Confirmation |  | 2022-05-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
007-120-010 | 448 | Thompson Creek Drive | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2022-05-16 |  | 2022-05-24 | Re-scrape | Nearby APNs cleared for arsenic. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
007-130-017 | 552 | Thompson Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-19 | 05/19/2022 | 2022-05-27 | Approved |  | Confirmation | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-017-001 | 411 | 2nd Street | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-020-010 | 990 | 26N24 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-06 | 05/06/2022 | 2022-05-13 | Approved | Onsite SBs have cobalt up to 28 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
108-211-008 | 380 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-131-002 | 214 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 12/02/2021 | 2021-11-19 | Re-scrape | Greenville Zone X. Onsite background soil borings have elevated lead up to 290 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 290 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 290 mg/kg is proposed for the subject APN based on soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for arsenic. | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2021-12-02 | 2021-12-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
129-300-078 | 713-200 | Jeters Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-29 | 04/25/2022 | 2022-04-06 | Re-scrape |  | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
129-640-005 | 713-400 | Jeters Road | Lassen | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-03 | Approved | SBs at 129-640-010 (0.2 miles) have arsenic up to 11 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
001-050-016 | 001-050-016 | No Address | Tehama | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-08 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
001-120-040 | 001-120-040 | No Address | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 05/13/2022 | 2022-05-06 | Re-scrape |  | Rescrape 1 |  | 2022-05-25 | Match |  |  |  | Match | 2022-05-13 | 2022-05-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/25/2022 | ["Soil Passes"] | Northern Division
001-160-054 | 001-160-054 | No Address | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 05/07/2022 | 2022-04-15 | Re-scrape |  | Rescrape 1 |  | 2022-05-16 | Match |  |  |  | Match | 2022-05-07 | 2022-05-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
001-190-002 | 001-190-002 | No Address | Tehama | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | ineligible | [5 empty] | No |  |  |  |  | Northern Division
001-210-025 | 001-210-025 | No Address | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-12 | 05/12/2022 | 2022-05-20 | Approved |  | Confirmation |  | 2022-05-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
001-240-006 | 001-240-006 | No Address | Tehama | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | ineligible | [5 empty] | No |  |  |  |  | Northern Division
001-260-033 | 001-260-033 | No Address | Tehama | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-14 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
001-260-034 | 001-260-034 | No Address | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/14/2022 | 2022-05-10 | Re-scrape |  | Rescrape 1 |  | 2022-05-24 | Match |  |  |  | Match | 2022-05-14 | 2022-05-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
002-090-006 | 002-090-006 | No Address | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-009 | 002-090-009 | No Address | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-010 | 002-090-010 | No Address | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-014 | 002-090-014 | No Address | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-020-022 | 005-020-022 | No Address | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-130-022 | 005-130-022 | No Address | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-210-010 | 009-210-010 | NO ADDRESS | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
015-010-025 | 015-010-025 | No Address | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 03/10/2022 | 2022-03-18 | Approved |  | Confirmation |  | 2022-03-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
015-010-028 | 015-010-028 | No Address | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-06 | 05/19/2022 | 2022-05-16 | Re-scrape |  | Rescrape 1 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
015-010-046 | 015-010-046 | No Address | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-06 | 05/19/2022 | 2022-05-16 | Re-scrape |  | Rescrape 1 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-280-034 | 017-280-034 | No address | Tehama | Ready for Tree Operations | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | tree only | [5 empty] | No |  |  |  |  | Northern Division
017-310-039 | 017-310-039 | No Address | Tehama | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 12/07/2021 | 2021-12-15 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
019-470-210 | 019-470-210 | no address | Siskiyou | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 05/17/2022 | 2022-04-18 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
019-470-430 | 019-470-430 | No Address | Siskiyou | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 05/17/2022 | 2022-04-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
019-690-090 | 019-690-090 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
019-700-090 | 019-700-090 | No Address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
019-700-100 | 019-700-100 | No address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
020-190-090 | 020-190-090 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-18 | 02/08/2022 | 2022-01-26 | Re-scrape |  | Rescrape 1 |  | 2022-02-17 | Match |  |  |  | Match | 2022-02-08 | 2022-02-16 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
097-240-005 | 097-240-005 | No address | Lassen | Ready for Debris Removal | Crew # 107 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
100-122-060 | 100-122-060 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-17 | 01/17/2022 | 2022-01-25 | Approved |  | Confirmation |  | 2022-01-27 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
100-142-080 | 100-142-080 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 01/19/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-01-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/29/2022 | ["Soil Passes"] | Northern Division
100-151-010 | 100-151-010 | No Address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
100-151-040 | 100-151-040 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-26 | 01/26/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/04/2022 | ["Soil Passes"] | Northern Division
100-151-130 | 100-151-130 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 01/19/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-01-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/29/2022 | ["Soil Passes"] | Northern Division
100-151-140 | 100-151-140 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 01/20/2022 | 2022-01-28 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-152-080 | 100-152-080 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-18 | 01/18/2022 | 2022-01-26 | Approved |  | Confirmation |  | 2022-01-27 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
100-152-120 | 100-152-120 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-14 | 01/14/2022 | 2022-01-24 | Approved |  | Confirmation |  | 2022-01-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
100-161-020 | 100-161-020 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 03/11/2022 | 2022-03-04 | Re-scrape |  | Rescrape 1 |  | 2022-03-22 | Match |  |  |  | Match | 2022-03-11 | 2022-03-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
100-161-040 | 100-161-040 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
100-171-020 | 100-171-020 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-22 | 01/22/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-171-090 | 100-171-090 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 |  | 2022-02-25 | Re-scrape | Two rescrapes conducted to eliminate very minimal exceedance of arsenic cleanup goal. The arsenic goal is 1.3 mg/kg and the three sample results were all 1.4 mg/kg. Final rescrape ended at bedrock where less than 0.5 inches of soil remained, therefore no further excavation is possible. Elevated final lead sample likely not result of debris. | Soil Boring 2 |  | 2022-05-03 | Match | 2022-03-24 | 2022-04-01 | Approved | Match | 2022-03-07 | 2022-03-15 | Soil Boring | Match | 2022-04-06 | 2022-04-14 | Soil Boring | Match |  |  |  | Match | Jason emailed IMT regarding A2 being bedrock; approved by Steve Eto to not continue sampling 05/02/22 | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/03/2022 | ["Soil Passes"] | Northern Division
100-171-140 | 100-171-140 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
100-202-060 | 100-202-060 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-17 | 02/04/2022 | 2022-01-25 | Re-scrape |  | Rescrape 1 |  | 2022-02-14 | Match |  |  |  | Match | 2022-02-04 | 2022-02-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
100-202-110 | 100-202-110 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-14 | 01/14/2022 | 2022-01-24 | Approved |  | Confirmation |  | 2022-01-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
100-232-010 | 100-232-010 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 | 01/10/2022 | 2021-12-17 | Re-scrape |  | Rescrape 1 |  | 2022-01-19 | Match |  |  |  | Match | 2022-01-10 | 2022-01-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/19/2022 | ["Soil Passes"] | Northern Division
100-232-020 | 100-232-020 | No Address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
100-232-030 | 100-232-030 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-14 | 01/14/2022 | 2022-01-24 | Approved |  | Confirmation |  | 2022-01-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
100-232-080 | 100-232-080 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-17 | 02/07/2022 | 2022-01-25 | Re-scrape |  | Rescrape 1 |  | 2022-02-16 | Match |  |  |  | Match | 2022-02-07 | 2022-02-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
100-232-090 | 100-232-090 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
100-233-020 | 100-233-020 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 01/21/2022 | 2022-01-31 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-233-040 | 100-233-040 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-22 | 12/22/2021 | 2022-01-05 | Approved |  | Confirmation |  | 2022-01-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/06/2022 | ["Soil Passes"] | Northern Division
100-233-060 | 100-233-060 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-09 | Approved |  | Confirmation |  | 2022-02-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/10/2022 | ["Soil Passes"] | Northern Division
100-233-070 | 100-233-070 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 03/22/2022 | 2022-03-11 | Re-scrape |  | Rescrape 1 |  | 2022-03-31 | Match |  |  |  | Match | 2022-03-22 | 2022-03-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
100-271-010 | 100-271-010 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 03/07/2022 | 2022-02-25 | Re-scrape |  | Rescrape 1 |  | 2022-03-17 | Match |  |  |  | Match | 2022-03-07 | 2022-03-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/17/2022 | ["Soil Passes"] | Northern Division
100-271-020 | 100-271-020 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 03/10/2022 | 2022-02-18 | Soil Boring | While the exceedence is 0.01 mg/kg over the cleanup goal, Onsite SBs do not show elevated arsenic. There are no nearby APNs with soil borings. | Rescrape 1 |  | 2022-03-21 | Match | 2022-02-24 | 2022-03-04 | Re-scrape | Match | 2022-03-10 | 2022-03-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
100-271-030 | 100-271-030 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | structure was built on top of bedrock, lots of rocks remain over area, minimal soil able to be sampled and ash still present. Email state and planning 1/21/22 resolved 1/29/22 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
100-271-040 | 100-271-040 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 02/04/2022 | 2022-01-31 | Re-scrape |  | Rescrape 1 |  | 2022-02-14 | Match |  |  |  | Match | 2022-02-04 | 2022-02-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
100-271-080 | 100-271-080 | No address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 |  | 2022-01-28 | Re-scrape | The first rescrape removed all soil at the target areas to bedrock, and further rescrapes were deemed not feasible by the field teams and concurred with by the State IMT. The rescrapes successfully reduced the arsenic concentrations from the original confirmation samples, but one sample remained slightly above the arsenic cleanup goal. Given that all the soil has been removed, there is no additional rescrape or sampling recommended, and the APN is recommended as Soil Passes. | Rescrape 2 |  | 2022-02-28 | Match |  |  |  | Match | 2022-02-07 | 2022-02-16 | Re-scrape | Match |  |  | Approved | Match |  |  |  | Match | 2/28/22 IMT determined no sampling is required because only bedrock remains. Only bedrock remains, Jason brodersen emailed pauline and steve eto about APN on 2/25/22 | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/28/2022 | ["Soil Passes"] | Northern Division
100-271-090 | 100-271-090 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 01/19/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-01-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/29/2022 | ["Soil Passes"] | Northern Division
100-272-110 | 100-272-110 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 01/20/2022 | 2022-01-28 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-301-050 | 100-301-050 | no address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-22 | 01/22/2022 | 2022-01-27 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-312-010 | 100-312-010 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-17 | 02/04/2022 | 2022-01-25 | Re-scrape |  | Rescrape 1 |  | 2022-02-14 | Match |  |  |  | Match | 2022-02-04 | 2022-02-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
100-312-030 | 100-312-030 | No address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
100-312-050 | 100-312-050 | No address | Siskiyou | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 03/15/2022 | 2022-03-23 | Approved |  | Confirmation |  | 2022-03-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
100-312-100 | 100-312-100 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-22 | 12/22/2021 | 2021-12-30 | Approved |  | Confirmation |  | 2022-01-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/04/2022 | ["Soil Passes"] | Northern Division
100-351-050 | 100-351-050 | No Address | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
100-391-050 | 100-391-050 | No address | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-010-021 | 108-010-021 | No Address | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-220-043 | 110-220-043 | No Address | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-300-021 | 110-300-021 | No Address | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 02/21/2022 | 2022-02-07 | Re-scrape | Outside of Greenville Zone X, but elevated lead. Note that added E2 because the Plumas Q unit outside of Zone X cleanup level for lead is being updated to 80 mg/kg. | Rescrape 1 |  | 2022-03-02 | Match |  |  |  | Match | 2022-02-21 | 2022-03-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
111-310-001 | 111-310-001 | No Address | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
111-310-005 | 111-310-005 | No Address | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
129-300-024 | 129-300-024 | No Address | Lassen | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
129-300-076 | 129-300-076 | No Address | Lassen | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-03-28 | 03/28/2022 | 2022-04-05 | Approved |  | Confirmation |  | 2022-04-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/06/2022 | ["Soil Passes"] | Northern Division
005-381-015 | 75 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 02/01/2022 | 2022-01-27 | Re-scrape | Nearby soil borings do not have elevated results. | Rescrape 1 |  | 2022-02-10 | Match |  |  |  | Match | 2022-02-01 | 2022-02-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/10/2022 | ["Soil Passes"] | Northern Division
005-382-010 | 56 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-08 | 02/01/2022 | 2022-01-14 | Re-scrape |  | Rescrape 1 |  | 2022-02-10 | Match |  |  |  | Match | 2022-02-01 | 2022-02-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/10/2022 | ["Soil Passes"] | Northern Division
005-383-004 | 97 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/02/2022 | 2022-02-10 | Approved |  | Confirmation |  | 2022-02-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/11/2022 | ["Soil Passes"] | Northern Division
108-290-020 | 274 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-290-027 | 278 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-290-003 | 285 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-290-004 | 287 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-090-008 | 10000 | Old Red Bluff Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-05-04 | 05/16/2022 | 2022-05-11 | Soil Boring | Onsite SBs have arsenic up to 6.5 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-05-26 | Match | 2022-05-16 | 2022-05-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | field team unable to access due to felled trees 03/30 alternative route has snow on road 04/06 | Soil Passes, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
011-090-016 | 12974 | Old Red Bluff Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-010-020 | 174 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-300-025 | 246 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-270-018 | 475 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 04/27/2022 | 2022-03-18 | Re-scrape | Onsite SBs have arsenic up to 180 mg/kg, supporting lower concentrations likely represent ambient or background conditions. Successful rescrape. | Rescrape 2 |  | 2022-05-06 | Match | 2022-04-13 | 2022-04-21 | Re-scrape | Match | 2022-03-26 | 2022-04-01 | Soil Boring | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
004-260-001 | 835 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-260-010 | 1121 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-260-011 | 1180 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 | 03/08/2022 | 2022-03-16 | Approved |  | Confirmation |  | 2022-03-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
004-280-011 | 1334 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 03/16/2022 | 2022-02-17 | Re-scrape |  | Rescrape 1 |  | 2022-03-25 | Match |  |  |  | Match | 2022-03-16 | 2022-03-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/25/2022 | ["Soil Passes"] | Northern Division
004-280-026 | 1520 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
009-210-005 | 471 | Carmen Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-340-004 | 1158 | Carmen Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-27 | 04/27/2022 | 2022-05-05 | Approved |  | Confirmation |  | 2022-05-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
110-190-017 | 127 | Round Valley Road | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-210-001 | 117 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 04/27/2022 | 2022-03-10 | Re-scrape | Greenville Zone X Background soil borings at the subject property have lead up to 140 mg/kg, arsenic up to 63 mg/kg, and SBs at 110-210-004 (200 ft) have mercury up to 5.6 mg/kg. The PPDR limit, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 140 mg/kg. SBs at 110-190-025 (0.12 miles) have arsenic at 240 mg/kg and mercury at 3 mg/kg, supporting confirmation below these concentration likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 2 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Re-scrape | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
008-210-047 | 311 | Underwood Mountain Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-12 | 03/02/2022 | 2022-01-20 | Soil Boring | Onsite SBs have arsenic up to 4.4 mg/kg indicating concentrations below that value are likely background or ambient conditions. Successful rescrape. | Rescrape 1 |  | 2022-03-11 | Match | 2022-02-09 | 2022-02-15 | Re-scrape | Match | 2022-03-02 | 2022-03-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
108-340-011 | 118 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-012 | 120 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-350-001 | 122 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-350-002 | 124 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-350-004 | 128 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-350-005 | 130 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-292-004 | 441 | Greenacre Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 02/28/2022 | 2022-03-08 | Approved |  | Confirmation |  | 2022-03-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
008-780-010 | 808 | Big Mountain Road | Trinity | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-064-017 | 111 | Bush Street | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape Results | Ready for Sampling | 2021-11-05 |  | 2021-11-15 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 110 mg/kg and do not have elevated mercury. Nearby soil borings at 110-064-013 (120 feet) have lead up to 630 mg/kg. A PPDR limit of 630 mg/kg is proposed for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Nearby soil borings at 110-120-044 (610 feet) have mercury at 2 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 2 |  |  | Match |  |  |  | Match | 2021-11-22 | 2021-12-02 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-064-018 | 115 | Bush Street | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape Results | Ready for Sampling | 2021-11-06 |  | 2021-11-12 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 230 mg/kg and do not have elevated mercury. Nearby soil borings at 110-064-013 (100 feet) have lead up to 630 mg/kg. A PPDR limit of 630 mg/kg is proposed for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Nearby soil borings at 110-120-044 (740 feet) have mercury at 2 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Areas with lead greater than this concentration, in addition to other metals above cleanup goals, are recommended for rescrapes. | Rescrape 2 |  |  | Match |  |  |  | Match | 2021-11-24 | 2021-12-03 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-072-035 | 120 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 11/15/2021 | 2021-11-23 | Approved | Greenville Zone X Soil borings at adjacent property 110-064-018 (160 feet) have lead up to 230 mg/kg. The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 230 mg/kg. Confirmation sample results at or below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
004-280-018 | 1887 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-08 | Approved | SBs at 004-280-019 (0.19 miles) have cobalt up to 55 mg/kg, supporting onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
004-280-018 | 1887 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Not Ready for Sampling | 2022-01-31 |  | 2022-02-08 | Approved |  |  |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-680-040 | 13511 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-25 | 01/25/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/04/2022 | ["Soil Passes"] | Northern Division
004-050-038 | 940 | Hilton Lane | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 05/12/2022 | 2022-03-09 | Soil Boring | Six onsite SBs have arsenic up to 8.3 mg/kg, clearing all but D1 and Z2 (8.5 mg/kg). Given (1) the high frequency of onsite elevated arsenic SBs, (2) the comparability of 8.3 mg/kg and 8.5 mg/kg, (3) SBs at 004-260-003 (0.3 miles), and (4) preponderance of elevated arsenic at all near APNs, it is likely that all onsite concentrations represent ambient or background conditions. | Soil Boring 2 |  | 2022-05-24 | Match | 2022-05-12 | 2022-05-20 | Approved | Match | 2022-04-19 | 2022-04-27 |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
009-340-011 | 386 | Horse Tail Road | Plumas | Ready for Debris Removal | Crew #113 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-161-004 | 126 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/08/2022 | 2022-03-01 | Re-scrape |  | Rescrape 1 |  | 2022-03-18 | Match |  |  |  | Match | 2022-03-08 | 2022-03-16 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
110-162-001 | 129 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-06 | 01/17/2022 | 2021-12-14 | Re-scrape |  | Rescrape 1 |  | 2022-01-27 | Match |  |  |  | Match | 2022-01-17 | 2022-01-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
110-190-027 | 93 | South Main Street | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
001-362-018 | 29567 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-01 | 04/08/2022 | 2021-12-09 | Re-scrape |  | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-08 | 2022-04-18 | Approved | Match |  |  |  | Match |  |  |  | Match | Trailer left onsite that needs to be removed before soil sampling takes place. State and planning notified 11/23. planning notified soils on 11/30 that the trailer is on a neighboring APN, soils will sample 12/1 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
009-200-014 | 13430 | 24N02 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Not Ready for Sampling | 2022-05-18 |  | 2022-05-26 | Approved |  |  |  | 2022-05-27 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-320-012 | 427 | Recon Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-120-037 | 101 | Red Hill Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-690-030 | 13925 | Forest Service Road | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-320-011 | 401 | Morningside Court | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-061-003 | 202 | NW Ann Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-033 | 209 | NW Ann Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Re-scrape Results | Ready for Sampling | 2022-02-24 |  | 2022-03-09 | Re-scrape | Greenville Zone X Onsite soil borings have elevated lead up to 120 mg/kg; however, nearby soil borings at 110-051-006 (350 feet) have lead up to 220 mg/kg. A PPDR limit of 220 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 2 |  |  | Match |  |  |  | Match | 2022-05-13 | 2022-05-23 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
111-050-004 | 368 | Old Green Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-350-066 | 746-485 | Old Indian Trail | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 01/15/2022 | 2021-12-20 | Soil Boring | Onsite SBs have arsenic up to 18 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-01-26 | Match | 2022-01-15 | 2022-01-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
141-350-067 | 746-600 | Old Indian Trail | Lassen | Debris Removal in Progress | Crew #501 (Lassen) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-160-061 | 2000 | 28N 77 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
001-160-062 | 2000 | 28N 77 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-26 | 05/03/2022 | 2022-04-01 | Soil Boring | SBs at 001-160-059 (0.17 miles) have arsenic up to 6.7 mg/kg, supporting all concentrations lower likely represent ambient or background conditions. | Rescrape 1 |  | 2022-05-12 | Match | 2022-04-13 | 2022-04-21 | Re-scrape | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
007-130-002 | 36665 | 28N01 | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Samples Shipped | 2022-05-21 | 05/21/2022 | 2022-05-27 | Re-scrape |  | Confirmation | 05/30/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-190-022 | 761 | Hideaway Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 03/15/2022 | 2022-03-08 | Re-scrape | SBs at 110-190-025 (0.23 miles) have arsenic up to 240 mg/kg and mercury up to 3.2 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrape for lead. | Rescrape 1 |  | 2022-03-24 | Match |  |  |  | Match | 2022-03-15 | 2022-03-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
110-190-030 | 782 | Hideaway Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 03/10/2022 | 2022-03-18 | Approved | SBs at 110-200-007 (0.16 miles) have arsenic up to 250 mg/kg and mercury up to 5.5 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-23 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
001-362-006 | 29571 | Highway 89 | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Re-scrape 2 Results | Samples Shipped | 2022-03-25 | 05/19/2022 | 2022-04-04 | Re-scrape |  | Rescrape 2 | 05/27/2022 |  | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Re-scrape | Match | 2022-05-19 | 2022-05-27 | Re-scrape | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
007-120-015 | 354 | Thompson Creek Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-06 | 05/06/2022 | 2022-05-13 | Approved |  | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
007-130-019 | 555 | Rand Drive | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample Results Rec'd from Lab | Samples Shipped | 2022-05-23 | 05/23/2022 | 2022-06-01 |  |  | Confirmation | 05/31/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
012-050-004 | 331 | Ranger Station Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 02/04/2022 | 2021-12-14 | Re-scrape |  | Rescrape 3 |  | 2022-02-15 | Match |  |  |  | Match | 2022-01-14 | 2022-01-24 | Re-scrape | Match | 2022-01-14 | 2022-01-24 | Re-scrape | Match | 2022-02-04 | 2022-02-14 | Approved | Match | 12/2/21 Field team found undocumented trailer onsite. Planning stated its a legacy item, waiting for confirmation from the state. issue resolved 12/7/21 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
108-320-026 | 509 | Eagle Crest Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-320-039 | 513 | Eagle Crest Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-130-009 | 283 | Clarks Ford Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Not Ready for Sampling | 2022-05-21 |  | 2022-05-27 | Approved |  |  |  | 2022-05-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
012-060-025 | 265 | Clement Road | Trinity | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
143-030-012 | 428-240 | Constantia Road | Lassen | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-016-002 | 213 | Hudson Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-171-002 | 156 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-26 | 01/26/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Concrete left onsite. Frank Gutham and Lacey Moore, working to find out why concrete is left onsite before soils can sample. Comment resolved | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
110-172-003 | 157 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved | SBs at 110-172-004 (0.01 miles) have arsenic at 680 mg/kg and mercury at 10 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
110-051-005 | 316 | Highway 89 | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 04/23/2022 | 2022-02-11 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 220 mg/kg. A PPDR limit of 220 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Areas with lead greater than this concentration, in addition to other metals above cleanup goals successfully rescraped. | Rescrape 1 |  | 2022-05-02 | Match |  |  |  | Match | 2022-04-23 | 2022-04-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/02/2022 | ["Soil Passes"] | Northern Division
110-300-022 | 401 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 02/28/2022 | 2022-02-04 | Soil Boring | Cobalt clears per previous recommendations. This APN is not cleared for lead. | Rescrape 1 |  | 2022-03-10 | Match | 2022-02-09 | 2022-02-17 | Re-scrape | Match | 2022-02-28 | 2022-03-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
110-064-013 | 138 | Church Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 04/20/2022 | 2022-02-18 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 630 mg/kg, but do not have elevated cobalt. A PPDR limit of 630 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape for cobalt. | Rescrape 1 |  | 2022-04-29 | Match |  |  |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
110-131-023 | 116 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 03/25/2022 | 2021-11-19 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for elevated lead. | Soil Boring 1 |  | 2022-04-08 | Match | 2022-03-25 | 2022-04-04 |  | Match | 2021-12-06 | 2021-12-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-132-043 | 117 | Jessie Street | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-01-13 | 04/13/2022 | 2022-01-21 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead to 120 mg/kg; however, soil borings at 110-132-045 (75 feet) have lead up to 200 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 200 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 200 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for arsenic. | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
011-232-008 | 7166 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-233-007 | 7179 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-241-005 | 7119 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-030-046 | 1943 | Pecks Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-064-001 | 100 | Pine Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-19 | 04/29/2022 | 2022-01-27 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated lead, arsenic or mercury; however, soil borings on nearby 110-063-013 (250 feet) have lead up to 340 mg/kg, arsenic up to 62 mg/kg, and mercury up to 3.4 mg/kg. A PPDR limit of 340 mg/kg is proposed for lead for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 340 mg/kg in this area may not be related to the Dixie Fire. In addition, a PPDR limit of 62 mg/kg is proposed for arsenic and a PPDR limit of 3.4 mg/kg is proposed for mercury. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-10 | Match |  |  |  | Match | 2022-04-29 | 2022-05-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
110-131-011 | 202 | Pine Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 04/13/2022 | 2021-11-18 | Soil Boring | Greenville Zone X Onsite background soil borings have elevated lead up to 460 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 460 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 460 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-22 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match | PG&E temporarily blocking access to APN, soils will sample 12/3 | Soil Passes PPDR Limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
110-131-016 | 204 | Pine Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 04/13/2022 | 2022-03-01 | Re-scrape | Greenville Zone X Nearby soil borings at 110-131-023 (200 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
011-252-009 | 7007 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-254-007 | 7008 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-254-008 | 7020 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 12/01/2021 | 2021-11-24 | Re-scrape | SBs at 011-262-004 (0.11 mi) has arsenic concentrations up to 8.8 mg/kg supporting onsite arsenic is likely ambient or background. | Rescrape 1 |  | 2022-03-24 | Match |  |  |  | Match | 2021-12-01 | 2021-12-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
009-340-003 | 1334 | Carmen Road | Plumas | Ready for Debris Removal | Eligibility Determination |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-063-004 | 205 | Pine Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 02/03/2022 | 2022-02-11 | Approved | Greenville Zone X Onsite soil borings have lead up to 110 mg/kg; however, nearby soil borings at 110-131-011 (100 feet) have lead up to 460 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 460 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-131-015 | 206 | Pine Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved | Greenville Zone X Onsite background soil borings have lead up to 200 mg/kg; however, nearby soil borings at 110-131-023 (150 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-241-007 | 1784 | Pinebrook Way | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-351-009 | 171 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 03/08/2022 | 2021-12-13 | Re-scrape |  | Rescrape 2 |  | 2022-03-18 | Match |  |  |  | Match | 2022-02-18 | 2022-02-28 | Re-scrape | Match | 2022-03-08 | 2022-03-16 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
110-352-034 | 172 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 03/03/2022 | 2022-03-11 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
111-010-017 | 1000 | Standart Mine Road | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Re-scrape Results | Ready for Sampling | 2022-05-03 |  | 2022-05-11 | Re-scrape |  | Rescrape 2 |  |  | Match |  |  |  | Match | 2022-05-17 | 2022-05-25 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
012-300-011 | 31 | Hart Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 02/21/2022 | 2021-12-01 | Re-scrape | DTSC performed rescrapes at C1, I2, L1, L2; however, they did not test for lead at I2, so Tetra Tech collected a confirmation sample at I2 in addition to rescrapes listed. DTSC mercury results: C1: 0.028 mg/kg; I2: 0.060 mg/kg; L1: 0.086 mg/kg; L2: 0.017 mg/kg. | Rescrape 1 |  | 2022-03-02 | Match |  |  |  | Match | 2022-02-21 | 2022-03-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | Yes |  |  | 03/02/2022 |  | Northern Division
129-300-077 | 713-400 | Hicks Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 12/08/2021 | 2021-12-16 | Approved |  | Confirmation |  | 2021-12-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/17/2021 | ["Soil Passes"] | Northern Division
129-300-084 | 713-700 | Hicks Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
129-300-086 | 713-900 | Hicks Road | Lassen | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-060-015 | 300 | Country Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/02/2022 | 2022-03-09 | Approved |  | Confirmation |  | 2022-03-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
141-230-013 | 434-370 | Foothill Lane | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-31 | 04/25/2022 | 2022-04-08 | Re-scrape |  | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
004-070-035 | 84 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
012-350-007 | 591 | Dutch Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-12 | 02/04/2022 | 2022-01-20 | Re-scrape |  | Rescrape 1 |  | 2022-02-15 | Match |  |  |  | Match | 2022-02-04 | 2022-02-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
012-350-012 | 615 | Dutch Creek Road | Trinity | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 12/31/2021 | 2021-12-14 | Re-scrape |  | Rescrape 1 |  | 2022-01-11 | Match |  |  |  | Match | 2021-12-31 | 2022-01-07 | Approved | Match |  |  |  | Match |  |  |  | Match | Trailer that homeowner wants to keep was left onsite where it burned. State and planning notified 11/23/21 issued resolved 12/7/21 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/11/2022 | ["Soil Passes"] | Northern Division
110-072-005 | 553 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 01/24/2022 | 2022-02-01 | Approved | Greenville Zone X Background soil borings at 110-072-008 (190 feet) have lead up to 170 mg/kg. While onsite soil borings do not have elevated lead results, the widespread pattern of lead in the confirmation samples suggests that concentrations less than 170 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-081-010 | 630 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-01 | 04/12/2022 | 2021-12-09 | Re-scrape | Greenville Zone X FSO SBs at 110-082-001 (250 ft) have lead up to 190 mg/kg and mercury up to 1.3 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Rescrape for lead at C2-R1 | Rescrape 2 |  | 2022-04-21 | Match |  |  |  | Match | 2022-01-17 | 2022-01-25 | Re-scrape | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-081-011 | 636 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/09/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
110-082-015 | 639 | Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-054-013 | 151 | Indian Falls Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 02/14/2022 | 2022-02-07 | Re-scrape |  | Rescrape 1 |  | 2022-02-25 | Match |  |  |  | Match | 2022-02-14 | 2022-02-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
141-360-002 | 746-355 | Doyle Grade Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-01 | 03/17/2022 | 2022-03-08 | Re-scrape |  | Rescrape 1 |  | 2022-03-28 | Match |  |  |  | Match | 2022-03-17 | 2022-03-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
108-042-003 | 133 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 11/15/2021 | 2021-11-23 | Approved |  | Confirmation |  | 2021-11-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/24/2021 | ["Soil Passes"] | Northern Division
110-072-024 | 302 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-01-11 | 01/11/2022 | 2022-01-19 | Approved | Greenville Zone X Onsite background soil borings do not have elevated lead; however, background soil borings at 110-072-014 (140 feet) have lead up to 370 mg/kg. The PPDR limit for this property is 370 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-132-002 | 305 | Bush Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 12/08/2021 | 2021-12-16 | Approved |  | Confirmation |  | 2021-12-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/17/2021 | ["Soil Passes"] | Northern Division
110-132-028 | 307 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 04/12/2022 | 2021-11-23 | Re-scrape | Greenville Zone X Elevated lead in onsite soil boring. | Rescrape 3 |  | 2022-04-21 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2021-11-29 | 2021-12-07 | Re-scrape | Match | 2021-12-10 | 2021-12-20 | Soil Boring | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
011-140-006 | 12874 | Chester Warner Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-27 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Boundary Issue with Explorer state has been notified, cant proceed until boundary issue resolved New SSF provided but flooded footprints due to broken water pipe 05/21 | [5 empty] | No |  |  |  |  | Northern Division
110-132-005 | 220 | Grand Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/23/2022 | 2022-03-14 | Re-scrape |  | Rescrape 1 |  | 2022-04-01 | Match |  |  |  | Match | 2022-03-23 | 2022-03-31 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/01/2022 | ["Soil Passes"] | Northern Division
110-132-009 | 324 | Hamblin Avenue | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 04/12/2022 | 2021-11-30 | Re-scrape | Greenville Zone X Soil borings at 110-132-026 (110 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
011-210-008 | 7339 | Rim Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
110-051-007 | 302 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/07/2022 | 2022-03-15 | Approved | Greenville Zone X Nearby background soil borings at 110-051-006 (60 feet) have lead up 220 mg/kg. A PPDR limit of 220 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below this concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-061-011 | 212 | Main Street | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-110-007 | 213 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Not Ready for Sampling | 2022-05-21 |  | 2022-05-27 | Re-scrape |  |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-240-005 | 5846 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 03/22/2022 | 2022-03-03 | Re-scrape |  | Rescrape 1 |  | 2022-03-31 | Match |  |  |  | Match | 2022-03-22 | 2022-03-30 | Approved | Match |  |  |  | Match |  |  |  | Match | Working with Frank Gutham and Taylor to fix SSF and determine where trees need to be moved for soil sampling to take place. Tree issue resolved 2/23/22 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
005-090-001 | 34143 | Highway 70 | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-090-005 | 34228 | Highway 70 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-392-008 | 36074 | Highway 70 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
097-240-002 | Lot 19 & 20, Block 67 | Juniper Lake Resort | Lassen | Chimney Tip Needed | Crew # 107 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
097-240-015 | Lot 8, Block 22 | Juniper Lake Resort | Lassen | ROE Received | Access Issues |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-022-006 | 256 | Kinder Avenue | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 05/04/2022 | 2022-02-17 | Re-scrape | Greenville Zone X Onsite soil borings have elevated lead up to 130 mg/kg. A PPDR limit of 130 mg/kg for lead is proposed for the subject APN based on soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 2 |  | 2022-05-16 | Match |  |  |  | Match | 2022-04-23 | 2022-04-29 | Re-scrape | Match | 2022-05-04 | 2022-05-12 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
110-023-008 | 259 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-023-017 | 263 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-04 | 11/04/2021 | 2021-11-12 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
110-063-006 | 126 | Crescent Street | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved | Greenville Zone X Nearby soil borings at 110-063-007 (50 feet) has a lead result at 140 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 140 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
110-063-016 | 136 | Crescent Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 04/20/2022 | 2021-11-16 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated concentrations; however, Soil borings at nearby 110-063-007 (150 feet) have lead at 380 mg/kg and 110-120-044 (280 feet) have mercury up to 2 mg/kg. First rescrape results did not generally lower the lead concentrations. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 380 mg/kg and the PPDR limit for mercury is 2 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 2 |  | 2022-04-29 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2021-11-20 | 2021-11-30 | Re-scrape | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
110-120-004 | 137 | Crescent Street | Plumas | Ready for Soil Sampling | Plumas Completed |  | Ready for Sampling | [5 empty] | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-120-033 | 147 | Crescent Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/02/2022 | 2022-02-10 | Approved | Greenville Zone X Onsite background soil borings have elevated lead up to 160 mg/kg; however, nearby soil borings at 110-063-007 (270 feet) have lead at 380 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 380 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 380 mg/kg is proposed for the subject APN based on soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-120-042 | 205 | Crescent Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-12 | 04/26/2022 | 2022-04-20 | Re-scrape |  | Rescrape 1 |  | 2022-05-05 | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
110-131-007 | 210 | Crescent Street | Plumas | Ready for Final Sign-off | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 04/05/2022 | 2022-03-04 | Re-scrape | Zone X rescrape recommended since lead exceedances are not widespread. Former Zone X Hold | Rescrape 1 |  | 2022-04-14 | Match |  |  |  | Match | 2022-04-05 | 2022-04-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
110-040-011 | 202 | Mill Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 03/15/2022 | 2022-03-23 | Approved | Greenville Zone X Nearby soil borings at 110-061-015 (300 feet) have lead up to 300 mg/kg. A PPDR limit of 300 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-061-004 | 203 | Mill Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-01 | 04/25/2022 | 2021-12-09 | Soil Boring | Greenville Zone X Onsite background soil borings have lead up to 110 mg/kg; however, soil borings at 110-061-015 (100 feet) have lead up to 300 mg/kg. A PPDR limit of 300 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Soil borings at 110-061-003 (75 feet) have arsenic up to 53 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Areas with lead greater than this concentration, in addition to other metals above cleanup goals, are recommended for rescrapes. | Rescrape 1 |  | 2022-05-04 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match | Structure 2 missed during debris removal. Debris will need to return before soil sampling can take place. structure was removed by debris and soils was able to sample | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
110-061-006 | 116 | NW Ann Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-22 | Approved | In Greenville Zone X boundary, but does not have elevated lead. Onsite background soil borings do not have elevated arsenic; however, nearby soil borings from 110-061-013 (200 feet) have arsenic up to 82 mg/kg. Indicating soil sample results up to 82 mg/kg are likely not related to fire debris and represent ambient levels. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
141-270-037 | 430-025 | Constantia Road | Lassen | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 05/03/2022 | 2022-04-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
141-360-035 | 745-200 | Doyle Grade Road | Lassen | Ready for Soil Sampling | Plumas Completed |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-054-014 | 142 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 03/15/2022 | 2022-03-23 | Approved |  | Confirmation |  | 2022-03-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
005-382-003 | 45 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-383-006 | 50 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-180-011 | 11544 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-223-004 | 7395 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
011-231-004 | 7247 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-233-001 | 7258 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-233-003 | 7216 | Chester Warner Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-233-005 | 7241 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-02 | 11/02/2021 | 2021-11-10 | Approved | Background level in Tv Unit established at 4.8 mg/kg, following time of CGS table generation. All arsenic concentrations are below background level. | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
012-300-012 | 24 | Hart Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-24 | 12/31/2021 | 2021-12-06 | Re-scrape |  | Rescrape 1 |  | 2022-01-11 | Match |  |  |  | Match | 2021-12-31 | 2022-01-07 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/11/2022 | ["Soil Passes"] | Northern Division
019-680-020 | 13519 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/04/2022 | 2022-02-11 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
005-140-001 | 37616 | Highway 70 | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-150-008 | 37800 | Highway 70 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/17/2022 | 2022-03-10 | Re-scrape |  | Rescrape 1 |  | 2022-03-28 | Match |  |  |  | Match | 2022-03-17 | 2022-03-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
110-110-010 | 115 | Highway 89 | Plumas | Asbestos Abatement Needed | Crew #106 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-254-004 | 6972 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-031-017 | 227 | Kinder Avenue | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 04/04/2022 | 2022-02-22 | Re-scrape | Zone X rescrape recommended since lead exceedances are not widespread. Former Zone X Hold | Rescrape 1 |  | 2022-04-13 | Match |  |  |  | Match | 2022-04-04 | 2022-04-12 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-032-004 | 228 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-05 | 11/05/2021 | 2021-11-15 | Approved |  | Confirmation |  | 2021-11-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/16/2021 |  | Northern Division
011-222-003 | 7442 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-223-001 | 7457 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
017-270-038 | 017-270-038 | Highway 36 East | Tehama | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-29 | 04/29/2022 | 2022-05-09 | Approved |  | Confirmation |  | 2022-05-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
019-070-003 | SEC 16 T27N R9W | Highway 36 West | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-06 | 05/06/2022 | 2022-05-16 | Approved |  | Confirmation |  | 2022-05-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/17/2022 | ["Soil Passes"] | Northern Division
108-032-006 | 136 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-132-017 | 110 | Grand Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 | 04/13/2022 | 2022-03-16 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 110 mg/kg; however, soil borings at 110-132-026 (310 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on onsite soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for arsenic. | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
004-260-004 | 922 | Lower Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 03/22/2022 | 2022-02-24 | Soil Boring | Onsite SBs have arsenic up to 10 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Rescrapes successful for higher concentrations. | Rescrape 1 |  | 2022-03-31 | Match | 2022-03-03 | 2022-03-11 | Re-scrape | Match | 2022-03-22 | 2022-03-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
004-350-003 | 2301 | Upper Pecks Valley Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 05/14/2022 | 2022-02-25 | Re-scrape | DTSC has successfully rescraped C1, D1, D2. C1A (subset of C1): lead 3.1 mg/kg, mercury 0.057 U mg/kg C1: lead 3.1 mg/kg, mercury 0.16 mg/kg D1: lead 6.8 mg/kg, mercury 0.057 U mg/kg D2: lead 5.8 mg/kg, mercury 0.056 U mg/kg | Rescrape 1 |  | 2022-05-24 | Match |  |  |  | Match | 2022-05-14 | 2022-05-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | Yes |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
111-300-001 | 18800 | Valley View Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 | 11/22/2021 | 2021-12-02 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
111-300-005 | 19100 | Valley View Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
111-300-007 | 19301 | Valley View Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-280-006 | 1532 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 02/26/2022 | 2022-01-27 | Re-scrape | Added H2 to rescrape list as a result of cleanup goal for lead changing from 103 to 80 mg/kg. | Rescrape 2 |  | 2022-03-08 | Match |  |  |  | Match | 2022-02-26 | 2022-03-04 | Re-scrape | Match | 2022-02-26 | 2022-03-04 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-280-021 | 1581 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 03/11/2022 | 2022-03-07 | Re-scrape | SBs from 004-280-019 (0.09 miles) have cobalt up to 35 mg/kg, supporting concentrations at or below likely represent ambient or background conditions. Successful rescrape for elevated cobalt. | Rescrape 1 |  | 2022-03-22 | Match |  |  |  | Match | 2022-03-11 | 2022-03-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
001-470-014 | 1463 | County Road 324 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 05/14/2022 | 2022-04-12 | Re-scrape | Onsite SBs have cobalt up to 30 mg/kg, clearing cobalt at A2, however, the first rescrape result at A1 is 33 mg/kg. Given (1) the comparability of 30 mg/kg and 33 mg/kg, (2) nearby APNs also show elevated cobalt, and (3) the initial confirmation result at A1 was 30 mg/kg, it is likely that A1 and A2 concentrations represent ambient or background conditions. | Soil Boring 1 |  | 2022-05-24 | Match | 2022-05-14 | 2022-05-20 | Approved | Match | 2022-04-29 | 2022-05-09 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
110-210-002 | 113 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved | SBs at 110-190-025 (0.11 miles) have arsenic up to 250 mg/kg and mercury up to 3.2 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
110-062-025 | 384 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 02/15/2022 | 2022-02-23 | Approved | Greenville Zone X Nearby soil borings at 110-062-027 (70 feet) have lead up to 200 mg/kg. A PPDR limit of 200 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-062-027 | 400 | Main Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-11-18 | 05/05/2022 | 2021-11-30 | Soil Boring | Greenville Zone X Onsite soil borings have lead up to 200 mg/kg; however, nearby soil borings at 110-063-013 (160 feet) have lead up to 340 mg/kg. A PPDR limit of 340 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-05-16 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-05-05 | 2022-05-13 | Approved | Match |  |  |  | Match |  |  |  | Match | 110-062-027 tarp with items on top of debris pile that requires sampling 11/17 Pauline confirmed area could be sample 11/18/21. | Soil Passes PPDR limit | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
108-273-004 | 310 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/13/2021 | 2021-11-19 | Approved | Onsite soil borings indicate elevated cobalt, supporting that all onsite levels likely represent background or ambient conditions. | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
108-273-006 | 314 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-273-011 | 324 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-190-004 | 15 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-02 | 02/19/2022 | 2021-12-10 | Soil Boring | Onsite SBs have arsenic up to 480 mg/kg and mercury up to 4.5 mg/kg, supporting likely ambient or background conditions. | Rescrape 1 |  | 2022-03-01 | Match | 2022-01-13 | 2022-01-21 | Re-scrape | Match | 2022-02-19 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match | logs left on top of sampling area 11/13. Soils team met with debris crew on 12/2 to show them where to move logs and conducted sampling. | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-200-007 | 25 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-18 | 03/18/2022 | 2022-03-28 | Approved | Onsite SBs have arsenic up to 250 mg/kg and mercury up to 5.5 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Sampling occurred at G1, G2, H2 following initial review and approval on 3/8/22, but recommendations do not change. APN is already in tree removal phase. | Confirmation |  | 2022-03-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
005-043-008 | 202 | Fourth Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 |  | 2022-02-07 | Approved | DTSC successful rescrapes for mercury: A1-R1: 0.13 mg/kg A2-R1: 0.14 mg/kg | Rescrape 1 |  | 2022-05-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes for DTSC | ["Soil Passes"] | ["Soil Passes"] | Soil Passes, see Notes for DTSC | Soil Passes, see Notes for DTSC | Yes | Soil Passes, see Notes for DTSC | Soil Passes, see Notes for DTSC | 05/06/2022 | ["Soil Passes"] | Northern Division
008-300-001 | 7133 | Frenchman Boulevard | Plumas | Pending Soil Sample Results | Pending Soils Results | Re-scrape Results Rec'd from Lab | Samples Shipped | 2022-04-04 | 05/23/2022 | 2022-04-12 | Re-scrape | No nearby SBs | Rescrape 1 | 05/31/2022 |  | Match |  |  |  | Match | 2022-05-23 | 2022-06-01 |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-300-007 | 7661 | Frenchman Boulevard | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-17 | 05/17/2022 | 2022-05-25 | Approved |  | Confirmation |  | 2022-05-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
110-032-024 | 290 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/06/2021 | 2021-11-15 | Approved |  | Confirmation |  | 2021-11-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/17/2021 | ["Soil Passes"] | Northern Division
110-162-004 | 141 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 02/12/2022 | 2022-02-18 | Approved | SBs at 110-172-002 (0.06 miles) have arsenic up to 1,300 mg/kg and mercury up to 7 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
110-162-010 | 143 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-15 | 01/15/2022 | 2022-01-21 | Approved | SBs at adjacent 110-162-011 (0.02 miles) have arsenic up to 280 mg/kg, and mercury 4 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-01-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
110-171-005 | 166 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-05 | 11/19/2021 | 2021-11-15 | Re-scrape |  | Rescrape 1 |  | 2021-12-03 | Match |  |  |  | Match | 2021-11-19 | 2021-12-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
110-172-006 | 167 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-08 | Approved | SBs at 110-172-004 (0.1 miles) have arsenic up to 680 mg/kg and mercury up to 10 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-02-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
110-172-007 | 169 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 02/21/2022 | 2022-03-01 | Approved | SBs from 110-172-004 (0.04 miles) have arsenic up to 680 mg/kg and mercury up to 10 mg/kg, supporting all concentrations are likely ambient or background. | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-172-008 | 171 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved | Greenville Zone X Soil borings at nearby 110-172-002 (350 feet) have arsenic up to 1,300 mg/kg and mercury up to 13 mg/kg, supporting all results likely represent ambient or background conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-172-009 | 173 | Hot Springs Road | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved | SBs at 110-172-002 (0.05 miles) have arsenic up to 1,300 mg/kg and mercury up to 13 mg/kg. SBs at 110-162-011 (0.1 miles) have lead up to 200 mg/kg. These soil borings support that onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-172-011 | 153 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved | SBs at 110-172-002 (0.02 miles) have arsenic up to 1,300 mg/kg and mercury up to 7 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
004-280-019 | 1601 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/02/2022 | 2022-02-09 | Approved |  | Confirmation |  | 2022-02-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/11/2022 | ["Soil Passes"] | Northern Division
004-280-025 | 1654 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 12/01/2021 | 2021-11-24 | Re-scrape |  | Rescrape 1 |  | 2021-12-10 | Match |  |  |  | Match | 2021-12-01 | 2021-12-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/10/2021 | ["Soil Passes"] | Northern Division
011-253-002 | 6927 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
110-352-004 | 159 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 03/10/2022 | 2022-03-18 | Approved |  | Confirmation |  | 2022-03-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
110-352-031 | 164 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-09 | 03/25/2022 | 2022-03-17 | Re-scrape |  | Rescrape 1 |  | 2022-04-05 | Match |  |  |  | Match | 2022-03-25 | 2022-04-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
005-042-007 | 254 | Thompson Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-02 | 12/02/2021 | 2021-12-10 | Approved |  | Confirmation |  | 2021-12-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
005-042-008 | 290 | Thompson Avenue | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-120-019 | 226 | Thompson Creek Drive | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2022-05-03 |  | 2022-05-11 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-25 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
111-010-038 | 18034 | Highway 89 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
001-160-059 | 1500 | 28N77 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-26 | 05/17/2022 | 2022-04-01 | Soil Boring | Onsite SBs have arsenic up to 7 mg/kg, supporting all concentrations below likely represent ambient or background conditions. While rescrapes from four areas slightly exceed 7 mg/kg (7.1, 7.1, 7.9, and 8.1 mg/kg), those concentrations are comparable to 7 mg/kg, and additionally, the consistent concentrations above the cleanup goal for rescrape and soil boring results strongly support all the concentrations likely represent ambient or background conditions. | Soil Boring 2 |  | 2022-05-26 | Match | 2022-05-17 | 2022-05-25 | Approved | Match | 2022-05-03 | 2022-05-11 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
011-130-010 | 12476 | Chester Warner Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape 2 | Ready for Sampling | 2021-12-01 |  | 2021-12-09 | Re-scrape |  | Rescrape 2 |  |  | Match |  |  |  | Match | 2022-04-28 |  | Re-scrape | Match | 2022-05-25 |  |  | Match |  |  |  | Match | Pauline notified soils that debris left onsite is legacy on 11/30. Soils sampled 12/1 debris pile left onsite, will need to be removed before soil sampling can take place. State and planning notified 11/23/21 | [5 empty] | No |  |  |  |  | Northern Division
011-150-017 | 12508 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 | 11/22/2021 | 2021-12-02 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
108-340-004 | 108 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-340-017 | 109 | Goose Bay View Trail | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-031-015 | 221 | Kinder Avenue | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 |  | 2022-03-16 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated lead; however, nearby soil borings at 110-031-017 (180 feet) have lead up to 89 mg/kg. A PPDR limit of 89 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Revised recommendation per CalOES direction | Rescrape 3 |  | 2022-05-19 | Match |  |  |  | Match | 2022-04-23 | 2022-04-29 | Re-scrape | Match | 2022-05-04 | 2022-05-12 | Approved | Match |  |  |  | Match |  | Soil Passes, rescrapes currently at 6 inches, no further rescrapes per CalOES. | ["Soil Passes"] | ["Soil Passes"] | Soil Passes, rescrapes currently at 6 inches, no further rescrapes. | Soil Passes, rescrapes currently at 6 inches, no further rescrapes. | No | Soil Passes, rescrapes currently at 6 inches, no further rescrapes. | Soil Passes, rescrapes currently at 6 inches, no further rescrapes. | 05/18/2022 | ["Soil Passes"] | Northern Division
110-032-006 | 224 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-06 | 02/07/2022 | 2021-12-14 | Re-scrape | SBs at 110-019-006 (0.19 miles) have lead up to 200 mg/kg, supporting lead under those levels likely represents ambient or background conditions. | Rescrape 1 |  | 2022-02-16 | Match |  |  |  | Match | 2022-02-07 | 2022-02-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
002-510-029 | 130 | Rush Creek Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
143-070-021 | 423-695 | Scott Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-16 | 03/16/2022 | 2022-03-24 | Approved |  | Confirmation |  | 2022-03-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/25/2022 | ["Soil Passes"] | Northern Division
005-384-001 | 117 | Indian Falls Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-001 | 337 | Ranger Station Road | Trinity | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-120-033 | 341 | Red Hill Road | Trinity | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-260-071 | 1061 | Red Hill Road | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-04 | 05/19/2022 | 2022-05-12 | Re-scrape |  | Rescrape 1 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-050-028 | 5295 | Tedoc Road | Tehama | Re-scrape Needed | Outer County Rescrape Crew #1 | Soil Sample Results | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-31 | Re-scrape |  | Confirmation | 05/30/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-460-120 | 12512 | Tennant Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 03/04/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match | Visible ash was found in the corner of the B1 DU the state directed debris to clean up the ash and have the field team take a new B1 sample before rescrape took place. | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
019-470-100 | 12550 | Tennant Road | Siskiyou | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 05/17/2022 | 2022-04-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
019-680-160 | 13515 | Tennant Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/01/2022 | 2022-04-11 | Approved |  | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
097-240-014 | 643-405 | The Bund | Lassen | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-010-006 | 309 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-019-002 | 310 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-031-014 | 241 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 12/01/2021 | 2021-11-23 | Re-scrape |  | Rescrape 1 |  | 2021-12-10 | Match |  |  |  | Match | 2021-12-01 | 2021-12-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/10/2021 | ["Soil Passes"] | Northern Division
110-032-026 | 242 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 02/21/2022 | 2022-03-01 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
011-140-008 | 12836 | Chester Warner Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2022-04-29 |  | 2022-05-09 | Re-scrape | No nearby elevated arsenic | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-25 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
145-040-005 | 10226 | Dixie Valley Road | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 03/30/2022 | 2022-04-07 | Approved | SBs at 145-040-004 (0.05 miles) have arsenic up to 7.4 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
001-362-017 | 29629 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-17 | Approved |  | Confirmation |  | 2022-03-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
120-120-043 | 777 | Genesee Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-070-034 | 104 | Williams Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 04/28/2022 | 2022-02-10 | Re-scrape |  | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
004-070-038 | 124 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 03/04/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-040-018 | 128 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-09 | Approved | Greenville Zone X Onsite background soil borings do not have exceedances for arsenic, lead, or mercury; however, nearby soil borings at 110-061-013 (155 feet) have arsenic up to 82 mg/kg and lead up to 320 mg/kg; soil borings at 110-061-011 (280 feet) have mercury up to 4.5 mg/kg. A PPDR limit of 82 mg/kg for arsenic, 320 mg/kg for lead, and 4.5 mg/kg for mercury are proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-110-018_Gym | 201 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/01/2022 | 2022-04-11 | Approved |  | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-110-018_House | 201 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/01/2022 | 2022-04-11 | Approved | Greenville Zone X Soil borings at the 110-110-019 (250 feet) have lead up to 320 mg/kg. The PPDR limit, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 340 mg/kg. Concentrations below the PPDR limit likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-05-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
110-110-018_Mobilehome | 201 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved |  | 2022-04-01 |  | 2022-04-11 | Approved |  |  |  | 2022-05-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-071-014 | 536 | Main Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/07/2022 | 2022-03-14 | Approved | Greenville Zone X Soil borings at nearby 110-072-014 (200 feet) have lead up to 370 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 370 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-072-011 | 537 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved | Greenville Zone X Soil borings at adjacent 110-072-014 (20 feet) have lead up to 370 mg/kg and soil borings at nearby soil borings at 110-132-015 (630 feet) have mercury up to 2.7 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 370 mg/kg and for mercury is 2.7 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-081-004 | 618 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2022-02-10 |  | 2022-02-18 | Re-scrape | Greenville Zone X FSO SBs from 110-082-001 (450 ft) have lead up to 190 mg/kg, supporting all concentrations below this likely represent ambient or background conditions. Rescrape for those concentrations higher than 190 mg/kg. Revised recommendation per CalOES direction | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-082-002 | 619 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 02/08/2022 | 2021-12-13 | Soil Boring | Greenville Zone X FSO. Onsite soil borings have arsenic up to 300 mg/kg, supporting all arsenic concentrations are likely background or ambient concentrations. Successful rescrape for mercury. | Rescrape 1 |  | 2022-03-22 | Match | 2022-01-18 | 2022-01-26 | Re-scrape | Match | 2022-02-08 | 2022-02-16 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
011-180-010 | 11566 | Chester Warner Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample Results Rec'd from Lab | Updated to Smartsheets | 2022-05-25 | 11/02/2021 | 2021-11-10 |  |  | Confirmation |  |  | Check Soil Sample Dates |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-210-004 | 7595 | Rim Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-013 | 326 | Main Street | Plumas | Ready for Soil Sampling | Pending Soils Results |  | Ready for Sampling | [5 empty] | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | team unable to sample CalHaz material on site 04/18, 04/19 | [5 empty] | No |  |  |  |  | Northern Division
110-062-014 | 328 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 03/03/2022 | 2022-03-11 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-063-012 | 333 | Main Street | Plumas | Ready for Final Sign-off | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-29 | 04/18/2022 | 2021-12-07 | Soil Boring | Greenville Zone X Onsite soil borings have lead up to 310 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 310 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. Areas with lead greater than this concentration, in addition to other metals above cleanup goals, are recommended for rescrapes. | Rescrape 1 |  | 2022-04-27 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-18 | 2022-04-26 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/27/2022 | ["Soil Passes"] | Northern Division
110-071-011 | 542 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2022-02-25 |  | 2022-03-07 | Re-scrape | Revised rescrape per CalOES direction. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-072-009 | 543 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 04/01/2022 | 2022-02-15 | Re-scrape | Zone X rescrape recommended since lead exceedances are not widespread. Rescrape not successful, immediately adjacent APNs have SBs with elevated lead. Soil borings at nearby 110-072-008 (100 feet) have lead up to 170 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 170 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-12 | Match |  |  |  | Match | 2022-04-01 | 2022-04-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
004-350-004 | 2132 | Secluded Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 02/21/2022 | 2022-03-01 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
004-350-005 | 2363 | Secluded Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-017-006 | 401 | Second Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 03/29/2022 | 2022-02-21 | Re-scrape | Greenville Zone X | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2022-03-29 | 2022-04-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-171-004 | 160 | Hot Springs Road | Plumas | Debris Removal in Progress | Holds |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-171-015 | 162 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
110-172-005 | 163 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved | SBs from 110-172-004 (0.01 miles) have arsenic up to 680 mg/kg and mercury up to 10 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-171-014 | 164 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-26 | 01/26/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/04/2022 | ["Soil Passes"] | Northern Division
004-070-021 | 174 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 11/30/2021 | 2021-12-08 | Approved |  | Confirmation |  | 2021-12-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
004-070-027 | 234 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/24/2022 | 2022-02-17 | Re-scrape | Nearby APNs cleared for lead and doesn't have Greenville Zone X signature | Rescrape 1 |  | 2022-03-08 | Match |  |  |  | Match | 2022-02-24 | 2022-03-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
110-081-015 | 650 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/21/2022 | 2022-03-10 | Re-scrape | Greenville Zone X FSO | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-21 | 2022-03-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
110-081-021 | 654 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/04/2022 | 2022-03-01 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-090-003 | 710 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-090-004 | 712 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
110-090-005 | 716 | Main Street | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-090-010 | 718 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-11 | 03/11/2022 | 2022-03-21 | Approved |  | Confirmation |  | 2022-03-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
110-410-003 | 830 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 12/04/2021 | 2021-12-13 | Approved | SBs at 110-410-004 (0.05 miles) have cobalt up to 38 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
110-410-004 | 876 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/19/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-410-005 | 918 | Main Street | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-263-004 | 352 | Osprey Loop | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-241-004 | 7137 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-032-003 | 116 | Lake Almanor West | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-041-001 | 121 | Lake Almanor West | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-231-002 | 7285 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 04/28/2022 | 2022-04-07 | Re-scrape |  | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
007-140-018 | 324 | Snow Flake Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
110-390-006 | 589 | Snowy Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
111-030-001 | 17201 | Highway 89 | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-050-050 | 298 | Apple Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/04/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-040-012 | 204 | Mill Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 11/15/2021 | 2021-11-23 | Approved | Greenville Zone X Soil borings from nearby 110-061-015 (130 feet) has elevated lead up to 300 mg/kg. While the subject APN has an onsite soil boring lead result at 83 mg/kg, the widespread pattern of lead suggests that concentrations above 83 mg/kg may not be related to the Dixie Fire. A PPDR limit of 300 mg/kg is proposed for the subject APN based on the nearby soil sample result. The APN is recommended for Soil Passes since the highest onsite concentration is 270 mg/kg. | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 |  | Northern Division
110-040-014 | 210 | Mill Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 04/25/2022 | 2022-03-01 | Re-scrape | Greenville Zone X Nearby soil borings at 110-061-015 (180 feet) have lead up to 300 mg/kg. A PPDR limit of 300 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
110-061-005 | 213 | Mill Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 04/25/2022 | 2021-12-16 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 110 mg/kg; however, soil borings at 110-061-015 (160 feet) have lead up to 300 mg/kg. A PPDR limit of 300 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
110-131-018 | 202 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 04/26/2022 | 2022-02-18 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead at 110 mg/kg; however, nearby soil borings at 131-023-013 (150 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-05 | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
110-430-018 | 83 | Round Valley Woods Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/07/2022 | 2022-03-15 | Approved |  | Confirmation |  | 2022-03-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/17/2022 | ["Soil Passes"] | Northern Division
005-031-010 | 330 | Indian Falls Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-035-015 | 335 | Indian Falls Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-131-024 | 110 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 | 11/22/2021 | 2021-12-02 | Approved | Greenville Zone X Soil borings at 110-131-007 (100 feet) have lead up to 94 mg/kg. A PPDR limit of 94 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
001-470-013 | 1451 | Highway 36 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-13 | 05/16/2022 | 2022-04-21 | Re-scrape | Onsite SBs have cobalt up to 38 mg/kg, supporting all onsite concentrations likely represent ambient or background concentrations. | Soil Boring 1 |  | 2022-05-26 | Match | 2022-05-16 | 2022-05-24 | Approved | Match | 2022-05-03 | 2022-05-11 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
017-270-016 | 44365 | Highway 36 East | Tehama | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-05-03 | 05/03/2022 | 2022-05-11 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
017-270-017 | 44415 | Highway 36 East | Tehama | Ready for Tree Operations | Tree Only Parcels |  | Ready for Sampling | [5 empty] | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | no qualifying debris 04/02/22 | [5 empty] | No |  |  |  |  | Northern Division
017-270-021 | 44485 | Highway 36 East | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-04-29 | 05/19/2022 | 2022-05-09 | Re-scrape |  | Rescrape 1 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-131-022 | 120 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 | 04/19/2022 | 2022-03-16 | Re-scrape | Greenville Zone X Nearby background soil borings at 110-131-023 (20 feet) have elevated lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for cadmium. | Rescrape 1 |  | 2022-04-28 | Match |  |  |  | Match | 2022-04-19 | 2022-04-27 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
110-132-038 | 121 | Jessie Street | Plumas | Final Sign Off Complete | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 04/13/2022 | 2022-02-18 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 140 mg/kg; however, soil borings at 110-131-023 (165 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
002-360-003 | 18176 | Rich Bar Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-03-31 | 04/20/2022 | 2022-04-08 | Re-scrape | Onsite SBs have lead up to 250 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Successful rescrape for elevated lead. | Rescrape 1 |  | 2022-04-29 | Match |  |  |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
004-060-012 | 317 | Country Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 03/14/2022 | 2022-03-04 | Re-scrape |  | Rescrape 1 |  | 2022-03-23 | Match |  |  |  | Match | 2022-03-14 | 2022-03-22 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/23/2022 | ["Soil Passes"] | Northern Division
004-330-003 | 5301 | Diamond Mountain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-018 | 2126 | Carmen Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
009-330-023 | 310 | Frenchman Cove Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-06-01 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-025 | 379 | Frenchman Cove Road | Plumas | Ready for Debris Removal | Crew # 114 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-026 | 435 | Frenchman Cove Road | Plumas | Debris Removal in Progress | Crew # 114 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-330-027 | 524 | Frenchman Cove Road | Plumas | Ready for Debris Removal | Crew # 114 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-020-005 | 1520 | FS RD 5N09 | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-02 | 05/20/2022 | 2022-05-10 | Re-scrape |  | Rescrape 1 | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match | 2022-05-20 | 2022-05-31 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-064-008 | 429 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 04/19/2022 | 2021-12-08 | Soil Boring | Greenville Zone X Onsite soil borings do not have elevated lead; however, soil borings on adjacent 110-064-013 (100 feet) have lead up to 630 mg/kg. A PPDR limit of 630 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Areas with lead greater than this concentration, in addition to other metals above cleanup goals, were recommended for rescrapes. | Rescrape 1 |  | 2022-04-28 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-19 | 2022-04-27 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
110-064-010 | 441 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-10 | 01/25/2022 | 2021-11-18 | Approved | Greenville Zone X Soil borings on adjacent 110-064-013 (100 feet) have lead up to 630 mg/kg. A PPDR limit of 630 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-12 | Match |  |  |  | Match | 2022-01-25 | 2022-02-03 |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-072-019 | 503 | Main Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 05/16/2022 | 2021-11-29 | Re-scrape | Greenville Zone X Onsite background soil borings have lead up to 180 mg/kg; however, background soil borings at 110-072-014 (230 feet) have lead up to 370 mg/kg. The PPDR limit for lead at this property is 370 mg/kg. SBs at 110-132-015 (670 feet) have mercury up to 2.7 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-05-26 | Match |  |  |  | Match | 2022-05-16 | 2022-05-24 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
110-071-012 | 546 | Main Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-09 | Approved | Greenville Zone X Soil borings from nearby 110-061-015 (300 feet) has elevated lead up to 370 mg/kg. While onsite soil borings do not have elevated lead results, the widespread pattern of lead in the confirmation samples suggests that concentrations less than 370 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 370 mg/kg is proposed for the subject APN based on nearby soil boring sample results. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-072-007 | 547 | Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-081-034 | 550 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/04/2022 | 2022-03-14 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-022-008 | 252 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 02/21/2022 | 2022-03-01 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-023-004 | 255 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/19/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
110-023-016 | 265 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-29 | 11/29/2021 | 2021-12-07 | Approved |  | Confirmation |  | 2021-12-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/08/2021 | ["Soil Passes"] | Northern Division
110-032-005 | 226 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved | SBs from 110-019-006 (0.18 miles) have lead up to 200 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
011-180-007 | 11628 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/13/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-180-006 | 11650 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-11-02 | 11/02/2021 | 2021-11-10 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-180-002 | 11680 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 11/11/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-180-004 | 11700 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
011-180-001 | 11720 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-170-004 | 11750 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/09/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-170-003 | 11778 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-22 | 11/22/2021 | 2021-12-02 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-170-002 | 11812 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
011-170-001 | 11926 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-130-007 | 12425 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-05 | 11/20/2021 | 2021-11-15 | Re-scrape |  | Rescrape 1 |  | 2021-12-01 | Match |  |  |  | Match | 2021-11-20 | 2021-11-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
011-130-011 | 12474 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 11/11/2021 | 2021-11-18 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-130-018 | 13215 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-130-022 | 011-130-022 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-131-025 | 115 | Church Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-04-19 | 04/19/2022 | 2022-04-27 | Approved | Greenville Zone X Soil borings on adjacent 110-131-015 (60 feet) have lead up to 200 mg/kg. A PPDR limit of 200 mg/kg is proposed for lead for the subject APN based on soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 200 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-28 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
011-130-021 | 12646 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-140-011 | 12780 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/12/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-140-010 | 12798 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/06/2021 | 2021-11-12 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-140-009 | 12816 | Chester Warner Valley Road | Plumas | No Asbestos Detected | Crew # 103 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
012-300-003 | 140 | Fire House Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/04/2022 | 2022-03-14 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
110-019-005 | 303 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/29/2021 | 2021-11-18 | Re-scrape |  | Rescrape 1 |  | 2021-12-08 | Match |  |  |  | Match | 2021-11-29 | 2021-12-07 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/08/2021 | ["Soil Passes"] | Northern Division
110-019-006 | 305 | First Street | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 01/24/2022 | 2021-11-19 | Re-scrape | Greenville Zone X Onsite soil borings have elevated lead up to 200 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 200 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 200 mg/kg is proposed for the subject APN based on soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for arsenic. | Soil Boring 1 |  | 2022-04-08 | Match | 2022-01-24 | 2022-01-28 | Approved | Match | 2021-11-29 | 2021-12-07 | Re-scrape | Match | 2021-12-10 | 2021-12-20 | Soil Boring | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
110-019-007 | 311 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-03 | 11/03/2021 | 2021-11-11 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
110-019-008 | 313 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 02/16/2022 | 2022-02-24 | Approved |  | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
004-270-013 | 601 | Powerline Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 01/18/2022 | 2021-12-16 | Soil Boring | Onsite soil borings have arsenic up to 11 mg/kg. Confirmation soil sample results of 11 mg/kg or below are likely ambient levels and not related to fire debris. | Soil Boring 1 |  | 2022-01-27 | Match | 2022-01-18 | 2022-01-26 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil clears. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
004-270-014 | 701 | Powerline Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 03/11/2022 | 2022-03-03 | Re-scrape | SBs at 004-270-013 (0.09) have arsenic up to 11 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrape for lead. | Rescrape 1 |  | 2022-03-22 | Match |  |  |  | Match | 2022-03-11 | 2022-03-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/22/2022 | ["Soil Passes"] | Northern Division
004-350-007 | 2459 | Quail Court | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
109-150-090 | 4820 | Quarry Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 03/01/2022 | 2022-02-22 | Re-scrape |  | Rescrape 1 |  | 2022-03-11 | Match |  |  |  | Match | 2022-03-01 | 2022-03-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
110-064-022 | 128 | Church Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-01 | 05/16/2022 | 2021-12-09 | Soil Boring | Greenville Zone X Onsite Soil borings have lead up to 120 mg/kg; however, nearby soil borings at 110-064-005 (110 feet) have lead up to 200 mg/kg. A PPDR limit of 200 mg/kg is proposed for the subject APN based on nearby soil boring sample results. The widespread pattern of lead in the confirmation samples suggests that concentrations less than 200 mg/kg in this area may not be related to the Dixie Fire. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 3 |  | 2022-05-26 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-18 | 2022-04-26 | Re-scrape | Match | 2022-05-03 | 2022-05-11 | Re-scrape | Match | 2022-05-16 | 2022-05-24 | Approved | Match |  | Soil Passes PPDR limit | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
110-131-021 | 135 | Church Street | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape Results | Ready for Sampling | 2021-11-09 |  | 2021-11-16 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead up to 120 mg/kg; however, nearby soil borings at 110-064-013 (60 feet) have lead up to 630 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 630 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 630 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 2 |  |  | Match |  |  |  | Match | 2021-11-20 | 2021-11-30 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-062-036 | 300 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Re-scrape Results | Ready for Sampling | 2022-01-31 |  | 2022-02-07 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 5,300 mg/kg and mercury up to 17 mg/kg. Soil borings at 110-061-008 (100 feet) have arsenic up to 56 mg/kg. A PPDR limit of 56 for arsenic, 5,300 mg/kg for lead and a PPDR limit of 17 for mercury are proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Onsite SBs support elevated PPDR limits for arsenic, lead, and mercury. Arsenic levels in first rescrapes still much higher than onsite SBs and nearby SBs. | Rescrape 1 |  |  | Match | 2022-05-12 | 2022-05-20 | Re-scrape | Match | 2022-04-23 | 2022-04-29 | Soil Boring | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-063-017 | 303 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-04-12 | 04/26/2022 | 2022-04-20 | Re-scrape | Greenville Zone X Soil borings at nearby 110-061-011 (260 feet) have lead up to 250 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 250 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-05 | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
008-300-010 | 225 | Pioneer Way | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 03/30/2022 | 2022-04-06 | Approved |  | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
110-032-017 | 217 | Greenville Wolf Creek Road | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Re-scrape Results | Ready for Sampling | 2022-02-09 |  | 2022-02-17 | Re-scrape | Greenville Zone X Onsite and nearby soil borings do not have lead high enough to clear the soil at this property. A PPDR limit of 80 mg/kg for lead is proposed for the subject APN. There is elevated arsenic in SBs, but not up to 70. Reevaluate following second rescrape. | Rescrape 2 |  |  | Match |  |  |  | Match | 2022-04-26 | 2022-05-04 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-032-022 | 219 | Greenville Wolf Creek Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 04/27/2022 | 2022-02-21 | Re-scrape |  | Rescrape 1 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
110-032-030 | 225 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-20 | 11/20/2021 | 2021-11-30 | Approved |  | Confirmation |  | 2021-12-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
110-032-031 | 276 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-16 | Approved |  | Confirmation |  | 2021-11-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/17/2021 | ["Soil Passes"] | Northern Division
005-054-010 | 206 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-02 | 12/02/2021 | 2021-12-10 | Approved |  | Confirmation |  | 2021-12-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
110-061-018 | 218 | Main Street | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-25 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-090-008 | 708 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/21/2022 | 2022-03-10 | Re-scrape | Greenville Zone X FSO? Appears to be outside the area with widespread lead contamination. | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-21 | 2022-03-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
001-362-014 | 29615 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-03-29 | 03/29/2022 | 2022-04-06 | Approved |  | Confirmation |  | 2022-04-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
007-110-003 | 39600 | 28N01 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-16 | 05/16/2022 | 2022-05-24 | Approved |  | Confirmation |  | 2022-05-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
011-110-038 | 370 | 28N11 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-024 | 127 | Bidwell Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 03/10/2022 | 2022-03-07 | Soil Boring | Onsite SBs have cobalt up to 47 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-21 | Match | 2022-03-10 | 2022-03-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
110-190-026 | 95 | South Main Street | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-252-010 | 7021 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 11/15/2021 | 2021-11-23 | Approved |  | Confirmation |  | 2021-11-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/24/2021 | ["Soil Passes"] | Northern Division
011-252-011 | 7031 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-11 | 11/23/2021 | 2021-11-19 | Re-scrape |  | Rescrape 1 |  | 2021-12-06 | Match |  |  |  | Match | 2021-11-23 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/06/2021 | ["Soil Passes"] | Northern Division
011-254-009 | 7032 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
011-262-001 | 7044 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-03 | 11/03/2021 | 2021-11-11 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-261-001 | 7051 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-261-002 | 7065 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-262-007 | 7068 | Warner Creek Drive | Plumas | Ready for Final Sign-off | DTSC Hold | Soil Samples Approved | Updated to Smartsheets | 2022-03-26 | 04/28/2022 | 2022-04-01 | Re-scrape | SBs at 011-262-004 (0.03 miles) have arsenic up to 8.8 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Successful rescrape. | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
011-261-003 | 7091 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-261-004 | 7118 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/23/2021 | 2021-11-19 | Re-scrape |  | Rescrape 1 |  | 2021-12-06 | Match |  |  |  | Match | 2021-11-23 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/06/2021 | ["Soil Passes"] | Northern Division
011-262-005 | 7135 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/06/2021 | 2021-11-12 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-262-006 | 7171 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 04/08/2022 | 2022-04-18 | Approved | SBs at 011-262-004 (0.09 miles) have arsenic up to 8.8 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
011-281-007 | 7198 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-07 | 04/07/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
004-120-043 | 4643 | North Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-120-044 | 4749 | North Valley Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-039 | 111 | NW Ann Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 05/06/2022 | 2022-04-01 | Re-scrape | Greenville Zone X Nearby soil borings at 110-061-011 (175 feet) have lead up to 250 mg/kg. A PPDR limit of 250 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentrations likely represent ambient, background, or legacy conditions. | Rescrape 2 |  | 2022-05-17 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Re-scrape | Match | 2022-05-06 | 2022-05-16 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limit | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/17/2022 | ["Soil Passes"] | Northern Division
110-190-015 | 96 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 02/03/2022 | 2022-02-11 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
110-190-025 | 97 | South Main Street | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-200-004 | 55 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
110-200-014 | 70 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 03/15/2022 | 2022-03-08 | Re-scrape |  | Rescrape 1 |  | 2022-03-24 | Match |  |  |  | Match | 2022-03-15 | 2022-03-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
110-200-015 | 70 | South Main Street | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-670-140 | 13718 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/17/2022 | 2022-02-09 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
005-051-001 | 175 | Carroll Avenue | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-120-007 | 76 | Baugus Drive | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-25 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-370-010 | 432-575 | Bay Drive | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
004-050-047 | 1160 | Lower Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-07 | 02/11/2022 | 2021-12-15 | Soil Boring | Onsite soil borings have arsenic up to 6.1 mg/kg and cobalt up to 39 mg/kg. Soil confirmation sample results up to those levels are likely representative of ambient or background levels. | Rescrape 1 |  | 2022-02-24 | Match | 2022-01-19 | 2022-01-27 | Re-scrape | Match | 2022-02-11 | 2022-02-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-240-006 | 5814 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-032-009 | 208 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/19/2021 | 2021-11-16 | Re-scrape |  | Rescrape 1 |  | 2021-12-03 | Match |  |  |  | Match | 2021-11-19 | 2021-12-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
110-132-007 | 212 | Grand Street | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-10 | 12/07/2021 | 2021-11-18 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead up to 95 mg/kg; however, soil borings at 110-132-026 (80 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrape for lead above PPDR limits. | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2021-12-07 | 2021-12-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
011-232-009 | 7150 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/30/2021 | 2021-11-24 | Re-scrape |  | Rescrape 1 |  | 2021-12-09 | Match |  |  |  | Match | 2021-11-30 | 2021-12-08 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/09/2021 | ["Soil Passes"] | Northern Division
011-242-010 | 7151 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-242-011 | 7165 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-016-008 | 401 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 | 12/09/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
110-016-009 | 405 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
110-016-011 | 413 | First Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
110-019-004 | 203 | Landon Avenue | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 05/12/2022 | 2021-12-17 | Re-scrape | Greenville Zone X Onsite soil borings have lead up to 120 mg/kg; however, soil borings at 110-019-006 (100 feet) have lead up to 200 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 200 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 200 mg/kg is proposed for the subject APN based on soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Mercury exceedances rescraped twice to a total depth of 6 - 9 inches below the debris, supporting all remaining concentrations likely represent ambient, legacy, or background conditions. | Soil Boring 2 |  | 2022-05-24 | Match | 2022-05-12 | 2022-05-20 | Approved | Match | 2022-01-27 | 2022-02-03 | Soil Boring | Match | 2022-04-18 | 2022-04-26 | Soil Boring | Match |  |  |  | Match |  | Soil Passes PPDR limit for lead, mercury stops after second rescrape. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
111-150-006 | 115 | Dixie Canyon Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-030-012 | 23333 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-10 | 03/10/2022 | 2022-03-18 | Approved | Onsite SBs have cobalt up to 29 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
015-080-019 | 41500 | Highway 36 East | Tehama | ROE Received | Eligibility Determination |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-280-013 | 44505 | Highway 36 East | Tehama | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
017-280-014 | 44525 | Highway 36 East | Tehama | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-26 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-280-033 | 44525 | Highway 36 East | Tehama | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-26 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-280-037 | 44570 | Highway 36 East | Tehama | Debris Removal in Progress | Crew # 302 (Tehama) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-290-007 | 44801 | Highway 36 East | Tehama | Returned to County | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | tree only | [5 empty] | No |  |  |  |  | Northern Division
017-310-031 | 45115 | Highway 36 East | Tehama | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/01/2022 | 2022-04-11 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-370-004 | 18815 | Highway 89 | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2021-12-07 |  | 2021-12-15 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-060-013 | 309 | Country Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
111-290-002 | 1583 | Forgay Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 03/03/2022 | 2022-02-25 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
141-130-002 | 435-345 | Diana Drive | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-15 | 01/15/2022 | 2022-01-21 | Approved |  | Confirmation |  | 2022-01-26 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
005-150-030 | 37337 | Roundhouse Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-03-26 | 03/26/2022 | 2022-04-01 | Approved |  | Confirmation |  | 2022-04-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | H/O placed RV in debris footprint M1 03/11 Team sampled 03/26 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
110-330-005 | 555 | Crescent Street | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Boring | Samples Shipped | 2022-05-18 | 05/18/2022 | 2022-05-26 | Soil Boring |  | Confirmation | 05/26/2022 |  | Match | 2022-05-31 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-360-013 | 632 | Crescent Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 | 03/26/2022 | 2022-03-16 | Re-scrape | Nearby APNs cleared for lead and arsenic by rescrape. | Rescrape 1 |  | 2022-04-04 | Match |  |  |  | Match | 2022-03-26 | 2022-04-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
110-360-016 | 668 | Crescent Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/21/2022 | 2022-03-10 | Re-scrape |  | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-21 | 2022-03-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
110-360-017 | 680 | Crescent Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 05/12/2022 | 2022-03-11 | Soil Boring | Onsite SBs have cobalt up to 37 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Soil Boring 2 |  | 2022-05-24 | Match | 2022-05-12 | 2022-05-20 | Approved | Match | 2022-04-19 | 2022-04-27 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
110-380-001 | 690 | Crescent Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-31 | Re-scrape |  | Confirmation | 05/30/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-390-001 | 400 | Hideaway Road | Plumas | Re-scrape Needed | DTSC Hold | Soil Sample Results | Ready for Sampling | 2022-03-09 |  | 2022-03-17 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
108-320-019 | 207 | Top Of The West Drive | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-320-020 | 209 | Top Of The West Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-330-011 | 309 | Top of the West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-330-012 | 315 | Top Of The West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-330-013 | 323 | Top of the West Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-330-014 | 327 | Top Of The West Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-330-015 | 331 | Top of the West Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-050-034 | 306 | Apple Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/07/2022 | 2022-02-15 | Approved |  | Confirmation |  | 2022-02-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
004-060-009 | 323 | Country Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 12/02/2021 | 2021-11-29 | Re-scrape |  | Rescrape 1 |  | 2021-12-13 | Match |  |  |  | Match | 2021-12-02 | 2021-12-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/13/2021 | ["Soil Passes"] | Northern Division
COUNTY ROAD 324_001 | NO ADDRESS | County Rd 324 | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-023-005 | 251 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 12/10/2021 | 2021-12-16 | Approved |  | Confirmation |  | 2021-12-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/17/2021 | ["Soil Passes"] | Northern Division
110-064-005 | 419 | Main Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 04/26/2022 | 2021-12-16 | Soil Boring | Greenville Zone X Onsite soil borings have lead up to 200 mg/kg; however, soil borings at 110-063-007 (375 feet) have lead at 380 mg/kg and 110-063-013 (320 feet) have mercury at 3.4 mg/kg. The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 380 mg/kg, and the PPDR limit for mercury is 3.4 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 2 |  | 2022-05-05 | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2022-04-12 | 2022-04-20 | Re-scrape | Match | 2022-04-26 | 2022-05-04 | Approved | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/05/2022 | ["Soil Passes"] | Northern Division
110-064-021 | 423 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-09 | Approved |  | Confirmation |  | 2022-02-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/10/2022 | ["Soil Passes"] | Northern Division
002-050-008 | 002-050-008 | Humbug Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-260-038 | 141 | Hummingbird Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
012-260-061 | 221 | Hummingbird Road | Trinity | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-380-013 | 19069 | Humphrey Circle | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 04/04/2022 | 2022-03-30 | Soil Boring | Onsite SBs have cobalt up to 44 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-13 | Match | 2022-04-04 | 2022-04-12 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-380-018 | 19159 | Humphrey Circle | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-08 | 05/02/2022 | 2022-04-18 | Re-scrape | SBs at 110-380-013 (0.09 miles) have cobalt up to 44 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrapes for antimony and lead. | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
011-243-001 | 7136 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-131-017 | 206 | Jessie Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 04/27/2022 | 2022-02-16 | Re-scrape | Greenville Zone X Nearby soil borings at 110-131-012 (180 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-06 | Match |  |  |  | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
129-300-090 | 714-300 | Hicks Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
001-470-010_01 | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
001-470-010_02 | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
001-470-010_03 | 1487 | County Road 324 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-470-010_13 | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
001-470-010_15 | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/05/2022 | 2022-04-13 | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
001-470-010_House | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
001-470-010_shop | 1487 | County Road 324 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
001-470-010_storage1 | 1487 | County Road 324 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/04/2022 | 2022-04-12 | Approved |  | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
001-470-010_storage2 | 1487 | County Road 324 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-04 | 04/29/2022 | 2022-04-12 | Re-scrape |  | Rescrape 1 |  | 2022-05-10 | Match |  |  |  | Match | 2022-04-29 | 2022-05-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
001-470-010 | 1487 | County Road 324 | Plumas | Ready for Tree Operations | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-470-010_11 | 1487 | County Road 324 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-05-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
004-050-033 | 322 | Apple Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-09 | 03/09/2022 | 2022-03-17 | Approved |  | Confirmation |  | 2022-03-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/18/2022 | ["Soil Passes"] | Northern Division
004-050-036 | 1270 | Lower Williams Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 04/18/2022 | 2022-03-22 | Re-scrape | SBs at 004-260-003 (0.25 miles) have arsenic up to 10 mg/kg, and SBs at 004-050-047 (0.13 miles) have cobalt up to 39 mg/kg, supporting levels below likely represent ambient or background conditions. Successful rescrapes. | Rescrape 1 |  | 2022-04-27 | Match |  |  |  | Match | 2022-04-18 | 2022-04-26 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/27/2022 | ["Soil Passes"] | Northern Division
MAIN ST_001 | NO ADDRESS | Main St | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-004 | 2064 | 27N38 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-005 | 2177 | 27N38 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-008 | 2180 | 27N38 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-190-020 | 7020 | Diamond Mountain Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-120-013 | 169 | Rand Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
007-120-016 | 225 | Rand Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
007-130-020 | 498 | Rand Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-011 | 2226 | Carmen Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-05 | 05/05/2022 | 2022-05-13 | Approved |  | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
009-330-031 | 2608 | Carmen Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-120-035 | 279 | Red Hill Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-260-006 | 768 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/11/2022 | 2022-03-03 | Soil Boring |  | Confirmation |  | 2022-04-28 | Match | 2022-03-10 | 2022-03-18 | Re-scrape | Match | 2022-03-31 | 2022-04-08 | Re-scrape | Match | 2022-04-19 | 2022-04-27 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-260-006 | 768 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 04/19/2022 | 2022-03-03 | Soil Boring | Onsite SBs have arsenic up to 24 mg/kg, supporting all concentrations likely represent ambient or background conditions. Successful rescrapes for lead. | Rescrape 2 |  | 2022-04-28 | Match | 2022-03-10 | 2022-03-18 | Re-scrape | Match | 2022-03-31 | 2022-04-08 | Re-scrape | Match | 2022-04-19 | 2022-04-27 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
004-260-007 | 778 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-320-005 | 6275 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-190-021 | 6950 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-160-007 | 450 | Forgay Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/10/2022 | 2022-03-01 | Soil Boring | Onsite SBs have cobalt up to 36 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-21 | Match | 2022-03-10 | 2022-03-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
111-290-007 | 1417 | Forgay Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
110-063-011 | 341 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved | Greenville Zone X Onsite soil borings have lead up to 110 mg/kg; however, soil borings at adjacent 110-063-012 (40 feet) have lead up to 310 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is 310 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
110-072-002 | 605 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-18 | 11/18/2021 | 2021-11-30 | Approved |  | Confirmation |  | 2021-12-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
110-081-006 | 608 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 04/06/2022 | 2022-02-24 | Re-scrape |  | Rescrape 1 |  | 2022-04-15 | Match |  |  |  | Match | 2022-04-06 | 2022-04-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
110-081-007 | 612 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-03 | 11/18/2021 | 2021-11-11 | Re-scrape |  | Rescrape 1 |  | 2021-12-01 | Match |  |  |  | Match | 2021-11-18 | 2021-11-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
110-082-001 | 613 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-23 | 02/08/2022 | 2021-12-03 | Re-scrape | Greenville Zone X FSO. Onsite soil borings have arsenic up to 640 mg/kg and lead up to190 mg/kg. Arsenic and lead exceedances up to these levels are likely representative of ambient concentrations and are not fire debris related. | Rescrape 2 |  | 2022-04-04 | Match | 2022-01-18 | 2022-01-26 | Re-scrape | Match | 2021-12-09 | 2021-12-17 | Soil Boring | Match | 2022-02-08 | 2022-02-16 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
141-270-007 | 430-155 | Constantia Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 12/03/2021 | 2021-12-13 | Approved |  | Confirmation |  | 2021-12-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/14/2021 | ["Soil Passes"] | Northern Division
008-260-002 | 1831 | FS Rd 5N21 | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-04 | 05/17/2022 | 2022-05-12 | Soil Boring | Onsite SBs have cobalt up to 480 mg/kg and nickel 4,600 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-05-26 | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
011-020-015 | 3611 | FS RD 5N21 | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-29 | 05/03/2022 | 2022-04-06 | Re-scrape | Onsite SBs have nickel up to 2,600 mg/kg, supporting all concentrations likely represent ambient or background conditions. Successful rescrape for arsenic. | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
011-020-020 | 3821 | FS Rd 5N21 | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-04-06 | 05/20/2022 | 2022-04-14 | Soil Boring | Onsite SBs have arsenic up to 5.9 mg/kg and cobalt up to 200 mg/kg, supporting all concentrations below likely represent ambient or background conditions. | Rescrape 1 | 05/30/2022 | 2022-06-01 | Match | 2022-05-02 | 2022-05-10 | Re-scrape | Match | 2022-05-20 | 2022-05-31 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
002-100-009 | 5420 | Seneca Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-16 | 05/02/2022 | 2022-03-24 | Soil Boring | Onsite SBs have arsenic up to 180 mg/kg, supporting all onsite concentrations likely represent ambient or background levels. Successful rescrape for lead | Rescrape 1 |  | 2022-05-12 | Match | 2022-03-29 | 2022-04-06 | Re-scrape | Match | 2022-05-02 | 2022-05-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
002-100-010 | 5440 | Seneca Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-16 | 03/29/2022 | 2022-03-24 | Soil Boring | Onsite SBs have arsenic at 70 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-08 | Match | 2022-03-29 | 2022-04-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 | ["Soil Passes"] | Northern Division
002-100-011 | 5630 | Seneca Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 04/06/2022 | 2022-03-30 | Soil Boring | Onsite SBs have arsenic up to 110 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-04-15 | Match | 2022-04-06 | 2022-04-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
110-352-005 | 156 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 02/28/2022 | 2022-03-08 | Approved |  | Confirmation |  | 2022-03-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/10/2022 |  | Northern Division
110-352-014 | 145 | Standart Mine Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-252-008 | 6995 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
011-254-006 | 6996 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-02 | 11/02/2021 | 2021-11-10 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
001-361-009 | 29646 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-23 | 04/28/2022 | 2022-03-31 | Re-scrape |  | Rescrape 2 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-09 | 2022-04-15 | Re-scrape | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-016 | 29649 | Highway 89 | Plumas | Debris Removal in Progress | Crew # 104 ( Plumas Commercial |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-370-005 | 1852 | Upper Pecks Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/19/2022 | 2022-03-07 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-370-005 | 1852 | Upper Pecks Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-25 | 02/25/2022 | 2022-03-07 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
008-010-002 | 1000 | 26N24 | Plumas | Pending Soil Sample Results | Ready for FSO | Soil Sample | Not Ready for Sampling | 2022-05-31 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-020-009 | 970 | 27N10 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-06 | 05/17/2022 | 2022-05-13 | Soil Boring | Onsite SBs have cobalt up to 37 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-05-26 | Match | 2022-05-17 | 2022-05-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/26/2022 | ["Soil Passes"] | Northern Division
012-300-013 | 31021 | State Highway 299 | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-190-005 | 740-935 | Sugar Loaf Road | Lassen | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-190-020 | 740-935 | Sugar Loaf Road | Lassen | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-03-30 | 03/30/2022 | 2022-04-07 | Approved |  | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
001-361-010_house | 29618 | Highway 89 | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/28/2022 | 2022-04-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-361-010_storage | 29618 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-19 | 05/03/2022 | 2022-04-27 | Re-scrape |  | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
001-361-010 | 29618 | Highway 89 | Plumas | ROE Received | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
100-151-060 | 12420 | Cedar Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-22 | 02/08/2022 | 2022-01-27 | Re-scrape |  | Rescrape 1 |  | 2022-02-17 | Match |  |  |  | Match | 2022-02-08 | 2022-02-16 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
108-042-005 | 110 | Marion Trail | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-161-005 | 130 | Hot Springs Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-161-006 | 134 | Hot Springs Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-162-012 | 135 | Hot Springs Road | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-280-006 | 1030 | 25N70 | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
145-010-008 | 10548 | Dixie Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample Results Rec'd from Lab | Samples Shipped | 2022-05-23 | 05/23/2022 | 2022-06-01 |  |  | Confirmation | 05/31/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | crew cleared the incorrect parcel | [5 empty] | No |  |  |  |  | Northern Division
145-020-006 | 10569 | Dixie Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-29 | 04/29/2022 | 2022-05-09 | Approved |  | Confirmation |  | 2022-05-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
108-290-023 | 268 | Osprey Loop | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-130-015 | 741 | Thompson Creek Road | Plumas | Debris Removal in Progress | Crew # 107 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
108-320-021 | 211 | Top of the WEst | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-360-028 | 746-100 | Bear Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-25 | 03/25/2022 | 2022-04-04 | Approved |  | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
002-100-003 | 5680 | Seneca Road | Plumas | Ready for Tree Operations | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
002-100-004 | 5720 | Seneca Road | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2022-03-21 | 05/02/2022 | 2022-03-29 | Re-scrape |  | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
002-100-008 | 6201 | Seneca Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Samples Shipped | 2022-03-24 | 05/20/2022 | 2022-04-01 | Re-scrape | Evaluate for elevated bkg lead after rescrape | Rescrape 2 | 05/30/2022 | 2022-06-01 | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Re-scrape | Match | 2022-05-20 | 2022-05-31 | Approved | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-050-021 | 1185 | Pecks Valley Hilltop Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-28 | 03/15/2022 | 2022-03-08 | Soil Boring | Onsite SBs have arsenic up to 8.9 mg/kg, supporting arsenic concentrations are likely ambient or background. | Soil Boring 1 |  | 2022-03-24 | Match | 2022-03-15 | 2022-03-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
004-070-011 | 163 | Pecks Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 02/14/2022 | 2022-02-22 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-070-012 | 167 | Pecks Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 02/15/2022 | 2022-02-23 | Approved |  | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
110-390-004 | 543 | Hideaway Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
110-390-015 | 572 | Hideaway Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-16 | 04/25/2022 | 2022-03-24 | Soil Boring | Onsite SBs have arsenic at 140 mg/kg and mercury at 1.5 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Successful rescrapes for higher concentrations. | Rescrape 1 |  | 2022-05-04 | Match | 2022-04-02 | 2022-04-08 | Re-scrape | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
110-390-016 | 623 | Hideaway Lane | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-390-020 | 349 | Hideaway Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-02 | 03/02/2022 | 2022-03-10 | Approved |  | Confirmation |  | 2022-03-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
110-012-006 | 501 | Greenville Wolf Creek Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-260-010 | 1835 | Greenville Wolf Creek Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-090-003 | 0 | Highway 70 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
019-670-120 | 13722 | Willow Lane | Siskiyou | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
019-690-010 | 13830 | Willow Lane | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-06 | 01/28/2022 | 2021-12-13 | Re-scrape |  | Rescrape 1 |  | 2022-02-08 | Match |  |  |  | Match | 2022-01-28 | 2022-02-07 | Approved | Match |  |  |  | Match |  |  |  | Match | area not sampled deemed as legacy noted in the SUM 12/14/21 | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
019-690-020 | 13830 | Willow lane | Siskiyou | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 12/10/2021 | 2021-12-16 | Approved |  | Confirmation |  | 2021-12-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/17/2021 | ["Soil Passes"] | Northern Division
005-392-007 | 36125 | Highway 70 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-200-006 | 35 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 12/09/2021 | 2021-11-23 | Re-scrape | SBs from 110-200-007 (0.03 miles) have arsenic up to 250 mg/kg and mercury up to 5.5 mg/kg. Original rescrape was not necessary. APN was on hold for Greenville Zone X but released following evaluation | Rescrape 1 |  | 2021-12-22 | Match |  |  |  | Match | 2021-12-09 | 2021-12-17 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/22/2021 | ["Soil Passes"] | Northern Division
110-200-013 | 40 | South Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-10 | 02/19/2022 | 2021-11-18 | Re-scrape | SBs from 110-200-007 (0.07 miles) have arsenic up to 250 mg/kg and mercury up to 5.5 mg/kg, supporting all onsite levels likely represent ambient or background conditions. Lead cleared previously from onsite SBs at 120 mg/kg. | Rescrape 2 |  | 2022-03-01 | Match | 2022-01-13 | 2022-01-21 | Re-scrape | Match | 2021-12-08 | 2021-12-17 | Soil Boring | Match | 2022-02-19 | 2022-02-25 | Approved | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
111-010-036 | 18162 | Highway 89 | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
016-160-067 | 1151 | Drinkwater Gulch Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 03/10/2022 | 2022-02-28 | Soil Boring | Onsite SBs have arsenic up to 100 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-21 | Match | 2022-03-10 | 2022-03-18 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/21/2022 | ["Soil Passes"] | Northern Division
016-160-069 | 1291 | Drinkwater Gulch Road | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-29 | 05/14/2022 | 2022-05-09 | Soil Boring | Onsite SBs have cobalt up to 56 mg/kg, supporting all concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-05-24 | Match | 2022-05-14 | 2022-05-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
017-260-018 | 44995 | Highway 36 East | Tehama | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 12/03/2021 | 2021-12-13 | Approved |  | Confirmation |  | 2022-04-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
017-310-027 | 45065 | Highway 36 East | Tehama | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 05/03/2022 | 2022-04-14 | Re-scrape |  | Rescrape 1 |  | 2022-05-12 | Match |  |  |  | Match | 2022-05-03 | 2022-05-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
017-310-037 | 45075 | Highway 36 East | Tehama | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-056-005 | 213 | Roeder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-06 | 01/13/2022 | 2021-12-14 | Re-scrape |  | Rescrape 1 |  | 2022-01-26 | Match |  |  |  | Match | 2022-01-13 | 2022-01-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
005-150-024 | 37400 | Roundhouse Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-150-026 | 37450 | Roundhouse Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-310-002 | 1230 | Dooley Road | Plumas | Ready for Debris Removal | Crew #113 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-320-001 | 1682 | Dooley Road | Plumas | Debris Removal in Progress | Crew #113 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-320-002 | 1908 | Dooley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-06-01 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-320-003 | 2134 | Dooley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-31 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-200-052 | 743-780 | Doyle Grade Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/02/2022 | 2022-02-10 | Approved |  | Confirmation |  | 2022-02-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/11/2022 | ["Soil Passes"] | Northern Division
141-200-053 | 743-800 | Doyle Grade Road | Lassen | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-27 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-231-001 | 7303 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-232-001 | 7314 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-050-049 | 290 | Williams Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 05/07/2022 | 2021-12-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-16 | Match |  |  |  | Match | 2022-05-07 | 2022-05-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
011-150-007 | 12620 | Chester Warner Valley Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/28/2022 | 2022-04-13 | Re-scrape |  | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
110-032-003 | 230 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-23 | 11/23/2021 | 2021-12-03 | Approved |  | Confirmation |  | 2021-12-06 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/06/2021 | ["Soil Passes"] | Northern Division
110-171-013 | 174 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 01/27/2022 | 2022-02-03 | Approved | Elevated zinc (1,100 mg/kg) identified at A1. | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
110-172-010 | 175 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/12/2021 | 2021-11-18 | Approved | Soil borings collected at subject APN indicate very elevated arsenic and mercury, supporting that onsite conditions likely represent background or ambient conditions, even with the mercury concentrations slightly higher than the soil borings, since there are no other elevated metals indicating the presence of ash. Given these concentrations, the state should alert the county regarding site conditions following final sign off. | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
110-172-013 | 177 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
005-031-011 | 329 | Carroll Avenue | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-390-013 | 285 | Cedar Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-222-005 | 7446 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-223-002 | 7435 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-140-005 | 10575 | Beckwourth Genesee Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-061-002 | 204 | Ann Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-18 | 03/18/2022 | 2022-03-28 | Approved |  | Confirmation |  | 2022-03-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
110-061-007 | 112 | NW Ann Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Samples Shipped | 2022-05-05 | 05/21/2022 | 2022-05-13 | Re-scrape | SBs at 110-061-011 (95 ft) have lead up to 250 mg/kg, and SBs at 110-063-013 (340 ft) have mercury up to 3.4 mg/kg, supporting lead below this concentration likely represents ambient or background levels, and not associated with the Dixie Fire. The PPDR limit for lead is recommended at 250. Rescrape recommended for elevated mercury. Revised recommendations per CalOES direction | Rescrape 1 | 05/30/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-21 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-062-022 | 110-062-022 | Bidwell Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 05/06/2022 | 2022-02-17 | Re-scrape | Greenville Zone X Onsite background soil borings do not have elevated lead; however, nearby soil borings at 110-062-015 (50 feet) have lead up to 190 mg/kg. A PPDR limit of 190 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Second rescrape did not meet PPDR limit and increased concentrations support lead is not related to Dixie Fire. | Rescrape 2 |  | 2022-05-17 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Re-scrape | Match | 2022-05-06 | 2022-05-16 | Approved | Match |  |  |  | Match |  | Soil Passes, above PPDR limit after 12 inches in one location | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/17/2022 | ["Soil Passes"] | Northern Division
009-340-009 | 8000 | Mule Ear Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Samples Shipped | 2022-05-13 | 05/26/2022 | 2022-05-23 | Re-scrape |  | Rescrape 1 | 06/03/2022 |  | Match |  |  |  | Match | 2022-05-26 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
014-420-037 | 1160 | New Country Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-12 | 01/12/2022 | 2022-01-20 | Approved |  | Confirmation |  | 2022-01-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/21/2022 | ["Soil Passes"] | Northern Division
145-050-007 | 9970 | Dixie Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
008-350-017 | 2045 | Beckwourth Taylorsville Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
012-300-008 | 50 | Berry Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-02 | 12/31/2021 | 2021-12-10 | Re-scrape |  | Rescrape 1 |  | 2022-01-11 | Match |  |  |  | Match | 2021-12-31 | 2022-01-07 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/11/2022 | ["Soil Passes"] | Northern Division
012-300-009 | 58 | Berry Lane | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-20 |  | 2021-12-28 | Approved | DTSC successfully addressed mercury at G1: 0.321 mg/kg. | Rescrape 1 |  | 2022-02-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | Yes |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
004-260-003 | 990 | Lower Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-21 | 03/30/2022 | 2022-02-28 | Soil Boring | Onsite SBs have arsenic up to 10 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrapes for other exceedances. | Rescrape 1 |  | 2022-04-11 | Match | 2022-03-10 | 2022-03-18 | Re-scrape | Match | 2022-03-30 | 2022-04-07 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
005-055-012 | 200 | Third Street | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
005-382-015 | 201 | Third Street | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-154-009 | 434-900 | Third Street | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 03/24/2022 | 2022-04-01 | Approved |  | Confirmation |  | 2022-04-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
011-252-004 | 6976 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved | SBs at 011-252-003 (0.02 miles) have arsenic up to 5.5 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | snow cover 04/12 | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
011-200-005 | 10050 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-200-007 | 10208 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-200-022 | 10397 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-290-014 | 11025 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-037 | 3282 | Dixie Valley Rd | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Samples Shipped | 2022-05-13 | 05/26/2022 | 2022-05-23 | Re-scrape |  | Rescrape 1 | 06/03/2022 |  | Match |  |  |  | Match | 2022-05-26 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
145-050-008 | 9916 | Dixie Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2021-12-10 |  | 2021-12-20 | Re-scrape | No elevated arsenic in nearby APNs or SBs | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-24 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-026 | 29523 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-03 | 03/02/2022 | 2021-12-13 | Re-scrape | Nearby SBs do not indicate elevated cobalt | Rescrape 1 |  | 2022-03-11 | Match |  |  |  | Match | 2022-03-02 | 2022-03-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
108-340-010 | 116 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-340-013 | 117 | Goose Bay View Trail | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-072-028 | 320 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-29 | 11/29/2021 | 2021-12-07 | Approved | Greenville Zone X Onsite background soil borings do not have elevated lead; however, background soil borings at 110-072-014 (300 feet) have lead up to 370 mg/kg. The PPDR limit, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 370 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 |  | Northern Division
110-072-031 | 336 | Bush Street | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape Results | Ready for Sampling | 2021-11-05 |  | 2021-11-15 | Re-scrape | Greenville Zone X The subject APN has an onsite background soil borings with lead up to 99 mg/kg; however ,background soil borings at 110-132-020 (325 feet) have lead up to 440 mg/kg. The PPDR limit for this property is 440 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 2 |  |  | Match | 2022-03-25 | 2022-04-04 | Re-scrape | Match | 2021-11-23 | 2021-12-03 | Soil Boring | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-132-016 | 120 | Grand Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 04/07/2022 | 2022-03-11 | Re-scrape | Former Zone X hold. Lead recommended for rescrape because of lack of widespread exceedances. | Rescrape 1 |  | 2022-04-18 | Match |  |  |  | Match | 2022-04-07 | 2022-04-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
004-240-002 | 5942 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-09 | 12/09/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
004-320-008 | 6075 | Diamond Mountain Road | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-221-001 | 7491 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-290-011 | 11089 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-062-026 | 414 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-03-01 | 03/01/2022 | 2022-03-09 | Approved | Greenville Zone X Onsite soil borings do not have elevated lead; however, nearby soil borings at 110-062-027 (160 feet) have lead up to 200 mg/kg. A PPDR limit of 200 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-064-015 | 415 | Main Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 01/21/2022 | 2022-01-31 | Approved | Note this APN is inside of Greenville Zone X. It passes the debris screen, but likely erosion control should not be implemented. | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
110-072-026 | 310 | Bush Street | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 04/05/2022 | 2022-02-23 | Re-scrape | Greenville Zone X Lead contamination on property does not appear to be widespread. | Rescrape 1 |  | 2022-04-14 | Match |  |  |  | Match | 2022-04-05 | 2022-04-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
110-132-041 | 311 | Bush Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 04/12/2022 | 2021-11-23 | Re-scrape | Greenville Zone X Onsite background soil borings do not have elevated lead; however, soil borings at 110-132-026 (80 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR Limit, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
108-300-001 | 251 | Osprey Loop | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
108-300-022 | 252 | Osprey Loop | Plumas | Withdrawn | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-061-008 | 224 | Main Street | Plumas | Asbestos Abatement Needed | Crew #106 (Plumas) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-110-019 | 225 | Main Street | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-06-01 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
111-010-032 | 19401 | Valley View Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/12/2021 | 2021-11-18 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
004-270-004 | 628 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Updated to Smartsheets |  | 02/26/2022 |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-270-004 | 628 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-270-018 | 685 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Updated to Smartsheets |  | 03/03/2022 |  |  |  | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-270-018 | 685 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-052-005 | 340 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 01/24/2022 | 2022-01-28 |  |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
110-300-006 | 346 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 02/11/2022 | 2022-02-01 | Re-scrape | This APN is a few homes away from Greenville Zone X boundary, but there are cleared lots between it and the boundary. If rescrapes fail, then add to Zone X. Update 2/22: soil passes after rescrape | Rescrape 1 |  | 2022-02-24 | Match |  |  |  | Match | 2022-02-11 | 2022-02-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
110-300-035 | 351 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 01/21/2022 | 2022-01-31 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
110-300-038 | 370 | Hillside Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-390-007 | 521 | Hideaway Lane | Plumas | Returned to County | FSO Sent to County | Soil Sample Results | Updated to Smartsheets | 2022-02-24 | 02/24/2022 | 2022-03-04 | Approved |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | No B samples because samples belonged on APN 110-390-006. Samples were moved after they were sent to the lab. | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
011-251-003 | 6991 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/24/2021 | 2021-11-17 | Re-scrape | Received note from state that legacy fill was identified at A1, A3, B1, B2, and C1, and therefore APN recommended for soil passes. | Rescrape 1 |  | 2021-12-08 | Match |  |  |  | Match | 2021-11-24 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/07/2021 | ["Soil Passes"] | Northern Division
011-252-003 | 6996 | Chester Warner Valley Road | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-15 | 05/14/2022 | 2021-11-23 | Re-scrape | Onsite SBs through E1, E2 indicate elevated arsenic at depth up to 19 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrape for very elevated arsenic. | Soil Boring 2 |  | 2022-05-24 | Match | 2022-05-14 | 2022-05-20 | Approved | Match | 2021-11-30 | 2021-12-08 | Soil Boring | Match | 2022-04-28 | 2022-05-06 | Soil Boring | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/24/2022 | ["Soil Passes"] | Northern Division
110-032-020 | 201 | Greenville Wolf Creek Road | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 04/04/2022 | 2022-02-16 | Re-scrape | Successful rescrape for lead. Cobalt not initially identified as elevated at A1, but rescrape concentration (because of lead) of 34 mg/kg is slightly above cleanup goal of 31 mg/kg. Since 34 mg/kg at A1-R1 does not appear related to debris, the same concentration at B1-R1 is also not likely related to debris, and likely represents ambient or background conditions. | Rescrape 1 |  | 2022-04-13 | Match |  |  |  | Match | 2022-04-04 | 2022-04-12 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-040-020 | 203 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-03 | 02/03/2022 | 2022-02-11 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
110-161-010 | 148 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/13/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
110-162-009 | 149 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-04 | 01/15/2022 | 2021-12-13 | Soil Boring | SBs from 110-171-003 (0.07 miles) have arsenic up to 120 mg/kg, and onsite SBs have lead up to 130 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-01-26 | Match | 2022-01-15 | 2022-01-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/26/2022 | ["Soil Passes"] | Northern Division
110-172-012 | 151 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/07/2022 | 2022-02-15 | Approved | SBs at adjacent 110-172-002 have arsenic at 1300 mg/kg and lead at 13 mg/kg indicating the arsenic and lead exceedances are ambient or background conditions. | Confirmation |  | 2022-02-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
011-281-002 | 7266 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/06/2021 | 2021-11-12 | Approved |  | Confirmation |  | 2021-11-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/15/2021 | ["Soil Passes"] | Northern Division
011-282-005 | 7285 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
145-020-005 | 10619 | Dixie Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-29 | 04/29/2022 | 2022-05-09 | Approved |  | Confirmation |  | 2022-05-10 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
110-014-001 | 302 | Hudson Avenue | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-180-008 | 11606 | Chester Warner Valley Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
110-171-003 | 158 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-04 | 11/18/2021 | 2021-11-12 | Re-scrape | Onsite soil boring has arsenic at 120 mg/kg, supporting that all onsite arsenic concentrations likely represent ambient or background levels. | Rescrape 1 |  | 2021-12-01 | Match |  |  |  | Match | 2021-11-18 | 2021-11-30 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/01/2021 | ["Soil Passes"] | Northern Division
110-172-004 | 159 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 01/17/2022 | 2021-12-16 | Re-scrape | Onsite soil borings have arsenic up to 680 mg/kg and mercury up to 10 mg/kg. All confirmation soil sample results are lower than soil boring results and thus are likely ambient levels and not fire-debris related. | Soil Boring 1 |  | 2022-01-27 | Match | 2022-01-17 | 2022-01-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/27/2022 | ["Soil Passes"] | Northern Division
108-032-005 | 134 | Goose Bay View Trail | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-11-17 | 12/06/2021 | 2021-11-29 | Re-scrape |  | Rescrape 1 |  | 2021-12-15 | Match |  |  |  | Match |  |  | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/15/2021 | ["Soil Passes"] | Northern Division
108-350-014 | 135 | Goose Bay View Trail | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-017-002 | 409 | 2nd Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 03/01/2022 | 2022-02-24 | Re-scrape |  | Rescrape 1 |  | 2022-03-11 | Match |  |  |  | Match | 2022-03-01 | 2022-03-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
110-017-004 | 405 | Second Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-14 | 02/14/2022 | 2022-02-22 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-070-001 | 137 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-11 | 01/11/2022 | 2022-01-19 | Approved |  | Confirmation |  | 2022-01-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 01/20/2022 | ["Soil Passes"] | Northern Division
004-070-037 | 144 | Williams Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-16 | 11/16/2021 | 2021-11-24 | Approved |  | Confirmation |  | 2021-11-29 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/29/2021 | ["Soil Passes"] | Northern Division
110-120-044 | 211 | Crescent Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2021-11-06 | 11/22/2021 | 2021-11-12 | Re-scrape | Greenville Zone X Onsite background soil borings have elevated lead at 270 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 270 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 270 mg/kg is proposed for the subject APN based on soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. First rescrape reduced elevated lead concentrations. | Rescrape 1 |  | 2022-04-08 | Match |  |  |  | Match | 2021-11-22 | 2021-12-02 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/08/2022 |  | Northern Division
100-161-180 | 100-161-180 | Martin Drive | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
129-300-015 | 459-400 | McClay Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-14 | 03/14/2022 | 2022-03-22 | Approved | Sample D1 was collected in a garden and therefore deemed ineligible per the State on 4/1/22. | Confirmation |  | 2022-04-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/12/2022 | ["Soil Passes"] | Northern Division
129-300-033 | 459-725 | McClay Road | Lassen | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-071-013 | 544 | Main Street | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Ready for Sampling | 2021-12-04 |  | 2021-12-13 | Re-scrape | Greenville Zone X Soil borings at nearby 110-072-014 (230 feet) have lead up to 370 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 370 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Areas greater than this concentration, in addition to other metals above nearby soil borings, are recommended for rescrapes. Revised recommendation per CalOES direction. | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-072-010 | 545 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/07/2022 | 2022-02-15 | Approved | Greenville Zone X Background soil borings at 110-072-014 (120 feet) have lead up to 370 mg/kg. The PPDR for this property is 370 mg/kg. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
004-050-026 | 378 | Apple Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 02/16/2022 | 2022-02-24 | Approved |  | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
110-120-037 | 105 | Ayoob Aly | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 04/25/2022 | 2022-03-04 | Re-scrape | Zone X rescrape recommended since lead exceedances are not widespread. New SB results from 110-120-049 (0.03 miles) have arsenic up to 110 mg/kg, supporting all concentrations below likely related to ambient or background conditions. | Rescrape 2 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-05 | 2022-04-13 | Re-scrape | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
145-040-010 | 10123 | Dixie Valley Road | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-04 | 05/04/2022 | 2022-05-12 | Approved | SBs at 145-040-004 (0.19 miles) have arsenic up to 7.4 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/16/2022 | ["Soil Passes"] | Northern Division
004-430-001 | 5320 | Lights Creek Lane | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-430-014 | 5366 | Lights Creek Lane | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
129-640-004 | 713-450 | Jeters Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-15 | 02/17/2022 | 2022-01-21 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
011-252-007 | 6979 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-13 | 11/23/2021 | 2021-11-19 | Re-scrape |  | Rescrape 1 |  | 2021-12-06 | Match |  |  |  | Match | 2021-11-23 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/06/2021 | ["Soil Passes"] | Northern Division
011-254-005 | 6984 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-28 | 04/28/2022 | 2022-05-06 | Approved | SBs at 011-252-003 (0.11 miles) have arsenic up to 5.5 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | snow cover 04/12 | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
108-300-023 | 250 | Osprey Loop | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-171-009 | 178 | Hot Springs Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-172-014 | 179 | Hot Springs Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/07/2022 | 2022-02-15 | Approved | SBs at nearby 110-172-002 (0.12mi) have arsenic at 1300 mg/kg and mercury at 13 mg/kg indicating the arsenic and lead exceedances are ambient or background conditions. | Confirmation |  | 2022-02-16 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/16/2022 | ["Soil Passes"] | Northern Division
011-210-006 | 7471 | Rim Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-12 | 11/12/2021 | 2021-11-19 | Approved |  | Confirmation |  | 2021-11-22 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/22/2021 | ["Soil Passes"] | Northern Division
011-210-012 | 7167 | Rim Drive | Plumas | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-210-017 | 7216 | Rim Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-06 | 04/28/2022 | 2022-04-14 | Re-scrape | SBs at 011-252-003 (0.21 miles) have arsenic up to 5.5 mg/kg, supporting all concentration lower likely represent ambient or background conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-09 | Match |  |  |  | Match | 2022-04-28 | 2022-05-06 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
011-222-001 | 7488 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-222-002 | 7462 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
011-222-007 | 7414 | Warner Creek Drive | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/09/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-223-006 | 7355 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-080-001 | 4600 | Seneca Road | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-100-012 | 4920 | Seneca Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Samples Shipped | 2022-03-23 | 05/19/2022 | 2022-03-31 | Re-scrape |  | Rescrape 2 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-02 | 2022-05-10 | Re-scrape | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-262-004 | 7090 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-11-29 | 03/15/2022 | 2021-12-07 | Soil Boring | Onsite SBs have arsenic up to 8.8 mg/kg supporting arsenic concentrations are likely ambient or background. | Soil Boring 1 |  | 2022-03-24 | Match | 2022-03-15 | 2022-03-23 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Inaccessible due to snow as of 3/10 Field team able to sample 03/15 | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/24/2022 | ["Soil Passes"] | Northern Division
011-281-006 | 7208 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-021 | 2500 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-090-022 | 2700 | 26N22 | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-360-002 | 18376 | Rich Bar Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-28 | 01/28/2022 | 2022-02-04 | Approved | SBs at 002-360-005 (0.13 miles) have lead up to 450 mg/kg, supporting all onsite levels likely represent ambient or background conditions. There are only 4 APNs in this isolated section of Hwy 70 - three have elevated lead. | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
002-360-005 | 002-360-005 | Rich Bar Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-31 | 04/20/2022 | 2022-04-08 | Re-scrape | Onsite SBs have lead up to 450 mg/kg and SBs at 002-360-003 (0.17 miles) have cobalt up to 120 mg/kg, supporting concentrations lower likely represent ambient or background conditions. Successful rescrape for elevated lead. | Rescrape 1 |  | 2022-04-29 | Match |  |  |  | Match | 2022-04-20 | 2022-04-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/29/2022 | ["Soil Passes"] | Northern Division
002-360-006 | 002-360-006 | Rich Bar Road | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-03-31 | 03/31/2022 | 2022-04-08 | Approved | SBs at 002-360-006 (0.13 miles) have lead at 450 mg/kg, supporting all concentrations higher than 450 mg/kg likely represent ambient or background conditions. SBs at 002-360-003 (0.25 miles) have cobalt up to 110 mg/kg, supporting all cobalt levels likely represent ambient or background conditions. Rescrape recommended for single elevated lead. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
004-240-007 | 5782 | Diamond Mountain Road | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-340-009 | 133 | Hideaway Lane | Plumas | Ready for Tree Operations | Tree Only Parcels |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-340-012 | 133 | Hideaway lane | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-390-017 | 467 | Hideaway Lane | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/07/2022 | 2022-03-15 | Approved |  | Confirmation |  | 2022-03-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/17/2022 | ["Soil Passes"] | Northern Division
011-231-003 | 7267 | Chester Warner Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-10 | 11/10/2021 | 2021-11-18 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
011-232-007 | 7180 | Harkness Drive | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-390-012 | 286 | Cedar Drive | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-390-014 | 339 | Cedar Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-25 | 03/25/2022 | 2022-04-04 | Approved |  | Confirmation |  | 2022-04-05 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
110-390-021 | 350 | Cedar Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/09/2021 | 2021-11-18 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
110-012-002 | 514 | First Street | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-230-025 | 434-330 | Foothill Lane | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-02 | 04/25/2022 | 2022-04-08 | Re-scrape |  | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
011-224-008 | 7303 | Warner Creek Drive | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Updated to Smartsheets | 2021-11-02 | 11/22/2021 | 2021-11-10 | Re-scrape |  | Rescrape 1 |  | 2021-12-03 | Match |  |  |  | Match | 2021-11-22 | 2021-12-02 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
005-382-004 | 33 | Hannon Avenue | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-200-015 | 13180 | 24N02 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-031-007 | 211 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 04/12/2022 | 2022-03-30 | Re-scrape | Greenville Zone X | Rescrape 1 |  | 2022-04-21 | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/21/2022 | ["Soil Passes"] | Northern Division
110-032-008 | 212 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-09 | 11/19/2021 | 2021-11-16 | Re-scrape |  | Rescrape 1 |  | 2021-12-03 | Match |  |  |  | Match | 2021-11-19 | 2021-12-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
110-032-033 | 216 | Kinder Avenue | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-08 | 12/08/2021 | 2021-12-16 | Approved |  | Confirmation |  | 2021-12-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/17/2021 | ["Soil Passes"] | Northern Division
110-061-012 | 208 | Main Street | Plumas | Debris Removal in Progress | Crew #800 (CAL HAZ LOAD OUT) |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-110-015 | 209 | Main Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 04/19/2022 | 2022-02-17 | Re-scrape | Greenville Zone X Onsite soil borings do not have elevated mercury and have lead up to 220 mg/kg; however, soil borings at 110-061-012 (100 feet) have mercury up to 4.5 mg/kg and lead up to 250 mg/kg . The PPDR limit for lead, which indicates the estimated legacy concentration of lead not associated with the Dixie Fire, for this property is 250 mg/kg and the PPDR for mercury for this property is 4.5 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. Successful rescrape for lead. | Rescrape 1 |  | 2022-04-28 | Match |  |  |  | Match | 2022-04-19 | 2022-04-27 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes PPDR limits, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
110-120-030 | 119 | Ayoob Aly | Plumas | Re-scrape Needed | DTSC Hold | Re-scrape Results | Ready for Sampling | 2022-02-15 |  | 2022-02-23 | Re-scrape | Greenville Zone X Soil borings at nearby 110-120-002 (200 feet) have lead up to 160 mg/kg. The PPDR limit, which indicates the estimated legacy concentration not associated with the Dixie Fire, for lead for this property is 160 mg/kg. Confirmation sample results below these concentrations likely represent ambient, background, or legacy conditions. Rescrape referred to DTSC for elevated mercury. | Rescrape 2 |  |  | Match |  |  |  | Match | 2022-04-12 | 2022-04-20 | Re-scrape | Match |  |  |  | Match |  |  |  | Match | [6 empty] | Yes |  |  |  |  | Northern Division
110-120-040 | 123 | Ayoob Aly | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved |  | Confirmation |  | 2021-12-20 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/20/2021 | ["Soil Passes"] | Northern Division
110-120-041 | 129 | Ayoob Aly | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-12-10 | 12/10/2021 | 2021-12-20 | Approved |  | Confirmation |  | 2021-12-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/21/2021 | ["Soil Passes"] | Northern Division
110-132-045 | 312 | Crescent Street | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2021-12-11 | 12/11/2021 | 2021-12-17 | Approved | Greenville Zone X Onsite background soil borings have lead up to 200 mg/kg; however, soil borings at 110-131-023 (250 feet) have lead up to 440 mg/kg. The widespread pattern of lead in the soil samples suggests that concentrations less than 440 mg/kg in this area may not be related to the Dixie Fire. A PPDR limit of 440 mg/kg is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results with lead below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-11 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/11/2022 | ["Soil Passes"] | Northern Division
110-390-002 | 485 | Crescent Street | Plumas | Returned to County | FSO Sent to County |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
008-400-005 | 452 | Sugarloaf Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-270-001 | 4053 | Section Old Red Bluff Road | Plumas | Ready for Soil Sampling | Plumas Completed |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
019-680-050 | 13507 | Willow Lane | Siskiyou | Ineligible | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-032-014 | 207 | Greenville Wolf Creek Road | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-18 | 02/18/2022 | 2022-02-28 | Approved | Greenville Zone X Nearby soil borings at 110-040-027 (350 feet) have lead up to 270 mg/kg. A PPDR limit of 270 mg/kg for lead is proposed for the subject APN based on nearby soil boring sample results. Confirmation sample results below this concentration likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limits. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
110-032-034 | 211 | Greenville Wolf Creek Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-09 | 02/09/2022 | 2022-02-17 | Approved |  | Confirmation |  | 2022-02-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/19/2022 | ["Soil Passes"] | Northern Division
110-230-007 | 214 | Greenville Wolf Creek Road | Plumas | Ready for Tree Operations | Erosion Control - Haz Tree | Soil Samples Approved | Updated to Smartsheets | 2022-03-24 | 04/13/2022 | 2022-04-01 | Re-scrape |  | Rescrape 1 |  | 2022-04-22 | Match |  |  |  | Match | 2022-04-13 | 2022-04-21 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/22/2022 | ["Soil Passes"] | Northern Division
011-222-014 | 7306 | Warner Creek Drive | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/23/2021 | 2021-11-17 | Re-scrape |  | Rescrape 1 |  | 2021-12-06 | Match |  |  |  | Match | 2021-11-23 | 2021-12-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/06/2021 | ["Soil Passes"] | Northern Division
011-224-007 | 7321 | Warner Creek Drive | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-08 | 11/08/2021 | 2021-11-17 | Approved |  | Confirmation |  | 2021-11-19 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 11/19/2021 | ["Soil Passes"] | Northern Division
100-122-040 | 12522 | Chalet Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-20 | 01/20/2022 | 2022-01-28 | Approved |  | Confirmation |  | 2022-02-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/01/2022 | ["Soil Passes"] | Northern Division
100-122-050 | 12522 | Chalet Road | Siskiyou | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-07 | Approved |  | Confirmation |  | 2022-02-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/08/2022 | ["Soil Passes"] | Northern Division
110-340-025 | 104 | Cheney Street | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-07 | 03/24/2022 | 2022-03-15 | Re-scrape |  | Rescrape 1 |  | 2022-04-04 | Match |  |  |  | Match | 2022-03-24 | 2022-04-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/04/2022 | ["Soil Passes"] | Northern Division
001-362-003 | 29689 | Highway 89 | Plumas | Pending Soil Sample Results | Plumas Rescrape Crew #2 | Soil Re-scrape | Ready for Sampling | 2022-05-16 |  | 2022-05-24 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-06-01 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_01 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-09 | 04/09/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
001-362-003_02 | 29689 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-09 | 04/29/2022 | 2022-04-15 | Re-scrape |  | Rescrape 1 |  | 2022-05-10 | Match |  |  |  | Match | 2022-04-29 | 2022-05-09 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/10/2022 | ["Soil Passes"] | Northern Division
001-362-003_03 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-09 | 04/09/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
001-362-003_04 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/05/2022 | 2022-04-13 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
001-362-003_05 | 29689 | Highway 89 | Plumas | Ready for Final Sign-off | Failed FSOs | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_06 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_07 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_08 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_09 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/05/2022 | 2022-04-13 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
001-362-003_10 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-05 | 04/05/2022 | 2022-04-13 | Approved |  | Confirmation |  | 2022-04-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
001-362-003_11 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_12 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_13 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_14 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_15 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_16 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_17 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_18 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_19 | 29689 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
001-362-003_20 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_21 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_22 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_23 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_24 | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_25 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_26 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_27 | 29689 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Ready for Sampling |  |  |  | Approved |  | Confirmation |  | 2022-04-30 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | approved not to sample, no qualifying debris | [5 empty] | No |  |  |  |  | Northern Division
001-362-003_28 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_29 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_30 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
001-362-003_31 | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_32 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
001-362-003_33 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-05-02 | 05/02/2022 | 2022-05-10 | Approved |  | Confirmation |  | 2022-05-12 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/12/2022 | ["Soil Passes"] | Northern Division
001-362-003_37 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_38 | 29689 | Highway 89 | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-04-30 | 04/30/2022 | 2022-05-06 | Approved |  | Confirmation |  | 2022-05-09 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/09/2022 | ["Soil Passes"] | Northern Division
001-362-003_A | 29689 | Highway 89 | Plumas | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-003_B | 29689 | Highway 89 | Plumas | Final Sign Off Complete | Ready for FSO | Soil Samples Approved | Updated to Smartsheets | 2022-04-09 | 04/09/2022 | 2022-04-15 | Approved |  | Confirmation |  | 2022-04-18 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/18/2022 | ["Soil Passes"] | Northern Division
001-362-003_C | 29689 | Highway 89 | Plumas | Ready for Final Sign-off | Ready for FSO | Soil Samples Approved | Not Ready for Sampling | [7 empty] | 2022-05-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
001-362-019 | 29563 | Highway 89 | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-18 | 12/06/2021 | 2021-11-30 | Re-scrape |  | Rescrape 1 |  | 2021-12-15 | Match |  |  |  | Match | 2021-12-06 | 2021-12-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/15/2021 | ["Soil Passes"] | Northern Division
110-063-007 | 116 | Crescent Street | Plumas | Final Sign Off Complete | FSO Complete Zone X | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-09 | Approved | Greenville Zone X Onsite soil borings have lead at 140, 380, and 1,200 mg/kg. The PPDR limit, which indicates the estimated legacy concentrations not associated with the Dixie Fire, for lead for this property is recommended at 140 mg/kg. Confirmation sample results at or below these concentrations likely represent ambient, background, or legacy conditions. | Confirmation |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil passes PPDR limit. See notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/13/2022 | ["Soil Passes"] | Northern Division
129-300-087 | 714-050 | Hicks Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-19 | 11/19/2021 | 2021-12-01 | Approved |  | Confirmation |  | 2021-12-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 12/03/2021 | ["Soil Passes"] | Northern Division
129-640-010 | 714-065 | Hicks Road | Lassen | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2021-11-30 | 02/24/2022 | 2021-12-08 | Re-scrape | Onsite SBs have arsenic up to 11 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful lead rescrape. | Soil Boring 1 |  | 2022-03-04 | Match | 2022-02-24 | 2022-03-03 | Approved | Match | 2022-01-31 | 2022-02-07 | Soil Boring | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
129-640-011 | 714-115 | Hicks Road | Lassen | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-040-007 | 107 | Greenville Wolfcreek Road | Plumas | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
110-180-008 | 320 | Greenville Park Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-080-002 | 002-080-002 | Little Seneca Road | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-26 | Re-scrape |  | Confirmation | 05/30/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-370-003 | 1523 | Lower Pecks Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-370-004 | 1617 | Lower Pecks Valley Road | Plumas | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
007-140-009 | 280 | Winter Way | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-25 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
007-140-010 | 525 | Winter Way | Plumas | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-05-23 | 05/23/2022 | 2022-05-27 | Approved |  | Confirmation | 05/31/2022 | 2022-05-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-200-028 | 432-505 | Wolfin Road | Lassen | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Ready for Sampling | 2022-05-25 |  |  |  |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
141-200-034 | 433-530 | Wolfin Road | Lassen | Pending Soil Sample Results | Pending Soils Results | Soil Re-scrape | Ready for Sampling | 2022-05-14 |  | 2022-05-20 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match | 2022-05-25 |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-281-001 | 7286 | Warner Creek Drive | Plumas | Final Sign Off Complete | Ready for FSO | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
145-040-004 | 10268 | Dixie Valley Road | Plumas | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-26 | 04/26/2022 | 2022-05-03 | Approved | Onsite SBs have arsenic up to 7.4 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-05-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
141-070-011 | 141-070-011 | Willow Drive | Lassen | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-27 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-261-006 | 7174 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
009-330-002 | 3151 | Dixie Valley Road | Plumas | Pending Soil Sample Results | Pending Soils Results | Soil Sample Results Rec'd from Lab | Samples Shipped | 2022-05-23 | 05/23/2022 | 2022-06-01 |  |  | Confirmation | 05/31/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-223-005 | 7375 | Chester Warner Valley Road | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
141-200-051 | 743-000 | Doyle Grade Road | Lassen | Pending Soil Sample Results | Pending Soils Results | Soil Sample | Not Ready for Sampling | 2022-05-31 | [7 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
009-460-003 | 460 | Grigby Creek Road | Plumas | Re-scrape Needed | Plumas Rescrape Crew #2 | Soil Sample Results | Samples Shipped | 2022-05-20 | 05/20/2022 | 2022-05-31 | Re-scrape |  | Confirmation | 05/30/2022 |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
017-290-005 | 017-290-005 | No Address | Tehama | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Samples Shipped | 2022-04-25 | 05/19/2022 | 2022-05-03 | Re-scrape |  | Rescrape 1 | 05/27/2022 | 2022-05-31 | Match |  |  |  | Match | 2022-05-19 | 2022-05-27 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
110-040-029 | 120 | Main Street | Plumas | Ready for Erosion Control | Erosion Control - Haz Tree | Soil Samples Approved | Not Ready for Sampling | 2022-04-04 |  | 2022-04-12 | Approved |  |  |  | 2022-04-13 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
011-261-005 | 7148 | Warner Creek Drive | Plumas | Final Sign Off Complete | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-282-002 | 7221 | Warner Creek Drive | Plumas | Ready for Tree Operations | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
011-282-001 | 7199 | Warner Creek Drive | Plumas | Returned to County | Tree Only Parcels | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
002-010-003 | 002-010-003 | No Address | Plumas | ROE Received | Holds | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
062-140-029 | 062-140-029 | Lakeside Way | Butte | Ready for Tree Operations | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
062-140-028 | 062-140-028 | Lakeside Way | Butte | Ready for Tree Operations | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
306-060-020 | 19937 | Little Acres Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/21/2022 | 2022-02-16 | Re-scrape | SBs at 306-060-028 (0.18 miles) have arsenic up to 47 mg/kg, supporting all onsite values likely represent ambient or background conditions. | Rescrape 1 |  | 2022-03-02 | Match |  |  |  | Match | 2022-02-21 | 2022-03-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-060-013 | 19970 | Lynn Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/04/2022 | 2022-02-14 | Approved |  | Confirmation |  | 2022-02-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
306-230-002 | 13863 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/24/2022 | 2022-02-18 | Soil Boring | Onsite SBs have arsenic up to 25 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-08 | Match | 2022-02-24 | 2022-03-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
306-220-011 | 20103 | Parocast Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 03/03/2022 | 2022-02-14 | Re-scrape |  | Rescrape 2 |  | 2022-03-15 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Re-scrape | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
306-160-045 | 13416 | Calle De Lorena | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 02/02/2022 | 2022-02-10 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-260-004 | 20952 | Dorothy Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 03/25/2022 | 2022-02-16 | Re-scrape | SB results at 306-260-001 (0.19 miles) have cobalt up to 31 mg/kg, supporting all concentrations lower likely represent ambient or background conditions. Successful rescrape for elevated cobalt and lead. | Rescrape 1 |  | 2022-04-05 | Match |  |  |  | Match | 2022-03-25 | 2022-04-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
306-240-015 | 13931 | Down Pages Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
306-230-023 | 13942 | Glorybound Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 03/23/2022 | 2022-01-28 | Re-scrape | SBs from 306-230-007 (0.21mi) have arsenic up to 100 mg/kg and cobalt up to 29 mg/kg indicating concentrations at or below are likely ambient or background. Original recommendation was to rescrape B2 only for cobalt above 29 mg/kg, which was successful. A1, A2, and A3 were subsequently rescraped and their cobalt results are above 29 mg/kg at 32 mg/kg and 36 mg/kg. SBs at 306-220-017 (0.34 miles) have cobalt up to 41 mg/kg, and although this distance is slightly further than standard PPDR limit clearances, given that the initial samples were cleared, it is most likely that the rescrape results represent ambient or background concentrations. | Rescrape 1 |  | 2022-04-01 | Match |  |  |  | Match | 2022-03-23 | 2022-03-31 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/01/2022 | ["Soil Passes"] | Northern Division
306-290-006 | 14426 | Janet Way | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/21/2022 | 2022-02-16 | Re-scrape | Onsite BKG samples cleared for Cobalt | Rescrape 1 |  | 2022-03-02 | Match |  |  |  | Match | 2022-02-21 | 2022-03-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-210-013 | 13980 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-01 | 02/01/2022 | 2022-02-08 | Approved |  | Confirmation |  | 2022-02-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
306-330-066 | 13905 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-26 | 02/17/2022 | 2022-02-03 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-060-010 | 19852/19848 | Little Acres Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-02 | 03/03/2022 | 2022-02-10 | Re-scrape | SBs from 306-060-028 (0.17 miles) have arsenic up to 47 mg/kg, supporting all onsite concentrations below likely represent ambient or background conditions. Successful rescrapes for higher concentrations. | Rescrape 1 |  | 2022-03-16 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/16/2022 | ["Soil Passes"] | Northern Division
306-220-023 | 13839 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-07 | Approved |  | Confirmation |  | 2022-02-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
306-230-018 | 20090 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved | SBs from 306-230-007 (0.12mi) have arsenic up to 100 mg/kg indicating arsenic at C2 is background or ambient. | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
306-230-029 | 20146 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/15/2022 | ["Soil Passes"] | Northern Division
306-230-007 | 20063 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 03/02/2022 | 2022-02-07 | Soil Boring | Onsite SBs have arsenic up to 100 mg/kg and cobalt up to 29 mg/kg indicating concentrations at or below these values are likely ambient or background. Successful rescrapes. | Rescrape 1 |  | 2022-03-11 | Match | 2022-02-16 | 2022-02-24 | Re-scrape | Match | 2022-03-02 | 2022-03-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
306-230-025 | 20127 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 01/31/2022 | 2022-02-07 | Approved | SBs from 306-230-007 (0.07mi) have arsenic up to 100 mg/kg indicating concentrations at or below are likely ambient or background | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
306-270-002 | 14076 | Windfall Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 01/29/2022 | 2022-02-04 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-180-035 | 13423 | Butte Summit Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-25 | 01/25/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-180-019 | 13582 | Echo Hill Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 02/17/2022 | 2022-01-28 | Re-scrape | Onsite BKG samples have arsenic up to 440 mg/kg, supporting all confirmation samples likely represent ambient or background conditions. Rescrape was for cobalt only. | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-190-006 | 20086 | Jacrene Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | HOLD Other | 2022-02-02 | 03/02/2022 | 2022-02-09 | Re-scrape | SBs at 306-180-019 (0.22 miles) have arsenic up to 440 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. SBs at 306-060-028 (0.25 miles) have cobalt up to 43 mg/kg; E2 likely also represents ambient or background conditions. Successful rescrape for lead. | Rescrape 2 |  | 2022-03-11 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Re-scrape | Match | 2022-03-02 | 2022-03-10 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
306-210-014 | 13764 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
306-060-014 | 19980 | Lynn Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-22 | 01/22/2022 | 2022-01-31 | Approved | SBs from 306-060-028 (0.06 miles) have cobalt up to 43 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-040-026 | 13652 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 04/05/2022 | 2022-02-03 | Re-scrape | Onsite SBs have cobalt up to 36 mg/kg indicating elevated cobalt does exist within the soils. While the result from the second rescrape is 71 mg/kg, since two rescrapes have been conducted, and the levels are increasing, it is likely that the concentration likely represents ambient or background conditions. | Rescrape 2 |  | 2022-04-14 | Match | 2022-03-17 | 2022-03-25 | Re-scrape | Match | 2022-04-05 | 2022-04-13 | Soil Boring | Match | 2022-04-05 | 2022-04-13 | Approved | Match |  |  |  | Match |  | Soil Passes, see Notes. | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
306-060-028 | 13592 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-29 | 02/18/2022 | 2022-02-04 | Soil Boring | Onsite SBs have arsenic up to 47 mg/kg and cobalt up to 43 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-02 | Match | 2022-02-18 | 2022-02-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-180-010 | 13545 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 01/27/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-220-017 | 13803 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-22 | 03/17/2022 | 2022-01-31 | Re-scrape | Onsite SBs have cobalt up to 41 mg/kg, supporting cobalt exceedance is likely ambient or background. | Soil Boring 1 |  | 2022-03-28 | Match | 2022-03-17 | 2022-03-25 | Approved | Match | 2022-02-17 | 2022-02-25 | Re-scrape | Match | 2022-03-02 | 2022-03-10 | Soil Boring | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
306-180-009 | 13553 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-31 | 02/17/2022 | 2022-02-07 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-190-003 | 20077 | Parocast Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 03/04/2022 | 2022-02-16 | Soil Boring | Onsite SBs have arsenic up to 530 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrape for lead. | Rescrape 1 |  | 2022-03-15 | Match | 2022-02-22 | 2022-03-02 | Re-scrape | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
306-200-006 | 20472 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
306-040-038 | 19915 | Woodchuck Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-21 | 01/21/2022 | 2022-01-31 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-510-001 | 13926 | Bear Cub Court | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 03/22/2022 | 2022-02-03 | Re-scrape | Onsite SBs have cobalt up to 26 mg/kg, supporting onsite concentrations likely represent ambient or background conditions. Successful rescrape for arsenic. | Soil Boring 1 |  | 2022-03-31 | Match | 2022-03-22 | 2022-03-30 | Approved | Match | 2022-02-17 | 2022-02-25 | Re-scrape | Match | 2022-03-07 | 2022-03-15 | Soil Boring | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
306-240-009 | 13961 | Blue Ridge Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 03/04/2022 | 2022-01-28 | Soil Boring | Onsite SBs have arsenic up to 59 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrapes for lead. | Rescrape 1 |  | 2022-03-15 | Match | 2022-02-18 | 2022-02-28 | Re-scrape | Match | 2022-03-04 | 2022-03-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
306-260-007 | 14378 | Christian Way | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-24 | 01/24/2022 | 2022-01-28 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
306-270-004 | 14020 | Windfall Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-01-27 | 01/27/2022 | 2022-02-03 | Approved |  | Confirmation |  | 2022-02-14 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/14/2022 | ["Soil Passes"] | Northern Division
034-410-210 | 034-410-210 | No Address | Siskiyou | Asbestos Abatement Complete | Siskiyou Crew |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-260-007 | 2731 | Coffee Creek Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
034-410-330 | 22335 | Coffee Creek Road | Siskiyou | Chimney Tip Needed | Siskiyou Crew |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
034-410-170 | 22230 | Coffee Creek Road | Siskiyou | No Asbestos Detected | Siskiyou Crew |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-360-001 | 31 | The Cedars | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-04 | 03/04/2022 | 2022-03-14 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-270-001 | 4109 | Coffee Creek Road | Trinity | Ready for Debris Removal | Eligibility Determination |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-370-006 | 5110 | Coffee Creek Road | Trinity | Ready for Erosion Control | Erosion Control | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 05/13/2022 | 2022-03-11 | Re-scrape |  | Rescrape 3 |  | 2022-05-25 | Match | 2022-04-26 | 2022-05-04 | Re-scrape | Match | 2022-03-21 | 2022-03-29 | Re-scrape | Match | 2022-04-06 | 2022-04-14 | Soil Boring | Match | 2022-05-13 | 2022-05-23 | Approved | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/25/2022 | ["Soil Passes"] | Northern Division
004-170-022 | 341 | The Cedars | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-23 | 03/23/2022 | 2022-03-31 | Approved |  | Confirmation |  | 2022-04-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/01/2022 | ["Soil Passes"] | Northern Division
004-260-017 | 3031 | Coffee Creek Road | Trinity | Re-scrape Needed | Rescrape Needed | Soil Sample Results | Ready for State | 2022-05-24 | 05/24/2022 |  | Re-scrape |  | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Bridge property priority per IMT. Samples sent with a 3-day TAT 05/24. | Rescrape A2 |  |  |  |  | No |  |  |  |  | Northern Division
004-260-019 | 2980 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-370-007 | 5321 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-03 | 03/03/2022 | 2022-03-11 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-260-001 | 3860 | Coffee Creek Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-260-013 | 3401 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
004-280-018 | 2103 | Coffee Creek Road | Trinity | Ineligible |  |  | Updated to Smartsheets |  | 01/31/2022 |  |  | SBs at 004-280-019 (0.19 miles) have cobalt up to 55 mg/kg, supporting onsite concentrations likely represent ambient or background conditions. | Confirmation |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/09/2022 | ["Soil Passes"] | Northern Division
004-280-018 | 2103 | Coffee Creek Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-260-006 | 2830 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 02/11/2022 | 2022-02-21 | Approved |  | Confirmation |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/24/2022 | ["Soil Passes"] | Northern Division
004-260-006 | 2830 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 04/19/2022 | 2022-02-21 | Approved | Onsite SBs have arsenic up to 24 mg/kg, supporting all concentrations likely represent ambient or background conditions. Successful rescrapes for lead. | Rescrape 2 |  | 2022-02-24 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/28/2022 | ["Soil Passes"] | Northern Division
004-280-020 | 150 | Little Boulder Creek | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-380-013 | 49 | Goldfield | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
004-380-005 | 201 | Lion Lake Trail | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-08 | 03/21/2022 | 2022-03-16 | Re-scrape | Nearby APNs cleared for lead. | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-21 | 2022-03-29 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
004-380-006 | 151 | Lion Lake Trail | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 03/03/2022 | 2022-02-25 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-380-015 | 101 | Lion Lake Trail | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/19/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
004-270-018 | 3931 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-15 | 03/03/2022 | 2022-02-23 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-270-018 | 3931 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Not Ready for Sampling | 2022-02-15 |  | 2022-02-23 | Re-scrape |  |  |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-270-017 | 4101 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-270-004 | 4271 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-270-004 | 4271 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Not Ready for Sampling | 2022-02-26 |  | 2022-03-04 | Approved |  |  |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-380-012 | 61 | Goldfield | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division
004-170-007 | 411 | The Cedars | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-17 | 03/17/2022 | 2022-03-25 | Approved |  | Confirmation |  | 2022-03-28 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/28/2022 | ["Soil Passes"] | Northern Division
004-360-009 | 921 | The Cedars | Trinity | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-250-004 | 4279 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-26 | 02/26/2022 | 2022-03-04 | Approved |  | Confirmation |  | 2022-03-08 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-370-002 | 410 | Middlteton Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-11 | 04/06/2022 | 2022-03-21 | Re-scrape |  | Rescrape 1 |  | 2022-04-15 | Match |  |  |  | Match | 2022-04-06 | 2022-04-14 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/15/2022 | ["Soil Passes"] | Northern Division
004-170-025 | 320 | Middlteton Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-15 | 04/27/2022 | 2022-03-23 | Soil Boring | Onsite SBs have cobalt up to 44 mg/kg and lead up to 160 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Successful rescrapes. | Rescrape 1 |  | 2022-05-06 | Match | 2022-03-29 | 2022-04-06 | Re-scrape | Match | 2022-04-27 | 2022-05-05 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/06/2022 | ["Soil Passes"] | Northern Division
004-260-018 | 2970 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-11 | 03/18/2022 | 2022-02-21 | Re-scrape | BKG samples at 004-260-006 ( 0.17 mi) have lead up to 130 mg/kg indicating onsite lead concentrations are likely ambient or background conditions. Rescrape H1 for arsenic successful. State recommended rescraping other lead exceedance. Rescrapes successful. | Rescrape 1 |  | 2022-03-30 | Match |  |  |  | Match | 2022-03-18 | 2022-03-28 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/30/2022 | ["Soil Passes"] | Northern Division
306-240-006 | 13960 | Blue Ridge Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/21/2022 | 2022-02-15 | Re-scrape |  | Rescrape 1 |  | 2022-03-02 | Match |  |  |  | Match | 2022-02-21 | 2022-03-01 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-260-001 | 14520 | Christian Way | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-07 | 02/22/2022 | 2022-02-15 | Soil Boring | Onsite SBs have cobalt up to 31 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Soil Boring 1 |  | 2022-03-03 | Match | 2022-02-22 | 2022-03-02 | Approved | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
004-280-027 | 1850 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-270-007 | 4310 | Coffee Creek Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
004-380-010 | 4421 | Coffee Creek Road | Trinity | Ineligible |  |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
306-260-006 | 20904 | Dorothy Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/17/2022 | 2022-02-14 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
004-240-012 | 3070 | FS RD 37N19Y | Trinity | ROE Received | Access Issues |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
306-170-004 | 13548 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
306-060-018 | 19920 | Little Acres Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/17/2022 | 2022-02-14 | Re-scrape |  | Rescrape 1 |  | 2022-03-01 | Match |  |  |  | Match | 2022-02-17 | 2022-02-25 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-060-012 | 19902 | Little Acres Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-04-01 | 04/25/2022 | 2022-04-11 | Re-scrape |  | Rescrape 1 |  | 2022-05-04 | Match |  |  |  | Match | 2022-04-25 | 2022-05-03 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 05/04/2022 | ["Soil Passes"] | Northern Division
034-410-150 | 034-410-150 | no address | Siskiyou | Chimney Tip Needed | Siskiyou Crew |  | Not Ready for Sampling | [8 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | [6 empty] | No |  |  |  |  | Northern Division
307-340-007 | 14001 | Old Oregon Trail | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-16 | 03/04/2022 | 2022-02-23 | Re-scrape | Soil borings have cobalt up to 32 mg/kg, supporting all concentrations below likely represent ambient or background conditions. Successful rescrapes for other exceedances. | Rescrape 1 |  | 2022-04-14 | Match | 2022-03-18 | 2022-03-28 | Re-scrape | Match | 2022-04-05 | 2022-04-13 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/14/2022 | ["Soil Passes"] | Northern Division
306-230-013 | 13951 | Shangrila Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-04 | 02/04/2022 | 2022-02-14 | Approved | SBs at 306-230-007 (0.09mi) have arsenic up to 100 mg/kg indicating onsite arsenic concentrations are ambient or background | Confirmation |  | 2022-02-25 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/25/2022 | ["Soil Passes"] | Northern Division
306-190-020 | 20077 | Elteda Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 03/02/2022 | 2022-02-18 | Re-scrape | SBs at 306-180-019 (0.24 miles) have arsenic up to 440 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. Successful rescrapes for cobalt. | Rescrape 1 |  | 2022-03-11 | Match |  |  |  | Match | 2022-03-02 | 2022-03-10 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/11/2022 |  | Northern Division
306-240-016 | 13915 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-10 | 02/10/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
306-230-016 | 20083 | Sunrise Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved | SBs from 306-230-007 (0.04 miles) have arsenic up to 100 mg/kg, supporting all onsite levels likely represent ambient or background conditions. | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-060-024 | 19981 | Lynn Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-08 | 02/08/2022 | 2022-02-16 | Approved |  | Confirmation |  | 2022-02-17 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/17/2022 | ["Soil Passes"] | Northern Division
306-190-017 | 13697 | Old Oregon Trail | Shasta | Ineligible |  | Soil Sample Results | Ready for Sampling | 2022-02-19 |  | 2022-02-28 | Re-scrape |  | Rescrape 1 |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match | Per Kelsie, "PO refusing rescrape. Baylor and County have attempted to make comms and work with PO for 6 weeks with no response or success. Removing from program as resources are demobing from operation." 04/23/2022 |  | ["Rescrape"] | ["Rescrape"] |  |  | No |  |  |  |  | Northern Division
306-170-003 | 20245 | Oakwood Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/19/2022 | 2022-02-28 | Approved |  | Confirmation |  | 2022-03-02 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/02/2022 |  | Northern Division
306-180-036 | 20076 | Miller Butte Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-12 | 02/12/2022 | 2022-02-18 | Approved |  | Confirmation |  | 2022-02-21 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 02/21/2022 | ["Soil Passes"] | Northern Division
306-230-011 | 13895 | Shangrila Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-17 | 02/17/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/01/2022 |  | Northern Division
306-330-042 | 13777 | Peace Valley Ln | Shasta | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
306-330-058 | 13883 | Kitty Hawk Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 03/25/2022 | 2022-02-28 | Soil Boring | Onsite SBs have cobalt up to 29 mg/kg, indicating that cobalt concentrations are likely background or ambient. Successful rescrape L1 for lead. | Rescrape 1 |  | 2022-04-05 | Match | 2022-03-08 | 2022-03-16 | Re-scrape | Match | 2022-03-25 | 2022-04-04 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/05/2022 | ["Soil Passes"] | Northern Division
306-060-019 | 19929 | Little Acres Lane | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 03/03/2022 | 2022-02-28 | Re-scrape |  | Rescrape 1 |  | 2022-03-15 | Match |  |  |  | Match | 2022-03-03 | 2022-03-11 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
306-200-008 | 13765 | Margam Way | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-22 | 03/07/2022 | 2022-03-02 | Re-scrape |  | Rescrape 1 |  | 2022-03-17 | Match |  |  |  | Match | 2022-03-07 | 2022-03-15 | Approved | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/17/2022 | ["Soil Passes"] | Northern Division
306-230-015 | 13961 | Shangrila Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-22 | 02/22/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2022-03-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
306-230-030 | 20198 | Casa Drive | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-22 | 02/22/2022 | 2022-03-02 | Approved |  | Confirmation |  | 2022-03-03 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/03/2022 |  | Northern Division
306-040-039 | 19924 | Woodchuck Trl | Shasta | Ineligible | [11 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
306-190-015 | 13629 | Echo Hill Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-22 | 03/22/2022 | 2022-03-30 | Approved | SBs at 306-180-019 (0.12 miles) have arsenic up to 440 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-03-31 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/31/2022 | ["Soil Passes"] | Northern Division
306-190-002 | 20059 | Parocast Road | Shasta | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-03-23 | 03/23/2022 | 2022-03-31 | Approved | SBs at 306-190-003 (0.07 miles) have arsenic up to 530 mg/kg, and SBs at 306-040-026 (0.22 miles) have cobalt up to 36 mg/kg, supporting all onsite concentrations likely represent ambient or background conditions. | Confirmation |  | 2022-04-01 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes, see Notes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 04/01/2022 | ["Soil Passes"] | Northern Division
004-370-005 | 4950 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/19/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/15/2022 |  | Northern Division
004-370-005 | 4950 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-19 | 02/25/2022 | 2022-02-25 | Approved |  | Confirmation |  | 2022-03-15 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/08/2022 |  | Northern Division
004-280-028 | 1650 | Coffee Creek Road | Trinity | Returned to County | FSO Sent to County | [10 empty] | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match
004-380-011 | 35 | Goldfield | Trinity | Returned to County | FSO Sent to County | Soil Samples Approved | Updated to Smartsheets | 2022-02-23 | 02/23/2022 | 2022-03-03 | Approved |  | Confirmation |  | 2022-03-04 | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  |  |  | Match |  | Soil Passes | ["Soil Passes"] | ["Soil Passes"] |  |  | No |  |  | 03/04/2022 |  | Northern Division