## Sheet1
| APN_ROW Segment | ROE Type | Structural Status | Haz Tree Status | Trees Next Step | Debris Crew | Tree Crew | Street # | Street Name | Unit # | City | County | Group | Property Type | Ash Profiling Recommended | Ash Profiling Sample Date | Ash Profile Results Received | Ash Profiling Recommendation | Priority | Elevation | Withdrawal | Not Eligible | Reason for Ineligibility | Determinant for Ineligibility | Hold | Hold Reason | Safety Concern Property | USFS Parcel? | Special Inclusion | Gate Locked? | Code_Key Location | Access Issues | Access Issues Type | Phase 1 Complete | Needs Milk Run or Phase 1 Revisit | 811 Called (A&M) | Site Assessment | RAD_MERC Sweep | RAD_MERC Detected | Chimney | Chimney Inaccessible for ASB | Chimney Tipped | NESHAP Walls | NESHAP Notification | In Ground Pool | Large Propane Tank | Well | Septic | Solar_Wind Power | Structural Walls | Need Contractor Assist for ASB | Vehicle(s) | Number of Passenger Vehicles | Number of ATV_UTV_snowmobiles | Number of Ag_Commercial_Construction Equipment | Number of Motorcycles | Number of RV's | Number of Trailers | Number of Vessels (Boat_Jetski) | Total Number of Vehicles | Vehicles Description | Vehicle Adjudication Complete | Number of Vehicles Removed | Vehicle Removal Complete | Propane Tank | Propane Tank Removal | Date Propane Tank Removed | ASB Assessment | ASB Suspected | ASB Sample Sent | ASB Results Received | ASB Results | ASB Abatement | CAC Clearance | Day to Asb Abatement from Results Rec'd | Bio Assessment | Bio Monitor Needed | Arch Assessment | Arch Monitor Needed | Tribal Clearance Required | Nesting Bird Survey Date | Nesting Bird Survey Results | Buffer (Feet) | Estimated Fledge Date | RPF Survey Status | RPF Boundary Review Needed | RPF Boundary Review Date | PLS Boundary Review Needed | PLS Boundary Review Date | Boundary Review Complete | RPF Hold | WLPZ Zone? | In lieu practices? | Salmon Habitat | OES EHP Attention Required | OES EHP Site Visit | OES EHP Notes | Water crossing/bridge needed? | Water crossing/bridge install | Water crossing/bridge removal | Permit(s) Needed | Permit(s) Received | 811 Called (DDHTR) | 811 Expiration Date | Ready for Debris Removal | Property Owner Contact for Debris | Property Owner Contact for Trees | Contact Notes | If Unable to Contact, Attempted # of Contacts | If Unable to Contact, Who Approved to Move Forward | Scheduled for Debris Removal | Debris Start | Debris Re-Start | Debris Finish | State Rep Sign-Off for DR | Damage Caused during DR | Explanation of Damage during DR | Days from Debris Finish to Soil Sample | Soil Sample | Soil Sample Results Rec'd from Lab | Day(s) From Soil Sample to Results Rec'd | Soil Sample Results | Soil Boring | Soil Boring Results Rec'd from Lab | Soil Boring Results | Soil Re-scrape | Re-scrape Results Rec'd from Lab | Re-scrape Results | Soil Re-scrape 2 | Re-scrape 2 Results Rec'd from Lab | Re-scrape 2 Results | Soil Rescrape 3 | Re-scrape 3 Results Rec'd from Lab | Re-scrape 3 Results | Soil Samples Approved | Haz Trees Assessment | Haz Trees Present? | Number of Trees | Tree Felling Start | Tree Felling Re-Start | Tree Felling Complete | Tree Removal Start | Tree Removal Re-Start | Tree Removal Complete (ISW) | TISW Complete | Number of Hazard Trees Felled | Erosion Control Complete | Erosion Control Waiver | Tree FSW | Debris FSO Complete | FSO Complete | FSO Sent to County | Owner Name | Owner Phone | Owner Email | ROE Notes | Special Notes | Latitude | Longitude | Fire Name | Declaration | Parcel Zoning Type | Insurance | ROE Date | ROE Verified | Division | Modified Date | Duplicate | Tree Work Duration | Propane Tanks | RPF Re-Survey
0 | 002-190-010 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Ready for FSO | Ready for FSO | 3415 | Hot Springs Road |  | Markleeville | Alpine |  | State Park | [5 empty] | 5914.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 4 | 2 | 0 | 2 | 0 | 4 | 0 | 12 |  |  | 4 |  | Yes | Take |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-11-01 | Bio Monitoring Needed for Debris AND Trees | 2021-10-28 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [10 empty] | 2021-11-02 | 2021-11-02 | 2022-01-31 | 11.2 Contacted Representative for State Park, approved debris removal 01/28/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/31/22 SPOKE WITH JOSH HE SAID TO REMOVE PROPANE TANKS. AND HE PRE APPROVED HAZARD TREE REMOVAL. JC |  |  |  | 2021-11-04 |  | 2021-11-12 | 2021-11-12 |  |  | 3 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape | 2022-01-29 | 2022-02-07 | Approved | 2021-12-11 | 2021-12-17 | Soil Boring | [6 empty] | 2022-02-09 | 2021-12-11 | No | 0 | [8 empty] | 2022-04-06 | [5 empty] | California State Parks | (530) 694-2420 |  | Safety Concerns Vehicles Onsite | "Debris Crew Leader/Crew# Zara Armani/#101 Debris Crew WO# Refer to IAP 11/6 to 11/10 Crew 101" | 38.7013 | -119.8395 | Tamarack |  | Recreation |  | 2021-10-21 | ROE Verified | Central Division | 2022-04-08T20:24:02Z | FALSE
1 | 002-230-055 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Alpine 1 | 17300 | Highway 89 |  | Markleeville | Alpine |  | Camp |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 6056.88 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Dennis Lampson (County contact) (775) 790-0406 Clayton (Grounds Keeper) (775) 335-6129 |  |  | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 3 |  | Yes | Leave |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | POSITIVE | 2021-10-21 | 2021-10-21 | 9 | 2021-10-23 | Bio Monitoring Needed for Debris AND Trees | 2022-03-21 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-01 | Nest Building Not Removed | 75 | 2022-05-16 | Survey Needed | Yes | 2022-03-17 | Yes |  | FALSE |  | Class II | Covered under suspension | FALSE | [10 empty] | 2021-11-16 | 2021-10-26 |  | 10.26 Spoke with Dennis Lampson and he acknowledged debris removal. Please call him (775) 790-0406 and Clayton (Grounds Keeper) (775) 335-6129 prior to debris removal to unlock gate. RCV 01/28/22 SPOKE WITH DENNIS HE WILL CHECK AND CALL ME BACK ABT PROPANE TANK. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-10-28 |  | 2021-11-04 | 2021-11-04 |  |  | 4 | 2021-11-09 | 2021-11-17 | 7 | Re-scrape | 2021-12-11 | 2021-12-20 | Approved | 2021-12-01 | 2021-12-09 | Soil Boring | [6 empty] | 2021-12-21 | 2022-04-04 | Yes | 3751 | 2022-03-28 | [6 empty] | 1236 | [7 empty] | Dennis Lampson (County contact) (775) 790-0406 Clayton (Grounds Keeper) (775) 335-6129 |  |  | "Debris Crew Leader/Crew# Zara Armani/01 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 101" | 38.7224 | -119.8026 | Tamarack |  | Other |  | 2021-10-04 | ROE Verified | Central Division | 2022-04-08T18:05:53Z | FALSE
2 | 002-240-007 | Full Program ROE (debris + trees) | Final Sign Off Complete | Passed Tree Completion Check | Next Step: N/A | Punchlist | Hold | 1785 | Airport Road |  | Markleeville | Alpine |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 5910.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | No | Yes | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | NEGATIVE |  |  |  | 2021-11-10 | Bio Monitoring Needed for Trees, not Debris | 2021-10-28 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-25 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-17 | Yes | 2022-03-22 | TRUE |  | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-10-26 |  | 10.26 SPOKE TO DANIEL SAID OK .PLEASE CALL BEFORE GOING OUT. PF 12.15 SPOKE WITH DANIEL ABT TREE REMOVAL HE SAID OK. JC |  |  | 2021-10-27 | 2021-10-27 |  | 2021-10-28 | 2021-10-28 |  |  | 5 | 2021-11-03 | 2021-11-11 | 7 | Re-scrape |  |  |  | 2021-12-01 | 2021-12-09 | Approved | [6 empty] | 2021-12-10 | 2022-03-04 | Yes | 73 | 2022-03-26 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-30 | 2022-03-31 | 73 | 2022-04-06 |  | 2022-04-01 | 2022-04-07 | 2022-04-07 |  | Daniel Seamans & Linda Hill | 510-301-1140 | seamandaniel@gmail.com |  | Debris Crew Leader/Crew# Zara Armani/#101 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 101 | 38.7331 | -119.7842 | Tamarack |  | Residential | Yes | 2021-09-20 | ROE Verified | Central Division | 2022-04-07T21:57:51Z | FALSE | 2
3 | 002-411-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 605 | Pleasant Valley Road |  | Markleeville | Alpine |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 5829.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | Yes |  | 2021-10-27 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | No |  |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-28 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-17 | Yes | 2022-03-22 | TRUE |  | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-10-27 |  | 10.27 Contacted homeowner, they acknowledged chimney tip and start of debris removal RCV |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 3 | 2021-11-03 | 2021-11-11 | 7 | Re-scrape |  |  |  | 2021-12-01 | 2021-12-09 | Approved | [6 empty] | 2021-12-10 | 2021-12-08 | Yes | 17 | 2022-03-24 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-26 | 2022-03-28 | 17 | 2022-04-06 |  | 2022-04-01 | 2022-04-08 | 2022-04-08 | 2022-04-08 | Raymond and Patricia Root | 619-749-7093 | browniemom44@juno.com | Vehicles Onsite | "Debris Crew Leader/Crew# Joeseph Richmond/102 Debris Crew WO# Refer to IAP 10/30 to 11/3 Crew 102" | 38.6848 | -119.802 | Tamarack |  | Residential | Yes | 2021-09-20 | ROE Verified | Central Division | 2022-04-08T15:57:12Z | FALSE | 2
4 | 002-412-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 606 | Pleasant Valley Road |  | Markleeville | Alpine |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 5832.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-28 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-17 | Yes | 2022-03-22 | TRUE |  | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-10-26 |  | 10.26 SPOKE TO RUTH AND SHE SAID OK RCV |  |  |  | 2021-10-27 |  | 2021-10-28 | 2021-10-28 |  |  | 5 | 2021-11-03 | 2021-11-11 | 7 | Re-scrape | 2021-12-11 | 2021-12-20 | Approved | 2021-12-01 | 2021-12-09 | Soil Boring | [6 empty] | 2021-12-21 | 2021-12-08 | Yes | 19 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-28 | 2022-03-28 | 19 | 2022-04-06 |  | 2022-04-01 | 2022-04-07 | 2022-04-07 | 2022-04-07 | Samuel & Ruth Carlisle | 985-630-7003 | ruth.carlisle@gmail.com |  | Debris Crew Leader/Crew# Daniel Cobb﻿/201 Debris Crew WO# Refer to IAP 10/28 to 10/30 Crew 102 | 38.6848 | -119.801 | Tamarack |  | Residential | Yes | 2021-09-20 | ROE Verified | Central Division | 2022-04-07T20:59:02Z | FALSE | 3
5 | 004-060-004 | Full Program ROE (debris + trees) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1 | Raymond Canyon Trail |  | Markleeville | Alpine |  | Residential | [5 empty] | 6540.79 |  | 2021-12-09 | Other - see comments |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [33 empty] | FALSE | [42 empty] | Do Not Assess | [15 empty] | Virginia York | 619-866-5022 | virginiamarguerite2016@gmail.com | Access Issues Other |  | 38.6318 | -119.8137 | Tamarack |  | Residential | No | 2021-10-21 | ROE NOT Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
6 | 011-170-002 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 10833 | Riverton Lane |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3351.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2022-02-09 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [42 empty] | Ok to Assess | [15 empty] | Curtis Devera | 415-318-6522 | cdv90024@gmail.com |  |  | 40.4258 | -121.334 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
7 | 011-170-006 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 3041 | Riverton Road |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3369.98 |  | 2022-02-04 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-08 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [41 empty] | 2022-02-04 | No | 0 | [14 empty] | Gwyn Adams | 530-703-822- | gwynadams@hotmail.com |  |  | 38.775 | -120.4057 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
8 | 011-170-007 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: Processing | TREE ONLY ROEs | Tree Assessment Needed | 3051 | Riverton Road |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3676.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | [5 empty] | No | Yes | No | No | No | Yes |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | [10 empty] | 2021-12-08 | Bio Monitoring Needed for Trees, not Debris | 2022-02-09 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [42 empty] | Ok to Assess | [15 empty] | Curtis Devera | 415-318-6522 | cdv90024@gmail.com |  |  | 38.7734 | -120.4069 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
9 | 012-036-020 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road |  | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | [6 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 28 | TRUE | No | [28 empty] | FALSE | [17 empty] | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 102 | [16 empty] | 2022-02-17 | 2021-12-16 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-03-07 | 2022-03-07 | 2022-03-07 | Robert Stinson | (360) 620-1434 | rojobaan@gmail.com | Other |  | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-18 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
10 | 012-036-020_01 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 01 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-27 | 2021-10-27 | 3 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-27 | 2021-11-04 |  | 10.29 Voicemail left RCV 11.01 Voicemail left RCV﻿ 11.03 Voicemail left RCV 11.3 SPOKE WITH SHIRLEY SHE SAID OK. JC | 3 | Kendall Wilson |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-16 |  |  | 2021-12-17 | 2021-12-17 | 2022-03-07 | Shirley Mickens | (707) 350-1133 | N/A |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
11 | 012-036-020_02 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 02 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-27 | 2021-10-27 | 3 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-27 | 2021-10-29 | 2021-12-16 | 10.29 Homeowner acknowledged debris removal 12.16. SPOKE WITH KEN HE SAID OK. |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | KEN ANDERSON | 707 461-4005 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
12 | 012-036-020_03 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 3 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-28 | 2021-10-28 | 4 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-11-03 |  | 10.29 Left a voicemail 11.03 RCV Contacted homeowner, acknowledged debris removal start RCV |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape | 2022-01-07 | 2022-01-17 | Approved | 2021-11-30 | 2021-12-08 | Re-scrape | 2021-12-10 | 2021-12-20 | Soil Boring |  |  |  | 2022-01-18 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Roy Dewitt | (707) 307-2522 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-21 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
13 | 012-036-020_04 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 4 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-28 | 2021-10-28 | 4 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [10 empty] | 2021-10-28 | 2021-10-29 |  | 10.29 Contacted homeowner, acknowledged debris removal RCV |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Soil Boring | 2021-12-15 | 2021-12-23 | Re-scrape | 2021-11-30 | 2021-12-08 |  | 2022-01-06 | 2022-01-14 | Approved |  |  |  | 2022-01-17 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-03-03 | 2022-03-03 | 2022-03-07 | Martha Jane Foltz | (707) 696-1615 | martijfoltz@aol.com | Other | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
14 | 012-036-020_05 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 05 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-28 | 2021-10-28 | 4 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-11-03 |  | 11.03 Contacted overall owner of the MHP who claims ownership over the bay. Acknowledged debris removal |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-12-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
15 | 012-036-020_06 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 06 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-28 | 2021-10-28 | 4 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-28 | 2021-11-03 |  | 11.03 Contacted homeowner, acknowledged debris removal start RCV |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-16 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Emily Broaddus | (707) 621-2723 | emelita55@gmail.com | Vehicles Onsite | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
16 | 012-036-020_07 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16425 | Dam Road | 7 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-29 | 2021-10-29 | 5 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-29 | 2021-11-05 |  | 11.3 NO ANS LEFT MESS. JC 11.4 NO ANS LEFT MESS. JC 11.5 SPOKE WITH ALAIN. HE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-16 |  |  | 2021-12-18 | 2021-12-18 | 2021-12-18 | Alain/Jennifer d'Heurle | (530) 205-5089 | adheurle@msn.com | Other | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
17 | 012-036-020_08 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 8 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-27 | POSITIVE | 2021-11-01 | 2021-11-01 | 4 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-11-01 | 2021-11-04 |  | 11.4 SPOKE WITH RICHARD. HE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-16 |  |  | 2022-01-03 | 2022-01-03 | 2022-03-07 | Richard/Yolanda Maldonado | (707) 701-1146 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
18 | 012-036-020_09 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 9 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-10-30 | 2021-10-30 | 5 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-30 | 2021-11-06 |  | 11.4 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC 11.5 Sent email. JC 11.6 NO ANS LEFT VM. JC GAVE TO RICHARD IMT. | 4 | Kendall Wilson |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-16 |  |  | 2022-01-03 | 2022-01-03 | 2022-03-07 | Sandra Matli | (707) 350-3999 | sandmat5425@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
19 | 012-036-020_10 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 10 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-27 | POSITIVE | 2021-11-01 | 2021-11-01 | 4 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-01 | 2021-11-04 |  | 11.4 SPOKE WITH OWNER SAID OK. JC |  |  |  | 2021-11-04 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Dillon Family Trust | (650) 867-2504 | mottly1@yahoo.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
20 | 012-036-020_11 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 11 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-01 | 2021-11-01 | 6 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-11-01 | 2021-11-05 |  | 11.4 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM . JC 11.5 SPOKE TO THOMAS NO TANKS. OK TO PROCEED. PF |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Thomas Willis | (707) 295-1521 | willisno5@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
21 | 012-036-020_12 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 12 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-23 | 2021-10-29 |  | 10.29 Contacted homeowner, acknowledged debris removal start RCV |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Sylvan/Clare Stenge | (707) 277-0972 | cjstenge@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
22 | 012-036-020_13 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 13 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-23 | 2021-11-05 |  | 11.5 NO PHONE NUMBER ON FILE. SEND EMAIL TO HO. JC 11.5 per christie HO said okay to proceed. PF |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 5 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Brenda McCoy | 707-802-8063 | bailey.c721@yahoo.com | Other Vehicles Onsite | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
23 | 012-036-020_14 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 14 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-05 | 2021-11-05 | 10 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-05 | 2021-11-06 |  | 11.6 SPOKE WITH ROBERT HE SAID OK. JC |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Robert Stinson | 360 620-1434 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-12-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
24 | 012-036-020_15 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 15 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-23 | 2021-11-06 |  | 10.29 called, but cannot accept voice mail RCV 11.6 SPOKE WITH JAYLENE SHE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Jaylene Binstock | (707) 350-4429 | binstockjaylene@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
25 | 012-036-020_21 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 21 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [10 empty] | 2021-10-23 | 2021-10-29 |  | 10.29 Contact with homeowner, acknowledged start of debris removal RCV |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Susan Gilbert | (707) 295-2067 | sulugi849@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
26 | 012-036-020_22 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 22 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-23 | Bio Monitoring Needed for Debris AND Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-23 | 2021-11-03 |  | 11.03 Reported to be owned by the county to be owned by the MHP. Owner notified of debris removal start |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-12-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
27 | 012-036-020_23 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 23 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-02 | 2021-11-02 | 7 | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-11-02 | 2021-11-06 |  | 11.5 NO ANS. LEFT VM MESS. JC 11.6 NO ANS LEFT VM. JC 11.6 DANIEL SAID OK AND NO PROPANE TANK. PF |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2022-02-04 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-03-07 | Daniel/Cheryl Barr | (707) 295-7423 | dbatech707@gmail.com | Keep Items | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
28 | 041-290-013 | Tree Only ROE (no qualifying debris) | Site Assessment Complete |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 4800 | Sciaroni Rd |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3998.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-07 |  | FALSE | [5 empty] | No | No | No | No | No |  |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-03-09 | No Bio Monitoring Needed for Debris or Trees | 2022-03-19 | Arch Monitoring Needed for Debris AND Trees | [73 empty] | Melvin Kelley, Robin Kelley | 530-409-3671/530-317-7729 | mel-rlk-kelley@outlook.com |  |  | 38.6452 | -120.5209 | Caldor | DR-4619 | Residential | Yes | 2022-03-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
29 | 041-290-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4770 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4014.31 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 |  |  | 3 | TRUE | Yes | Leave |  | 2021-11-01 | Yes | 2021-11-02 | 2021-11-05 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-22 | 2021-11-19 | 2022-02-22 | 11.17 NO ANS LEFT VM. JC 11.19 SPOKE WITH DANIEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS VOICEMAIL FULL SENT EMAIL. JC 02/22/22 SPOKE WITH DANIEL SAID OK FOR TREE REMOVAL. BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-04 | 2021-12-13 | 6 | Soil Boring | 2022-01-17 | 2022-01-25 | Approved | [9 empty] | 2022-01-27 | 2022-01-29 | Yes | 18 | 2022-02-26 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-03 | 2022-03-04 | 18 | 2022-03-09 |  | 2022-03-06 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Daniel Lauther | 530-919-8610 | pyrography4u@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Antonio Ruiz/#816106/510 Debris Crew WO# Refer to IAP 11/24 to 12/01Crew 510 | 38.6455 | -120.52 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
30 | 041-290-015 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 4772 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4002.24 |  | 2021-11-16 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2021-11-16 | No | 0 | [14 empty] | MARK & SUSAN ALMER | 530-559-3774 | susanandmarkalmer@gmail.com |  |  | 38.6458 | -120.5205 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
31 | 041-290-021 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 041-290-021 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3993.2 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 4853 |  |  | Yes |  | TRUE | 2022-01-17 | 2022-01-17 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 7 | 1 | 0 | 1 | 3 | 7 | 1 | 20 |  |  |  |  | No |  |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | POSITIVE | 2022-01-25 | 2022-01-25 | 29 | 2022-01-14 | Bio Monitoring Needed for Debris AND Trees | 2022-02-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-19 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-11 | 2022-02-08 | 2022-03-16 |  | 02/09/22 NO ANS MAILBOX FULL SENT TEXT. JC 02/10/22 SPOKE WITH FRANKLIN HE SAID THE FAMILY NEEDS TIME TO MARK ITEMS THEY DO NOT WANT REMOVED. HE ASKED THAT DEBRIS IS PLACED ON HOLD UNTIL HE SPEAKS TO A COUNTY REP. ﻿JC 03/02/22 follow up call. No ans left vm & text. jc 03/03/22 NO ANS LEFT VM TI FOLLOW UP. JC 03/04/22 NO ANS LEFT VM. JC 03/10/22 FOLLOW UP CALL BUT NO ANS NO UNABLE TO LEAVE MESSAGE. Sent email JC 03/11/22 SPOKE WITH MICHAEL. HE WOULD LIKE TO MEET WITH SOMEONE FROM CREW. HE GAVE UPDATED CONTACT PHONE NUMBER. JC 03/16/22 HO C/B SAID OK FOR DEBRIS REMOVAL. PF |  |  |  | 2022-03-25 |  | 2022-03-31 | 2022-03-31 |  |  | 2 | 2022-04-01 |  | 6 | [14 empty] | 2022-04-01 | Yes | 32 | [14 empty] | Franklin & Michael Lucas (Candace Tyler) 530-306-7261 | 530 556-0129 | lucus672@gmail.com |  | "Debris Crew Leader/Crew# Carla Herber/ #514 Debris Crew WO# Refer to IAP 03.30 to 04.02 Crew 514 | 38.6487 | -120.5203 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
32 | 012-036-020_49 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 49 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-09 | 2021-11-09 | 12 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-11-09 | 2021-11-06 |  | 11.9 RICHARD NOTED ON SMART SHEET THAT THIS DOES NOT HAVE ROE AT THIS TIME. JC 11.6 SPOKE WITH ROBERT HE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2021-12-21 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2022-01-03 | 2022-01-03 | 2022-03-07 |  | (707) 533-9619 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-10-19 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
33 | 012-036-020_OFFICE | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | Office | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 5 | 1 | 0 | 0 | 1 | 3 | 1 | 11 |  |  |  | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-06 | 2021-11-06 | 10 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [10 empty] | 2021-11-06 | 2021-11-03 |  | 11.03 Contacted overall owner of the MHP who claims ownership over the bay. Acknowledged debris removal |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2021-12-21 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
34 | 012-036-040 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16535 | Dam Road |  | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-20 | [13 empty] | FALSE | [7 empty] | 0 |  |  | 1 | TRUE | No |  |  | 2021-10-20 | No | [6 empty] | 2021-10-23 |  | 2021-10-26 | [15 empty] | FALSE | [13 empty] | 10.25 NO ANSWER LEFT MESS |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-08 |  |  | 107 | [16 empty] | 2022-03-11 | 2021-12-16 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-04-05 | 2022-04-05 | 2022-04-05 | Andrew Burgess | (707) 485-8072 | lee@cerropacific.com |  |  | 38.9234 | -122.6037 | Cache |  | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
35 | 012-036-040_49 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16535 | Dam Road | 49 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-27 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-27 | 2021-11-05 |  | 11.5 Contacted homeowner via text message, approved start of debris removal RCV |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-04-05 |  |  |  |  | Debris Crew Leader/Crew# Carla Herbert/#201 Debris Crew WO# Refer to IAP 11/13 To 11/17 Crew 201 | 38.9234 | -122.6037 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
36 | 012-036-040_50 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16535 | Dam Road | 50 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-20 | No | [6 empty] | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-12-06 | 2021-12-16 |  | 12.07 GAVE TO RICHARD. NO CONTACT INFO NOR ROE ATTACHED. JC 12.16 TFL relayed that bay owner wanted vehicle removed RCV |  |  |  | 2021-12-17 |  | 2021-12-17 | 2021-12-17 |  |  | 2 | 2021-12-20 | 2021-12-29 | 7 | Re-scrape |  |  |  | 2022-01-06 | 2022-01-14 | Approved | [6 empty] | 2022-01-17 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-04-05 | 2022-04-05 | 2022-04-05 | [5 empty] | 38.9234 | -122.6037 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
37 | 012-036-040_51 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16535 | Dam Road | 51 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-27 | POSITIVE | 2021-11-05 | 2021-11-05 | 8 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-05 | 2021-11-05 |  | 11.5 Homeowner approved start of debris removal RCV |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Soil Boring | 2022-02-09 | 2022-02-17 | Approved | [9 empty] | 2022-03-11 | 2021-11-09 | No | 0 | [8 empty] | 2022-04-04 |  |  | 2022-04-04 | 2022-04-04 | 2022-04-05 |  |  |  |  | Debris Crew Leader/Crew# Carla Herbert/#201 Debris Crew WO# Refer to IAP 11/13 To 11/17 Crew 201 | 38.9234 | -122.6037 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-05T15:35:03Z | FALSE
38 | 012-036-040_GARAGE | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16535 | Dam Road | Garage | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-27 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [10 empty] | 2021-10-27 | 2021-11-08 |  | """11.5 Voicemail left RCV 11.6 GAVE TO RCV "" 11.8 SPOKE LEE HE SAID OK. PF" |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2022-02-04 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-18 | 2022-02-18 | 2022-04-05 |  |  |  |  | Debris Crew Leader/Crew# Carla Herbert/#201 Debris Crew WO# IAP - 11/06/21 - 11/10/21 | 38.9234 | -122.6037 | Cache |  | Residential |  | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T14:49:37Z | FALSE
39 | 012-036-080 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16475 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1375.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 3 |  |  | 2 | TRUE | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-21 | 2021-10-25 |  | 10.25 SPOKE TO JEANNE AND SHE SAID OK |  |  |  | 2021-10-27 |  | 2021-10-28 | 2021-10-28 |  |  | 7 | 2021-11-05 | 2021-11-15 | 7 | Approved | [12 empty] | 2021-11-16 | 2021-11-11 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-29 | 2021-12-29 | 2021-12-30 | Randy/Jeanne Judy | (707) 483-3068 | jeanne.judy@gmail.com | Vehicles Onsite | Debris Crew Leader/Crew# Carla Herbst﻿/201 Debris Crew WO# Refer to IAP 10/28 to 10/30 Crew 201 | 38.9238 | -122.6043 | Cache |  | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
40 | 012-036-130 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16385 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-11-02 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-21 | 2021-10-23 |  | 10.23 SPOKE TO HOME OWNER AND SHE SAID OK |  |  |  | 2021-10-26 |  | 2021-10-27 | 2021-10-27 |  |  | 7 | 2021-11-04 | 2021-11-12 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2021-12-21 | Nora J. Moore | (707) 295-6686 | gmanora1@icloud.com | Other | "Debris Crew Leader/Crew# Carla Herbst﻿/201 Debris Crew WO# Refer to IAP 10/23 to 10/27 Crew 201" | 38.9235 | -122.606 | Cache |  | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
41 | 038-101-038 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Needs Assessment | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 7284 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6614.42 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-02 | 2021-12-03 |  | 12.03 SPOKE WITH JACK HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 89 | [18 empty] | Ok to Assess | [15 empty] | JACK & DEBORAH GALE | 650 224-3482 | JACKGALE@GMAIL.COM | Septic | Debris Crew Leader/Crew# Melanie Poole /#512 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 512 | 38.8038 | -120.1068 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
42 | 038-101-041 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Needs Assessment | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 7316 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6521.18 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-11 | 2021-11-16 | FALSE | No |  |  | Yes | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-20 | 2021-11-20 | 4 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-03 | 2021-12-06 |  | 11.22 NO ANS LEFT VM. JC 12.03 NO ANS LEFT VM. JC 12.04 SPOKE WITH NANCY SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2021-12-06 |  | 2021-12-06 | 2021-12-06 |  |  | 89 | [18 empty] | Ok to Assess | [15 empty] | NANCY PEDE & DAVID GEORGE | 510-502-2356 | npede@comcast.net | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 512 | 38.804 | -120.1055 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
43 | 038-101-042 | Full Program ROE (debris + trees) | Re-scrape Needed | Needs Assessment | Next Step: N/A | ELD Twin Bridges Rescrapes | Tree Assessment Needed | 7332 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6603.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-16 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-04-13 | 2021-12-02 | 2021-12-03 |  | 12.3 SPOKE WITH JACK HE SAID OK. CREW CALLED THIS MORNING. JC 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/26/22 SPOKE WITH ROLAND HE SAID DO NOT REMOVE THE PROPANE TANK. JC |  |  |  | 2021-12-03 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Re-scrape | [14 empty] | Ok to Assess | [15 empty] | STONE ROLAND & WILLIAM | 209-303-2969 | tamarackrock@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 512 | 38.8038 | -120.105 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-02T01:15:41Z | FALSE
44 | 038-101-046 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7268 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6609.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-23 | 2021-11-23 | 6 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-23 | 2021-11-24 |  | 11.23 NO ANS LEFT VM JC 11.24 SPOKE WITH BRIAN HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-02 | 2021-12-02 |  |  | 3 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2021-12-06 | Yes | 22 | [14 empty] | SARAH & BRIAN YOST | 916-207-8158 | fosc57@hotmail.com | SEPTIC | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 512 | 38.8038 | -120.1072 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
45 | 038-101-047 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 038-101-047 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6628.96 |  | 2021-12-06 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | FALSE | [32 empty] | 2021-12-06 | Do Not Assess | 0 | [14 empty] | James & Gemma Brooks | 916-485-3082, 916-483-2146 | jim1899@yahoo.com, gemmaabrooks@yahoo.com |  |  | 38.8036 | -120.1063 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
46 | 038-101-049 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7252 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6591.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-22 | 2021-11-22 | 5 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-23 | 2021-11-24 |  | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL JC 11.24 SPOKE WITH NORMA SHE SAID OK BUT PLEASE CALL HER SON (LANCE) IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-12-07 | Yes | 41 | [14 empty] | HOMER & NORMA CARSON/ LANCE CARSON (SON) | 916 718-7772 | juballeecarson@gmail.com |  | Debris Crew Leader/Crew# Melanie Poole /#512 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 512 | 38.8037 | -120.108 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
47 | 038-101-050 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | TWB Pending | 7260 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6607.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | Yes |  | 2021-12-06 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-20 | Bio Monitoring Needed for Trees, not Debris | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-06 | 2021-12-03 |  | 12.03 SPOKE WITH SUSAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [17 empty] | 2021-12-07 | Yes | 24 | [14 empty] | SCOTT STEELE A & SUSAN | 916-212-2094 | sue6161@sbcglobal.net | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 512 | 38.8037 | -120.1076 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
48 | 038-361-005 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7069 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6545.92 |  | 2021-12-07 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | KNIGHT CHARLES & CYNTHIA | 916-213-3300 | Terryknight916@yahoo.com | Septic |  | 38.8063 | -120.1073 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
49 | 038-361-008 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7085 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6553.39 |  | 2021-12-08 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-10 | No | [6 empty] | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | Stella &Paul Kambas | 916-475-2329 | paulkambas@aol.com | Septic |  | 38.8067 | -120.1067 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
50 | 038-361-009 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7089 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6561.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 | 2021-11-16 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 | [31 empty] | 2021-12-06 | Yes | 3 | [14 empty] | DONALD & NANCY MAR | 510-845-4111 | mauimar@hotmail.com | Vehicles on site Septic |  | 38.8068 | -120.1064 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
51 | 038-361-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7097 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6562.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-19 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH VAUGHN HE SAID OK BUT PLEASE CALL IN ADVANCE. HE DOES NOT NEED TO BE THERE. HE OWNS THE PROPANE TANK BUT IS SURE IF THE TANK BURNED. JC 01/25/22 VAUGHN SAID REMOVE TANK IF DAMAGED. JC |  |  |  | 2021-11-24 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-12-07 | Yes | 4 | [14 empty] | VAUGHN & LAVERNE SHELL | 916-521-1716 | mshell224@yahoo.com |  | Debris Crew Leader/Crew# Carla Herost /#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8068 | -120.1061 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
52 | 038-361-011 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7101 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6560.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-13 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-15 | [31 empty] | 2021-12-06 | Yes | 7 | [14 empty] | JEAN TAYLOR | 908-209-4750 | taylor.jean.e@gmail.com |  |  | 38.8069 | -120.1059 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
53 | 038-361-012 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7107 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6564.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 | 2021-11-11 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-03-21 | Bio Monitoring Needed for Debris AND Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2021-12-06 | Yes | 13 | [14 empty] | Karen Almgren | 301-219-3827 | ktalmg@yahoo.com |  |  | 38.8069 | -120.1057 | Caldor | DR-4619 | Residential | No | 2021-11-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
54 | 038-361-013 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 7111 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6561.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-03-21 | Bio Monitoring Needed for Debris AND Trees | [8 empty] | Yes | [7 empty] | FALSE | [8 empty] | FALSE | [32 empty] | 2022-03-30 | Yes | 10 | [14 empty] | Karen Almgren | 301-219-3827 | ktalmg@yahoo.com |  |  | 38.8069 | -120.1055 | Caldor | DR-4619 | Residential | No | 2021-12-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
55 | 038-361-014 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7115 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6563.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | 2021-12-10 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 | [31 empty] | 2021-12-04 | Yes | 6 | [14 empty] | Karen Almgren | 301-219-3827 | ktalmg@yahoo.com |  |  | 38.8069 | -120.1053 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
56 | 041-482-019 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6862 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3991.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 4 |  |  | 3 |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-23 | POSITIVE | 2021-11-30 | 2021-11-30 | 4 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-28 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-07 | 2021-12-06 | 2022-03-15 | 12.06 SPOKE WITH JOSEPH HE SAID OK BUT PLEASE CALL IN ADVANCE. JC VENDOR HANDLING PROPANE TANK. JC 03/15/22 SPOKE WITH JOSEPH HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 38 | 2022-02-02 | 2022-02-10 | 7 | Re-scrape |  |  |  | 2022-02-17 | 2022-02-25 | Approved | [6 empty] | 2022-03-01 | 2022-01-20 | Yes | 37 | 2022-03-30 |  | 2022-03-31 | 2022-03-31 |  | 2022-04-02 | 2022-04-04 | 37 |  |  | 2022-04-05 |  |  |  | Joseph Gilmete | 510-292-5000 | joegilmete1@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Romero /#502 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 502 | 38.6438 | -120.5246 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T15:54:38Z | FALSE | 2
57 | 041-483-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7061 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3998.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 2 | 0 | 4 | 0 | 1 | 0 | 8 |  |  |  |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-11-24 | 2021-11-24 | 3 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-21 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-24 |  | 2022-03-21 | 11.24 SPOKE WITH BREANNE SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/19/22 NO ANS LEFT VM, TEXT AND EMAIL. JC 01/20/22 NO ANS LEFT VM. GAVE TO RICHARD. JC 01/21/22 per Melissa clear to proceed. JC 03/01/22 SPOKE WITH BREANNE. SHE SAID OK FOR TREE REMOVAL. JC 03/18/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/19/22 FOLLOW UP CALL NO ANS LEFT VM & SENT EMAIL. JC 3.21.22 NO ANS. LEFT MESS PF 2ND EMAIL PF 3.21 BREANNE C/B AND SAID OK PF | 2 | State Planner: Melissa Perry |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2022-01-19 | Yes | 32 | [14 empty] | Josh & Breanne Huberty | 530-409-3755 | brooklynsmommy101110@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 502 | 38.6434 | -120.5234 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
58 | 041-642-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4787 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3835.58 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | No | No | No | No |  | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 |  |  | 1 | TRUE | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-10-27 | 2021-10-27 | 6 | 2021-10-22 | Bio Monitoring Needed for Trees, not Debris | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [7 empty] | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-18 | 2021-11-17 | 2022-02-01 | 11.17 SPOKE WITH CHARLES HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE SMALL PROPANE TANKS. JC 02/01/22 SPOKE WITH CHARLES HE SAID OK. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-04 | 2021-12-10 | 5 | Re-scrape |  |  |  | 2022-01-18 | 2022-01-26 | Approved | [6 empty] | 2022-01-27 | 2022-02-12 | Yes | 43 | 2022-02-11 |  | 2022-02-12 | 2022-02-12 |  | 2022-02-17 | 2022-02-18 | 43 | 2022-03-10 |  | 2022-02-19 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Charles Sherwood | 530-499-0522 | Charlessherwood@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 509 | 38.638 | -120.5386 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 5
59 | 041-642-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4955 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 3 |  |  | 1 | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-28 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | Class III | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-18 | 2021-11-17 |  | 11.17 SPOKE WITH TROY HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2022-01-10 | Yes | 15 | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  | 2022-01-17 | 2022-01-19 | 15 | 2022-01-28 |  | 2022-01-22 | 2022-02-16 | 2022-02-16 | 2022-02-17 | Troy and Janet Gruber | 530-417-1846 | GruberJanet@att.net | Vehicles on site Septic | "Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 509 | 38.6382 | -120.5395 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
60 | 012-036-190 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16335 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | gate code: 1225 |  |  | Yes |  | TRUE | 2021-10-21 | 2021-11-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 13 | 6 | 21 |  |  | 20 | TRUE | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-26 | 2021-10-26 | 4 | 2021-10-27 | Bio Monitoring Needed for Trees, not Debris | 2021-10-26 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-27 | 2021-10-29 |  | 10.25 NO ANSWER 10.28 Left a voicemail and text message RCV 10.29 SPOKE TO MATT HE SAID OK BUT CALL FIRST PLEASE. PF |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 6 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Re-scrape | 2021-12-17 | 2021-12-28 | Approved |  |  |  | 2022-01-04 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-04 |  |  | 2022-02-07 | 2022-02-07 | 2022-02-07 | Matt Reed | (707) 490-5665 |  | Vehicles Onsite | "Debris Crew Leader/Crew# Carla Herbst/#201 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 201" | 38.9244 | -122.6073 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
61 | 012-036-200 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16345 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | Yes | No | No | Yes | FALSE | TRUE | 0 | 4 | 0 | 2 | 0 | 5 | 3 | 14 |  |  | 9 | TRUE | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-26 | 2021-10-26 | 4 | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-10-30 | Arch Monitoring Needed for Debris, not Trees | Yes | [11 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-30 | 2021-10-25 |  | 10.25 SPOKE TO MR SILLS AND HE SAID OK |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 4 | 2021-11-09 | 2021-11-17 | 7 | Approved | [12 empty] | 2021-11-19 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-29 | 2021-12-29 | 2021-12-30 | James Sill | (707) 326-5497 | irishjimsill@gmail.com | Keep Items Other Safety Concerns Vehicles Onsite Well | "Debris Crew Leader/Crew# Carla Herbst﻿/201 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 201" | 38.9239 | -122.6064 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
62 | 012-036-250 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16375 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-21 | 2021-10-25 |  | 10.25 SPOKE TO HO AND SHE SAID OK |  |  |  | 2021-10-26 |  | 2021-10-26 | 2021-10-26 |  |  | 8 | 2021-11-04 | 2021-11-12 | 7 | Approved | [12 empty] | 2021-11-16 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2022-01-24 | 2022-01-24 | 2022-01-24 | Pamela Jane Mulder | (707) 529-2490 | pamax123@yahoo.com | Other | Debris Crew Leader/Crew# Carla Herbst﻿/201 Debris Crew WO# Refer to IAP 10/23 to 10/27 Crew 201 | 38.9246 | -122.6058 | Cache |  | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
63 | 012-036-270 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16355 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1340.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 4 | 0 | 0 | 5 | 0 | 1 | 2 | 12 |  |  | 11 | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-04 | 2021-11-04 | 9 | 2021-11-02 | Bio Monitoring Needed for Debris AND Trees | 2021-11-02 | Arch Monitoring Needed for Debris, not Trees | Yes | [11 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-11-04 | 2021-10-25 |  | 10.25 SPOKE TO HO AND HE SAID OK BUT WANTS TO BE CALL BECAUSE HE HAS STUFF HE WANTS TO BE KEPT. |  |  |  | 2021-11-05 |  | 2021-11-06 | 2021-11-06 |  |  | 4 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2022-02-02 | 2022-02-02 | 2021-12-21 | Milton Lewis | (510) 928-4462 | miltlewis1@yahoo.com | Other Vehicles Onsite Well | "Debris Crew Leader/Crew#1 Carla Herbst﻿/201 Debris Crew WO# Refer to IAP 11/13 To 11/17 Crew 201 | 38.9238 | -122.6061 | Cache |  | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
64 | 012-036-280 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16455 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-10-27 | 2021-10-27 | 6 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-25 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-27 | 2021-10-28 |  | "10.25 SPOKE TO MRS WILDER AND SHE SAID OK SHE WANTS TO BE CALLED BY TFL 10.28 MS WILDER SAID OK AND THEY WILL MEET THE TEAM THERE IN A FEW MIN. PF" |  |  |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 |  |  | 5 | 2021-11-04 | 2021-11-12 | 7 | Approved | [12 empty] | 2021-11-16 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2021-12-21 | Kristi/Bill Wilder | (707) 350-3676 | mausersma@earthlink.net | Keep Items Vehicles Onsite Well | Debris Crew Leader/Crew# Carla Herbst/#201 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 201 | 38.9243 | -122.6041 | Cache |  | Residential | Yes | 2021-10-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
65 | 027-040-025 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 11902 | Aspen Gold Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1809.07 |  | 2022-01-03 | Debris heavily disturbed/moved from footprint | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | [5 empty] | No | Yes | Yes | No | No | No |  | TRUE | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | [10 empty] | 2021-11-19 | Bio Monitoring Needed for Debris AND Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | [31 empty] | 2022-01-03 | Do Not Assess | 0 | [14 empty] | Betty Fong and Kevin Yates | (510) 384-4463 - Betty (925) 393-3430 - Kevin | betty.nsd@gmail.com | Other Septic Vehicles Onsite Well |  | 39.1005 | -120.9886 | River Fire | DR-4601 | Residential | No | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
66 | 027-040-035 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 11868 | Aspen Gold Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1849 |  | 2022-01-03 | Debris heavily disturbed/moved from footprint | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | [5 empty] | No | No | Yes | No | No | No |  | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2021-12-22 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 | [31 empty] | 2022-01-03 | Do Not Assess | 0 | [14 empty] | Betty Fong and Kevin Yates | (510) 384-4463-Betty (925)393-3430-Kevin | betty.nsd@gmail.com | Other Septic Vehicles Onsite Well |  | 39.1 | -120.9885 | River Fire | DR-4601 | Residential | No | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
67 | 027-050-009 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 20050 | Silver Leaf Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2024.49 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-23 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 | [31 empty] | 2022-01-03 | Do Not Assess | 0 | [14 empty] | Stanley R. and Gail C. Webster | (408) 728-3234 or 9408) 728-3236 | placerstan@sbcglobal.net or thatnightngale@gmail.com | Other Septic Well |  | 39.0874 | -120.9935 | River Fire | DR-4601 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
68 | 027-050-031 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19963 | Silver Leaf Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1803.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 7 |  |  | 10 | TRUE | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-11-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | 2021-11-18 | 2021-11-19 |  | 11.19 SPOKE WITH Jaylene she said ok but please call in advance. Vendor handling. JC |  |  |  | 2021-12-03 |  | 2021-12-06 | 2021-12-06 |  |  | 4 | 2021-12-09 | 2021-12-17 | 7 | Re-scrape | 2022-03-03 | 2022-03-11 | Approved | 2022-01-19 | 2022-01-27 | Re-scrape | 2022-02-16 | 2022-02-24 | Soil Boring |  |  |  | 2022-03-15 | 2021-11-12 | Do Not Assess | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-19 | 2022-03-19 | 2022-03-19 | Mary Elizabeth Mcknight Family Trust Sadi Jaylene McKnight, Trustee | (530) 344-3054 | mountainbaby4u@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 302 | 39.0875 | -120.99 | River Fire | DR-4601 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
69 | 027-050-032 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 20030 | Silver Leaf Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1929.31 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 |  | FALSE | [5 empty] | No | No | Yes | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-30 | Bio Monitoring Needed for Trees, not Debris | 2021-12-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | [31 empty] | 2022-01-03 | Do Not Assess | 0 | [14 empty] | Mary Elizabeth McKnight Family Trust; Sadi Jaylene McKnight Trustee | (530) 344-3054 | mountainbaby4u@gmail.com |  |  | 39.0868 | -120.9903 | River Fire | DR-4601 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
70 | 027-050-033 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19765 | Silver Leaf Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2018.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 | 2021-11-23 | 2021-11-29 |  | 11.24 NO ANS LEFT VM. JC 11.29 NO ANS LEFT VM. SENT EMAIL JC 11.29 SPOKE WITH CHRISTOPHER HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE ANY PROPANE TANKS. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 4 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-12 | Do Not Assess | 0 | [8 empty] | 2022-01-14 |  |  | 2022-01-19 | 2022-01-19 | 2022-01-19 | Christopher Rademacher and Jill M. Rist | (805) 610-9679 | cjrademacher1@hotmail.com | Other Septic Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 302 | 39.0898 | -120.9905 | River Fire | DR-4601 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
71 | 027-050-035 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 19879 | Silver Leaf Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1929.09 |  | 2021-11-22 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-19 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-10-28 | Bio Monitoring Needed for Trees, not Debris | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | [31 empty] | 2021-11-10 | Do Not Assess | 0 | [14 empty] | Shanna and Joshua Schaap | (916) 747-9970 or (916) 410-6630 | jschaap80@hotmail.com; shanna.schaap@fairwaymc.com | Septic Well |  | 39.0886 | -120.9899 | River Fire | DR-4601 | Residential | Yes | 2021-10-06 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
72 | 028-221-038 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Ready for Tree Felling | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 16008 | Mount Olive Road |  | Grass Valley | Nevada |  | Commercial | Yes | 2022-02-25 | 2022-03-17 | Waste profile results indicate no California Hazardous or RCRA wastes; okay to proceed with normal debris removal |  | 2302.91 |  |  |  |  | FALSE |  |  | N/A | Approved |  |  |  |  | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | Yes | FALSE | TRUE | 0 | 3 | 1 | 0 | 2 | 2 | 0 | 8 |  |  |  |  | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-21 | POSITIVE | 2021-11-05 | 2021-11-05 | 12 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | Active Nest |  |  | Complete | Yes | 2022-03-11 | No |  | TRUE |  | Class II | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-04-20 | 2021-11-05 | 2021-10-27 | 2021-10-27 | 10.27 NO ANS LEFT MESS PF10.27 NO ANS LEFT MESS PF10.27 SPOKE TO MR GEOTZ SAID OK PF 11.2 Spoke to Michael. He called vendor to remove the tank. JC |  |  |  | 2022-03-28 |  | 2022-03-30 | 2022-03-30 |  |  | 3 | 2022-04-01 |  | 6 | [14 empty] | 2022-02-09 | Yes | 15 | [14 empty] | Michael Goetze | (530) 906-3500 | goetze@inreach.com | Other Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Carondlet Dunbar/ #301 Debris Crew WO# Refer to IAP 03.30 to 04.02 Crew 301 | 39.1466 | -120.9729 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
73 | 028-261-022 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19661 | Last Mile Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2203.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 5 |  |  | 4 | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-10-20 | 2021-10-29 |  | "10.27 NO ANS. LEFT MESS PF 10.28 MIKE C/B PER HIS VOICEMAIL SAID OK PF 11.2 Spoke to owner and they would like to have tank removed. JC 10.29 MIKE C/B AND SAID PLEASE CALL WITH DATE YOU ARE GOING THERE. PF" |  |  |  | 2021-11-03 |  | 2021-11-06 | 2021-11-06 |  |  | 4 | 2021-11-11 | 2021-11-18 | 6 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Sierra Rose Casaday/Hunter | (530) 613-2764 | mikeybasich@gmail.com | Other Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 301" | 39.1373 | -120.9784 | River Fire | DR-4601 | Residential | Yes | 2021-09-22 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
74 | 028-261-023 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19457 | Last Mile Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2276.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-22 | 2021-11-24 |  | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL JC 11.24 SPOKE WITH OWNER SHE SAID OK BUT PLEASE CALL CHARLEEN 530 206-6373 IN ADVANCE. ALSO, PLEASE USE CALL BUTTON ON GATE WHEN COMING TO PROPERTY. NO PROPANE. JC 01/28/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/28/22 SPOKE WITH CHARLEEN. VENDOR HANDLED PROPANE TANK. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape |  |  |  | 2022-01-19 | 2022-01-27 | Approved | [6 empty] | 2022-01-29 | 2022-01-03 | Do Not Assess | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-18 | 2022-02-18 | 2022-02-18 | Heather Dewitt; Katherine Dewitt-Drew; Agent: Pat Dewitt | (530) 575-8975 Agent Pat Dewitt 530 206-6373 ***see notes for new contact | dewcar1@aol.com | Other Septic | Debris Crew Leader/Crew# Joshua Dragon /#301 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew301 | 39.1395 | -120.9748 | River Fire | DR-4601 | Residential | Yes | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
75 | 028-261-029 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 15865 | Mount Olive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2309.92 |  |  |  |  | TRUE | Nesting Birds |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | Yes |  | 2021-11-02 | No | TRUE | No | No | No | Yes | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-25 | POSITIVE | 2021-10-30 | 2021-10-30 | 5 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-14 | Active Nest | Mount Olive | 2022-06-11 | Complete | Yes | 2022-03-11 | No |  | TRUE |  | Class II | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-28 | 2021-10-30 | 2021-11-06 | 2021-12-06 | "11.5 NO ANS LEFT VM. JC 11.6 SPOKE TO PAUL AND HE SAID OK BUT PLEASE CALL BEFORE COMING OUT. "PF 12.06 NO ANS LEFT VM AND TEXT FOR TREE REMOVAL. JC 12.06 SPOKE WITH PAUL HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-17 | Yes | 1 | [14 empty] | Paul Bernacki | (530) 575-9710 | pkinpie@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 301 | 39.1449 | -120.9749 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
76 | 028-261-030 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 15909 | Mount Olive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2288.07 |  |  |  |  | TRUE | Nesting Birds |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | Yes |  | 2021-11-02 | No | TRUE | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-20 | POSITIVE | 2021-10-29 | 2021-10-29 | 8 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-14 | Active Nest | Mount Olive | 2022-06-11 | Complete | Yes | 2022-03-11 | No |  | TRUE |  | Class II | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-24 | 2021-10-29 | 2021-11-06 |  | 11.5 UNABLE TO LEAVE VM. SENT EMAIL. JC 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH ERICA SHE SAID OK BUT PLEASE CALL IN ADVANCE﻿. VENDOR HANDLED THE PROPANE TANK. JC |  |  |  | 2021-11-08 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-18 | Yes | 5 | [14 empty] | Chris and Erica Salter | (530) 263-4044 or (530) 263-6140 | chris.erica.salter@gmail.com | Septic Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 301 | 39.145 | -120.9741 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
77 | 028-261-031 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19150 | Deer Hollow Way |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2338.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-16 | No Bio Monitoring Needed for Debris or Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-10-18 | 2021-10-27 |  | 10.27 SPOKE TO JOSE AND HE SAID OK. CALL FIRST PF 11.2 Mailbox full could not leave mess on tank removal. JC 11.3 Spoke with Jose he already contacted vendor. JC |  |  |  | 2021-11-03 |  | 2021-11-03 | 2021-11-03 |  |  | 5 | 2021-11-09 | 2021-11-18 | 8 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Jose Sandoval | (415) 720-5822 | deerholloway@gmail.com | Other Septic Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 301 | 39.1442 | -120.9743 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
78 | 028-261-032 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19180 | Deer Hollow Way |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2333.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | Yes | Yes | No | No | No | FALSE | TRUE | 3 | 1 | 0 | 0 | 0 | 4 | 0 | 8 |  |  | 11 | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-21 | POSITIVE | 2021-11-04 | 2021-11-04 | 11 | 2021-10-16 | No Bio Monitoring Needed for Debris or Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE |  |  |  | No |  |  |  |  | TRUE | 2022-02-26 | 2021-11-22 | 2021-11-04 |  | 11.3 NO ANS LEFT MESS. JC 11.4 SPOKE WITH DAVID, HE SAID OK. VENDOR IS HANDLING THE TANK. JC |  |  |  | 2021-11-30 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | David and Mary French | (530) 906-1250 or (530) 906-1280 | ldfrench@hotmail.com and mefrench42@yahoo.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp /#301 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 301 | 39.1436 | -120.9742 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
79 | 028-261-033 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19220 | Deer Hollow Way |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2276.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 8 | 1 | 3 | 0 | 3 | 6 | 3 | 24 |  |  | 21 | TRUE | No |  |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-22 | POSITIVE | 2021-11-03 | 2021-11-03 | 9 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class II | None | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-11-03 | 2021-11-04 |  | 11.3 NO ANS LEFT MESS. JC 11.4 SPOKE WITH OWNER, HE SIAD OKAY. PLEASE CALL IN ADVANCE. JC |  |  | 2021-11-03 | 2021-11-20 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Re-scrape |  |  |  | 2022-03-01 | 2022-03-09 | Re-scrape | 2022-03-01 |  | Approved |  |  |  | 2022-03-11 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-19 | 2022-03-19 | 2022-03-19 | Lawrence Heinrich | (360) 921-9670 | loh831@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 301 | 39.1423 | -120.9736 | River Fire | DR-4601 | Residential | No | 2021-10-01 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
80 | 028-261-034 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19189 | Deer Hollow Way |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2234.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | Yes | FALSE | TRUE | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 5 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-11-04 | 2021-11-09 | NEGATIVE |  |  |  | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | Active Nest | 650 | 2022-06-11 | [9 empty] | FALSE |  |  |  | Yes | 2021-11-17 | 2022-03-30 |  |  | TRUE | 2022-03-24 | 2021-10-19 | 2021-10-28 |  | 10.27 NO ANS. LEFT MESS PF 10.28 SPOKE TO SHIREE SAID OK BUT PLEASE CALL BEFORE GOING. PF 11.2 Left message on tank removal. JC 11.3 Spoke to Justin he will call vendor. JC |  |  |  | 2021-10-30 |  | 2021-11-17 | 2021-11-17 |  |  | 8 | 2021-11-30 | 2021-12-08 | 7 | Re-scrape | 2022-03-03 | 2022-03-11 | Approved | 2022-01-17 | 2022-01-25 | Re-scrape | 2022-02-11 | 2022-02-21 | Soil Boring |  |  |  | 2022-03-15 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-22 | 2022-03-22 | 2022-03-22 | Justin Brown and Shiree Rezendes | (530) 261-1182 or (530) 306-9228 | flyagaric@gmail.com; shireerezendes@gmail.com | Keep Items Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 301" | 39.1426 | -120.9725 | River Fire | DR-4601 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
81 | 028-261-042 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 19205 | State Highway 174 |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2581.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 21 | 3 | 0 | 0 | 0 | 1 | 0 | 25 |  |  | 18 |  | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2022-03-08 | POSITIVE | 2021-12-02 | 2021-12-02 | -68 | 2021-11-15 | Bio Monitoring Needed for Trees, not Debris | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | Active Nest | 30 | 2022-04-22 | Complete | Yes | 2022-03-11 | No |  | TRUE |  | Class III | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-21 | 2021-12-02 | 2021-11-24 |  | 11.23 NO ANS VM FULL JC 11.24 SPOKE WITH LISA SHE SAID OK BUT PLEASE CALL IN ADVANCE. LISA WANTS TO BE THERE DURING DEBRIS REMOVAL CALL 530 460-9439. PLEASE REMOVE SMALL PROPANE TANKS. JC |  |  |  | 2021-12-10 |  | 2021-12-21 | 2021-12-21 |  |  | 13 | 2022-01-08 | 2022-01-14 | 5 | Soil Boring | 2022-01-19 | 2022-01-27 | Re-scrape | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2022-01-05 | Yes | 54 | [14 empty] | Sky Meyer | (530) 615-9852 or Reginald King (530) 913-5874 and Lisa Lakoduk (530) 460-9439 | reginalddking@gmail.com; Lisalakoduk53@gmail.com; skymeyer10@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Joshua Dragon/ #301 Debris Crew WO# Refer to IAP 12/22 to 12/29 Crew 301 | 39.1427 | -120.9695 | River Fire | DR-4601 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
82 | 028-261-050 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19631 | Last Mile Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2211.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | Yes | No | No | No | FALSE | TRUE | 2 | 3 | 0 | 2 | 1 | 1 | 1 | 10 |  |  | 10 | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 | 2021-11-22 | 2021-11-16 |  | 11.16 SPOKE WITH LARLEI SHE SAID OK. PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | John Wilson and LariLei Solomon | (530) 263-4753 or (530) 263-4796 | lariso2@yahoo.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Joshua Dragon /#301 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 301 | 39.1373 | -120.9772 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
83 | 028-261-052 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19486 | Last Mile Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2240.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | Yes |  | 2021-11-09 | No | TRUE | No | No | Yes | Yes | No | Yes | FALSE | TRUE | 9 | 1 | 0 | 1 | 1 | 6 | 0 | 18 |  |  | 12 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | POSITIVE | 2021-11-05 | 2021-11-05 | 12 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class II | None | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-11-09 | 2021-11-03 |  | 11.3 NO ANS LEFT MESS. JC 11.3 SPOKE TO KAREN. SHE SAID OK AND PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2022-01-03 | Do Not Assess | 0 | [8 empty] | 2022-01-14 |  |  | 2022-01-21 | 2022-01-21 | 2022-01-21 | Sean and Karen Ambrose | (530) 263-3182 and (530) 308-5635 | ambcrashfixer@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP -11/24 to 12/01- Crew 301 | 39.139 | -120.9784 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
84 | 028-261-054 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19676 | Last Mile Drive |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2213.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | 2021-11-01 | 2021-11-08 |  | 11.8 NO ANS LEFT VN JC 11.8 SPOKE WITH KENNETH HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT BURNED. JC |  |  |  | 2021-11-11 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Kenneth and Carol Mosbacher | (530) 615-8873 | m2155@nccn.net and carolmosbacher@gmail.com | Other Septic Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 301 | 39.1381 | -120.9784 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
85 | 041-562-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5012 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3953.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 |  | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-12-02 | Bio Monitoring Needed for Debris, not Trees | 2022-01-29 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-04 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-29 | 2022-01-31 | 2022-03-09 | 01/31/22 NO ANS LEFT VM & TEXT. JC 01/31/22 Chris c/b he said ok but please do not damage the concrete driveway. No Propane tank on property. jc 03/08/22 NO ANS LEFT VM & TEXT. JC 03/09/22 CHRIS GAVE CONSENT VIA VOICEMAIL. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Approved | [12 empty] | 2022-02-17 | 2022-01-29 | Yes | 28 | [14 empty] | Chris A. Britton | 707-479-5448 | cbritton@rightoverhere.com |  | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 507 | 38.636 | -120.5173 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
86 | 041-562-018 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4986 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3923.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-17 | 2021-12-01 | Yes | 2021-12-01 | 2021-12-08 | POSITIVE | 2022-01-21 | 2022-01-21 | 32 | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2022-01-22 | 2022-01-24 | 2022-03-04 | 12.10 SPOKE WITH PAT SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE. JC 01/24/22 ﻿SPOKE WITH PAT SHE SAID OK. JC 03/03/22 NO ANS MAILBOX FULL SENT TEXT. JC 03/04/22 SPOKE WITH PAT SHE SAID OK FOR TREE REMOVAL. JC 3.15 Spoke to Pat per MP email. Answered her questions about her trees and property and also she says she didn't get her 12-24 hr call. But she's ok now. PF |  |  |  | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Approved | [12 empty] | 2022-02-16 | 2022-01-22 | Yes | 49 | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-16 | 2022-03-17 | 49 | 2022-03-25 |  | 2022-03-21 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Lamont & Pat Olson | 425-290-2445 | olson432@yahoo.com | Septic | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 507 | 38.6371 | -120.5169 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
87 | 041-562-019 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4980 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3920.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-19 | 2021-10-26 | 2022-01-20 | 10.26 SPOKE TO MR. WELCH AND HE SAID OK. PFC 12.4 SPOKE WITH CHRISTOPHER HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/20/22 SPOKE WITH CHRISTOPHER HE SAID OK. JC 01/25/22 SPOKE WITH CHRISTOPHER HE SAID REMOVE. 01/26/22 CHRIS C/B AND SAID VENDOR WILL HANDLE PROPANE. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 9 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2022-01-27 | Yes | 29 | 2022-01-27 |  | 2022-01-27 | 2022-01-27 |  | 2022-01-29 | 2022-01-31 | 29 | 2022-02-10 |  | 2022-02-02 | 2022-02-11 | 2022-02-11 | 2022-02-11 | CHRISTOPHER WELCH | 408-420-4002 | cj@cjwelch.com |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 10/30- 11/03 Crew 502 | 38.6374 | -120.5169 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
88 | 041-562-020 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4972 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3916.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 2 | TRUE | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-01 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-07 | 2022-01-21 |  | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 SPOKE WITH TRACY HE SAID OK BUT WANTS TO BE ON SITE DURING DEBRIS REMOVAL SO PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 TRACY SAID OK BUT CALL IN ADVANCE. JC 03/03/22 SPOKE WITH TRACY HE SAID OK. KC |  |  |  | 2022-01-21 |  | 2022-01-24 | 2022-01-24 |  |  | 4 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2021-12-02 | Yes | 22 | 2022-03-05 |  | 2022-03-05 | 2022-03-05 |  | 2022-03-11 | 2022-03-14 | 22 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Tracy & Gini Sturges | 530-613-3445 | trace10808@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 507 | 38.6378 | -120.5169 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
89 | 041-562-023 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5002 | Parkside Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3875.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 | 2021-11-17 | 2021-11-20 | 2022-01-19 | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.19 SENT EMAIL. JC 11.19 JODI REPLIED TO EMAIL/SAID WILL CALL OFFICE. JC 11.20 SPOKE WITH JODI SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLE PROPANE TANK. PLEASE REMOVE SMALLER PROPANE TANKS. JC 01/19/22 NO ANS LEFT VM & TEXT and EMAIL. JC 01/19/22 JODI C/B SHE SAID OK BUT THERE ARE THREE NEAR THE HOUSE THAT BURNED AND WERE NOT MARKED TO BE REMOVED. SHE WOULD LIKE TO HAVE THESE TREES REMOVE. JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-11 | Yes | 74 | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  | 2022-01-25 | 2022-01-26 | 74 | 2022-02-01 |  | 2022-01-27 | 2022-02-04 | 2022-02-04 | 2022-02-04 | LAUTHER JODI | 530-363-4076 | jmlauth9@live.com | SEPTIC | Debris Crew Leader/Crew# Glenn Adams/#501 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 501 | 38.6359 | -120.5192 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
90 | 041-571-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5003 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4006.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | [11 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | Yes |  | FALSE |  | No | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 |  |  | 2022-01-20 | 01/20/22 SPOKE WITH LINDA SHE SAID OK. JC | [27 empty] | 2022-03-25 | Yes | 37 | 2022-03-25 |  | 2022-03-26 | 2022-03-26 |  | 2022-03-30 | 2022-03-31 | 36 |  |  | 2022-04-01 |  | 2022-04-01 | 2022-04-04 | Linda Patrick | 925-852-1747 | lindap_2954@yahoo.com |  |  | 38.6423 | -120.5174 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
91 | 041-571-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5015 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4007.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 3 |  |  | 5 |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-25 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-25 | No |  | TRUE |  | No | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 | 2021-11-30 | 2022-01-24 | 2022-03-18 | 12.03 SPOKE WITH TONY HE SAID OK BUT PLEASE CALL BACK AFTER 5PM FOR DETAILS ON PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 PHONE NUMBER NO LONGER BELONGS TO LINDA. SEND EMAIL. JC 01/24/22 NO REPLY TO EMAIL GAVE TO IMT. JC﻿ 01/24/22 sent email. per Melissa clear for debris removal. JC 3.18 NO ANS. LEFT MESS & TEXT PF 3.18 LINDA'S FIANCE (TONY) C/B AND HE SAID OK. PF |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 5 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2021-11-04 | Yes | 19 | 2022-03-26 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-31 | 2022-04-01 | 20 |  |  | 2022-04-04 |  |  |  | Linda Patrick | Mobile 925-727-1270/ Home 916-671-3903 | lindap_2954@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Crystal Egan/#505 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 509 | 38.6424 | -120.517 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-04T20:41:57Z | FALSE | 3
92 | 041-571-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5023 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4003.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-02-01 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | Yes | 2022-02-16 |  |  | No | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 |  |  | 2022-02-24 | 02/21/22 NO ANS NO VM SENT EMAIL. JC 02/22/22 NO ANS NO VM SENT 2ND EMAIL. JC 02/23/22 NO ANS NO VM SENT 3RD EMAIL. JC 02/24/22 NO ANS NO VM. JC 02/24/22 proceed for tree removal per Melissa Perry. JC | 3 | State Planner: Melissa Perry | [25 empty] | 2021-11-22 | Yes | 36 | 2022-03-11 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-23 | 2022-03-25 | 36 |  |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 | Linda Patrick | 925-852-1749 | lindap_2954@yahoo.com |  |  | 38.6426 | -120.5167 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
93 | 041-572-012 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4961 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3939.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-01 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 |  |  | 2022-01-20 | 01/20/22 NO ANS LEFT VM TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2021-11-20 | Yes | 35 | 2022-02-10 |  | 2022-02-11 | 2022-02-11 |  | 2022-02-17 | 2022-02-18 | 35 |  |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | Anthony Zepczyk & Georgia Boles | 925-300-8741 | cocacolagrandma@msn.com | Vehicle on site |  | 38.6406 | -120.5165 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
94 | 041-572-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7299 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3939.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | Bio Monitoring Needed for Debris AND Trees | 2021-11-29 | Arch Monitoring Needed for Debris, not Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | 2022-04-02 | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-22 | 2021-11-29 |  | 11.24 NO ANS LEFT VM. JC 11.29 SPOKE WITH ANTON HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 3 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2022-04-06 | Yes | 86 | [14 empty] | Anton & Carol Weaver-Madsen | 510-378-1131 , 510-656-8937 | weaver-madsen@comcast.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#501 Debris Crew WO# Refer to IAP 12/01 to 12/04Crew 501 | 38.6408 | -120.5176 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-07T00:10:40Z | FALSE
95 | 041-591-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4978 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3951.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | No |  |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-12-07 | 2021-11-30 | 2022-03-24 | 11.29 SPOKE WITH JENNIFER SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/19/22 NO ANS LEFT VM & TEXT. JC 01/19/22 SPOKE WITH JENNIFER SHE SAID OK. JC 02/26/22 SPOKE WITH JENNIFER SHE SAID OK. JC 03/24/22 follow-up SPOKE WITH JENNIFER SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 3 | 2021-12-11 | 2021-12-17 | 5 | Approved | [12 empty] | 2021-12-20 | 2022-03-24 | Yes | 5 | [14 empty] | Christopher & Jennifer Allen | 530-391-7273, 530-391-8945 | jenniferallen@yahoo.com | Vehicle on site Keep items Septic | Debris Crew Leader/Crew# Glenn Adams /#508 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 508 | 38.6408 | -120.5133 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
96 | 041-591-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4984 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3947.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3 |  |  | 5 |  | No |  |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-14 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-22 | 2021-11-29 | 2022-03-24 | 11.29 SPOKE WITH ANTONINA SHE SAID OK BUT PLEASE CALL INADVANCE. NO PROPANE TANKS. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 HO GAVE CONSENT VIA TEXT. JC 03/24/22 FOLLOW-UP SPOKE WITH ANTONINA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 38 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-03-24 | Yes | 11 | [14 empty] | Antonina Myshyakova | 530-219-6752 | mas200812@hotmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#508 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 508 | 38.6408 | -120.5136 | Caldor | DR-4619 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
97 | 041-593-007 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7396 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3943.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | Yes |  | 2021-12-10 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | POSITIVE | 2021-12-04 | 2021-12-04 | 1 | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2022-01-05 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-10 | 2022-01-22 |  | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH MARQUEZ HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE IS WAS NOT DAMAGED DO NOT REMOVE. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-02-10 |  | 2022-02-10 | 2022-02-10 |  |  | 2 | 2022-02-12 | 2022-02-22 | 7 | Approved | [12 empty] | 2022-02-21 | 2021-12-02 | No | 0 | [8 empty] | 2022-03-09 |  |  | 2022-03-10 | 2022-03-10 | 2022-03-10 | HILLES MARK | 530-409-2737 | hillesmark180@gmail.com | Septic | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/05 to 02/12 Crew 504 | 38.6392 | -120.5135 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
98 | 041-593-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 2 | 7410 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3954.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No |  | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 3 |  | Yes | Take | 2022-02-16 | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | POSITIVE | 2021-12-03 | 2021-12-03 | 3 | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-02 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-03 | 2021-12-04 |  | 12.03 NO ANS LEFT VM. JC 12.04 NO ANS LEFT VM. JC 12.4 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE. JC 01/27/22 MICHAEL SAID HE WILL CHECK WITH VENDOR. JC 01/27/22 MICHAEL C/B HE SAID PLEASE REMOVE PROPANE TANK. JC 03/15/22 NO ANS LEFT VM & TEXT. JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 48 | 2022-02-15 | 2022-02-23 | 7 | Approved | [12 empty] | 2022-02-25 | 2022-01-25 | Yes | 13 | [14 empty] | FOURIE, MICHAEL | 707-642-0386 | none | Septic Vehicles Onsite | Debris Crew Leader/Crew# Christer Richter /#503 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 5073 | 38.6391 | -120.513 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-09T00:29:35Z | FALSE
99 | 041-601-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7620 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4055.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-07 | 2022-02-26 | 11.29 NO ANS LEFT VM. JC 11:30 NO ANS LEFT VM AND EMAIL. JC 12/01 Left voicemail RCV 12.07 NO ANS LEFT VM & TEXT. JC 12.07 Homeowner contact made, okayed debris removal RCV 02/26/22 SPOKE WITH DENNIS HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Approved | [12 empty] | 2022-02-16 | 2021-11-30 | Yes | 4 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | 4 | 2022-03-17 |  | 2022-03-11 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Dennis @ Michael Alexander | 510 331-5850 | DENALE56@GMAIL.COM | Septic | Debris Crew Leader/Crew# Fernando Montealegre /#515 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 511 | 38.6422 | -120.5101 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
100 | 041-601-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7610 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4052.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-21 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-01-26 | 01/26/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 01/26/22 HO GAVE CONSETN VIA TEXT. HO SAID NO PROPANE TANK ON PROPERTY. JC | [27 empty] | 2022-01-21 | Yes | 3 | 2022-02-15 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-17 | 2022-02-18 | 3 |  |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | ALEXANDER, MICHAEL DAVID | 510-209-1221 | m.alexander7276@sbcglobal.net |  |  | 38.6422 | -120.5097 | Caldor | DR-4619 | Residential | No | 2021-11-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
101 | 041-601-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7602 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4055.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-30 | 2021-11-01 | 2022-01-20 | 11.1SPOKE TO RICHARD AND HE SAID OK PF 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC 01/26/22 SPOKE WITH RICHARD HE SAID VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-02 |  | 2021-11-02 | 2021-11-02 |  |  | 19 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-04 | Yes | 3 | 2022-02-15 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-17 | 2022-02-18 | 3 | 2022-02-21 |  | 2022-02-19 | 2022-02-28 | 2022-02-28 | 2022-02-28 | RICHARD & STEPHANIE BECK | 530-957-6809 | beck.computer@gmail.com |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 501 | 38.6421 | -120.5093 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
102 | 041-601-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7592 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4059.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-30 | 2021-11-01 | 2021-12-04 | "11.1 NO ANS LEFT MESS PF 11.1SPOKE TO MICHAEL HE SAID OK AND PLEASE CALL BEFORE GOING TO PROPERTY. PF" 11.2 Spoke with owner and they contacted the vendor to remove tank. JC 12.4 SPOKE WITH HO HE SAID OK. JC 01/14/22 HO SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 7 | 2021-11-11 | 2021-11-18 | 6 | Approved | [12 empty] | 2021-11-20 | 2022-01-05 | Yes | 5 | 2022-01-07 |  | 2022-01-07 | 2022-01-07 |  | 2022-01-11 | 2022-01-17 | 5 | 2022-01-25 |  | 2022-01-19 | 2022-01-28 | 2022-01-28 | 2022-01-28 | JEANINE PATTERSON | 916-947-5305 | MPATTERSON328@GMAIL.COM |  | "Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 501 | 38.6421 | -120.509 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
103 | 041-601-007 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7586 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4075.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-05 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-01 | 2021-12-02 | 2022-03-08 | 12.02 Homeowner okayed start of removal RCV 03/08/22 SPOKE WITH RICHARD HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-04 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape |  |  |  | 2022-02-07 | 2022-02-15 | Approved | [6 empty] | 2022-02-16 | 2022-02-02 | Yes | 2 | 2022-03-28 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-28 | 2022-03-29 | 2 |  |  | 2022-03-30 |  |  |  | SCHOONOVER, RICHARD | 408-679-6969 | SCHOONOVER47@yahoo.com | Vehicles Onsite | Debris Crew Leader/Crew# Christer Richter/#501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 501 | 38.6421 | -120.5085 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
104 | 100-190-004 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100-190-004 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2291.63 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2021-12-07 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2022-01-03 | No | 0 | [15 empty] | (650) 387-4268 | csg@guenzer.com |  |  | 39.0999 | -120.9814 | River | DR-4610 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
105 | 100-190-006 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100-190-006 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2008.2 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2021-12-07 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2022-01-03 | No | 0 | [15 empty] | (650) 387-4268 | csg@guenzer.com |  |  | 39.0983 | -120.9848 | River | DR-4610 | Residential | No | 2021-11-30 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
106 | 100-190-007 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100-190-007 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2246.51 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2021-12-07 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2022-01-03 | No | 0 | [15 empty] | (650) 387-4268 | csg@guenzer.com |  |  | 39.0982 | -120.9802 | River | DR-4610 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
107 | 100-200-008 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Nevada/Placer Pending Results | Tree Assessment Needed | 100-200-008 | No Address |  | Colfax | Placer |  | Commercial | [5 empty] | 2182.12 |  |  |  |  | TRUE | Inclusion Approval |  | N/A | Pending |  |  |  |  | Yes |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 4 |  |  |  |  | No |  |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | POSITIVE |  |  | 85 | 2021-12-07 | Bio Monitoring Needed for Debris, not Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 |  |  |  | 12.14 NO ANS LEFT VM. JC 12.15 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL 530 320-9301 IN ADVANCE. JC 12.16 NO ANS LEFT VM FOR GATE CODE. JC | [44 empty] | James Wegman, Kathleen Dutra, Frank Dutra | 530-888-0608 new number 530-320-9301 | nank@ssctv.net | Septic Vehicles Onsite |  | 39.1064 | -120.9816 | River | DR-4610 | Residential | No | 2021-12-07 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
108 | 100-200-013 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1520 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2325.77 |  | 2021-11-16 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 |  |  |  |  | Yes |  |  | 2021-10-13 | No | [6 empty] | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | [31 empty] | 2021-11-22 | No | 0 | [14 empty] | Lynnette Heilig | (530) 346-9631 | Lynnetteheilig@gmail.com | Septic |  | 39.1064 | -120.9739 | River | DR-4610 | Residential | Yes | 2021-10-01 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
109 | 100-200-022 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 24920 | Saddleback Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2324.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-19 | 2021-10-27 |  | 10.27 SPOKE TO MR MAGAN ANDHE SAID TFL ALREADY CALLED AND OK. PF |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 10 | 2021-11-13 | 2021-11-19 | 5 | Re-scrape | 2022-01-28 | 2022-02-07 | Approved | 2021-12-03 | 2021-12-13 | Re-scrape | 2022-01-14 | 2022-01-24 | Soil Boring |  |  |  | 2022-02-08 | 2021-11-16 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-16 | 2022-02-16 | 2022-02-16 | Andrew Magan | (530) 401-5124 | acmagan@gmail.com | Keep Items Septic | Debris Crew Leader/Crew# Jason Lowe/402 Debris Crew WO# Refer to IAP 10/28 to 10/30 Crew 402 | 39.105 | -120.9782 | River | DR-4610 | Residential | Yes | 2021-10-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
110 | 100-200-031 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 24955 | Saddleback Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2453.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | NEGATIVE |  |  |  | 2021-11-03 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | 2021-11-09 | 2021-11-10 |  | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH WHITNEY SHE SAID OK BUT CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 6 | 2021-11-22 | 2021-12-02 | 7 | Re-scrape |  |  |  | 2021-12-08 | 2021-12-16 | Approved | [6 empty] | 2021-12-17 | 2021-11-16 | No | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-15 | 2022-01-15 | 2022-01-14 | Robert Dougall | (209) 598-8502 | whitneyisetta@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 402 | 39.1025 | -120.9783 | River | DR-4610 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
111 | 100-200-032 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 24945 | Saddleback Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2420.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | Yes | Yes | Yes | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 0 | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-19 | 2021-10-28 |  | 10.27 NO ANS. PF 10.28 Spoke with Whitney, approved debris removal start RCV |  |  |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 |  |  | 11 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-24 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Whitney Isetta | (209) 598-8502 | whitneyisetta@gmail.com | Other Septic | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 402 | 39.1021 | -120.9777 | River | DR-4610 | Residential | Yes | 2021-10-01 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
112 | 041-011-024 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5001 | Cosumnes Mine Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3418.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2022-02-01 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No |  |  |  | TRUE |  |  |  | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-02-01 | 2022-02-07 |  | 02/02/22 NO ANS LEFT VM AND TEXT. JC 02/03/22 NO ANS LEFT VM & EMAIL. JC 02/03/22 SPOKE WITH KIM. SHE ASKED THAT WE PUT ON HOLD UNTIL SHE CONTACTS THE COUNTY REP. JC 02/04/22 PHONED TO FOLLOW UP. NO ANS LEFT VM, TEXT AND SENT EMAIL. JC 02/07/22 NO ANS SENT VM, TEXT AND EMAIL. JC 02/07/2022 - JOE M. SPOKE WITH OWNER, SHE IS OKAY WITH US PROCEEDING 02/07/22 HO EMAILED BACK. SHE SAID OK TO PROCESS WITH DEBRIS REMOVAL. JC |  |  |  | 2022-02-08 |  | 2022-02-08 | 2022-02-08 |  |  | 4 | 2022-02-11 | 2022-02-21 | 7 | Approved | [12 empty] | 2022-02-24 | 2022-02-11 | Yes | 199 | [14 empty] | Kim L McNeely | 925-570-5032 | 4mcboys@gmail.com | Septic | Debris Crew Leader/Crew# Carondlet Dunbar / #505 Debris Crew WO# Refer to IAP 02/12 To 02/16 Crew 505 | 38.6563 | -120.5507 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-09T00:17:37Z | FALSE
113 | 041-011-030 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5821 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3799.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-23 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | 2022-03-17 | TRUE |  | Class I | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-23 | 2021-11-24 | 2022-03-31 | 11.24 SPOKE TO CHRISTINA SHE SAID OK BUT PLEASE CALL ADVANCE. THE OWNERS WANT TO BE THERE FOR THE DEBRIS REMOVAL. DO NOT REMOVE PROPANE TANK. JC 03/31/22 NO ANS LEFT VM & TEXT. JC 03/31/22 CHRISTINA C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2022-02-03 | Yes | 358 | [14 empty] | James and Christina Holum | 916-271-9251 | christinaholum@gmail.com |  | Debris Crew Leader/Crew# Mattson Adams /#507 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 507 | 38.6489 | -120.5388 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
114 | 041-662-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5047 | Cary Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3930.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-14 | Yes | 2022-02-28 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-04 | 2021-12-07 | 2022-03-03 | "12.07 NO ANS LEFT VM & TEXT. JC 12.07 HO GAVE CONSENT VIA TEXT. JC" 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/14/22 HO TEXT BACK HE SAID TO REMOVE PROPANE TANK. JC "03/03/22 NO ANS LEFT & TEXT JC 03/03/22 HO GAVE CONSENT VIA TEXT. JC" 04/08/22 Call abt. vehicle on property. No ans left vm & text. JC 04/08/22 HO text back that vehicles were removed from property during debris removal. jc |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 24 | 2022-01-15 | 2022-01-21 | 5 | Approved | [12 empty] | 2022-01-26 | 2021-12-21 | Yes | 46 | [14 empty] | Christopher & Dana Douglas | 530-391-5234 | ao1douglas@gmail.com |  | Debris Crew Leader/Crew# Matthew Dorenzo #505 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 505 | 38.6398 | -120.5327 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T19:45:36Z | FALSE
115 | 041-663-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 4972 | Coralaine Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3951.25 |  |  |  |  | TRUE | Boundary Line Issues |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-28 | 2021-10-28 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-04 | 2021-11-05 | 2022-01-14 | "11.5 SPOKE WITH ANTHONY SAID OK AND PLEASE TAKE PROPANE TANK. BUT PLEASE CALL IN ADVANCE. JC 12.07 SPOKE WITH ANTHONY HE GAVE PRE APPROVAL TO REMOVE HAZARDOUS TREES. BUT PLEASE CALL IN ADVANCE. JC" 01/14/22﻿ SPOKE WITH ANTHONY HE SAID OK. |  |  |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-10-30 | Yes | 43 | [14 empty] | ANTHONY & CAROL TAMBLE | 520-483-7150 | tamblewoodsranch@yahoo.com | Septic | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 504 | 38.6401 | -120.5309 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
116 | 041-663-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 4919 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3922.4 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-17 | Bio Monitoring Needed for Debris AND Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-25 | Yes |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-12-03 | 2021-12-07 |  | 12.06 NO ANS LEFT VM AND TEXT. JC 12.06 NO ANS SENT EMAIL. JC 12.07 SPOKE WITH DEBRA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-13 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-11-08 | Yes | 29 | [14 empty] | Debra Weed | 530-919-7517 | debbiekaouch@gmail.com | SEPTIC | Debris Crew Leader/Crew# Eric Rocha/ #505 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 505 | 38.6396 | -120.5316 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
117 | 041-663-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4971 | Coralaine Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3935.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-22 | Bio Monitoring Needed for Trees, not Debris | 2021-11-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-02 | 2021-11-03 | 2021-12-04 | 11.3 SPOKE WITH GREGORY HE SAID OK. PLEASE CALL IN ADVANCE. JC "12.4 NO ANS LEFT VM FOR TREE REMOVAL JC 12.4 SPOKE WITH GREG HE SAID OK. JC" |  |  |  | 2021-11-09 |  | 2021-11-09 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-01 | Yes | 50 | 2021-12-11 |  | 2021-12-17 | 2021-12-17 |  | 2021-12-18 | 2021-12-18 | 50 | 2022-01-18 |  | 2022-01-12 | 2022-01-26 | 2022-01-26 | 2022-01-26 | GREGORY & TRUDY GAGE | 408-507-2056 | bigfootgage20@yahoo.com |  | "Debris Crew Leader/Crew# Adam Hutcheson/504 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 504" | 38.6401 | -120.5313 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
118 | 041-673-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5133 | String Canyon Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3845.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-17 | Bio Monitoring Needed for Debris AND Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | Yes | 2022-03-29 | TRUE |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-12-07 | 2021-12-09 | 2022-03-30 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & SENT EMAIL. JC 12.09 SPOKE WITH PHIL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/30/22 SPOKE WITH PHILLIP HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-11 |  | 2022-01-13 | 2022-01-13 |  |  | 3 | 2022-01-17 | 2022-01-25 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-03-01 | Yes | 48 | [14 empty] | Phillip Mora | 530-306-2794 | jlaw@rivervalleyins.com | Septic Vehicles on site | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 504 | 38.6375 | -120.5319 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
119 | 041-673-016 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4529 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3832.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-05 | POSITIVE | 2021-11-08 | 2021-11-08 | 2 | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-08 | 2021-11-09 | 2022-02-10 | 11.9 SPOKE TO MICHAEL HE SAID OK. BUT PLEASE CALL IN ADVANCE. PROPANE TANK DID NOT BURN DO NOT REMOVE PROPANE TANK. JC 01/14/22 SPOKE WITH MICHAEL HE SAID OK. JC 02/10/22 SPOKE WITH MICHAEL HE SAID OK TO TREE REMOVAL. JC |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2022-03-19 | Yes | 67 | 2022-03-19 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-23 | 2022-03-25 | 67 | 2022-03-30 |  | 2022-03-26 | 2022-04-01 | 2022-04-01 | 2022-04-01 | MICHAEL SZCZERBA | 530-919-1611 | mikestazman@gmail.com |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 502 | 38.6371 | -120.5341 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
120 | 041-673-017 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5088 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3802.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-11-29 | Yes | 2021-11-29 | 2022-03-25 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-18 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | Yes | 2022-02-28 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-02 | 2021-12-07 | 2022-02-23 | 12.07 NO ANS LEFT VM & TEXT JC 12.07 HO GAVE CONSENT VIA TEXT. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM AND EMAIL. JC 02/23/22 TAMARA SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-22 | Yes | 57 | 2022-03-18 |  | 2022-03-19 | 2022-03-19 |  | 2022-03-23 | 2022-03-25 | 57 | 2022-03-30 |  | 2022-03-26 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Edward & Tamara Pestana | 510-612-1559 , 510-612-1560 | lipsz1@aol.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 507 | 38.6372 | -120.5347 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
121 | 041-681-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5110 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | Bio Monitoring Needed for Debris AND Trees | 2021-11-24 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-02 | TRUE |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-24 | 2021-12-07 | 2022-03-31 | 12.06 NO ANS LEFT VM AND TEXT. JC 12.06 SENT EMAIL. JC 12.07 SPOKE WITH JASON HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 01/28/22 SPOKE WITH JASON ABT REMOVING TREE IN WAY OF DEBRIS REMOVAL. HE SAID OK. JC 03/31/22 SPOKE WITH JASON HE OK FOR TREE REMOVAL. JC |  |  |  | 2022-03-03 |  | 2022-03-04 | 2022-03-04 |  |  | 1 | 2022-03-04 | 2022-03-14 | 7 | Approved | [12 empty] | 2022-03-15 | 2021-11-08 | Yes | 98 | [14 empty] | JASON & SARAH WILLIAMS | 619-933-8615 | JASON.BRIAN.WILLIAMS@GMAIL.COM | Septic | Debris Crew Leader/Crew# Carondlet Dunbar / #514 Debris Crew WO# Refer to IAP 03/02 to 03/05 Crew 514 | 38.6365 | -120.5347 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-06T18:27:47Z | FALSE
122 | 041-683-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5095 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3783.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-01 | 2022-03-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-01 | Yes | 2022-03-01 | 2022-03-07 | NEGATIVE |  |  |  | 2022-03-01 | Bio Monitoring Needed for Debris AND Trees | 2022-03-01 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-30 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-01 | Yes | 2022-03-16 | TRUE |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-03-07 | 2022-03-08 |  | Abatement Site - No contact Needed Warrant letter 3.28 ok per MP PF | 0 | Melissa Perry |  | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  |  | 3 | 2022-03-16 | 2022-03-24 | 7 | Approved | [12 empty] | 2022-03-25 | 2022-03-31 | Yes | 39 | 2022-03-31 |  | 2022-04-01 | 2022-04-01 |  | 2022-04-06 | 2022-04-07 | 39 |  |  | 2022-04-08 | [7 empty] | Debris Crew Leader/Crew# Fernando Montealegre /#519 Debris Crew WO# Refer to IAP 03/12 to 03/16 Crew 519 | 38.6374 | -120.5359 | Caldor | DR-4619 | Residential |  | 2022-02-28 | Abatement | Central Division | 2022-04-08T19:46:52Z | FALSE | 5
123 | 041-522-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 4968 | Edgewood Cir |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3969.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-07 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  |  |  | FALSE | [41 empty] | 2022-04-02 | Yes | 6 | [14 empty] | Lise Lebel | 530-647-6549 | liselebel237@gmail.com |  |  | 38.6402 | -120.521 | Caldor | DR-4619 | Residential | No | 2022-02-15 | ROE Verified | Central Division | 2022-04-04T23:29:18Z | FALSE
124 | 041-732-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5316 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3775.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-11 | 2021-12-14 | 2022-03-15 | 12.14 NO ANS LEFT VM & TEXT. JC 12.14 SPOKE WITH FRED HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/15/22 SPOKE WITH FRED HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-06 | Yes | 11 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-31 | 2022-04-01 | 11 |  |  | 2022-04-02 |  |  |  | Evelyn Batten, Fred Batten owners Karin Ikesaki agent | 530-919-1074 | battenfred@yahoo.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/ 502 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 502 | 38.6299 | -120.5353 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-02T20:21:57Z | FALSE | 6
125 | 041-732-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5326 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3767.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2022-01-19 | 2022-02-28 | 12.16 NO ANS LEFT VM & TEXT. JC 12.16 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/19/22 NO ANS LEFT VM & TEXT. JC 01/19/22 HO GAVE CONSENT VIA TEXT. JC 02/28/22 NO ANS LEFT VM & TEXT. JC 02/28/22 ROBERT C/B HE SAID OK FOR TREE REMOVAL. JC 03/09/22 Robert called requesting damage claim form. I emailed form to ho on 03/09/22. JC |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 5 | 2022-01-26 | 2022-02-03 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2021-12-23 | Yes | 30 | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  | 2022-03-10 | 2022-03-11 | 30 | 2022-03-17 |  | 2022-03-14 | 2022-03-18 | 2022-03-18 | 2022-03-18 | CHIGAZOLA FRANCES C & ROBERT | 916-955-1155 , 530-503-5684 | bobcfranc@gmail.com |  | Debris Crew Leader/Crew# Enedith Montiel / #501 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 501 | 38.6296 | -120.5353 | Caldor | DR-4619 | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
126 | 041-732-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5401 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3765.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 | 2021-12-11 | 2021-12-14 | 2022-02-21 | 12.14 NO ANS LEFT VM & TEXT. JC 12.14 SPOKE WITH ANDREA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HAN\DLING PROPANE. JC 02/21/22 SPOKE WITH ANDREA SHE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  |  | 5 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2021-10-30 | Yes | 33 | 2022-03-04 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-11 | 2022-03-14 | 33 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | ANDREA LEWIS | 530-503-7621 | kruuis@hotmail.com |  | Debris Crew Leader/Crew# Antonio Ruiz/ #501 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 501 Vehicles on site SEPTIC | 38.6297 | -120.5349 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
127 | 041-732-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5381 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3776.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | Yes | 2022-03-01 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-10 | 2021-12-16 | 2022-03-02 | 12.15 NO ANS LEFT VM. JC 12.16 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/02/22 NO ANS NO VOICEMAIL. SENT EMAIL. JC 03/02/22 SPOKE WITH ROBERT HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-18 | 2022-01-18 |  |  | 5 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-17 | Yes | 12 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-11 | 2022-03-14 | 12 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Robert Ericksen | 916-397-1899 | bobericksen@comcast.net | Septic | Debris Crew Leader/Crew# Sahoi Mclean/ #501 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 501 | 38.6303 | -120.5348 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
128 | 041-581-006 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 7685 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3992.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-27 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-26 | No | [6 empty] | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | N/A | Yes | 2022-03-14 | Yes | 2022-04-02 | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 |  |  | 2022-04-04 | 12.4 SPOKE WTH VICKY SHE SAID OK. JC 01/17/22 NO ANS LEFT VM & TEXT. JC 01/25/22 SPOKE WITH VICKY SHE SAID OK AND VENDOR WILL HANDLE PROPANE TANK. JC 04/04/22 FOLLOW-UP CALL. SPOKE WITH VICKY SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2021-11-02 | Yes | 21 | [14 empty] | VICKY BRUNDIGE | 530-919-7547 | vbrundige@sbcglobal.net |  |  | 38.6419 | -120.513 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-05T02:07:47Z | FALSE
129 | 041-582-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7676 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4012.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-15 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-08 | No | [6 empty] | 2022-02-12 | Bio Monitoring Needed for Trees, not Debris | 2021-12-10 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 |  |  | 2022-01-20 | 01/20/22 SPOKE WITH GREGORY HE SAID OK. JC | [27 empty] | 2021-11-03 | Yes | 67 | 2022-02-12 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-16 | 2022-02-17 | 67 |  |  | 2022-02-18 |  | 2022-02-18 | 2022-02-18 | GREGORY COBABE | 916-289-9665 | gregcobabe@outlook.com |  |  | 38.6424 | -120.5126 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | -3
130 | 041-522-005 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4978 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3963.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-22 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-22 | 2021-11-03 |  | 11.3 NO ANS LEFT MESS. JC |  |  |  | 2021-11-06 |  | 2021-11-09 | 2021-11-09 |  |  | 4 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-10 |  |  | 2021-12-11 | 2021-12-11 | 2021-12-13 | Wallace and Lisa Lebel | 530-957-5611 |  |  | "Debris Crew Leader/Crew# Cynthia Sanderson/503 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 503" | 38.6402 | -120.5205 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
131 | 041-522-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7235 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3925.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-02-21 | 02/01/22 SPOKE WITH SHERRON SHE GAVE PRE APPROVAL. . NO PROPANE TANKS ON PROPERTY. JC 02/21/22 SPOKE WITH SHERRON SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-24 | Yes | 47 | 2022-03-02 |  | 2022-03-03 | 2022-03-03 |  | 2022-03-10 | 2022-03-11 | 47 |  |  | 2022-03-14 |  | 2022-03-14 | 2022-03-14 | Sherron Patricia Burleson | 530-417-7728 | burlesonsherron@yahoo.com |  |  | 38.6397 | -120.5204 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
132 | 041-523-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7230 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3884.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-13 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-22 | 2021-11-23 | 2022-01-19 | 11.22 NO ANS LEFT VM. JC 11.23 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/19/22 NO ANS LEFT VM. TEXT AND EMAIL. JC 01/19/22 JOHN C/B HE SAID OK. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2022-01-19 | Yes | 19 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-05 | 2022-03-07 | 19 | 2022-03-10 |  | 2022-03-08 | 2022-03-19 | 2022-03-19 | 2022-03-19 | JOHN THARP | 916-833-5525 | ROBERTDABRUCE1972@GMAIL.COM | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#501 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 501 | 38.6391 | -120.5206 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
133 | 041-523-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7220 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3908.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | 2022-03-04 | Yes | 2022-03-04 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-22 | 2021-12-21 | 2022-03-23 | "12.21 NO ANS LEFT VM & TEXT. JC 12.21 HO GAVE CONSENT VIA TEXT. JC" 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/25/22 WALTER C/B HE SAID PLEASE REMOVE THE PROPANE TANK. HE GIVES PRE CONSENT TO REMOVE HAZARDOUS TREES. JC 03/23/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/23/22 WALTER GAVE VERBAL CONSENT VIA VOICEMAIL. JC |  |  |  | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  |  | 6 | 2022-01-24 | 2022-02-01 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2022-01-24 | Yes | 19 | [14 empty] | NAKABAYASHI WALTER | 530-919-7198 | walkonwally@gmail.com | Septic | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP -- to -- Crew 504 | 38.6392 | -120.521 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
134 | 041-523-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7227 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3871.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 7 | 3 | 0 | 1 | 0 | 3 | 0 | 14 |  |  | 12 | TRUE | Yes | Leave |  | 2021-12-10 | Yes | 2021-12-10 | 2021-12-15 | NEGATIVE |  |  |  | 2021-11-30 | Bio Monitoring Needed for Debris AND Trees | 2021-12-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-15 | 2022-01-21 | 2022-02-26 | "12.20 NO ANS LEFT VM & TEXT. JC 12.20 HO GAVE CONSENT VIA TEXT. JC" 01/21/22 MAUREEN SAID OK. JC 02/14/22 VENDOR HANDLING PROPANE. JC 02/26/22 NO ANS LEFT VM & TEXT. JC 02/26/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-25 |  | 2022-01-27 | 2022-01-27 |  |  | 5 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-08 | Yes | 3 | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  | 2022-03-10 | 2022-03-21 | 3 | 2022-03-25 |  | 2022-03-23 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Maureen Flores | 530-957-8768 | moefrancesflores@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson / #507 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 507 | 38.6387 | -120.5205 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
135 | 041-532-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7290 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3884.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2022-02-21 | Bio Monitoring Needed for Trees, not Debris | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-13 | 2021-11-15 | 2022-02-10 | 11.15 NO ANS LEFT VM.JC 11.15 SPOKE WITH TERRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE TANK JC 02/10/22 SPOKE WITH TERRY HE SAID OK TO TREE REMOVAL. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-05 | Yes | 23 | 2022-02-25 |  | 2022-02-26 | 2022-02-26 |  | 2022-03-04 | 2022-03-05 | 23 | 2022-03-10 |  | 2022-03-08 | 2022-03-14 | 2022-03-14 | 2022-03-14 | TERRY & KIM MALONE | 916-726-0255 | malonekch@yahoo.com | Septic | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 502 | 38.6398 | -120.518 | Caldor | DR-4619 | Residential | Yes | 2021-10-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
136 | 041-532-013 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 7259 | Grizzly Creek Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3863.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-02-04 | Bio Monitoring Needed for Trees, not Debris | 2022-02-07 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [58 empty] | Lindsey & Curtis Roles | 530-417-4691 | Lroles@marshallmedical.org |  |  | 38.6388 | -120.5195 | Caldor | DR-4619 | Residential | Yes | 2022-01-26 | ROE Verified | Central Division | 2022-04-07T20:40:31Z | FALSE
137 | 041-532-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7249 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3860.66 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | Yes | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-12-07 | 2021-11-30 |  | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH LINDSEY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 SPOKE WITH LINDSEY SHE SAID OK. JC |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 6 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-25 | Yes | 6 | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  | 2022-03-10 | 2022-03-11 | 6 | 2022-03-17 |  | 2022-03-14 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Curtis & Lindsey Roles | 530-417-4691 | lroles@marshallmedical.org | Septic | Debris Crew Leader/Crew# Zara Armani/ #503 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 503 | 38.6386 | -120.5198 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
138 | 041-541-007 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7244 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-24 | 2021-11-29 |  | 11.29 SPOKE WITH JOLENE SHE SAID OK BUT SHE WANTS TO BE THERE FOR THE REMOVAL. PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 34 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2021-12-07 | No | 0 | [8 empty] | 2022-02-10 |  |  | 2022-02-12 | 2022-02-12 | 2022-02-12 | Jolene Gillespie | 530-559-1699 | Jolenemg@sbcglobal.net | Other Septic | Debris Crew Leader/Crew# Cynthia Sanderson /#501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 501 | 38.638 | -120.5197 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
139 | 041-541-009 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Ready for Tree Felling | Next Step: N/A | Soil Borings | Hold | 7230 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3846.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 16 | 0 | 1 | 0 | 0 | 3 | 0 | 20 |  |  | 9 |  | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-16 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-14 | 2022-01-21 |  | 12.10 NO ANS LEFT VM. JC 12.11 NO ANS LEFT VM JC 12.14 SPOKE WITH GREGG HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 HO SAID OK. JC 04/08/22 Call abt. vehicle on property. No ans left VM & text. jc |  |  |  | 2022-01-24 |  | 2022-01-26 | 2022-01-26 |  |  | 5 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape | 2022-04-01 |  |  | 2022-02-17 | 2022-02-25 | Re-scrape | 2022-03-18 | 2022-03-28 | Soil Boring |  |  |  |  | 2021-12-02 | Yes | 12 | [14 empty] | Gregg Weed | 530-957-1382 | gummybear99@att.net | Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 515 | 38.6381 | -120.5204 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T18:55:09Z | FALSE
140 | 041-541-010 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7222 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3850.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 |  |  | 4 |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-05 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-25 | 2022-01-26 | 2022-03-05 | 01/26/22 SPOKE WITH SANFORD HE SAID OK. VENDOR HANDLING PROPANE TANK. JC 03/05/22 SPOKE WITH SANFORD HE SAID OK. JC |  |  |  | 2022-01-29 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-07 | Yes | 10 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-24 | 2022-03-25 | 10 |  |  | 2022-03-30 |  |  |  | Sanford L. Graves | 310-686-2150 | samjr@att.net |  | Debris Crew Leader/Crew# Adan Mattsson/ #507 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 507 | 38.6382 | -120.5208 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 14
141 | 041-541-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7212 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3851.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No | Take |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-29 | 2021-12-02 | 2022-03-05 | 12.02 Contacted homeowner, okayed debris removal RCV 01/18/22 SPOKE WITH CAROLYNDA SHE SAID OK. JC 03/05/22 NO ANS LEFT VM & TEXT. JC 03/05/22 ﻿CAROLYNDA C/B SHE SAID OK FOR TREE REMOVAL. JC 03/27/22 Spoke to with Carolynda she said to please remove the propane tank. jc |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-20 | Yes | 13 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-17 | 2022-03-18 | 13 | 2022-03-25 |  | 2022-03-23 | 2022-04-02 | 2022-04-02 | 2022-04-04 | Roy & Carolynda Rodgers | 530-305-3451 | carolynda7212@sbcglobal.net | Septic | Debris Crew Leader/Crew# Cynthia Sanderson /#501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 501 | 38.6382 | -120.5211 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-04T23:40:11Z | FALSE | 8
142 | 041-551-008 | Full Program ROE (debris + trees) | Ready for Final Sign-off | Passed Tree Completion Check | Next Step: N/A | FSO Pending Vehicles | Ready for FSO | 5018 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3848.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 |  | No |  |  | No |  |  | Yes |  |  |  |  | FALSE | FALSE | [7 empty] | 0 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-08 | 2022-01-21 | 2022-03-04 | 12.09 SPOKE WITH RUSSELL HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE IS NOT DAMAGED PLEASE DO NOT REMOVE. JC 01/21/22 RUSSELL SAID OK. JC "03/03/22 NO ANS LEFT VM & TEXT. JC 03/04/22 NO ANS LEFT VM & EMAIL.JC" 03/04/22 - Left a VM and text - MP - clearing for scheduling | 4 | Melissa Perry |  | 2022-01-24 |  | 2022-01-25 | 2022-01-25 |  |  | 4 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2022-01-20 | Yes | 16 | 2022-03-08 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-17 | 2022-03-25 | 16 | 2022-03-30 |  | 2022-03-26 |  |  |  | Russell Owen | 530-556-0848 | russcarrie@msn.com |  | Debris Crew Leader/Crew# Adam Mattsson/ # 507 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 507 | 38.6381 | -120.5225 | Caldor | DR-4619 | Residential | Yes | 2021-11-19 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
143 | 041-551-012 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4997 | Merrywood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3891.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-24 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-24 | 2021-11-29 | 2022-01-24 | 11.29 SPOKE WITH CAROLYN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/19/22 NO ANS LEFT VM, TEXT AND EMAIL. JC 01/24/22 SPOKE WITH CAROLYN SHE SAID OK. JC |  |  |  | 2021-12-02 |  | 2021-12-04 | 2021-12-04 |  |  | 2 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2022-01-19 | Yes | 52 | 2022-02-21 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-03 | 2022-03-04 | 52 | 2022-03-11 |  | 2022-03-07 | 2022-03-24 | 2022-03-24 | 2022-03-24 | William & Carolyn Schuster | 650-444-3889 | carolandbill15@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 503 | 38.6387 | -120.5231 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 3
144 | 041-562-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4969 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3879.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | Yes |  | 2021-11-08 | No | TRUE | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | POSITIVE | 2021-11-03 | 2021-11-03 | 3 | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-13 | 2021-11-15 | 2022-01-20 | 11.15 NO ANS LEFT VM. JC 11.15 SPOKE WITH JED HE SAID OK BUT PLEASE CALL IN ADVANCE. 12-2 VENDOR HANDLING PROPANE TANK. PF 01/20/22 SPOKE WITH JED HE SAID OK. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Approved | [12 empty] | 2021-12-03 | 2021-11-05 | Yes | 54 | 2022-01-26 |  | 2022-01-26 | 2022-01-26 |  | 2022-01-29 | 2022-02-03 | 54 | 2022-02-10 |  | 2022-02-04 | 2022-02-12 | 2022-02-12 | 2022-02-12 | JED SHAPRIO & TERRIE TAYLOR | 916-768-2952 | jed.b.shapiro@gmail.com | Septic | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 509 | 38.6377 | -120.5176 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
145 | 041-562-012 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 5011 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3906.78 |  |  |  |  | TRUE | New Owner |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  |  | 02/21/22 NO ANS NO VM SENT EMAIL. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 HO C/B SHE SAID SHE NO LONGER OWNS THE PROPERTY AND TO PLEASE STOP CALLING HER. JC | [27 empty] | 2022-03-09 | Yes | 106 | [14 empty] | Robin L. Lewis | 520-848-1430 | robinlaurielewis@gmail.com |  |  | 38.6363 | -120.5184 | Caldor | DR-4619 | Residential | No | 2021-11-09 | ROE Verified | Central Division | 2022-04-07T20:40:58Z | FALSE
146 | 041-562-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5013 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3926.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No |  | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-01 | Yes | 2021-11-02 | 2021-11-05 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-18 | 2021-11-19 | 2022-01-25 | 11.19 NO ANS LEFT VM 11.19 SPOKE WITH DEBRA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. PEASE REMOVE SMALL TANKS. JC 01/24/22 NO ANS LEFT VM & TEXT. JC 01/25/22 NO ANS LEFT VM & EMAIL. JC 01/25/22 DEBRA C/B AND SAID OK. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 6 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2022-01-20 | Yes | 63 | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  | 2022-02-01 | 2022-02-03 | 63 | 2022-02-10 |  | 2022-02-05 | 2022-02-11 | 2022-02-11 | 2022-02-11 | TODD & DEBRA GREGORY | 530-863-8022 | octium08@gmail.com | Septic | Debris Crew Leader/Crew# Glenn Adams /#501 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 501 | 38.6359 | -120.518 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 4
147 | 041-581-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7717 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4012.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2021-12-10 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-03 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-10 | 2021-12-11 | 2022-03-25 | 12.11 SPOKE WITH ROSA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 ROSA SAID OK. JC 3.25 NO ANS. LEFT MESS AND TEXT PF 3.25 NO ANS. LEFT MESS AND TEXT PF 3.25 SPOKE TO ROSA AND SHE SAID OK PF |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Approved | [12 empty] | 2022-02-17 | 2022-01-26 | Yes | 14 | [14 empty] | Rosa Avitia | 818-808-6860 | rose916@gmail.com | Septic | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/02 to 02/6 crew 505 | 38.6425 | -120.5147 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
148 | 041-581-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7701 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4000.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-04 | 2021-12-07 | 2022-02-21 | 12.07 SPOKE LENA SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/21/22 SPOKE WITH PER HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 24 | 2022-01-15 | 2022-01-21 | 5 | Approved | [12 empty] | 2022-01-26 | 2021-11-30 | Yes | 6 | [14 empty] | Lena Radford Per Jermehag | 916-719-0718 | perjermehag@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz Jr /#510 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 510 | 38.642 | -120.5138 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
149 | 041-581-016 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5109 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3985.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | Yes | 2022-02-16 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-30 | 2021-11-03 | 2022-02-21 | 11.3 Spoke with Vicky she said ok. Please call before going. JC 12.4 SPOKE WITH VICKY SHE SAID OK. JC 01/14/22 VICKY SHE SAID OK. JC 01/25/22 SPOKE WITH VICKY SHE SAID VENDOR WILL HANDLE PROPANE TANK. JC 02/21/22 VICKY SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-10 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-05 | Yes | 14 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-14 | 2022-03-15 | 14 | 2022-03-24 |  | 2022-03-17 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Vicky Brundige | 530-919-7547 | vbrundige@sbcglobal.net | Septic | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 502 | 38.6418 | -120.5135 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
150 | 041-582-009 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7710 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4018.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-29 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No |  |  |  | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-30 | 2021-11-03 | 2022-01-24 | 11.3 SPOKE WITH JEFF. HE SAID OK BUT PLEASE CALL IN ADVANCE. HE HAS CONTACTED THE VENDOR ABT TANK. JC 01/24/22 SPOKE WITH JEFFREY HE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-10 |  | 2021-11-11 | 2021-11-11 |  |  | 4 | 2021-11-16 | 2021-11-19 | 4 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Approved | [6 empty] | 2021-12-07 | 2021-11-02 | Yes | 24 | 2022-02-11 | [6 empty] | 12 | [6 empty] | JEFFREY CARTER | 530-919-4016 | j-lcarter@att.net |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 502 | 38.6425 | -120.5139 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
151 | 041-582-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7331 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4033.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-04 | No |  | TRUE |  | Class III | None | FALSE | [10 empty] | 2022-01-24 | 2022-01-25 | 2022-03-25 | 01/25/22 NO ANS LEFT VM & TEXT. JC 01/25/22 PAUL C/B HE SIAD OK. BUT PLEASE CALL IN ADVANCE. THE DRIVEWAY TI HOUSE IS OFF CAPPS CROSSING SIDE. DO NOT REMOVE PROPANE TANK. JC 3.25 SPOKE TO PAUL AND HE SAID OK PF |  |  |  | 2022-01-28 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-31 | Yes | 40 | [14 empty] | Paul & Stephanie Affron | 615-457-4711 | paulaffron@hotmail.com |  | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 510 | 38.6427 | -120.5133 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
152 | 041-591-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4964 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3938.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-20 | 2021-11-24 | 2022-02-10 | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL . JC 11.24 SPOKE WITH GEORGIA SHE SAID OK BUT PLEASE CALL ADVANCE. OWNS PROPANE TANK BUT DOES NOT KNOW IF DESTROYED BY FIRE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 HO WANT PROPANE TANK REMOVED. JC 02/10/22 NO ANS LEFT VM AND TEXT ABT TREE REMOVAL. JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-04 | 2021-12-13 | 6 | Re-scrape |  |  |  | 2022-01-21 | 2022-01-31 | Approved | [6 empty] | 2022-02-01 | 2021-11-18 | Yes | 2 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-23 | 2022-03-25 | 2 | 2022-03-30 |  | 2022-03-26 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Anthony Zepczyk & Georgia Boles | 925-300-8741 | cocacolagrandma@msn.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Crystal Egan/#508 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 508 | 38.6405 | -120.5161 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 8
153 | 041-591-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5090 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3958.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 | 2021-11-15 | 2021-11-17 | 2022-01-20 | 11.17 NO ANS LEFT VM. JC 11.17 ﻿SPOKE WITH TRAVOR HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE LARGE PROPANE TANK BUT PLEASE REMOVE SMALLER TANKS. JC 01/20/22 SPOKE WITH TREVOR HE SAID OK. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-05 | Yes | 5 | 2022-02-14 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-18 | 2022-02-19 | 5 | 2022-03-09 |  | 2022-02-21 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Trevor & Hannah Hammonds | 530-306-7001, 530-409-8245 | hannahhammonds30@gmail.com | Vehicle on site Septic | Debris Crew Leader/Crew# Mattson Adam/#507 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 507 | 38.6411 | -120.5141 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
154 | 041-591-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5106 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3959.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-17 | 2021-11-17 | 2022-03-02 | 11.17 NO ANS MAILBOX FULL. SEND EMAIL JC 11.17 SPOKE WITH NATALYA SHE SAID OK BUT PLEASE CALL IN ADVANCE. SHE IS UNSURE IF THE PROPANE TANK WAS BURNED. JC 01/26/22 SPOKE WITH NATALYA SHE SAID REMOVE TANK IF DAMAGED. JC 03/01/22 NO ANS MAILBOX FULL SENT EMAIL. JC 03/02/22 SPOKE WITH NATALYA SHE OF FOR TREE REMOVAL. CREW DOES NOT NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Soil Boring | 2022-01-11 | 2022-01-19 | Re-scrape | 2022-01-25 | 2022-02-02 | Approved | [6 empty] | 2022-02-04 | 2021-11-24 | Yes | 4 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-10 | 2022-03-11 | 4 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Natalya Duncan | 267-300-2339 | nduncan@guardianassetmgt.com |  | Debris Crew Leader/Crew# Crystal Egan/#508 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 508 | 38.6411 | -120.5134 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
155 | 038-421-005 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 16269 | Strawberry Lane |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 5765.77 |  | 2021-12-04 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-18 | No | [6 empty] | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | Jay & Margaret Draeger | 916-708-0517 | draeger3@gmail.com |  |  | 38.7966 | -120.1425 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
156 | 038-431-003 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 16323 | Strawberry Lane |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 5742.1 |  | 2021-12-04 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-04 | No | 0 | [14 empty] | J. Stephen Schoff | 916-275-0889 | jsschoff@hotmail.com |  |  | 38.7952 | -120.1439 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
157 | 039-230-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 6507 | Silver Fork Road |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 6355.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-08 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [41 empty] | 2021-12-08 | Yes | 34 | [14 empty] | John Sundberg | 925-209-8669 | johnsundberg@gmail.com | Vehicles Onsite |  | 38.6683 | -120.2175 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
158 | 040-020-014 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Not Eligible for Haz Tree Removal | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 104 | 8N49 |  | Somerset | El Dorado |  | Residential | [5 empty] | 4176.59 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1777 |  |  | Yes |  | TRUE | 2022-03-03 | 2022-03-03 | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | TRUE | 5 | 0 | 1 | 1 | 1 | 0 | 0 | 8 | [7 empty] | 2022-03-04 | Yes | 2022-03-04 | 2022-03-09 | POSITIVE | 2022-03-10 | 2022-03-10 | 2 | 2021-12-11 | Bio Monitoring Needed for Debris, not Trees | 2022-03-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-04 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2022-03-10 | 2022-03-14 |  | 3.14 Spoke to Robert its okay t proceed. Gate code 1777 PF |  |  |  | 2022-04-04 |  | 2022-04-06 | 2022-04-06 |  |  | 3 | [18 empty] | Do Not Assess | 0 | [14 empty] | BORTHWICK, ROBERT | 530-642-8532 | RobertABorthwick@yahoo.com | Vehicles Onsite |  | 38.5773 | -120.4909 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
159 | 041-582-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7664 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4032.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-22 | Bio Monitoring Needed for Debris AND Trees | 2021-11-30 | Arch Monitoring Needed for Debris, not Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | Yes | 2022-03-04 | TRUE |  | Class III | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-11-30 | 2021-12-02 | 2022-03-09 | 12.02 Contacted homeowner, okayed debris removal RCV 03/09/22 NO ANS LEFT VM & TEXT JC 03/09/22 SPOKE WITH MELINDA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 34 | 2022-01-27 | 2022-02-04 | 7 | Re-scrape |  |  |  | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2022-01-26 | Yes | 13 | 2022-03-28 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-29 | 2022-03-30 | 13 |  |  | 2022-04-02 |  |  |  | Melinda Morris & Jerrell Huckobey | 916-508-4812 | mkmmorris@yahoo.com |  | Debris Crew Leader/Crew# Antonio Ruiz /#510 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 510 | 38.6423 | -120.512 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-02T20:46:26Z | FALSE | 1
160 | 041-591-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5116 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-11-29 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-14 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-29 | 2021-12-03 | 2022-04-05 | 12.3 NO ANS LEFT VM. JC 12.03 Homeowner okayed start of debris removal RCV 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 VENDOR HANDLING PROPANE TANK. JC 02/21/22 SPOKE WITH BARBARA SHE SAID OK. 03/09/22 BARBARA SAID OK FOR TREE REMOVAL. JC 04/05/22 FOLLOW-UP CALL. SPOKE WITH BARBARA SHE WAS THANKFUL THAT WE CALLED WITH AN UPDATE AND OK FOR TREE REMOVAL. JC" |  |  |  | 2021-12-08 |  | 2021-12-10 | 2021-12-10 |  |  | 35 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2021-12-01 | Yes | 11 | [14 empty] | Barbara Landberg | 530-748-3266 | bubblie4me1@gmail.com |  | Debris Crew Leader/Crew# Glenn Adams/#508 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 508 | 38.6411 | -120.513 | Caldor | DR-4619 | Residential | No | 2021-11-02 | ROE Verified | Central Division | 2022-04-06T01:18:18Z | FALSE
161 | 041-591-021 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4962 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3930.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-13 | 2021-11-15 | 2022-01-20 | 11.15 NO ANS LEFT VM. JC 11.15 SPOKE WITH VIVIAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. WILL CALL VENDOR ABT PROPANE TANK. PF 01/20/22 SPOKE WITH VIVIAN SHE SAID OK.JC |  |  |  | 2021-11-15 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Approved | [6 empty] | 2021-12-15 | 2021-11-19 | Yes | 42 | 2022-03-15 |  | 2022-03-16 | 2022-03-16 |  | 2022-03-23 | 2022-03-25 | 42 | 2022-03-30 |  | 2022-03-26 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Vivian Maroni | 916-247-2073 | vivianmaroni@gmail.com | Septic | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 502 | 38.64 | -120.5162 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
162 | 041-592-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4985 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3930.89 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | Yes |  | 2022-01-26 | No | TRUE | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  | 2022-01-26 |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-10 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-03-10 | Yes | 2022-03-14 | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-14 |  |  |  | 12.16 NO ANS LEFT VM. JC 12.16 SPOKE WITH TOJO HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/15/22 SPOKE TOJO HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-27 |  | 2022-01-29 | 2022-01-29 |  |  | 3 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-03-14 | Yes | 13 | [14 empty] | Tania & Tojo Thomas | 925-876-2677 | tojothomas@sbcglobal.net | Septic | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 510 | 38.6402 | -120.5136 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
163 | 041-611-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4963 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3944.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-02 | No | [6 empty] | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2022-01-05 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-05 | 2022-01-11 | 2022-04-01 | "01/11/22 NO ANS LEFT & TEXT. JC 01/11/22 SPOKE WITH PALOMINO SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 4.01 NO ANS LEFT MESS & SENT TEXT PF" 4.01 @4:16PALOMINO TEXTED BACK AND GAVE HER CONSENT. PF |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-04-01 | Yes | 22 | [14 empty] | PALOMINO GERELLY | 408-509-7691 | gerelly.palomino@gmail.com |  | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 510 | 38.6403 | -120.5126 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-01T23:22:16Z | FALSE
164 | 041-611-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7609 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4007.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2022-02-25 | Bio Monitoring Needed for Debris AND Trees | 2021-12-09 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-18 |  |  | Class II | true | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-09 | 2021-12-10 | 2022-02-21 | 12.10 NO ANS LEFT NO VM SENT EMAIL 12.10 Consent given via email. jc 02/21/22 SPOKE WITH BETTY SHE SAID OK BUT PLEASE CALL SON IN ADVANCE AT 321 745-7158. JC |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 5 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2021-11-23 | Yes | 18 | 2022-02-25 |  | 2022-02-25 | 2022-02-25 |  | 2022-03-02 | 2022-03-03 | 18 | 2022-03-09 |  | 2022-03-04 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Betty Lukacs | 408-378-6669 /SON 321 745-7158 | lynn85463@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani/ #503 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 503 | 38.6403 | -120.5096 | Caldor | DR-4619 | Residential | Yes | 2021-11-01 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 5
165 | 041-611-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7593 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4023.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-30 | 2021-10-30 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 4 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2022-01-17 | Bio Monitoring Needed for Trees, not Debris | 2021-12-09 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-08 | 2021-11-09 | 2022-01-14 | 11.9 SPOKE WITH JENNIFER SHE SAI OK BUT PLEASE CALL IN ADVANCE. TANK WAS HANDLED BY VENDOR. JC 01/14/22 SPOKE WITH JENNIFER SHE SAID OK. JC |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-03 | Yes | 27 | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  | 2022-01-21 | 2022-01-22 | 27 | 2022-02-01 |  | 2022-01-24 | 2022-02-02 | 2022-02-02 | 2022-02-02 | Jennifer Maratsos | 916-792-6248 | jlpecorado@gmail.com | Vehicle On Site Septic | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 509 | 38.6405 | -120.5088 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
166 | 041-611-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7511 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4026.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 4 |  |  |  | TRUE | Yes | Take | 2022-03-07 | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-15 | Bio Monitoring Needed for Debris AND Trees | 2021-12-09 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | true | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-26 | 2022-02-11 | 110.25 Left a voicemail RCV. 10.26 SPOKE TO DELVIN HE SAID OK PLEASE CALL 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 SPOKE WITH DEVIN SAID TO REMOVED PROPANE TANK IF DAMAGED. JC 02/10/22 MAILBOX FULL LEFT TEXT ABT TREE REMOVAL. JC 02/11/22 SPOKE WITH DEVIN HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 |  |  | 24 | 2021-12-04 | 2021-12-10 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-02-14 | Yes | 22 | 2022-03-02 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-08 | 2022-03-09 | 22 | 2022-03-11 |  | 2022-03-10 | 2022-03-24 | 2022-03-24 | 2022-03-24 | DEVIN COMBELLACK | 530-306-0229 | devin8zcombellack@gmail.com |  | Debris Crew Leader/Crew# Sthephanie Fairlee/#502 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 502 | 38.6396 | -120.5087 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
167 | 041-611-020 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Crew ELD 2 | 7455 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3980.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-01-27 | Bio Monitoring Needed for Trees, not Debris | 2022-02-08 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | N/A | Yes | 2022-03-15 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [12 empty] | 2022-02-21 | 02/21/22 SPOKE WITH ALBERTO HE SAID OK FOR TREE REMOVAL. PLEASE CALL IN ADVANCE. DO NOT REMOVE PROPANE TANK. JC | [27 empty] | 2022-01-28 | Yes | 9 | [14 empty] | Alberto D. Reyes | 530-903-3133 | alberto2317@att.net |  |  | 38.6397 | -120.5109 | Caldor | DR-4619 | Residential | Yes | 2022-01-24 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
168 | 041-611-025 | Full Program ROE (debris + trees) | Ready for Tree Operations |  | Next Step: N/A | Ready for Tree Ops (Full Program) | NO ELIGIBLE TREES | 7425 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3955.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 4 |  |  |  |  | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-20 | Bio Monitoring Needed for Trees, not Debris | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-10-20 | 2021-10-26 | 2022-02-16 | 10.26 NO ANS LEFT MESS PF 10.26 SPOKE TO BEV. NEEDS TO BE CALLED FIRST BY TFL. 11.2 Spoke with Paula, she will contact vendor to remove tank. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SPOKE WITH PAULA SHE SAID OK. JC 01/24/22 SPOKE WITH PAULA SHE SAID OK. JC 02/16/22 SPOKE WITH PAULA SHE SAID OK. JC |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 8 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2021-10-27 | Ok to Assess | 0 | [14 empty] | BRIAN & PAULA COLE | 530-409-4262 | PAULA.COLE@ATT.NET |  | "Debris Crew Leader/Crew# Stefanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 502 | 38.6396 | -120.5123 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
169 | 041-611-026 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7413 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3934.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2022-01-05 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-02 | Yes | 2022-03-04 | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-04 | 2022-01-05 | 2022-01-11 | 2022-03-09 | 01/11/22 SPOKE WITH ALEX HE OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/09/22 NO ANS LEFT VM & TEXT JC 03/09/22 ALEX C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-26 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-25 | Yes | 26 | [14 empty] | Alex Cornelsion | 916-767-3065 | alexjcornelison@gmail.com |  | Debris Crew Leader/Crew# Fernando Montealegre/ #515 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 515 | 38.6398 | -120.5127 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
170 | 041-611-027 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7487 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4014.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-10-08 | Yes | 2021-10-11 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-15 | Bio Monitoring Needed for Debris AND Trees | 2021-12-09 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | Class II | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-20 | 2021-11-05 | 2022-01-22 | 11.3 no ans. Left Mess PF 11.4 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC. 11.5 SPOKE WITH RICHARD, HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS THE PROPANE TANK BUT DOES NOT KNOW IF IN WORKING CONDITION. JC "12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 HO GIVES CONSENT VIA TEXT MESS. JC" 01/22/22 NO ANS LEFT VM & TEXT. JC 01/22/22 RICHARD GAVE CONSENT VIA TEXT & VM. JC |  |  |  | 2021-11-08 |  | 2021-11-08 | 2021-11-08 |  |  | 4 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-01 | Yes | 86 | 2022-01-24 |  | 2022-01-26 | 2022-01-26 |  | 2022-01-28 | 2022-01-28 | 80 | [6 empty] | RICHARD & CAROLYNN HALL | 209-603-8151 | ucdavismustangs@gmail.com |  | "Debris Crew Leader/Crew# Stephanie Fairlee/502 Debris Crew WO# Refer to IAP 11/03 to 11/06/ Crew 502" | 38.6397 | -120.5093 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T01:16:30Z | FALSE | 2
171 | 041-611-028 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 2 | 7633 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3972.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2021-12-09 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-02 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-02 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-09 | 2022-01-19 | 2022-03-28 | "12.10 NO ANS LEFT VM & TEXT.JC 12.10 NO ANS SENT EMAIL. JC 12.11 NO ANS LEFT VM. JC" GAVE TO RICHARD. JC 01/14/22 NO ANS LEFT VM & TEXT. JC 01/19/22 NO ANS LEFT VM & TEXT & EMAIL. JC 01/19/22 GARY C/B HE SAID OK. VENDOR HANDLING PROPANE. JC 03/25/22 NO ANS LEFT VM & TEXT. JC 03/26/22 NO ANS LEFT VM & EMAIL. JC 03/28/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/28/22 GARY C/B HE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-29 | 2022-02-07 | 6 | Approved | [12 empty] | 2022-02-09 | 2022-01-26 | Yes | 68 | 2022-04-07 | [6 empty] | 25 | [6 empty] | Gary & Natalyn Browning | 916-257-6470 | garyandn@yahoo.com |  | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 515 | 38.6403 | -120.5106 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T18:12:23Z | FALSE
172 | 041-613-011 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Ready for TFSW | 7512 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4053.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | POSITIVE | 2021-12-01 | 2021-12-01 | 4 | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-05 | No |  | TRUE |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-12-09 | 2022-01-21 |  | 12.10 SPOKE WITH KENNETH HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 KENNETH SAID OK. JC 02/02/22 RETURNED CALL FROM EMAIL. NO ANS LEFT VM & TEXT. JC 02/03/22 KENNETH﻿ CALLED TO CHECK STATUS. JC 03/15/22 SPOKE KENNETH HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-03 |  | 2022-02-04 | 2022-02-04 |  |  | 4 | 2022-02-09 | 2022-02-17 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-01-27 | Yes | 49 | 2022-03-31 |  | 2022-04-02 | 2022-04-02 |  | 2022-04-05 | 2022-04-06 | 49 | [6 empty] | Kenneth & Pamela Trone | 530-622-1508 | ktrone@hotmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 515 | 38.6392 | -120.508 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-08T01:18:18Z | FALSE | 3
173 | 041-613-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 2 | 7516 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4034.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-06 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-24 | 2021-12-02 | 2022-03-02 | 11.29 NO ANS LEFT VM. JC 11:30 NO ANS LEFT VM JC 12.1 SENT EMAIL. JC 12.02 Left voicemail and text RCV 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 SPOKE WITH ZACH HE DOES NOT WANT ANY TREES REMOVED UNTIL HE SEE PHOTOS OF TAGGED HARZARD TREES. HE DOES NOT WANT THE BIG CEDAR TREE THAT FRONTS THE ROAD REMOVED. PLEASE REMOVE PROPANE TANK. 02/04/22 SPOKE WITH ZACH HE REQUEST A COPY OF SURVEY BEFORE TREE REMOVAL PROCESS. Call Zach 415 753- 6020. JC 03/01/22 SPOKE WITH ZACH HE WANTS COPY OF TREE SURVEY BEFORE ANY TREES ARE REMOVED. JC 03/02/22 SENT ZACH THE SURVEY. HE SAID OK FOR TREE REMOVAL. JC 03/02/22 HO SAID OK FOR TREE REMOVAL. JC | Kendall Wilson |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 2 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-11-30 | Yes | 10 | [14 empty] | Zach Trenholm Keiko Trenholm | 415-624-5525///Call Zach 415 753- 6020 | kokomama152@yahoo.com |  | Debris Crew Leader/Crew# Christine Richter/#501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 501 | 38.6395 | -120.5079 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:15:00Z | FALSE
174 | 041-613-013 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7520 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4030.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-02-04 | 01/26/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 01/26/22 SPOKE WITH ZACH HE DOES NOT WANT ANY TREES REMOVED UNTIL HE SEE PHOTOS OF TAGGED HARZARD TREES. HE DOES NOT WANT THE BIG CEDAR TREE THAT FRONTS THE ROAD REMOVED. PLEASE REMOVE PROPANE TANK. Call Zach 415 753- 6020 . JC 02/03/22 CALLED HO TO INFORM HIM THAT i EMAILED THE TREE SURVEY. NO ANS LEFT VM. EMAILED TREE SURVEY. JC 02/04/22 SPOKE WITH ZACK. HE SAID HE WILL CONTACT US BACK AFTER REVIEWING THE SURVEY AS TO IF HE WANTS TO PROCEED WITH HAZARD TREE REMOVAL. JC 02/04/04 HO C/B HE SAID OK TO PROCEED. JC | [27 empty] | 2022-01-22 | Yes | 14 | 2022-03-01 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-07 | 2022-03-09 | 14 |  |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | Zach Trenholm Keiko Trenholm | 415-624-5525/// Call Zach 415 753- 6020 | kokomama152@yahoo.com |  |  | 38.6397 | -120.5079 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
175 | 041-613-014 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7528 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4030.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | Yes | 2022-03-03 | TRUE |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-02 | 2021-12-03 | 2022-03-09 | 12.03 NO ANS LEFT VM. JC 12.03 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL IN ADVANCE. HE HAS 2 PROPANE TANKS;VENDOR WILL HANDLE 1 TANK AND HE WANTS TO REMOVE THE OTHER. HE WILL DISCUSS WHICH ONE WITH CREW LEADER. JC 03/09/22 NO ANS LEFT VM & TEXT JC 03/09/22 JAMES C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 |  |  | 40 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-26 | Yes | 17 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-03-30 | 2022-03-31 | 17 |  |  | 2022-04-04 |  |  |  | James Rideout | 360-632-9992 | jtrideout@icloud.com | Septic | Debris Crew Leader/Crew# Christie Richter/#503 Debris Crew WO# Refer to IAP 12/04/21 to 12/08/21 Crew 503 | 38.64 | -120.5079 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-04T20:16:15Z | FALSE | 1
176 | 041-620-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4681 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3698.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-17 | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-30 | Bio Monitoring Needed for Trees, not Debris | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-10 | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-12-07 | 2021-12-07 | 2022-03-24 | 12.07 NO ANS LEFT VM AND TEXT. JC 12.07﻿ SPOKE WITH CRAIG HE SAID OK. BUT PLEASE CALL IN ADVANCE. NOT SURE IF PROPANE TANK IS DAMAGED BUT WILL DISCUSS WITH CREW LEADER WHEN THEY CALL. JC 03/24/22 NO ANS LEFT VM & TEXT. JC 03/24/22 CRAIG C/B HE SAID OK FOR TREE REMOVAL. NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 27 | 2022-01-19 | 2022-01-27 | 7 | Approved | [12 empty] | 2022-01-29 | 2021-12-02 | Yes | 115 | [14 empty] | Craig & Margaret Lindsay | 916-813-0104 | craig.lindsay@comcast.net | Septic | Debris Crew Leader/Crew# Birdie Bell #504 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 504 | 38.6414 | -120.5374 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
177 | 041-620-015 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4800 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3751.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-03-01 | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-12-08 | 2021-12-09 | 2022-03-23 | 12.09 SPOKE WITH JEREMY HE SAID OK BUT CALLED IN ADVANCE. OWNS PROPANE TANK BUT NOT SURE IF DAMAGED BY FIRE. JC 03/23/22 SPOKE WITH JEREMY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-20 | 2022-01-20 |  |  | 6 | 2022-01-27 | 2022-02-04 | 7 | Re-scrape | 2022-03-10 | 2022-03-18 | Approved | 2022-02-18 | 2022-02-28 | Soil Boring | [6 empty] | 2022-03-21 | 2021-11-22 | Yes | 574 | [14 empty] | Jeremy Swann | 925-989-7766 | jeremyswann@sbcglobal.net | Vehicle on site Septic | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 504 | 38.6393 | -120.5365 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
178 | 041-021-037 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 041-021-037 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4084.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-15 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2022-01-26 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-14 | No |  | TRUE |  |  |  | FALSE | [41 empty] | 2022-03-25 | Yes | 955 | [14 empty] | Richard Schoonover | 408-679-6969 | schoonover47@yahoo.com |  |  | 38.6427 | -120.5096 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
179 | 041-031-007 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5020 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3424.99 |  | 2021-11-16 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-11 | Bio Monitoring Needed for Trees, not Debris | [14 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-02-15 | [31 empty] | 2021-11-16 | No | 0 | [14 empty] | Ernest & Mary Lory | 530-344-1642 | ernielory@aol.com |  |  | 38.6411 | -120.5497 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
180 | 041-040-022 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 041-040-022 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4244.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-02 |  | FALSE | [5 empty] | No | No | No | No | No |  |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-03-09 | Bio Monitoring Needed for Trees, not Debris | 2022-03-21 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [41 empty] | 2022-04-08 | Yes | 175 | [14 empty] | Jan Christensen | 916-261-0284 | jcpinecne7@att.net |  |  | 38.6373 | -120.493 | Caldor | DR-4619 | Residential | Yes | 2022-02-25 | ROE Verified | Central Division | 2022-04-08T18:11:24Z | FALSE
181 | 041-040-043 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 041-040-043 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4166.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 2 | 5 | 0 | 0 | 5 | 1 | 17 |  |  | 7 |  | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-29 | 2021-11-29 | 6 | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [10 empty] | 2021-11-30 | 2021-12-02 | 2022-03-24 | 12.02 Contacted property owner, okayed debris removal start RCV 02/14/22 SPOKE WITH ANNEMARIE SHE SAID TANK WAS REMOVED FROM THIS PROPERTY. BUT PLEASE REMOVE PROPANE TANK FROM 7881 CAPPS CROSSING. JC 3.24 NO ANS. GOT VERIZON V/M.SAYING NOT AVAIL. TRY LATER. SENT TEXT PF"3.24 NO ANS. GOT VERIZON V/M.SAYING NOT AVAIL. TRY LATER. SENT TEXT PF 3.24 ANNEMARIE C/B AND SAID OK PF" |  |  |  | 2022-01-26 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-17 | 2022-02-25 | Approved | [6 empty] | 2022-03-01 | 2022-04-06 | Yes | 490 | [14 empty] | HARRINGTON ROBERT D & ANNEMARIE | 530-957-1550 | dorej1956@hotmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar / #509 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 509 | 38.636 | -120.4962 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-07T04:09:23Z | FALSE
182 | 041-040-044 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7881 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4154.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No |  | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Take |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | Arch Monitoring Needed for Debris AND Trees | Yes | [5 empty] | Yes | 2022-03-14 | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-02 | 2021-12-03 |  | DOGS ON SITE PLEASE CALL TO SCHEDULE ANY SITE VISITS!!!!! 12.03 SPOKE WITH JEANNE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE BOTH PROPANE TANKS. JC 01/21/22 CELL PHONE NOT AVAIL FOR TAKING CALLS sent email abt putting dogs inside for tree assessment. JC 02/14/22 HO WANTS TO SCHEDULE 02/16/22 FOR CREW TO RETURN. JC 03/10/22 SPOKE WITH JEANNE SHE SAID CREW CAN COME OUT ON 02/14/22 AT 9AM OR 02/15/22 AT 9AM. JC 03/11/22 JEANNE SAID OK FOR CREW TO COME OUT ON MONDAY BTW 10AM -12PM ON 03/14/22. JC﻿ 03/17/22 JEANNE TEXT FOR STATUS. SPOKE WITH JEANNE AND GAVE CURRENT STATUS. JC |  |  |  | 2021-12-04 |  | 2021-12-08 | 2021-12-08 |  |  | 37 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-04-07 | Yes | 628 | [14 empty] | HARRINGTON ,ROBERT & DORE, JEANNE | 530-957-1550 | dorej1956@hotmail.com | Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 506 | 38.6358 | -120.4936 | Caldor | DR-4619 | Residential | No | 2021-11-04 | ROE Verified | Central Division | 2022-04-08T16:04:41Z | FALSE
183 | 041-472-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7036 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.31 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-22 | 2021-11-22 | 3 | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-24 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-07 | 2021-11-29 | 2022-02-21 | 11.29 NO ANS LEFT VM. JC 11.29 SPOKE WITH RICK ﻿HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE ALL PROPANE TANKS. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 RICK C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 34 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2021-11-30 | Yes | 21 | 2022-03-01 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-07 | 2022-03-08 | 21 | 2022-03-11 |  | 2022-03-10 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Ricky Charles Yadon, Trustee Yadon Family Revocable Tr | 916-956-3106 | realicky@aol.com | Septic | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 502 | 38.6444 | -120.5232 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
184 | 041-472-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7030 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3979.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 4 |  |  |  | TRUE | Yes | Take | 2022-03-07 | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-20 | 2021-10-25 | 2022-01-20 | 10.25 Spoke with Dennis, acknowledged debris removal start. Would like to be present. RCV 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 SPOKE WITH DENNIS HE SAID OK. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 DENNIS SAID HE WILL CALL VENDOR AND CALL US BACK. 02/14/22 SPOKE WITH DENNIS HE SAID PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 5 | 2021-11-06 | 2021-11-12 | 5 | Re-scrape | 2021-12-04 | 2021-12-10 | Approved | 2021-11-19 | 2021-12-01 | Soil Boring | [6 empty] | 2021-12-13 | 2021-11-02 | Yes | 17 | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  | 2022-02-04 | 2022-02-07 | 17 | 2022-02-11 |  | 2022-02-08 | 2022-02-15 | 2022-02-15 | 2022-03-08 | DENNIS WOMBLE | 707-552-4967 | basecamp7030@sbcglobal.net |  | Debris Crew Leader/Crew# Cindy Sanderson/#503 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 503 | 38.6447 | -120.5231 | Caldor | DR-4619 | Residential | Yes | 2021-10-08 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 1
185 | 041-472-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7006 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3979.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-04 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-02-02 | Bio Monitoring Needed for Trees, not Debris | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | No | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-14 |  |  | 2022-01-24 | 12.4 NO ANS LEFT VM. JC 01/22/22 NO ANS LEFT VM & TEXT. JC 01/24/22 NO ANS LEFT VM & EMAIL. JC 01/24/22 HO GAVE CONSENT VIA EMAIL. JC 01/29/22 NO ANS LEFT VM TO INFORM HO THAT CREW COMING OUT NEXT WEEK. JC | [27 empty] | 2021-12-01 | Yes | 31 | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  | 2022-02-03 | 2022-02-17 | 31 |  |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | Mark & Lisa Mallder | 916-316-3236 | markmallder@gmail.com |  |  | 38.6454 | -120.5223 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
186 | 041-472-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6928 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3957.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2022-02-07 | Bio Monitoring Needed for Trees, not Debris | 2021-11-03 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | Class II | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-05 | 2022-01-19 | 11.4 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC. SPOKE WITH TYLER, HE SAID OK. PLEASE CALL IN ADVANCE. VENDOR TOOK CAR OF TANK. PF 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.06 LEFT VM. JC 01/18/22 NO ANS LEFT VM & TEXT. JC 01/19/22 NO ANS LEFT VM & EMAIL JC 01/19/22 LARRY C/B SAID OK. JC |  |  |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-23 | Yes | 114 | 2022-02-07 |  | 2022-02-09 | 2022-02-09 |  | 2022-02-11 | 2022-02-12 | 114 | 2022-02-18 |  | 2022-02-14 | 2022-03-01 | 2022-03-01 | 2022-03-01 | LARRY & JENNIFER PRADO | 925-202-8968 | jenniferprad@yahoo.com |  | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 503 | 38.6457 | -120.5235 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
187 | 041-481-001 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Ready for TFSW | 7107 | Pinehaven Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | Yes |  | 2022-02-02 | Yes | TRUE | No | Yes | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-08 | 2022-01-19 | Yes | 2022-01-19 | 2022-01-24 | NEGATIVE |  | 2022-02-02 |  | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-02-02 | 2022-02-09 | 2022-03-22 | 02/09/22 NO ANS LEFT VM & TEXT. JC 02/09/22 SPOKE WITH CORBETT HE SAID OK. PLEASE REMOVE PROPANE TANK IF DAMAGED. JC 3.22 MAILBOX IS FULL PF SENT TEXT 3.22 MAILBOX IS FULL PF SENT TEXT PF 3.22 CORBETT C/B AND SAID OK TO PROCEED PF |  |  |  | 2022-02-15 |  | 2022-02-16 | 2022-02-16 |  |  | 2 | 2022-02-17 | 2022-02-25 | 7 | Approved | [12 empty] | 2022-03-01 | 2022-01-20 | Yes | 27 | 2022-04-02 |  | 2022-04-04 | 2022-04-04 |  | 2022-04-07 | 2022-04-08 | 27 | [6 empty] | CORBETT STANDRIDGE | 770-855-1068 | CORBETTSTANDRIDGE@GMAIL.COM |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 505 | 38.6444 | -120.5253 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-08T22:59:27Z | FALSE | 3
188 | 041-481-002 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6867 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3989.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 |  |  | 7 |  | Yes | Leave |  | 2022-01-19 | Yes | 2022-01-19 | 2022-01-24 | NEGATIVE |  | 2022-01-24 |  | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-24 | 2022-01-25 | 2022-03-17 | 01/24/22 NO ANS LEFT VM & TEXT. JC 01/25/22 SPOKE WITH DANNY HE SAID OK. BUT PLEASE CALL IN ADVANCE. PLEASE DO NOT REMOVE THE PROPANE TANK. JC 03/15/22 NO ANS LEFT VM & TEXT. JC 03/16/22 NO ANS LEFT VM & EMAIL.JC 3.17 Spoke to Danny and he said ok PF |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-02-02 | Yes | 3 | 2022-03-29 |  | 2022-03-29 | 2022-03-29 |  | 2022-03-31 | 2022-04-01 | 3 |  |  | 2022-04-02 |  |  |  | Danny Taylor | 916-639-3876 | Taylor.madedanny@yahoo.com |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #509 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 509 | 38.6442 | -120.5251 | Caldor | DR-4619 | Residential | Yes | 2021-12-09 | ROE Verified | Central Division | 2022-04-02T20:53:50Z | FALSE | 2
189 | 041-481-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6855 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3996.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2022-01-20 | Yes | 2022-01-20 | 2022-01-25 | POSITIVE | 2022-01-27 | 2022-01-27 | 3 | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-27 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-27 | 2022-01-27 | 2022-03-22 | 01/27/22 SPOKE WITH TIFFANY SHE SAID OK. BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK ON PROPERTY. JC 3.21 No Ans. No V/M SENT TEXT PF 3.21 Since this PO has no v/m sat up on her phone I sent an email today.PF 3.22 NO ANS. NO V/M SENT TEXT PF 3.22 TIFFANY ANSWERED THE EMAIL SAYING ALL TREES WERE CUT DOWN BY PGE. I EXPLAINED WE HAVE TO GO THERE-SHE AGREED TO PROCEED. PF |  |  |  | 2022-02-12 |  | 2022-02-14 | 2022-02-14 |  |  | 1 | 2022-02-14 | 2022-02-22 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-03-21 | Yes | 40 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-04-02 | 2022-04-02 | 40 |  |  | 2022-04-05 |  |  |  | Tiffany Cawelti | 530-903-7815 | tcawelti@peterseng.com |  | Debris Crew Leader/Crew# Carondlet Dunbar / #505 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 505 | 38.6441 | -120.5256 | Caldor | DR-4619 | Residential | Yes | 2021-12-03 | ROE Verified | Central Division | 2022-04-06T15:58:46Z | FALSE | 4
190 | 041-481-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6849 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4002.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2021-12-07 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-06 | 2021-12-07 | 2022-03-04 | 12.07 SPOKE WITH ALI HE SAID OK BUT CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/04/22 SPOKE WITH ALI HE SAID OK. JC |  |  |  | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  |  | 4 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-02 | 2022-01-31 | Yes | 1 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-08 | 2022-03-09 | 1 | 2022-03-10 |  | 2022-03-10 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Wais M.Ali | (415)900‐8185 | lazaruslost@gmailecOm |  | Debris Crew Leader/Crew# Terrance Harrison / #502 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 502 | 38.6436 | -120.5257 | Caldor | DR-4619 | Residential | Yes | 2021-11-22 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 1
191 | 041-481-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6841 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4009.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [10 empty] | 2021-11-30 | 2021-12-06 | 2022-03-03 | 12.03.2021 TRIED CALLING BUT LINE KEEPS GETTING DISCONNECTED. SENT EMAIL. JC 12.04 GAVE TO RICHARD. JC 12.06 Attempted call, line is 'temporarily unavailable'﻿. Sent a text and follow up email. RCV 12.07 MICHELLE GAVE CONSENT TO MOVE FORWARD VIA EMAIL. JC 01/25/22 SENT EMAIL REQUESTING UPDATED CONTACT INFORMATION AND ABT PROPANE TANK. JC 01/26/22 HO EMAILED BACK VENDOR WILL HANDLE PROPANE TANK. JC 03/03/22 SPOKE WITH MICHELLE SHE SAID OK. | 3 | Kendall Wilson |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 38 | 2022-01-28 | 2022-02-07 | 7 | Re-scrape |  |  |  | 2022-02-11 | 2022-02-21 | Approved | [6 empty] | 2022-02-24 | 2022-01-31 | Yes | 2 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-08 | 2022-03-09 | 2 | 2022-03-10 |  | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Michelle Garner | 951-581-0046 | michellegarner78@yahoo.com | Other Septic | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 502 | 38.6433 | -120.5258 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
192 | 041-481-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6823 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4021.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-18 | 2021-11-19 | 2022-01-18 | 11.19 SPOKE WITH CHRIS HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/18/22 SPOKE WITH CHRIS AND HE SAID DO NOT REMOVE ANY TREES. HE DOES NOT WANT TREES REMOVED FROM HIS PROPERTY. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-11-17 | Yes | 5 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-08 | 2022-03-09 | 5 | 2022-03-10 |  | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Chris Sheean | 661-964-9796 | chrissheean55@gmail.com | Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 503 | 38.6427 | -120.5258 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
193 | 041-481-009 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6807 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4034.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 0 | 3 | 1 | 8 |  |  | 8 | TRUE | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-16 | 2021-11-16 |  | 11.16 SPOKE WITH PHILLIP HE SAID OK. BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Soil Boring | 2022-01-26 | 2022-02-03 | Re-scrape | 2022-02-09 | 2022-02-17 | Approved | [6 empty] | 2022-02-19 | 2022-01-26 | No | 0 | [8 empty] | 2022-03-09 |  |  | 2022-03-10 | 2022-03-10 | 2022-03-10 | Phillip Dayton | 916-849-5672 |  | Septic Vehicles on site | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 503 | 38.6421 | -120.5258 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
194 | 041-482-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 6850 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3997.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 5 | 0 | 7 | [7 empty] | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | Yes | 2022-04-02 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 |  |  | 2022-04-04 | 01/19/22 SPOKE WITH JOSEPH HE SAID OK. JC 4.4 SPOKE TO JOESPH AND HE SAID OK PF | [27 empty] | 2022-01-19 | Yes | 30 | [14 empty] | Joseph Gilmete | 510-292-5000 | joegilmete1@gmail.com | Vehicles Onsite |  | 38.6435 | -120.525 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T02:05:42Z | FALSE
195 | 041-482-007 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6820 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4008.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 |  |  | 2022-02-22 | 02/21/22 NO ANS MAILBOX FULL LEFT & TEXT. JC 02/21/22 JEFF GAVE CONSENT VIA TEXT MESSAGE. JC | [27 empty] | 2022-01-22 | Yes | 20 | 2022-03-08 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-18 | 2022-03-19 | 20 |  |  | 2022-03-21 |  | 2022-03-21 | 2022-03-21 | Jeff Ifey | 408-857-9613 | jefftheiman444@gmail.com |  |  | 38.6425 | -120.5251 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
196 | 041-482-008 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6810 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4010.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-04 |  | FALSE | [5 empty] | No | No | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-07 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 |  |  | 2022-03-09 | 12.4 SPOKE WITH LINDA SHE SAID OK. JC 01/20/22 SPOKE WITH RICHARD HE SAID OK BUT CALL IN ADVANCE. JC 03/09/22 SPOKE WITH RICHARD TO GIVE UPDATED STATUS ON TREE REMOVAL. HE SAID OK FOR TREE REMOVAL BUT PLEASE CALL IN ADVANCE. JC 03/30/22 SPOKE WITH RICHARD HE WANTS SOMEONE TO COME TO RE-ASSESS THE SOUTH SIDE OF THE PROPERTY FOR BURNED TREES THAT ARE NOT MARKED FOR REMOVAL. JC | [27 empty] | 2022-03-21 | Yes | 26 | 2022-03-26 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-31 | 2022-04-01 | 26 |  |  | 2022-04-02 |  | 2022-04-02 | 2022-04-04 | Richard and Linda Kroneder | 925-413-0302, 925-413-0301 | lkroneder@comcast.net |  |  | 38.6422 | -120.5251 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-04T16:12:42Z | FALSE | 3
197 | 041-514-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4961 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4005.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-29 | 2021-12-06 | "10.28 NO ANS LEFT MESS PF 10.29 SPOKE TO MR STONE HE SAID OK BUT PLESE CALL BEFORE GOING. PF" 11.2 Left mess. JC 11.3 left mess. JC 11.3 Robert called back, he contacted vendor. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL JC 12.06 SPOKE WITH ROBERT HE SAID OK. JC 01/14/22 LEFT VM FOR HO ABT TREE REMOVAL. JC 01/17/22 NO ANS LEFT VM & TEXT. JC 01/17/22 ROBERT CALLED TO COMFIRM WORK TO BE COMPLETED. JC |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 4 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-19 | 2021-11-09 | Yes | 31 | 2022-01-08 |  | 2022-01-10 | 2022-01-10 |  | 2022-01-12 | 2022-01-17 | 31 | 2022-01-31 |  | 2022-01-18 | 2022-02-04 | 2022-02-04 | 2022-02-04 | ROBERT STONE | 707-332-1870 | stonicus@att.net |  | "Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 503" | 38.6414 | -120.5193 | Caldor | DR-4619 | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
198 | 041-514-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4953 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4012.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-28 | 2021-12-04 | "10.28 NO ANS LEFT MESS PF 10.28 SHARON C/B AND SAID OK. CALL FIRST PLEASE PF" "12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SENT5 TEXT MESS. JC 12.4 SHANEA GAVE CONSENT VIA TEXT. JC" |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 5 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-20 | 2021-10-28 | Yes | 10 | 2022-01-10 |  | 2022-01-11 | 2022-01-11 |  | 2022-01-13 | 2022-01-14 | 10 | 2022-01-31 |  | 2022-01-15 | 2022-02-03 | 2022-02-03 | 2022-02-03 | MICHAEL & SHANEA TUCKER | 530-919-9961 | SHANEABISHOP@HOTMAIL.COM |  | "Debris Crew Leader/Crew# Cynthia Sanderson﻿/503 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 503" | 38.6414 | -120.5197 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
199 | 041-514-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7171 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4025.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | Yes |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 5 |  |  |  | TRUE | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-18 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-17 | 2022-01-18 | 2022-02-10 | 01/18/22 SPOKE WITH AMANDA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT.JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC 02/18/22 SPOKE WITH AMANDA ABT MOVIN BUS FOR TREE CREW. SHE IS CALLING HUSBAND TO GO TO PROPERTY TO ASSIST. OWNERS DO NOT WANT BURNED VEHICLES REMOVED. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-17 | Yes | 36 | 2022-02-18 |  | 2022-02-26 | 2022-02-26 |  | 2022-02-28 | 2022-03-08 | 36 | 2022-03-11 |  | 2022-03-09 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Don & Amanda Lee | 530-434-8334 | alee@paradiseoaks.com |  | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP --- to --- Crew 503 | 38.6416 | -120.5201 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
200 | 041-514-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7185 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4039.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-17 | No Activity/Nest Building Removed |  |  | Complete | N/A | [5 empty] | No | None | FALSE | [12 empty] | 2022-02-10 | 02/10/22 SPOKE WITH MARSHALL HE SAID OK BUT PLEASE CALL IN ADVANCE. JC | [27 empty] | 2022-01-29 | Yes | 32 | 2022-02-17 |  | 2022-02-18 | 2022-02-18 |  | 2022-02-21 | 2022-02-25 | 32 |  |  | 2022-02-26 |  | 2022-02-26 | 2022-02-28 | Marshall Stone | 530-621-1019 |  |  |  | 38.6418 | -120.5193 | Caldor | DR-4619 | Residential | No | 2021-12-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
201 | 041-514-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7229 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4024.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-05 | 2021-11-09 | 2022-01-14 | 11.8 NO ANS LEFT VM. JC 11.9 SPOKE WITH MR. CARDER HE SAID OK, BUT PLEASE CALL IN ADVANCE. VENDOR IS HANDLING PROPANE TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SPOKE WITH CARL HE SAID OK. JC 01/14/22 HO SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 1 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-04 | Yes | 20 | 2022-01-31 |  | 2022-01-31 | 2022-01-31 |  | 2022-02-02 | 2022-02-03 | 20 | 2022-02-11 |  | 2022-02-05 | 2022-02-11 | 2022-02-11 | 2022-02-11 | CARL CARDER | 916-508-0413 | pierianstudio@gmail.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 506 | 38.6426 | -120.5174 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
202 | 041-522-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4948 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3972.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 2 |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | 2022-03-30 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-22 | 2021-11-24 | 2022-03-01 | 11.23 NO ANS LEFT VM. JC 11.24 SPOKE WITH JULIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 03/01/22 NO ANS LEFT & TEXT. JC 03/01/22 HO GAVE CONSENT VIA TEXT. JC 04/01/22 FOLLOW-UP CALL. NO ANS LEFT VM & TEXT. JC 04/01/22 JULIE C/B SHE IS OK WITH TREE REMOVAL. JC |  |  |  | 2021-12-01 |  | 2021-12-04 | 2021-12-04 |  |  | 2 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2022-04-01 | Yes | 34 | [14 empty] | Julie Lawson | 916-531-9163 | lawsonjewels@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#508 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 508 | 38.6407 | -120.522 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T23:16:33Z | FALSE
203 | 041-691-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10115 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3847.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | POSITIVE | 2021-12-03 | 2021-12-03 | 2 | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-21 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-08 | 2022-02-22 | 12.08 SPOKE WITH AMY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/22/22 SPOKE WITH AMY SHE SAID TO CALL JANE AT 916 849-2177. JANE SAID OK FOR TREE REMOVAL BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-12-11 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-08 | Yes | 16 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-19 | 2022-03-21 | 16 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | ODEN CORY & ELIAS AMY ANNE PER AMY: PLEASE CALL JANE GOING FORWARD. | 916 849-2177 | amywck9@gmail.com | Septic | Debris Crew Leader/Crew# / #509 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 509 | 38.6329 | -120.5358 | Caldor | DR-4619 | Residential |  | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
204 | 041-620-027 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5255 | Humbug Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3552.4 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 3 |  |  |  | TRUE | No |  |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2022-01-17 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-17 | 2022-01-18 |  | "12.11 NO ANS LEFT VM & TEXT. JC 12.11 SPOKE WITH JARED HE SAID OK BUT WOULD LIKE TO BE ON SITE DURING DEBRIS REMOVAL PROCESS. NO PROPANE TANKS. JC" 01/18/22 NO ANS LEFT VM & TEXT. JC 01/18/22 HO GAVE CONSENT VIA TEXT. JC 04/05/22 Called to see owner wants to keep or remove truck and trailer on plastic. No Ans left VM and Text. JC |  |  |  | 2022-02-09 |  | 2022-02-14 | 2022-02-14 |  |  | 2 | 2022-02-15 | 2022-02-23 | 7 | Approved | [12 empty] | 2022-02-25 | 2021-12-01 | No | 0 | [8 empty] | 2022-04-05 |  |  | 2022-04-06 | 2022-04-06 | 2022-04-06 | Jared & Monica Spencer | 916-212-9727 | j2spencersison@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani/ #507 Debris Crew WO# Refer to IAP 02/16 To 02/19 Crew 507 | 38.6419 | -120.5454 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
205 | 041-620-028 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5230 | Humbug Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3485.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-10-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-15 | POSITIVE | 2021-11-12 | 2021-11-12 | 21 | 2021-10-14 | Bio Monitoring Needed for Trees, not Debris | 2021-11-22 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-22 | 2021-11-29 | 2022-01-19 | 11.23 NO ANS LEFT VM JC 11.24 NO ANS LEFT VM. SENT EMAIL. JC 11.29 SPOKE WITH ERNEST HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/19/22 SPOKE WITH MARY SHE SAID OK. JC |  |  |  | 2021-12-03 |  | 2021-12-03 | 2021-12-03 |  |  | 6 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2022-01-19 | No | 0 | [8 empty] | 2022-04-05 |  |  | 2022-04-06 | 2022-04-06 | 2022-04-06 | ERNEST &MARY LORY | 530-344-1642 | ERNIELORY@AOL.COM |  | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 504 | 38.6421 | -120.5474 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-06T15:40:05Z | FALSE
206 | 041-631-001 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 7 | 4932 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3851.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | Yes |  | 2022-01-26 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-12-12 | POSITIVE | 2022-01-18 | 2022-01-18 | 26 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-25 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-26 | 2022-01-28 | 2022-03-31 | 12.11 NO ANS LEFT VM. JC 12.14 MO ANS LEFT VM & TEXT. JC 12.14 SENT EMAIL. RALPH SAID OK VIA EMAIL BUT PLEASE CALL IN ADVANCE BECAUSE HE WANT TO BE ON SITE DURINING THE DEBRIS REMOVAL PROCESS. VENDOR HANDLING PROPANE. JC 01/28/22 Ralph said ok. Crew leader left him a voicemail. JC 03/31/22 NO ANS LEFT VM & TEXT. JC 03/31/22 RALPH C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-31 |  | 2022-01-31 | 2022-01-31 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape | 2022-03-10 | 2022-03-18 | Approved | 2022-02-18 | 2022-02-28 | Soil Boring | [6 empty] | 2022-03-21 | 2021-12-02 | Yes | 3 | 2022-04-08 |  | 2022-04-08 | 2022-04-08 |  |  |  | 2 | [6 empty] | HUGHES, RALPH E & TEMME, DAVID | 916-730-7055, 916-799-2887 | rehchoir@gmail.com, dctsacto@gmail.com | Septic | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 502 | 38.6391 | -120.5404 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-08T23:39:10Z | FALSE
207 | 041-631-005 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Tree Removal in Progress | Next Step: N/A | TREE ONLY ROEs | Tree Crew ELD 7 | 4890 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-05 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-05 | No | [6 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-15 | Yes | 2022-03-30 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-04-01 | 01/19/22 NO ANS LEFT VM , TEXT & EMAIL . JC 01/19/22 CAROLYN C/B SHE SAID OK. JC 02/21/22 CAROLYN SAID OK FOR TREE REMOVAL. JC 04/01/22 FOLLOW-UP CALL. NO ANS LEFT VM & TEXT. JC 04/01/22 CAROLYN C/B SHE IS OK WITH TREE REMOVAL. JC | [27 empty] | 2022-01-19 | Yes | 16 | 2022-04-07 |  | 2022-04-08 | 2022-04-08 |  |  |  | 16 | [6 empty] | LYNNE VESEY & CAROLYN BOWKER | 408-255-6657 | CARECARE48@SBCGLOBAL.NET |  |  | 38.6408 | -120.5406 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-09T00:02:47Z | FALSE
208 | 041-631-012 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1b | 4828 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3837.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-01 | 2022-03-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No |  | FALSE | TRUE | 4 | 1 | 0 | 2 | 0 | 1 | 0 | 8 | [7 empty] | 2022-03-01 | Yes | 2022-03-01 | 2022-03-07 | NEGATIVE |  |  |  | 2022-03-01 | Bio Monitoring Needed for Debris AND Trees | 2022-03-01 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-30 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-11 | Yes | 2022-03-14 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-03-07 | 2022-03-08 |  | Abatement Site - No contact Needed 3.28 Warrant Letter | 0 | Melissa Perry |  | 2022-03-10 |  | 2022-03-14 | 2022-03-14 |  |  | 3 | 2022-03-16 | 2022-03-24 | 7 | Approved | [12 empty] | 2022-03-25 | 2022-03-08 | Yes | 40 | 2022-04-01 |  | 2022-04-04 | 2022-04-04 |  |  |  | 40 | [10 empty] | Debris Crew Leader/Crew# Fernando Montealegre /#519 Debris Crew WO# Refer to IAP 03/12 to 03/16 Crew 519 | 38.6397 | -120.5383 | Caldor | DR-4619 | Residential |  | 2022-02-28 | Abatement | Central Division | 2022-04-05T01:13:05Z | FALSE
209 | 041-940-011 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 4783 | Eagle Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3632.21 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [13 empty] | 12.4 LEFT VM. JC | [28 empty] | Do Not Assess | 0 | [14 empty] | Qamar fareed | 916-835-8059 | Qfareed916@gmail.com |  |  | 38.6377 | -120.5452 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
210 | 041-940-014 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Ready for FSO | NO ELIGIBLE TREES | 5037 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3583.85 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1272 |  |  | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-04-05 | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-09 | 2021-12-11 |  | 12.11 NO ANS LEFT VM & TEXT. JC 12.11 HO GAVE CONSENT VIA TEXT. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/14/22 HO TEXT BACK HE SAID TO REMOVE PROPANE TANK. JC |  |  |  | 2022-01-24 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape |  |  |  | 2022-02-18 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-27 | No | 0 | [8 empty] | 2022-04-05 | [5 empty] | Qamar fareed | 916-835-8059 | Qfareed916@gmail.com | Septic | Debris Crew Leader/Crew# Fernando Montealegre / 515 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 515 | 38.6381 | -120.5459 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-05T23:24:00Z | FALSE
211 | 041-940-020 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 4645 | Eagle Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3497.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 5 | 5 | 2 | 7 | 3 | 5 | 0 | 27 |  |  |  |  | Yes | Leave |  | 2022-01-17 | Yes | 2022-01-17 | 2022-01-20 | POSITIVE | 2022-01-25 | 2022-01-25 | 4 | 2021-12-08 | Bio Monitoring Needed for Debris AND Trees | 2022-01-31 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2022-01-31 | 2022-02-01 |  | 02/01/22 NO ANS LEFT VM & TEXT. JC 02/01/22 SPOKE WITH FRANK HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE ANY OF THE SMALL PROPANE TANKS. ﻿JC |  |  |  | 2022-03-08 |  | 2022-03-11 | 2022-03-11 |  |  | 2 | 2022-03-14 | 2022-03-22 | 7 | Approved | [12 empty] | 2022-03-23 | 2022-02-01 | No | 0 | [14 empty] | STENGER, FRANK | 510-828-5286 | fstenger56@gmail.com |  | Debris Crew Leader/Crew# Carla Herbert /#514 Debris Crew WO# Refer to IAP 03/09 to 03/12 Crew 514 | 38.6363 | -120.5504 | Caldor | DR-4619 | Residential | No | 2021-11-19 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
212 | 028-450-007 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 15490 | Las Encinitas Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1953.96 |  | 2021-11-29 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A |  | TRUE | 1801 |  |  | No |  | TRUE | 2021-11-23 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 | [31 empty] | 2021-11-12 | Do Not Assess | 0 | [14 empty] | Celia Hulett, Joan Hoss and Kirsten Mitchell | (530) 210-1769 | cgh@gv.net; joan.hoss@gmail.com | Other Septic Well |  | 39.1154 | -120.9786 | River Fire | DR-4601 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
213 | 028-450-008 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 15390 | Tecolode Trail |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1926.58 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1801 |  |  | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | Yes | No | Yes | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | POSITIVE | 2021-11-02 | 2021-11-02 | 8 | 2021-10-28 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-20 | 2021-11-02 | 2021-11-03 |  | 11.3 NO ANS. LEFT MESS. JC "11.3 NO ANS. LEFT MESS. JC 11.3 CELIA C/B AND SAID OK BUT PLEASE CALL BEFORE GOING THERE LEAVE V/M IF NO ANSWER PF" |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Soil Boring | 2021-12-20 | 2021-12-29 | Approved | [9 empty] | 2022-01-04 | 2021-11-18 | Do Not Assess | 0 | [8 empty] | 2022-01-14 |  |  | 2022-01-21 | 2022-01-21 | 2022-01-21 | Celia Hulett, Joan Hoss and Kirsten Mitchell | (530) 210-1769 | cgh@gv.net; joan.hoss@gmail.com | Other Septic Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 302 | 39.1148 | -120.9797 | River Fire | DR-4601 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
214 | 034-070-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 1350 | Apache Avenue |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6387.54 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2022-03-31 | Yes | 39 | [14 empty] | Anne Battle | 650-305-0615 | brakandbnl@yahoo.com |  |  | 38.851 | -120.0138 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
215 | 036-530-010 | Tree Only ROE (no qualifying debris) | No Asbestos Detected | No Hazard Trees | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 3021 | Reindeer Way |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6468.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-18 | No | [6 empty] | 2021-11-29 | Bio Monitoring Needed for Trees, not Debris | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2022-04-01 | No | 0 | [14 empty] | Daniel Kramer | 530-314-1895 | kramerdank@hotmail.com |  |  | 38.828 | -120.0145 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
216 | 037-010-004 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 20255 | US Highway 50 |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 7343.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [32 empty] | Ok to Assess | [15 empty] | FEDANE, ROHIT | 408-242-6164 | rohitfedane@gmail.com | Septic Vehicles Onsite |  | 38.825 | -120.065 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
217 | 037-010-033 | Full Program ROE (debris + trees) | Site Assessment Complete | Not Eligible for Haz Tree Removal | Next Step: N/A | ELD Pending | NO ELIGIBLE TREES | 037-010-033 | No Address |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 7126.47 |  |  |  |  | TRUE | DTSC Attn |  | N/A | [5 empty] | No | Phase 1 Revisit | TRUE | 2021-11-08 | 2021-11-08 | FALSE | [5 empty] | No | No | Yes | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No | [28 empty] | FALSE | [8 empty] | TRUE | 2022-03-30 | [32 empty] | Do Not Assess | 0 | [14 empty] | Pamela Bernier | 707-477-6182 | pbernier@sonic.net | Other |  | 38.821 | -120.0501 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
218 | 037-070-003 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 20465 | Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 7171.31 |  | 2021-12-08 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | Yes | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | Deborah Hibbard | (801) 712-3258 | hibbardz@pacbell.net | Safety concerns |  | 38.8261 | -120.0551 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
219 | 041-651-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4915 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3954.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | Yes |  | 2021-12-10 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | POSITIVE | 2021-12-04 | 2021-12-04 | 1 | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-10 | 2021-12-10 |  | 12.07 PH# ON FILE NOT ACCEPTING CALLS. JC 12.08 NOT ACCEPTING CALLS SENT EMAIL. JC 12.10 SPOKE WITH PATRICIA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC "3.28 THIS IS NOT A WORKING # PER RECORDING. SENT TEXT AND email PF 3.28 PATRICIA EMAILED BACK AND SAID:It is ok to proceed. Thank you again.PF" |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 6 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-25 | Yes | 34 | [14 empty] | patricia covarrubias flores | NEW PH # 831 210-6971 | acovar2536@yahoo.com | Vehicles Onsite | Debris Crew Leader/Crew# Eric Rocha/ #505 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 505 | 38.6415 | -120.5324 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
220 | 041-620-006 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5011 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3692.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 9 | 0 | 0 | 0 | 0 | 1 | 0 | 10 |  |  | 7 | TRUE | Yes | Leave |  | 2022-01-17 | Yes | 2022-01-17 | 2022-01-20 | NEGATIVE |  |  |  | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | Arch Monitoring Needed for Debris AND Trees | [12 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-20 | 2022-01-21 |  | 01/21/22 SPOKE WITH KELSEY. HO SAID OKAY. PROPANE TANK IS WORKING DO NOT REMOVE. PLEASE CALL IN ADVANCE. JC |  |  |  | 2022-01-29 |  | 2022-01-31 | 2022-01-31 |  |  | 5 | 2022-02-04 | 2022-02-14 | 7 | Re-scrape |  |  |  | 2022-02-18 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2021-11-16 | No | 0 | [8 empty] | 2022-04-05 |  |  | 2022-04-07 | 2022-04-07 | 2022-04-07 | Kelsey Withrow | 916-307-8998 | snowscanyon@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Fernando Montealegre/ #515 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 515 | 38.6381 | -120.5445 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
221 | 041-620-007 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 4975 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3757.29 |  | 2022-01-13 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-18 | No | [6 empty] | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-14 | Arch Monitoring Needed for Debris AND Trees | [12 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | [31 empty] | 2021-11-16 | No | 0 | [14 empty] | Rahul and Nidhi Shekatkar | 925-783-5903 | rahul_rvs@hotmail.com |  |  | 38.6379 | -120.5435 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
222 | 041-620-008 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 4961 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3811.01 |  | 2022-01-27 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [41 empty] | 2022-01-27 | No | 0 | [14 empty] | Lori Carpenter | 530-409-9116 | hedooc@gmail.com |  |  | 38.6378 | -120.5424 | Caldor | DR-4619 | Residential | Yes | 2021-12-02 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
223 | 041-620-009 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-620-009 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3825.11 |  | 2022-01-21 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-11 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [41 empty] | 2022-01-21 | No | 0 | [14 empty] | Thomas & Dorota Hand | 925-234-2670 | notifyth@gmail.com |  |  | 38.638 | -120.5412 | Caldor | DR-4619 | Residential | No | 2021-12-07 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
224 | 041-620-010 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4820 | Blaze Trail |  | Somerset | El Dorado |  | Residential | [5 empty] | 3676.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | Yes |  | 2022-01-26 | No | TRUE | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 3 |  |  |  | TRUE | Yes | Take | 2022-02-17 | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | POSITIVE | 2022-01-20 | 2022-01-20 | 28 | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-02 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-02-02 | 2022-02-03 |  | 02/03/22 NO ANS LEFT VM AND TEXT. JC 02/03/22 HOMEOWNER TEXT BACK TO SAY THEY WANT TO BE ON SITE DURING DEBRIS REMOVAL. PLEASE CALL IN ADVANCE . Do not remove propane tank. JC 02/04/22 HO TEXT BACK TO REQUEST THAT WE TAKE PROPANE TANK. PLEASE REMOVE PROPANE TANK. JC 03/23/22 No Ans left vm & text regarding ATV's left behind. Asked if should be removed or left in place. JC |  |  |  | 2022-02-07 |  | 2022-02-08 | 2022-02-08 |  |  | 3 | 2022-02-10 | 2022-02-18 | 7 | Approved | [12 empty] | 2022-02-21 | 2021-12-21 | No | 0 | [8 empty] | 2022-03-14 |  |  | 2022-03-29 | 2022-03-29 | 2022-03-29 | Jake Biddlecomb and Yvette Taylor | 530-957-3406 | eviegrl73@gmail.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 502 | 38.6425 | -120.5427 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
225 | 038-081-029 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7131 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6604.42 |  | 2021-12-06 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris |  |  | Yes | [11 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-23 |  |  |  | 11.18 SPOKE WITH OWNER . SAID OK BUT PLEASE CALL IN ADVANCE. JC | [27 empty] | 2021-12-06 | Do Not Assess | 0 | [14 empty] | JAMES METCALFE | 650-207-8129 | dasbricka@me.com |  |  | 38.8083 | -120.1057 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
226 | 038-081-030 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7093 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6565.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Trees, not Debris | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class III |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-15 |  | 11.15 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2022-03-23 | Yes | 12 | [14 empty] | John Mamola & Imelda Ramirez | 916-600-7714 | j.mamola@yahoo.com | Septic | Debris Crew Leader/Crew# Melanie Poole /#512 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 512 | 38.8075 | -120.1076 | Caldor | DR-4619 | Residential | Yes | 2021-10-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
227 | 038-081-031 | Full Program ROE (debris + trees) | Ready for Debris Removal | Haz Trees Present | Next Step: N/A | Twin Bridges Ready | Tree Assessment Complete | 7091 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6573.72 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | Yes |  | 2021-12-06 | Yes | TRUE | No | No | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-26 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-28 | 2021-12-06 | 2022-04-08 |  | 12.03.21 NO ANS/LEFT VM IN REPLY TO EMAIL DATED 12.02.21 12.04 Homeowner okayed debris start RCV 01/21/22 NO ANS LEFT VM & TEXT; JC 01/22/22 HO SAID OK. JC 02/14/22 SPOKE WITH HO. SHE ASKED THAT WE DO NOT REMOVE THE RETAINING WALL THAT IS ALONGSIDE THE HILL. SHE WILL RETURN CALL ABT PROPANE TANK. JC vendor handling propane tank. jc 03/30/22 HO CALL AND ASKED THAT SHE BE CONTACTED 24 PRIOR TO ENTERING HER PROPERTY BECAUSE SHE WOULD LIKE TO BE THERE DURING REMOVAL PROCESS. JC 04/08/22 SPOKE ﻿DEANA SHE OK FOR DEBRIS REMOVAL. SHE ASKED THAT CALL HER IN ADVANCE BECAUSE SHE WANTS TO BE ON SITE TO DIRECT CREW ON THE ROAD. DEANA WANTS TO MAKE SURE THE CREW FOLLOWS THE CORRECT ROAD AND NOT TO DAMAGE THE RETAINING WALL. JC | [27 empty] | 2022-03-23 | Yes | 29 | [14 empty] | Deana & Jay Johnson | 530-545-0527 , 916-765-1848 | denajj@yahoo.com | Septic |  | 38.8073 | -120.1079 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T23:22:14Z | FALSE
228 | 038-081-034 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 7137 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6598.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2022-03-29 | Yes | 23 | [14 empty] | TREVOR J SAXTY & JILLIAN A SAXTY | 510-337-0930 | tjs@firstflight.com |  |  | 38.8079 | -120.1054 | Caldor | DR-4619 | Residential | No | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
229 | 038-081-035 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7129 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6591.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Trees, not Debris | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-18 |  | 11.18 NO PH# ON FILE SENT EMAIL JC 11.18 SPOKE TREVOR SHE SAID OK AND DOES NOT NEED TO BE THERE. PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2022-03-24 | Yes | 5 | [14 empty] | SAXTY TREVOR JOHN TR & JILLIAN ACKERMAN | 510 305-6419 | tjs@firstflight.com | Septic Safety concerns | Debris Crew Leader/Crew# Melanie Poole /#512 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 512 | 38.8078 | -120.1056 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
230 | 038-081-036 | Full Program ROE (debris + trees) | Ready for Tree Operations | Needs Assessment | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Needed | 1181 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6619.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 |  | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-16 | 2021-11-18 |  | 11.16 NO ANS LEFT VM. JC 11.16 SPOKE WITH ADAM HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 |  | Ok to Assess | [15 empty] | Adam & Alina Hansel | 530-400-1816 | adhansel1@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Melanie Poole #512 Debris Crew WO# Refer to IAP 11/24 to 12/1 Crew 512 | 38.8084 | -120.1069 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-05T21:34:41Z | FALSE
231 | 038-081-037 | Full Program ROE (debris + trees) | Re-scrape Needed | Needs Assessment | Next Step: N/A | ELD Twin Bridges Rescrapes | Tree Assessment Needed | 1185 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6614.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-21 | 2021-10-21 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-21 | Yes | 2021-10-22 | 2021-10-27 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-08 | 2021-11-10 |  | 11.8 NO ANS LEFT VM. JC 11.10 SPOKE WITH BRAD HE SAID OK BUT PLEASE CALL IN ADVANCE. THE VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape | [14 empty] | Ok to Assess | [15 empty] | BRAD & ANDREA KELLER | 916-214-2220 | traneinvain@yahoo.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 512 | 38.8083 | -120.1069 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-02T01:11:28Z | FALSE
232 | 038-081-038 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1189 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6606.73 |  | 2021-12-09 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | Brad R. Keller & Andrea M. Keller | 916-214-2220 | traneinvain@yahoo.com |  |  | 38.8082 | -120.1069 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
233 | 038-081-039 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1193 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6595.12 |  | 2021-12-08 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | Brad R. Keller & Andrea M. Keller | 916-214-2220 | traneinvain@yahoo.com |  |  | 38.808 | -120.1069 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
234 | 038-082-003 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7084 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6548.09 |  | 2021-12-07 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | [7 empty] | 2022-02-11 | [23 empty] | 2021-12-07 | No | 0 | [14 empty] | Michael, Janice, Robert & Julie Brozek | 916-846-8980 , 916-444-5812 | jsbrozek@aol.com |  |  | 38.8069 | -120.1072 | Caldor | DR-4619 | Residential | Yes | 2021-11-23 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
235 | 038-082-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7116 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6565.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-10 | No | [6 empty] | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 | [31 empty] | 2021-12-06 | Yes | 6 | [14 empty] | FOREST CABINS LLC/PATTY BERRY | 530-644-3000 | pattyberrymail@gmail.com |  |  | 38.8072 | -120.1062 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
236 | 038-082-009 | Full Program ROE (debris + trees) | Pending Asbestos Results | Haz Trees Present | Next Step: N/A | Twin Bridges Pending | Tree Assessment Complete | 7122 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6567.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2022-04-05 | Yes | 2022-04-05 | 2022-04-08 |  |  |  |  | 2022-03-21 | Bio Monitoring Needed for Debris AND Trees | [14 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-15 |  | 2022-04-08 |  | 4.8 SPOKE TO PO DENNIS & LAURA AND THEY SAID OK PF | [27 empty] | 2022-03-26 | Yes | 6 | [14 empty] | Dennis Norgord & Laura Raycraft | 530-391-3004 | dennis@norgord.com |  |  | 38.8072 | -120.1059 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-09T00:01:49Z | FALSE
237 | 038-082-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7128 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6569.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-19 |  | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.19 SPOKE WITH LAURIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 5 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-12-06 | Yes | 4 | [14 empty] | PETER & LAURIE CAIETTI & THOMAS & LISA LENGTAT | 916-416-7577 OR 530 220-5993 | caietti@aol.com, shortfuse4me@aol.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 512 | 38.8072 | -120.1057 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
238 | 038-082-011 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7132 | Sierra Pines Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6568.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-23 | No | [6 empty] | 2021-11-29 | Bio Monitoring Needed for Trees, not Debris | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2021-12-06 | Yes | 3 | [14 empty] | Peter& Laurie Caietti | 916-416-7577 | caietti@aol.com, shortfuse4me@aol.com |  |  | 38.8073 | -120.1055 | Caldor | DR-4619 | Residential | Yes | 2021-11-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
239 | 038-082-012 | Full Program ROE (debris + trees) | Withdrawn | Needs Assessment | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7140 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6577.86 | 2021-11-19 |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-11-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-22 | Yes | 2021-10-23 | 2021-10-27 | POSITIVE | 2021-11-06 | 2021-11-06 | 8 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-23 |  |  |  | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC | [28 empty] | Ok to Assess | [15 empty] | COTTRELL ROGER TR & BARBARA A TR | 650-296-0779, 650-804-0990 | cottrell@slac.stanford.edu, barb_cottrell@yahoo.com | Septic |  | 38.8073 | -120.1052 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
240 | 038-091-004 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | Tree Assessment Complete | 7052 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6545.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class III |  | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-12 | 2021-11-15 |  | 11.15 NO ANS LEFT VM. JC 11.15 SPOKE WITH DOUG HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANKS. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape | [13 empty] | 2022-03-21 | Yes | 7 | [14 empty] | DOUG & HEATHER WRIGHT | 916-802-9184 | dwright72@gmail.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 512 | 38.806 | -120.1081 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-02T02:52:19Z | FALSE
241 | 038-091-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7060 | Sierra Pines Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6543 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | POSITIVE | 2021-12-03 | 2021-12-03 | 6 | 2021-11-20 | Bio Monitoring Needed for Trees, not Debris | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-03 | 2021-12-03 |  | 12.03 SPOKE WITH SHANNON SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2021-12-06 |  | 2021-12-06 | 2021-12-06 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2022-03-21 | Yes | 18 | [14 empty] | Irene Thomas, Shannon Lane (agent) | 415 272-4490 | sirl1@sbcglobal.net | Septic | Debris Crew Leader/Crew# Carla Herbst /#514 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 514 | 38.8062 | -120.1079 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
242 | 038-091-011 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7072 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6547.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2021-12-07 | Yes | 23 | [14 empty] | Arthur & Barbara Huges & Patricia Gahagan | 209 753-8586 | ach57@comcast.net | Septic |  | 38.8065 | -120.1076 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
243 | 038-101-003 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Needs Assessment | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 19056 | Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6546.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH ROBERT HE SAID OK AND HE DOES NOT NEED TO BE THERE. PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 04/07/22 Robert Kennedy called for status. JC |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [18 empty] | Ok to Assess | [15 empty] | ROBERT & TIMOTHY KENNEDY | 916-207-1282 | KENNEDY_1763@MSN.COM | SEPTIC | Debris Crew Leader/Crew# Carla Herbst /#512 Debris Crew WO# Refer to IAP 12/04t o 12/08 Crew 512 | 38.8048 | -120.1066 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
244 | 038-101-007 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7244 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6570.76 |  | 2021-12-08 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-11 | 2021-11-16 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | LEE JAMES E CO TR & JUDY A CO TR | 916-634-6619 | jelee@nogn.org | Septic |  | 38.804 | -120.1084 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
245 | 038-101-017 | Full Program ROE (debris + trees) | Ready for Soil Sampling | No Hazard Trees | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 7308 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6559.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-12-06 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [11 empty] | Tree | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-06 | 2021-11-23 |  | 11.20 NO ANS LEFT VM. JC 11.23 SPOKE WITH ABBAS BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [17 empty] | 2021-12-04 | No | 0 | [14 empty] | ABBAS TOURZANI | 916-220-1294 | tourzani@yahoo.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 512 | 38.8041 | -120.1057 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
246 | 038-101-021 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 038-101-021 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6557.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-15 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Debris AND Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [32 empty] | Ok to Assess | [15 empty] | James & Gemma Brooks | 916-485-3082, 916-483-2146 | jim1899@yahoo.com, gemmaabrooks@yahoo.com |  |  | 38.8044 | -120.1068 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
247 | 038-101-025 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7292 | Sayles Canyon Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6592.43 |  | 2021-12-08 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | James Brooks | 916-483-2146 , 916-485-3082 | jim1899@yahoo.com, gemmabrooks@yahoo.com | Septic |  | 38.8041 | -120.1064 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
248 | 038-101-026 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7300 | Sayles Canyon Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6590.23 |  | 2021-12-08 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | Yes | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | [10 empty] | 2021-12-01 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-08 | No | 0 | [14 empty] | James & Gemma Brooks | 916-483-2146 , 916-485-3082 | jim1899@yahoo.com, gemmabrooks@yahoo.com | Septic |  | 38.8041 | -120.1061 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
249 | 038-101-034 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 038-101-034 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6540.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [32 empty] | Ok to Assess | [15 empty] | Robert Wilfred Hunt | 916-607-5830 | rabbitfarmworks@yahoo.com |  |  | 38.8048 | -120.1076 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
250 | 038-101-035 | Full Program ROE (debris + trees) | Ready for Tree Operations | Needs Assessment | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Needed | 7324 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6589.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-02 | 2021-12-03 |  | 12.03 SPOKE WITH PAUL HE SAID OK. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-04 |  | 2021-12-04 | 2021-12-04 |  |  | 2 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 |  | Ok to Assess | [15 empty] | PAUL & AMY STRICK | 916-716-3198 | DSTRICK@SUREWEST.NET | Vehicles on site Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 512 | 38.8038 | -120.1053 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
251 | 041-651-017 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4930 | Coralaine Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3969.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 4 |  | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-12-02 | POSITIVE | 2021-12-04 | 2021-12-04 | 2 | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-06 | 2022-02-10 | 12.06 SPOKE WITH MARY SHE SAID OK BUT PLEASE CALL MICHELLE AT (916) 807-6800 IN ADVANCE. OWNS PROPANE TANK SHE SAID REMOVE SMALL TANKS BUT DOES NOT KNOW IF LARGE TANK IS DESTROYED. JC 01/25/22 SPOKE WITH MARY SHE SAID REMOVE TANK IF DAMAGED. JC 02/10/22 SPOKE WITH MARY JOE SHE SAID OK. JC |  |  |  | 2022-01-15 |  | 2022-01-15 | 2022-01-15 |  |  | 4 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-11-15 | Yes | 24 | [14 empty] | Mary Joe Kaupan | 916-241-5281 | micheleverree@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 505 | 38.6415 | -120.5319 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
252 | 041-651-018 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4918 | Coralaine Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 4 |  |  |  |  | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-23 | 2021-11-29 | 2022-01-28 | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL. JC 11.29 SPOKE WITH KENNETH HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS THE PROPANE TANK AND WANTS TO DISCUSS REMOVAL WITH CREW LEADER WHEN THEY CALL. JC 01/27/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 01/28/22 NO ANS LEFT VM & EMAIL. JC 01/28/22 HO GAVE CONSENT VIA TEXT. JC 01/28/22 DO NOT REMOVE PROPANE THANK JC 03/25/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/25/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-11-01 | Yes | 19 | [14 empty] | Kenneth and Geneva Paulson | 916-747-2484 | gmaep101@gmail.com | Septic Vehicle On Site | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 505 | 38.6419 | -120.5318 | Caldor | DR-4619 | Residential | No | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
253 | 041-653-001 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 041-653-001 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3990.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  |  | 2022-02-21 | 02/21/22 SPOKE WITH MICHELLE SHE SAID OK FOR TRE REMOVAL. JC | [27 empty] | 2022-01-22 | Yes | 29 | [14 empty] | Michelle Hensley William Nattrass | 530-499-2873 | Misha.hensley@hotmail.com |  |  | 38.642 | -120.5309 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
254 | 041-653-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4925 | Coralaine Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3983.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-14 | 2021-10-25 | 2021-12-04 | 10.25 Spoke with Charles, acknowledged start of debris removal RCV 12.4 SPOKE WITH CHARLES HE SAID. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/26/22 HO TEXT BACK. VENDOR WILL REMOVE PROPANE TANK. JC |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 5 | 2021-11-06 | 2021-11-12 | 5 | Approved | [12 empty] | 2021-11-16 | 2021-11-04 | Yes | 44 | 2021-12-08 |  | 2021-12-10 | 2021-12-10 |  | 2021-12-20 | 2021-12-20 | 44 | 2022-01-25 |  | 2022-01-14 | 2022-01-26 | 2022-01-26 | 2022-01-26 | CHARLES BEACH | 916-216-0536 | BEACH.C@SBCGLOBAL.NET |  | Debris Crew Leader/Crew# Adam Hutchenson/#504 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 5014 | 38.6416 | -120.5311 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 10
255 | 041-653-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4970 | Coralaine Court |  | Somerset | El Dorado |  | Residential | [5 empty] | 3973.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-28 | 2021-10-28 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-05 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-05 | 2021-11-08 | 2021-12-04 | 11.6 NO ANS LEFT VM. JC 11.8 SPOKE WITH MARGARET, SAID OK,BUT PLEASE CALL IN ADVANCE. NO PROPANCE TANK. JC 12.4 SPOKE WITH ﻿MARGARET SHE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-19 | Yes | 43 | 2021-12-10 |  | 2021-12-10 | 2021-12-10 |  | 2021-12-21 | 2021-12-22 | 43 | 2022-01-25 |  | 2022-01-12 | 2022-01-26 | 2022-01-26 | 2022-01-26 | MARGARET CROOKS | 530-409-0178 | guydonahue@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6408 | -120.5309 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 11
256 | 041-661-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5067 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3885.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-10-06 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-14 | 2021-10-26 | 2021-12-04 | 10.26 SPOKE TO SUSAN AND SHE SAID OK PF 11.3 Susan called and she she spoke to vendor and crew. Everything in fine. JC 12.04 SPOKE WITH SUSAN SHE OK. BUT PLEASE CALL IN ADVANCE. |  |  |  | 2021-11-01 |  | 2021-11-03 | 2021-11-03 |  |  | 6 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-20 | 2021-11-01 | Yes | 50 | 2022-01-06 |  | 2022-01-08 | 2022-01-08 |  | 2022-01-11 | 2022-01-14 | 50 | 2022-01-25 |  | 2022-01-14 | 2022-01-27 | 2022-01-27 | 2022-01-27 | SUSAN MASCORELLA | 530-219-2998 | DSARSMOM@GMAIL.COM |  | Debris Crew Leader/Crew# Adan Hutchenson/#504 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 504 | 38.6391 | -120.5343 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 3
257 | 041-661-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 5039 | Rollingwood Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3860.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-02 |  | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-03 | No | [6 empty] | 2022-02-28 | Bio Monitoring Needed for Trees, not Debris | 2022-02-28 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [41 empty] | 2022-04-07 | Yes | 20 | [14 empty] | Earl Craft | 530-919-9714 | craftd80@yahoo.com |  |  | 38.64 | -120.5343 | Caldor | DR-4619 | Residential | No | 2022-02-18 | ROE Verified | Central Division | 2022-04-08T03:58:08Z | FALSE
258 | 041-662-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5070 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3928.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-03 | 2021-12-21 | 2022-03-28 | "12.21 NO ANS LEFT VM & TEXT. JC 12.21 HOMEOWNER GAVE CONSENT VIA TEXT. JC" 02/21/22 SPOKE WITH BRIAN HE SAID OK FOR TREE REMOVAL. JC 03/28/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/28/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-02-02 | Yes | 25 | [14 empty] | ODELL BRIAN R & EDITH L | 925-586-5978 | brianrodell@sbcglobal.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Tarrence Harrison /#515 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 515 | 38.6389 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
259 | 041-662-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5084 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3914.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-11-13 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | POSITIVE | 2021-10-26 | 2021-10-26 | 6 | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-13 | 2021-11-15 | 2021-12-10 | 11.15 SPOKE WITH DONALD HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE TAKE PROPANE TANK. JC 12.10 SPOKE WITH DONALD ABT TREE REMOVAL HE SAID OK. JC |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Approved | [12 empty] | 2021-12-07 | 2021-12-22 | Yes | 46 | 2021-12-22 |  | 2022-01-04 | 2022-01-04 |  | 2022-01-08 | 2022-01-10 | 46 | 2022-01-18 |  | 2022-01-15 | 2022-01-27 | 2022-01-27 | 2022-01-27 | DONALD SNYDER | 530-409-8578 | SNYDERDONALD76@YAHOO.COM |  | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 504 | 38.6386 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
260 | 041-663-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4959 | Coralaine Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3946.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-06 | 2021-12-10 | 2022-03-18 | 12.09 NO ANS LEFT VM & TEXT. JC 12.10 NO ANS LEFT VM & EMAIL. JC 12.10 HO GAVE CONSENT VIA EMAIL. JC 03/16/22 NO ANS NO VM SENT TEXT . JC 3.17 No ans. no v/m. PF 2nd email PF 03/18/22 NO ANS LEFT NO VOICEMAIL. SENT FOR IMT. JC 03/18/22 Clear to proceed per MP. jc | 3 | State Planner: Melissa Perry |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 5 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2021-12-22 | Yes | 19 | [14 empty] | Karla Guenzler | 916-689-2252 | karlaguenzler@gmail.com | Septic | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 505 | 38.6404 | -120.5319 | Caldor | DR-4619 | Residential | Yes | 2021-11-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
261 | 041-664-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5046 | Cary Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3926.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-12-23 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-25 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-23 | 2022-01-12 | 2022-03-25 | 01/11/22 NO ANS LEFT VM &TEXT . JC 01/12/22 NO ANS LEFT VM & EMAIL. JC 01/12/22 SPOKE WITH SCOTT HE SAID OK BUT CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 02/28/22 NO ANS LEFT VM & TEXT. JC 02/28/22 SCOTT C/B HE SAID OK. JC 03/25/22 ﻿FOLLOW UP CALL. LEFT VM AND TEXT. JC 03/25/22 SCOTT C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 |  |  | 5 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2021-12-21 | Yes | 66 | [14 empty] | SIKORSKI, SCOTT M & STEVIE | 530-306-4999 , 530-306-3836 | thesikorskis92@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Crystal Egan / #505 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 505 | 38.6394 | -120.5323 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
262 | 041-664-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5060 | Cary Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3924.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | POSITIVE | 2021-12-08 | 2021-12-08 | 5 | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-08 | 2021-12-07 | 2022-03-08 | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH AMIEL SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC "03/04/22 NO ANS LEFT VM & TEXT JC 03/05/22 NO ANS LEFT VM & EMAIL. JC 03/07/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/08/22 NO ANS LEFT VM SENT TO IMT. JC 03/08/22 CLEAR TO PROCEED. PER MELISSA PERRY. JC 03/08/22 HO C/B HE WOULD LIKE TO KEEP WOOD FROM CEDAR TREES, AND WOULD LIKE TO HOLD OFF UNTIL HE SPEAKS WITH SOMEONE FROM THE COUNTY. JC 03/16/22 CLEAR TO PRECEED PER DAVID TETER. JC 04/05/22 ﻿Amiel called wanting to know if someone can come back out to look at two unmarked burned tree in the front of lot. He believes these two trees are dangerous and should be marked for felling. JC | 4 | State Planner: Melissa Perry |  | 2021-12-11 |  | 2022-01-13 | 2022-01-13 |  |  | 3 | 2022-01-17 | 2022-01-25 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-02-16 | Yes | 24 | [14 empty] | Amiel Magarowicz | 530-295-5523 | ajmklm13@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha/#505 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 505 | 38.6391 | -120.5325 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-05T21:26:18Z | FALSE
263 | 041-664-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-664-006 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3865.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-04 | 03/04/22 SPOKE WITH MARGARET SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-21 | Yes | 48 | 2022-03-19 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-25 | 2022-03-26 | 48 |  |  | 2022-03-28 |  | 2022-03-28 | 2022-03-29 | Margaret Katz | 916-343-6003 | mkatz01@hotmail.com |  |  | 38.6382 | -120.5324 | Caldor | DR-4619 | Residential | No | 2021-11-19 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
264 | 041-664-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4458 | String Canyon Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3880.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-01 | 2021-12-03 | 2022-03-16 | 12.03 SPOKE WITH STEVEN HE SAID OK BUT PLEASE IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC "3.16 No Ans. left PF sent text 3.16 Steven c/b and dsaid ok PF" |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 4 | 2021-12-11 | 2021-12-17 | 5 | Approved | [12 empty] | 2021-12-20 | 2022-02-07 | Yes | 28 | [14 empty] | Steven Seiberlich | 530-306-3074 | stevenseiberlich@sbcglobal.net | Septic | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 504 | 38.6388 | -120.5321 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
265 | 041-664-009 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 4906 | Rollingwood Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3892.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-02-03 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-02-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-15 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [41 empty] | 2022-04-05 | Yes | 52 | [14 empty] | Stephan Schulz | 831-252-0978 | mail@sfschulz.com |  |  | 38.6391 | -120.5319 | Caldor | DR-4619 | Residential | No | 2022-02-01 | ROE Verified | Central Division | 2022-04-05T18:15:51Z | FALSE
266 | 041-892-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-892-001 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4040.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-01-22 | Arch Monitoring Needed for Trees, not Debris | Yes | 2022-03-24 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-02-26 | 02/26/22 SPOKE WITH DIANA SHE SAID OK FOR TREE REMOVAL. PLEASE CALL IN ADVANCE. JC | [27 empty] | 2022-01-25 | Yes | 280 | 2022-03-24 |  | 2022-03-30 | 2022-03-30 |  | 2022-04-05 | 2022-04-06 | 280 |  |  | 2022-04-08 |  | 2022-04-08 | 2022-04-08 | Daina Edie | 530-333-5770 | gerdee@sbcglobal.net |  |  | 38.6436 | -120.5164 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-08T19:49:51Z | FALSE | 6
267 | 041-940-007 | Full Program ROE (debris + trees) | Ready for Final Sign-off | Needs Assessment | Next Step: N/A | Pending Soil Sampling Results | Ready for FSO | 5083 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3563.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 6 | 0 | 0 | 2 | 4 | 3 | 0 | 15 |  |  |  |  | Yes | Leave |  | 2022-01-15 | Yes | 2022-01-17 | 2022-01-21 | POSITIVE | 2022-02-01 | 2022-02-01 | 8 | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2022-02-03 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [11 empty] | TRUE | [8 empty] | TRUE | 2022-04-14 | 2022-02-03 | 2022-02-04 |  | 02/04/22 SPOKE WITH NICHOLAS HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK ONLY IF DAMAGED. JC |  |  |  | 2022-04-01 |  | 2022-04-04 | 2022-04-04 |  |  | 2 | 2022-04-05 |  | 4 | [15 empty] | Ok to Assess | [9 empty] | 2022-04-05 | [5 empty] | Nicholas Yates | 530-903-2795 | nicholasryates@yahoo.com |  | Debris Crew Leader/Crew# Greg Lopez / #518 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 518 | 38.6371 | -120.5483 | Caldor | DR-4619 | Residential | No | 2021-11-11 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
268 | 041-290-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4809 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4048.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 2 | 1 | 3 | 0 | 9 |  |  | 3 | TRUE | Yes | Take | 2022-03-07 | 2021-11-01 | Yes | 2021-11-02 | 2021-11-05 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-18 |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-11-09 | 2021-11-10 | 2022-02-21 | 11.10 SPOKE TRACI SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE THE PROPANE TANKS. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 TRACI GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-12-03 | Yes | 24 | 2022-02-28 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-03 | 24 | 2022-03-09 |  | 2022-03-05 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Traci &Paul Barsuglia | 916-349-1707 | processcomplete@netzero.com | Vehicle on site Safety concerns | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 506 | 38.6439 | -120.5201 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
269 | 041-290-022 | Full Program ROE (debris + trees) | Pending Soil Sample Results | No Hazard Trees | Next Step: N/A | Soil Borings | NO ELIGIBLE TREES | 041-290-022 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3897.65 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 4853 |  |  | Yes |  | TRUE | 2022-01-25 | 2022-01-25 | FALSE | Yes |  | 2022-02-12 | No | TRUE | No | Yes | Yes | No | No | No | TRUE | TRUE | 17 | 13 | 4 | 9 | 1 | 14 | 0 | 58 |  |  | 2 |  | Yes |  |  | 2022-01-27 | Yes | 2022-01-27 | 2022-02-01 | POSITIVE | 2022-02-04 | 2022-02-04 | 4 | 2022-01-14 | Bio Monitoring Needed for Debris AND Trees | 2022-02-09 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-16 | Active Nest | 75 | 2022-05-30 | [9 empty] | TRUE | [8 empty] | TRUE | 2022-03-15 | 2022-02-12 | 2022-03-16 |  | 02/14/22 SPOKE WITH FRANKLIN HE SAID THE FAMILY NEEDS TIME TO MARK ITEMS THEY DO NOT WANT REMOVED. HE SAID HE TALKED WITH A CREW MEMBER AND WILL MEET SOMEONE TODAY TO WALK THE PROPERTY TO DETERMINE IF THEY WANT TO STAY IN PROGRAM. JC 03/02/22 follow up call. No ans left vm & text. jc" 03/03/22 NO ANS LEFT VM. JC 03/04/22 NO ANS LEFT VM. JC 03/10/22 FOLLOW UP CALL BUT NO ANS NO UNABLE TO LEAVE MESSAGE. JC 03/11/22 SPOKE WITH MICHAEL. HE WOULD LIKE TO MEET WITH SOMEONE FROM CREW. HE GAVE UPDATED CONTACT PHONE NUMBER. JC 03/16/22 HO C/B SAID OK FOR DEBRIS REMOVAL. PF |  |  |  | 2022-03-16 |  | 2022-03-25 | 2022-03-25 |  |  | 1 | 2022-03-26 | 2022-04-01 | 5 | Soil Boring | 2022-04-05 | [12 empty] | 2022-03-22 | No | 0 | [14 empty] | LUCAS FRANKLIN L & MICHAEL A Candace Tyler 530-306-7261 | 530 556-0129 | lucus672@gmail.com |  |  | 38.6484 | -120.5254 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-08T03:34:19Z | FALSE
270 | 041-381-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 7 | 5148 | Woodhaven Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3768.84 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Call for access |  |  | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-20 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-24 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-04 | No |  | TRUE |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-24 | 2021-12-02 | 2022-03-28 | 12.02 Contacted homeowner, okayed start of debris removal RCV 01/25/22 NO ANS LEFT VM & TEXT ABT PROAPANE TANK JC 01/26/22 SPOKE ROSALIE SHE WANTS PROPANE TANK REMOVED ONLY IF DAMAGED. JC3.28 SPOKE TO MICHELLE (DAUGHTER) SAID OK PF |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 29 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-02-01 | Yes | 6 | [14 empty] | ROSALIE MOYA | 510-918-3773 | MSAN5530@COMCAST.NET |  | Debris Crew Leader/Crew# Mattson Adam #507 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 507 | 38.6356 | -120.5445 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
271 | 041-381-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5106 | Woodhaven Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-15 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-02-01 | 02/01/22 SPOKE WITH BRICE HE SAID OK. DO NOT REMOVE PROPANE TANK. JC | [27 empty] | 2021-11-17 | Yes | 1 | 2022-02-09 |  | 2022-02-09 | 2022-02-09 |  | 2022-02-09 | 2022-02-14 | 1 |  |  | 2022-02-15 |  | 2022-02-15 | 2022-02-16 | BRICE HARRIS | 916-715-7272 | harrisbrice@att.net |  |  | 38.6372 | -120.544 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
272 | 041-381-012 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5054 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3887.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-06 | No | [6 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-02-11 | 12.4 SPOKE WITH JOHN HE SAID OK. JC 01/14/22 SPOKE WITH JOHN HE SAID OK. JC 02/11/22 SPOKE WITH JOHN HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2021-11-02 | Yes | 17 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-21 | 2022-02-25 | 17 |  |  | 2022-02-28 |  | 2022-02-28 | 2022-03-01 | JOHN R. & CHRISTINA A. ROGERS | 530-558-0762 | JRROGER99@GMAIL.COM |  |  | 38.6371 | -120.5412 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
273 | 038-050-035 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 8033 | Tori Way |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6637.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-12-08 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [32 empty] | Ok to Assess | [15 empty] | Thomas & Mary Raycraft | 530-391-8346 | Lizpadcraft@gmail.com |  |  | 38.808 | -120.102 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
274 | 038-050-036 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 8041 | Tori Way |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6682.57 |  | 2021-12-06 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | TRUE | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2021-12-06 | No | 0 | [14 empty] | Michael E. Cantwell Marie M. Cantwell Joshua M. Cantwell | 650-906-7272 | life@harvestrc.org | Septic Vehicles Onsite |  | 38.8081 | -120.1011 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
275 | 038-050-041 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 038-050-041 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6552.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-15 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | [8 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-11 | Yes | 309 | [14 empty] | Robert Hencken | 650-380-1756 | rhencken@hdc-llc.net |  |  | 38.8059 | -120.1051 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
276 | 038-050-042 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 038-050-042 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6554.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-15 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-06 | Yes | 18 | [14 empty] | Robert Hencken | 650-380-1756 | rhencken@hdc-llc.net |  |  | 38.8056 | -120.104 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
277 | 038-080-002 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Complete | 7152 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6579.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-23 | Bio Monitoring Needed for Debris AND Trees | 2021-12-01 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-06 | 2021-12-07 |  | 12.06 NO ANS LEFT VM AND TEXT. JC 12.07 SPOKE WITH CAROL SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [17 empty] | 2022-03-26 | Yes | 122 | [14 empty] | Carol Lehman | 925-462-5334 | carol@travel-desk.com |  | Debris Crew Leader/Crew# Carla Herbst /#514 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 514 | 38.8075 | -120.1045 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
278 | 038-081-002 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 1184 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6606.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-11-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-10-22 | Yes | 2021-10-23 | 2021-10-27 | POSITIVE | 2021-11-17 | 2021-11-17 | 16 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-17 | 2021-11-18 |  | 11.18 SPOKE WITH HENRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-19 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-08 | No | 0 | [14 empty] | HENRY & RHONDA PROTZEL | 408-390-3803 | protzelr@gmail.com | Vehicle On Site Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/24 to 12/1 Crew 512 | 38.8084 | -120.1074 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
279 | 038-081-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 1200 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6594.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-17 | 2021-11-18 |  | 11.18 SPOKE WITH JEFFREY HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK DID NOT BURN PLEASE DO NOT REMOVE. JC |  |  |  | 2021-11-20 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-12-08 | Yes | 9 | [14 empty] | SCHULD JEFFREY | 916-712-3551 | jschuld@cal.net | Debris Crew Leader/Crew# Robert Boyer/#512 Debris Crew WO# Refer to IAP 11/20/2021 to 11/24/2021 Crew 512 | SEPTIC | 38.8078 | -120.1078 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
280 | 038-081-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7081 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6564.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Take |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-26 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-26 | 2021-11-18 |  | 11.18 SPOKE WITH ARNE HE SAID OK BUT PLEASE CALL IN ADVANCE. HE DO NOT NEED TO BE THERE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 3 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2022-03-21 | Yes | 26 | [14 empty] | Arne & Patricia Hove | 510-209-8767 | aj_hov@comcast.net | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 512 | 38.8071 | -120.108 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
281 | 038-081-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7111 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6612.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  | 2021-11-15 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-22 | Yes | 2021-10-23 | 2021-10-27 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-15 | 2021-11-17 |  | 11.16 NO ANS LEFT VM JC 11.17 NO ANS LEFT VM. JC 11.17 ﻿SPOKE WITH OWNER, SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANKS. DO NOT REMOVE. JC |  |  |  | 2021-11-18 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Approved | [12 empty] | 2021-12-03 | 2021-12-07 | Yes | 2 | [14 empty] | JAMES METCALFE | 650-207-8129 | dasbricka@me.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 512 | 38.808 | -120.1064 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
282 | 038-081-015 | Full Program ROE (debris + trees) | Ready for Debris Removal | Haz Trees Present | Next Step: N/A | Twin Bridges Ready | Tree Assessment Complete | 7121 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6611.36 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | Yes |  | 2021-11-22 | Yes | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-04-11 | 2021-11-22 | 2022-01-21 |  | 11.18 SPOKE WITH OWNER . SAID OK AND THEY DO NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC 4.8 NO ANS. LEFT V/M AND SENT TEXT PF4.8 JAMES RESPONDED BACK ON TEXT @5:02 ACKNOWLEGDING MOBILIZATION. I TEXTED BACK AND EXPLAINED THE POSSIBILITY OF BAD WEATHER SLOWING DOWN THE CREW'S MOBILIZING. PF | [27 empty] | 2022-03-31 | Yes | 13 | [14 empty] | JAMES METCALFE | 650-207-8129 | dasbricka@me.com | Septic |  | 38.808 | -120.1061 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-09T00:28:06Z | FALSE
283 | 038-081-018 | Full Program ROE (debris + trees) | Ready for Tree Operations | Needs Assessment | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Needed | 7133 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6597.42 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-18 |  | 11.18 SPOKE WITH DAVID HE SAID OK AND HE DOES NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. JC 01/25/22 SPOKE WITH DAVID HE SAID DO NOT REMOVE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 |  | Ok to Assess | [15 empty] | DAVID AND CONNIE DERICK | 916-806-8808 | davederick@comcast.net | Keep items | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 512 | 38.8083 | -120.1054 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
284 | 038-081-020 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7145 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6590.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-18 |  | 11.18 SPOKE WITH CHARLES HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WOULD LIKE TO BE THERE. PROPANE WAS NOT BURNED. JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 3 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2022-03-24 | Yes | 48 | [14 empty] | CHARLES SCANDLYN | 707-291-2017 | charlesscandlyn@gmail.com | SEPTIC | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/20 to 11/24Crew 512 | 38.8081 | -120.105 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
285 | 038-081-023 | Full Program ROE (debris + trees) | Ready for Erosion Control | Not Eligible for Haz Tree Removal | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 1180 | Ralston Trail |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6644.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | POSITIVE | 2021-11-17 | 2021-11-17 | 4 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-22 |  | 11.16 NO ANS LEFT VM JC 11.18 NO ANS LEFT VM AND EMAIL. JC 11.19 NO ANS LEFT VM. JC GAVE TO RCV 11.22 SPOKE WITH JOSH HE SAID OK BUT PLEASE CALL IN ADVANCE. OWNS PROPANE TANK BUT DOES NOT KNOW IF DESTROYED. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-12-08 | Do Not Assess | 0 | [14 empty] | LYNN SMITH & JOSH KAMPLING | 510-710-2851, 510-710-2856 | lynnms8@sbcglobal.net, jkampling@sl.usd.us | SEPTIC | Debris Crew Leader/Crew# Melanie Pool/#512 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 512 | 38.8084 | -120.1082 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
286 | 038-081-028 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7125 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6593.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | POSITIVE | 2021-11-16 | 2021-11-16 | 3 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-19 | 2021-11-22 |  | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.22 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL IN ADVANCE. THERE ARE TWO PROPANE TANKS ON PROPERTY, ONE IS OWNED AND HE WANTS REMOVED AND OTHER VENDOR WILL HANDLE. HE HAS MARKED EACH TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2021-12-07 | Yes | 3 | [14 empty] | James Bitner | 530-318-7148 | libra1234@ymail.com | Septic Safety concerns | Debris Crew Leader/Crew# Melannie Poole/#512 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 512 | 38.8078 | -120.1058 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
287 | 041-290-023 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 041-290-023 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3917.77 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 4853 |  |  | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | Yes | Yes | No | No | TRUE | TRUE | 1 | 2 | 1 | 5 | 1 | 5 | 2 | 17 |  |  | 7 |  | No |  |  | 2021-12-10 | Yes | 2021-12-10 | 2021-12-15 | POSITIVE | 2022-01-25 | 2022-01-25 | 29 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2022-02-03 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [10 empty] | 2022-02-03 | 2022-02-07 |  | 02/04/22 Unable to make contact cell phone not available sent text. JC 02/07/22 Problem with phone number, calls not connecting. Sent email. JC 02/07/22 SPOKE WITH LOUISE SHE SAID OK. PHONE NUMBER IS UPDATED ON CARD. PLEASE CALL IN ADVANCE. NO LARGE PROPANE TANKS ON THE PROPERTY. JC |  |  |  | 2022-02-10 |  | 2022-02-12 | 2022-02-12 |  |  | 5 | 2022-02-18 | 2022-02-28 | 7 | Soil Boring | 2022-03-10 | 2022-03-18 | Approved | [9 empty] | 2022-03-21 | 2022-02-07 | No | 0 | [14 empty] | TYLER JAMES RICHARD & LOUISE ROSE CANDACE TYLER (PARCEL OWNER) | Louise 530-306-2402/Son 530 503-7135 CANDACE TYLER 530-306-7261 | jalotyler@att.net | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 502 | 38.6484 | -120.5304 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-08T01:03:07Z | FALSE
288 | 041-330-016 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 8480 | Grizzly Flat Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3140.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 5 |  |  | 1 |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-11-29 | 2021-11-29 | 4 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [8 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-29 | 2021-11-18 |  | 11.8 SPOKE TO SALVATORE HE SAID OK BUT PLEASE CALL IN ADVANCE. PF 04/06/22 The property was sold on 03/28/22 to Courtney Irvine. She can be reached at 916 804-8886. ROE received 04/06/22. Spoke with Courtney to inform her will be completed before deadline. per Melissa Perry. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Re-scrape | 2022-03-10 | 2022-03-18 | Approved | 2022-01-31 | 2022-02-08 | Re-scrape | 2022-02-19 | 2022-02-28 | Soil Boring |  |  |  | 2022-03-21 | 2021-11-20 | No | 0 | [14 empty] | Courtney and Patrick Irvine | 916-804-8886 | paddyallday@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Mattsson Adam/#507 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 507 | 38.6191 | -120.5916 | Caldor | DR-4619 | Residential | No | 2021-11-02 | ROE Verified | Central Division | 2022-04-06T22:58:39Z | FALSE
289 | 041-330-079 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 8700 | Grizzly Flat Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3122.79 |  | 2021-11-20 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | Bio Monitoring Needed for Trees, not Debris | [7 empty] | Complete | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2021-11-20 | No | 0 | [14 empty] | Greg Bowers | 925-200-9976 | gregbowers@protonmail.com |  |  | 38.62 | -120.5837 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
290 | 041-381-010 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5032 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3883.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-07 | 2021-12-07 |  | 12.07 SPOKE WITH JESSICA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Soil Boring | 2022-02-04 | 2022-02-14 | Re-scrape | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-25 | No | 0 | [8 empty] | 2022-03-17 |  |  | 2022-03-18 | 2022-03-18 | 2022-03-18 | Craig Jetton & Jessica McPherson | 916-509-5413 , 916-878-0581 | jcjetton88@gmail.com, craigjetton@gmail.com |  | Debris Crew Leader/Crew# Tarrence Harrison /#502 Debris Crew WO# Refer to IAP -- to -- Crew 502 | 38.6362 | -120.5421 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
291 | 041-383-001 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 7 | 5047 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3906.11 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | Yes | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4 |  |  | 3 |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-20 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-11-23 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-02 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-03 | 2021-12-06 | 2022-03-25 | 12.06 SPOKE WITH JACK HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE LARGE PROPANE TANK BUT PLEASE REMOVE SMALL PROPANE TANKS. JC 3.25 NO ANS LEFT MESS AND SENT TEXT PF "3.25 NO ANS LEFT MESS AND TEXT 3.25 SPOKE TO JACK AND HE SAID OK PF" |  |  |  | 2022-01-13 |  | 2022-01-13 | 2022-01-13 |  |  | 3 | 2022-01-17 | 2022-01-25 | 7 | Re-scrape |  |  |  | 2022-01-31 | 2022-02-08 | Approved | [6 empty] | 2022-02-09 | 2022-03-23 | Yes | 28 | 2022-04-08 | [13 empty] | KILLOUGH, JACK | 510-334-2464 | cactusjackal@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz/#501 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 501 | 38.6363 | -120.541 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-08T23:39:40Z | FALSE
292 | 041-392-003 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 4962 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3917.01 |  | 2021-11-02 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-04 |  | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2021-10-05 | No | [6 empty] | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-23 | [31 empty] | 2021-11-01 | No | 0 | [14 empty] | ANDREW JAMES HALTON | 530-903-3202 | ATONSGIRL@AOL.COM |  |  | 38.6336 | -120.5425 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
293 | 041-393-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4971 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3929.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | N/A | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-02-11 | 02/10/22 NO ANS LEFT VM & TEXT. JC 02/11/22 SPOKE WITH ERICA SHE PLEASE REMOVE 3 TREES LEANING ON GATE. JC | [27 empty] | 2021-11-20 | Yes | 24 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-21 | 2022-02-25 | 24 |  |  | 2022-03-01 |  | 2022-03-01 | 2022-03-01 | BURKE ERICA CHANEL & ADAM LON | 916-899-9194 | beachburke@gmail.com | Keep Items Septic |  | 38.634 | -120.5418 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
294 | 041-393-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5114 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3915.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-23 | 2021-11-23 | 6 | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-23 | 2021-11-18 | 2022-02-21 | 11.18 SPOKE WITH STEPHEN HE SAID OK AND HE WOULD LIKE TO BE THERE. PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE THE PROPANE TANK. JC 02/21/22 SPOKE WITH STEPHEN HE SAID OK BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 5 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-12-04 | Yes | 64 | 2022-03-05 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-14 | 2022-03-21 | 64 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Stephen & Rachelle Carter | 661-496-2719, 661703-9650 | scarter@bak.rr.com, rachelle.carter@gmail.com | Other Septic | Debris Crew Leader/Crew# Adam Mattson/#507 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 507 | 38.6336 | -120.5401 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
295 | 041-393-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 9991 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3928.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 3 | 1 | 1 | 0 | 0 | 4 | 1 | 10 |  |  | 10 | TRUE | Yes | Leave |  | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-18 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-09 | 2021-11-10 | 2022-01-14 | 11.10 PHONE BUSY. JC 11.10 SPOKE WITH PERRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/14/22 NO ANS /NO VM SENT EMAIL JC 01/14/22 SPOKE WITH DEBBIE SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-15 |  | 2021-11-17 | 2021-11-17 |  |  | 7 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-10-30 | Yes | 15 | 2022-02-18 |  | 2022-02-18 | 2022-02-18 |  | 2022-02-26 | 2022-03-02 | 15 | 2022-03-10 |  | 2022-03-03 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Perry & Debbie Miller | 209-874-9745 | perrymiller888@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 507 | 38.6334 | -120.5411 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
296 | 041-393-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 9981 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3931.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-10-06 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 7 |  |  | 5 | TRUE | No |  |  | 2021-10-04 | Yes | 2021-10-06 | 2021-10-11 | POSITIVE | 2021-10-27 | 2021-10-27 | 13 | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-27 | 2021-11-02 | 2022-01-24 | 11.2 SPOKE TO ERIC AND HE SAID OK PF 01/24/22 NO ANS LEFT VM & TEXT. JC 01/24/22 ERIC C/B HE SAID OK BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 12 | 2021-11-20 | 2021-12-01 | 6 | Re-scrape |  |  |  | 2021-12-04 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-10-30 | Yes | 62 | 2022-02-07 |  | 2022-02-09 | 2022-02-09 |  | 2022-02-09 | 2022-02-14 | 62 | 2022-02-21 |  | 2022-02-15 | 2022-03-01 | 2022-03-01 | 2022-03-01 | ERIC & KATRINA RASBOLD | 530-651-4675 | GENTELEM@SBCGLOBAL.NET |  | "Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 505" | 38.6332 | -120.5417 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 0
297 | 041-401-001 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 9900 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3924.63 |  | 2021-11-02 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-04 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-06 | No | [6 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2021-10-30 | No | 0 | [14 empty] | LYNETTE HOGUE | 415-794-1228 | LAHogue@aol.com | Septic |  | 38.6322 | -120.545 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
298 | 041-571-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4973 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4005.78 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | No |  | TRUE | 2022-02-01 |  | FALSE |  | FALSE |  |  | FALSE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-22 | Bio Monitoring Needed for Trees, not Debris | 2022-01-22 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-19 | No Activity/Nest Building Removed |  |  | Complete | Yes |  | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-03-16 | 03/15/22 NO ANS LEFT VM & TEXT JC 03/16/22 NO ﻿ANS LEFT VM & EMAIL.JC 03/16/22 ROBERT C/B HE SAID OK FOR TREE REMOVAL. JC | [7 empty] | FALSE | [19 empty] | 2022-01-22 | Yes | 53 | 2022-03-22 |  | 2022-03-23 | 2022-03-23 |  | 2022-03-25 | 2022-03-26 | 53 |  |  | 2022-03-28 |  | 2022-03-28 | 2022-03-29 | Robert E. Stone | 707-332-1870 | stonicus@att.net |  |  | 38.6417 | -120.5187 | Caldor | DR-4619 | Residential | No | 2021-12-13 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
299 | 041-572-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4908 | Deerwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3961.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-11-22 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-11-22 | 2021-11-24 | 2022-03-25 | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. 11.24 SPOKE WITH MATTHEW HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC "3.25 tHE # IS NO LONGER A WORKING # PF I sent a TEXT AND AN EMAIL PF" 3.25 MATT C/B AND SAID OK AND GAVE NEW #. PF |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-04 | 2021-12-13 | 6 | Re-scrape |  |  |  | 2022-01-21 | 2022-01-31 | Approved | [6 empty] | 2022-02-01 | 2021-11-30 | Yes | 18 | [14 empty] | Matthew Faulkner | 712-360-0052 (NEW #) | matthfaulkner@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/24 to 12/01Crew 505 | 38.6412 | -120.5179 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
300 | 041-572-008 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5040 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3982.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-20 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-18 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-05 | 2021-11-06 | 2022-03-03 | 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH CHERYL SHE SAID OK. PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. PF 03/03/22 NO ANS LEFT VM & TREE. JC 03/03/22 HO C/B SHE SAID OK FOR TREE REMOVAL. JC 03/22/22 Cheryl called for status update. JC |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 1 | 2021-11-15 | 2021-11-23 | 7 | Re-scrape |  |  |  | 2021-12-03 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2021-11-08 | Yes | 61 | 2022-03-18 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-24 | 2022-03-28 | 61 |  |  | 2022-04-01 |  |  |  | Cheryl Adam | 530-409-6678 | mtnmama59@sbcglobal.net |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 502 | 38.6419 | -120.5161 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
301 | 041-572-009 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5056 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3974.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | Yes | No | No | No | No |  | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Yes | Take | 2022-02-17 | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2021-12-10 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-10 | 2021-12-11 | 2022-03-01 | 12.11 NO ANS LEFT VM & TEXT. JC 12.11 HO GAVE CONSENT VIA TEXT. JC 01/25/22 NO AND LEFT VM & TEXT ABT PROPANE TANK. HO TEXT BACK TO SAY PLEASE REMOVE TANK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/01/22 ﻿HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  |  | 6 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-03-14 | Yes | 49 | 2022-03-18 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-28 | 2022-03-29 | 49 |  |  | 2022-03-30 |  |  |  | David & Brigitte Issel | 530-786-2120 | brigitteissel@live.com | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 510 |  | 38.6415 | -120.516 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
302 | 041-572-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4949 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3967.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | No |  |  | 2021-11-17 | Yes | 2021-11-17 | 2021-11-30 | NEGATIVE |  |  |  | 2021-11-15 | Bio Monitoring Needed for Trees, not Debris | 2021-11-29 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-19 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-08 | 2022-03-31 | 12.07 PH ON FILE NOT IN SERVICE SENT EMAIL. JC 12.08 NO ANS LEFT VM. JC 12.08 SPOKE WITH BRUCE HE SAID OK BUT HE WANTS TO BE CALLED BEFORE GOING TO PROPERTY. HE WANTS TO BE ONSITE DURING THE DEBRIS REMOVAL. NO PROPANE. JC 03/29/22 NO ANS LEFT VM & TEXT JC. 03/30/22 NO ANS LEFT VM & EMAIL. JC 03/31/22 SPOKE WITH BRUCE HE SAID OK FOR TREE REMOVAL. BUT PLEASE CALL HIS CELL PHONE @ 510 520-7697 IN ADVANCE﻿. JC |  |  |  | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  |  | 22 | 2022-03-03 | 2022-03-11 | 7 | Approved | [12 empty] | 2022-03-15 | 2021-12-03 | Yes | 40 | [14 empty] | BEUTLER BRUCE L TR & HELEN M KWOK TR | 510-582-2024 | sheba1700@aol.com | Septic |  | 38.6413 | -120.5161 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
303 | 041-572-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4959 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3951.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-15 | Bio Monitoring Needed for Trees, not Debris | 2021-11-22 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | [6 empty] | Class III | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-22 | 2021-11-30 | 2022-01-20 | "11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL. JC 11.29 LEFT MESS WITH SEAN FOR DAVID TO RETURN CALL. JC 11.29 LEFT VM FOR STEVE WEAVER. JC" 11:30 SPOKE WITH STEVE HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. PLEASE CALL IN ADVANCE BECAUSE HE WOULD LIKE TO BE ON SITE DURING REMOVAL. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-20 | Yes | 19 | 2022-02-12 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-17 | 2022-02-18 | 19 | 2022-03-11 |  | 2022-02-19 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Steve Weaver and agent is David Velez | HO 916 955-2578 cell / Agent 530-676-8146 | dvelez@farmersagent.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar/ #509 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 509 | 38.6409 | -120.5166 | Caldor | DR-4619 | Residential | Yes | 2021-10-23 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
304 | 041-651-003 | Full Program ROE (debris + trees) | Returned to County |  | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5005 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3857.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-03 | 2021-12-06 |  | 12.06 SPOKE WITH BRANDON HE SIAD OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE. JC |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 25 | 2022-01-15 | 2022-01-21 | 5 | Approved | [12 empty] | 2022-01-26 | 2022-02-04 | Ok to Assess | 0 | [8 empty] | 2022-02-21 |  |  | 2022-02-28 | 2022-02-28 | 2022-02-28 | Brandon Krigbaum | 530-845-2677 | ecv3bk@gmail.com | Septic | Debris Crew Leader/Crew# Mathew Dorenzo /#505 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 505 | 38.6414 | -120.5343 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
305 | 041-651-012 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 4907 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3963.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 |  |  | 2022-02-21 | 02/21/22 NO ANS LEFT VM AND TEXT. JC 02/21/22 Gerald CB HE SAID OK BUT PLEASE CALL IN ADVANCE. JC | [27 empty] | 2021-12-22 | Yes | 60 | [14 empty] | Gerald Silver | 510-209-2415 | geraldsilver@comcast.net |  |  | 38.6419 | -120.5322 | Caldor | DR-4619 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
306 | 037-222-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7854 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6891.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-13 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [14 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-28 | [31 empty] | 2021-12-01 | Yes | 15 | [14 empty] | JARED & EMILY SHERMAN | 916-743-1641 | jaredkci@verizon.net |  |  | 38.8156 | -120.0782 | Caldor | DR-4619 | Residential | No | 2021-10-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
307 | 037-222-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7864 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6892.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 |  |  | 2 |  | Yes | Take |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-10 | 2021-11-11 |  | 11.11 SPOKE WITH JOAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE TAKE PROPANE TANK. JC |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 3 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-12-01 | Yes | 46 | [14 empty] | RICE WILLIAM C & JOAN CANNON | 515-231-6112 | wcrjcr@gmail.com | Vehicle on site Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 511 | 38.8157 | -120.078 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
308 | 037-222-004 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7870 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6890.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-04-14 | 2021-11-19 | 2021-11-19 |  | 11.18 NO ANS LEFT VM. JC 11.19 SPOKE WITH KEVIN BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Re-scrape | [13 empty] | 2021-12-01 | Yes | 23 | [14 empty] | GAVIN KEVIN B & CLARE L | 530-919-0926 | kgavincalpacific@gmail.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/20 To 11/24 Crew 511 | 38.8158 | -120.0776 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-02T03:01:17Z | FALSE
309 | 037-222-005 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7855 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6888.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [8 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2021-11-18 | 2021-11-18 |  | 11.18 SPOKE WITH ONWER, SAID OK ADN DO NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | [13 empty] | 2021-11-30 | Yes | 64 | [14 empty] | Casey& Margaret Adams | 307-760-1633 | wyocowboy90@gmail.com | Septic Keep items | Debris Crew Leader/Crew# Robert Boyer/#512 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 513 | 38.8152 | -120.0786 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-02T03:16:22Z | FALSE
310 | 037-222-006 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7863 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6891.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2021-12-06 | Yes | 73 | [14 empty] | MORGAN SMITH | 510-381-0279 | morgan@schridersmith.net |  |  | 38.8153 | -120.0783 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
311 | 037-222-007 | Full Program ROE (debris + trees) | Re-scrape Needed |  | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7837 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6894.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-11-16 | FALSE | Yes |  | 2021-11-13 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-10-22 | Yes | 2021-10-23 | 2021-10-27 | POSITIVE | 2021-11-06 | 2021-11-06 | 8 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | On Hold | [8 empty] | FALSE | [8 empty] | TRUE | 2022-03-18 | 2021-11-16 | 2021-11-17 |  | 11.17 NO ANS LEFT VM. JC 11.17 SPKE WITHJANS SHE OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK JC. |  |  | 2021-11-16 | [6 empty] | #INVALID DATA TYPE | 2021-11-23 | 2021-12-03 | 7 | Re-scrape | [30 empty] | JANIS STONER | 916-718-5738 | JANISSS@ATT.NEt | Septic |  | 38.8154 | -120.078 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
312 | 037-222-008 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7879 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6896.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-21 | 2021-11-22 | 2021-11-18 |  | 11.18 SPOKE WITH OWNER. SAID OK BUT PLEASE CALL IN ADVANCE. DOES NOT NEET TO BE THERE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | [13 empty] | 2021-12-08 | Yes | 21 | [14 empty] | Barbara Hargreaves | 510-263-8393 | ca150fd@yahoo.com | Septic | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 513 | 38.8155 | -120.0778 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-02T03:19:36Z | FALSE
313 | 037-222-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7832 | Hemlock Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6874.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 2 |  | No |  |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE MARIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. THEY DO NOT NEED TO BE THERE. NO PROPANE TANK .JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-15 | 2021-12-04 | Yes | 52 | [14 empty] | GLEN & MARIE GOLLNICK | 916-752-4261 | mcgollnick@gmail.com | Vehicles on site ﻿Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8153 | -120.0791 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
314 | 037-222-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7846 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6888.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  |  |  | Yes | Take |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | POSITIVE | 2021-11-13 | 2021-11-13 | 3 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-22 |  | 11.19 NO ANS LEFT VM. JC 11.20 NO ANS LEFT VM. JC 11.22 SPOKE WITH DAVID HE SAID OK BUT HE WANTS TO BE THERE. PLEASE CALL IN ADVANCE. HE OWNS TWO PROPANE TANKS BUT UNSURE IF DESTROYED. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2021-12-06 | Yes | 113 | [14 empty] | ROGER & DAVID STONIER | 916-716-6504 | davestobro@comcast.net | Vehicles on site Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8155 | -120.0786 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
315 | 037-222-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7841 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6870.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-15 | POSITIVE | 2021-11-17 | 2021-11-17 | 3 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-18 | 2021-11-17 | 2021-11-18 |  | 11.16 SPOKE WITH TRISTAN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Approved | [12 empty] | 2021-12-07 | 2022-04-01 | Yes | 37 | [14 empty] | Tristan Klosterman & Margaret Riordan | 513-545-6668 | tristan.klosterman@gmail.com | Septic | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 513 | 38.815 | -120.0792 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-02T00:38:28Z | FALSE
316 | 037-222-014 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 7845 | Phillips Heights Avenue |  | ECHO LAKE | El Dorado |  | Residential | [5 empty] | 6876.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2022-04-02 | Yes | 3 | [14 empty] | Brandon , Vernon & Christine Patterson | 707-249-0896 | bepatterson79@gmail.com |  |  | 38.815 | -120.0791 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-04T23:29:18Z | FALSE
317 | 037-222-015 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Complete | 7849 | Phillips Heights Avenue |  | ECHO LAKE | El Dorado |  | Residential | [5 empty] | 6881.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | Yes |  | 2021-12-06 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-22 | Yes | 2021-11-22 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | 2021-12-06 | 2021-12-07 |  | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH BRANDON HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [17 empty] | 2022-04-02 | Yes | 22 | [14 empty] | Brandon , Vernon & Christine Patterson | 707-249-0896 | bepatterson79@gmail.com | Septic | Debris Crew Leader/Crew# Crystal Egan /#513 Debris Crew WO# Refer to IAP 12/08 to 12/11Crew 513 | 38.8151 | -120.0789 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
318 | 037-223-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7824 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6898.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-12 | 2021-11-16 |  | "11.15 NO ANS LEFT VM. JC 11.16 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CALL PREVIOUS OWNER TO SEE IF PROPANE TANK IS LEASED OR OWNED. JC 11.16 MICHAEL CALLED BACK, HE OWNS TANK AND WANTS REMOVED. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-29 | Yes | 5 | [14 empty] | Micheal & Stephanie Wengel | 916-956-1403 | michael.wengel@crowe.com | Septic | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 513 | 38.8144 | -120.0797 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
319 | 037-223-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7828 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6878.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-19 | 2021-11-19 | 4 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-19 |  | 11.18 SPOKE WITH BYRON HE SAID OK AND DO NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-11-29 | Yes | 10 | [14 empty] | BYRON & PAMELA TOMLINSON | 925-286-3497 | bjt1@astound.net |  | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 513 | 38.8145 | -120.0795 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
320 | 037-223-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7850 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6890.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-22 | Yes | 2021-10-23 | 2021-10-27 | POSITIVE | 2021-11-06 | 2021-11-06 | 8 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [8 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 HO CALLED BACK SAID OK BUT PLEASE CALL ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/27/22 VENODR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 3 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-24 | Yes | 51 | [14 empty] | Margaret Negrelli | 631-553-4939 | margaret.negrelli@gmail.com |  | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 513 | 38.8147 | -120.0786 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
321 | 037-223-006 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Ready for Tree Felling | Next Step: N/A | Ready for Soil Sampling | TWB Pending | 7866 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6898.99 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-19 | Yes | TRUE | No | No | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-19 | 2021-11-19 |  | 11.17 SPOKE WITH DANIEL HE SAID OKAY BUT PLEASE CALL IN ADVANCE. HE HAS ITEMS THAT ARE NOT TO BE REMOVED. NO PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 87 | [17 empty] | 2021-11-24 | Yes | 13 | [14 empty] | DANIEL & ANNE ROSS | 916-220-6100 | drosscpa@me.com | SEPTIC | Debris Crew Leader/Crew# Crystal Egan /#513 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 513 | 38.8149 | -120.0781 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
322 | 037-223-007 | Full Program ROE (debris + trees) | Chimney Tip Needed | Ready for Tree Felling | Next Step: N/A | Twin Bridges Ready | TWB Pending | 7870 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6900.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  |  | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-26 |  |  |  | 11.18 NO ANS LEFT VM. JC 11.18 MORGAN CALLED BACK SAID OK BUT PLEASE CALL ADVANCE. JC | [27 empty] | 2021-11-24 | Yes | 10 | [14 empty] | MORGAN SMITH | 510-381-0281 | morgan@schridersmith.net | Septic |  | 38.815 | -120.0778 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
323 | 037-223-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7878 | Phillips Heights Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6903.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-22 | Yes | 2021-10-23 | 2021-11-12 | POSITIVE | 2021-11-12 | 2021-11-06 | 1 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-19 | 2021-11-18 |  | 11.18 SPOKE WITH MORGAN. THEY WOULD LIKE TO BE THERE AT DEBRIS REMOVAL. BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-24 | Yes | 4 | [14 empty] | SMITH MORGAN & SMITH MORGAN | 510-381-0279 | morgan@schridersmith.net | Septic | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 513 | 38.8151 | -120.0776 | Caldor | DR-4619 | Residential | No | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
324 | 037-223-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7868 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6910.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-16 | 2021-11-17 |  | 11.16 NO ANS LEFT VM JC 11.17 SPOKE WITH DANIEL HE SAID OKAY BUT PLEASE CALL IN ADVANCE. HE HAS ITEMS THAT ARE NOT TO BE REMOVED. NO PROPANE TANK. JC |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-11-24 | Yes | 8 | [14 empty] | DANIEL & ANNE ROSS | 916-220-6100 | drosscpa@me.com | SEPTIC | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 513 | 38.8145 | -120.0779 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
325 | 037-223-011 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 037-223-011 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6877.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-23 | [31 empty] | 2021-12-06 | Yes | 35 | [14 empty] | Margaret Negrelli | 631-553-4940 | margaret.negrelli@gmail.com |  |  | 38.8145 | -120.0785 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
326 | 037-223-013 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 037-223-013 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3881.67 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [14 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | [34 empty] | Ok to Assess | [15 empty] | MORGAN SMITH | 510-381-0280 | morgan@schridersmith.net |  |  | 38.8148 | -120.0777 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
327 | 037-223-015 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7834 | Phillips Heights Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6893.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-16 | 2021-11-18 |  | 11.18 NO ANS LEFT VM.JC 11.﻿18 SPOKE WITH CLARICE MIEARS SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-29 | Yes | 29 | [14 empty] | Clarice Miears | 805-757-8315 | claricelynn@gmail.com | Septic | Debris Crew Leader/Crew# Robert Boyer/#513 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 513 | 38.8144 | -120.0791 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
328 | 037-372-007 | Full Program ROE (debris + trees) | Ready for Debris Removal | Needs Assessment | Next Step: N/A | Twin Bridges Ready | Tree Assessment Needed | 8342 | Tamarack Court |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7137.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-28 | 2021-12-08 | 2022-01-21 |  | 12.09 NO ANS LEFT VM & TEXT. JC 12.10 NO ANS LEFT VM SENT EMAIL. JC GAVE TO RICHARD. JC 12.10 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE POPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC | [28 empty] | Ok to Assess | [15 empty] | John A. Kessler & Karen Kessler | 530-295-7464 | jkessler14@gmail.com | Septic Well |  | 38.8234 | -120.0579 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-02T02:33:28Z | FALSE
329 | 037-372-008 | Tree Only ROE (no qualifying debris) | No Asbestos Detected | No Hazard Trees | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 2011 | Audrain Road |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7135.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2022-04-01 | No | 0 | [14 empty] | Ronald Modeste | 408-241-2369 | ronaldmodeste@sbcglobal.net |  |  | 38.8234 | -120.0584 | Caldor | DR-4619 | Residential | Yes | 2021-11-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
330 | 037-372-009 | Full Program ROE (debris + trees) | Ineligible | Needs Assessment | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 8343 | Tamarack Court |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7114.84 |  | 2021-11-22 | Other - see comments | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [32 empty] | Ok to Assess | 0 | [14 empty] | CONOLEY MEGAN & KENNETH W | 214-681-9784 , 214-536-1338 | meganconoley@gmail.com, kenny@2415realty.com | Other Septic |  | 38.8239 | -120.0578 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
331 | 037-380-016 | Full Program ROE (debris + trees) | Re-scrape Needed | Needs Assessment | Next Step: N/A | ELD Twin Bridges Rescrapes | Tree Assessment Needed | 2060 | Huckleberry Heights Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 7090.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2022-03-25 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-04-14 | 2021-11-17 | 2021-11-18 |  | 11.18 SPOKE WITH ROBERTA SHE SAID OK BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Re-scrape | [14 empty] | Ok to Assess | [15 empty] | RILEY PATRICK J TR & ROBERTA L TR | 530-622-3658 | BERTRILEY@SBCGLOBAL.NET | Septic | Debris Crew Leader/Crew# /#513 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 513 | 38.821 | -120.0628 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-02T03:14:37Z | FALSE
332 | 037-380-025 | Full Program ROE (debris + trees) | Ready for Soil Sampling | No Hazard Trees | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 2070 | Huckleberry Road |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7183.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-21 | 2021-11-23 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 MRS. DOUB RETURENED CALL AND SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 89 | [17 empty] | 2022-04-01 | No | 0 | [14 empty] | Stephen Doub | 559-776-1336 | ydoub@csufresno.edu | Septic | Debris Crew Leader/Crew# Crystal Egan/#513 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 513 | 38.82 | -120.0631 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
333 | 037-380-033 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Needed | 2080 | Huckleberry Heights Road |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7215.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2022-03-25 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-03-18 | 2021-11-17 | 2021-11-18 |  | 11.18 NO ANS LEFT VM .JC 11.18 SPOKE WITH JIM HE SAID OK AND WANTS TO BE THERE. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2022-04-01 | No | 0 | [14 empty] | Edmund & Sally Ellsworth | 530-878-1842 | sparkyryan@doglover.com | Septic Keep items | Debris Crew Leader/Crew# Joshua Coronado/#513 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 513 | 38.8201 | -120.0626 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
334 | 037-390-009 | Full Program ROE (debris + trees) | ROE Received | Needs Assessment | Next Step: N/A | Need Site Assessment | Tree Assessment Needed | 2150 | Audrain Way |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7117.72 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | TRUE | Weather-related | No |  | TRUE |  |  | FALSE |  | FALSE |  |  | FALSE | [6 empty] | FALSE | FALSE | [7 empty] | 0 | [33 empty] | FALSE | [8 empty] | FALSE |  |  |  |  | 02/07/22 SPOKE WITH RACHEL SHE SAID BURNED BUILDING ON THE PROPERTY. JC | [7 empty] | FALSE | [20 empty] | Ok to Assess | [15 empty] | Tyler & Rachel Carscaden | 805-235-3792 | rachelacarscaden@gmail.com |  |  | 38.8226 | -120.0605 | Caldor | DR-4619 | Residential | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-02T20:11:48Z | FALSE
335 | 037-400-003 | Full Program ROE (debris + trees) | Re-scrape Needed | No Hazard Trees | Next Step: N/A | ELD Twin Bridges Rescrapes | NO ELIGIBLE TREES | 2065 | Finn Court |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 7125.83 |  |  |  |  | TRUE | DTSC Attn |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-15 | POSITIVE | 2021-11-20 | 2021-11-20 | 5 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No |  | FALSE | [8 empty] | TRUE | 2022-04-14 | 2021-11-20 | 2021-11-22 |  | 11.18 SPOKE WITH TERRY HE SAID OK AND DOES WANT TO BE THERE. BUT PLEASE CALL IN ADVANCE. HE WILL LET CREW LEADER KNOW IF HE WANTS PROPANE TANK REMOVED. JC 01/26/22 SPOKE WITH TERRY HE SAID TO REMOVE PROPANE TANK ONLY IF DAMAGED﻿. JC |  |  |  | 2021-12-02 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape | [13 empty] | 2021-12-04 | No | 0 | [14 empty] | TERRY ZAZZI | 916-290-3486 | TERRYZAZZI@GMAIL.COM | SEPTIC | Debris Crew Leader/Crew# Crystal Egan/#513 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 513 | 38.8202 | -120.0637 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-04T16:36:57Z | FALSE
336 | 038-040-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7180 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6587.92 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Inquiring from homeowner. |  | Locked gate | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | Arch Monitoring Needed for Debris, not Trees | [12 empty] | Class III |  | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-12 | 2021-11-16 |  | 11.15 NO ANS LEFT VM. JC 11.15 NANCY LEFT MESS SAYING SHE IS WORKING TODAY AND TO CALL HER BACK 11.16. JC 11.16 SPOKE WITH NANCY SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC ....DO NOT CALL HOME OWNER UNDER ANY CIRCUMSTANCES. |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 5 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2022-03-29 | Yes | 83 | [14 empty] | Nancy Jackson | 916-622-7724 | ndh0602@comcast.net | Vehicle on site Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/20 to 11/22 Crew 512 | 38.8076 | -120.1036 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
337 | 038-041-003 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | TWB Pending | 7185 | Sierra Pines Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6603.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-01 | 2021-12-02 |  | 12.03 Spoke with parcel owner Sean, gave consent for debris removal operations to begin RCV |  |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 89 | [17 empty] | 2021-12-07 | Yes | 49 | [14 empty] | LARSEN HAROLD, Sean Christman (agent) | 530-659-7800 | sean@Sierracedar.com | Vehicles Onsite | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 514 | 38.8083 | -120.1033 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
338 | 038-042-003 | Full Program ROE (debris + trees) | Pending Asbestos Results | Haz Trees Present | Next Step: N/A | Twin Bridges Pending | Tree Assessment Complete | 7184 | Sierra Pines Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6595.05 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-05 | 2022-04-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-05 | Yes | 2022-04-05 | 2022-04-08 |  |  |  |  | 2022-03-21 | Bio Monitoring Needed for Debris AND Trees | [8 empty] | Yes | [7 empty] | FALSE | [8 empty] | FALSE |  |  |  |  | 02/07/22 NO ANS LEFT VM AND TEXT ABT ELIGIBLE DEBRIS. JC 02/07/02 Cheryl c/b she said burned structures on property. JC | [27 empty] | 2022-03-29 | Yes | 5 | [14 empty] | Cheryl Moore | 916-718-1560 | cwaves2u@gmail.com |  |  | 38.8077 | -120.103 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-09T00:01:21Z | FALSE
339 | 038-042-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7200 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6593.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Trees, not Debris | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-12 | 2021-11-15 |  | 11.15 SPOKE WITH HUGH HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2022-03-29 | Yes | 25 | [14 empty] | HUGH & RICA PIERCY | 925-786-2794 | hughpiercy@att.net |  | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 512 | 38.8075 | -120.1029 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
340 | 038-042-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7210 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6590.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Trees, not Debris | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-12 | 2021-11-16 |  | 11.15 NS NAS LEFT VM. JC 11.16 NO ANS LEFT VM. JC 11.16 SPOKE CORY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLE PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2022-03-30 | Yes | 38 | [14 empty] | CORY WATERS | 530-306-9206 | waterscory@gmail.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 512 | 38.8073 | -120.1029 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
341 | 038-042-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7216 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6589.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-18 |  | 11.18 SPOKE WITH DAVID HE SAID OK AND DOES NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2022-03-30 | Yes | 10 | [14 empty] | DAVID & DOROTHY CRISWELL | 916-218-2463 | dcriswell62@icloud.com | SEPTIC | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/24/to 12/01 Crew 512 | 38.8072 | -120.1027 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
342 | 038-042-009 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 7232 | Sierra Pines Road |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 6582.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | [8 empty] | Yes | 2022-04-01 | Yes | [5 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2022-03-30 | Yes | 10 | [14 empty] | Kathleen O'Brien | 916-533-6227 | kobatwilton@gmail.com | Septic |  | 38.8066 | -120.1025 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
343 | 038-042-011 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | Tree Assessment Complete | 7240 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6579.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-01 | Yes | [5 empty] | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-15 | 2021-11-16 |  | 11.16 NO ANS LEFT VM. JC 11.16 SPOKE WITH HENERIETTA SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT BURNED. DO NOT REMOVE. JC |  |  | 2021-11-15 | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Re-scrape | [13 empty] | 2022-03-30 | Yes | 16 | [14 empty] | WILLIAM BENNETT & HENERIETTA SANTOS-COY | 916-996-0994 | henrisc2@gmail.com | Septic | Debris Crew Leader/Crew# Melanie Poole/#512 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 512 | 38.8062 | -120.1024 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-02T01:35:28Z | FALSE
344 | 038-042-012 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Complete | 7248 | Sierra Pines Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6578.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | Yes |  | 2021-12-06 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | POSITIVE | 2021-12-02 | 2021-12-02 | 4 | 2021-11-23 | Bio Monitoring Needed for Debris AND Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-01 | Yes | [5 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | 2021-12-06 | 2021-12-04 |  | 12.04 Homeowner okayed debris start RCV |  |  |  | 2021-12-07 |  | 2021-12-07 | 2021-12-07 |  |  | 88 | [17 empty] | 2022-03-30 | Yes | 19 | [14 empty] | Mark Marncik | 415-731-9135 | none |  | Debris Crew Leader/Crew# Carla Herbert /#514 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 514 | 38.806 | -120.1024 | Caldor | DR-4619 | Residential | Yes | 2021-11-19 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
345 | 041-651-023 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4902 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3879.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-13 | 2022-01-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-12-23 | Yes | 2021-12-23 | 2021-12-29 | NEGATIVE |  |  |  | 2021-12-23 | No Bio Monitoring Needed for Debris or Trees | 2022-01-18 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-07 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2022-01-18 | 2022-01-21 | 2022-03-22 | 01/20/22 NO ANS LEFT VM & TEXT. JC 01/21/22 SPOKE WITH ROBERTA SHE SAID SHE WANTS TO BE THERE FOR DEBRIS REMOVE DUE TO CONCERNS ABT RETAINING WALLS. ROBERTA IS SCHEDULED FOR SURGERY ON JAN 26 AND REQUEST DEBRIS REMOVAL BEFORE OR AFTER THAT DATE. VENDOR HANDLING PROPANE TANK. JC 3.22 NO ANS. LEFT MESS AND SENT TEXT PF 3.22 NO ANS. LEFT MESS AND SENT TEXT PF 3.22 ROBERTA C/B AND OK TO PROCEED PF |  |  |  | 2022-01-28 |  | 2022-01-31 | 2022-01-31 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-03-21 | Yes | 115 | [14 empty] | Roberta Hall | 916 704-5384 | levihall@me.com |  | Debris Crew Leader/Crew# Crystal Egan/#505 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 505 | 38.6424 | -120.5333 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
346 | 041-652-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4982 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3928.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | Yes |  | 2021-11-08 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | POSITIVE | 2021-11-05 | 2021-11-05 | 3 | 2021-10-30 | Bio Monitoring Needed for Trees, not Debris | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-08 | 2021-11-10 | 2021-12-08 | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH ROY ﻿HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 12.4 NO ANS LEFT FOR TREE REMOVAL. JC 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & TEXT. JC 12.08 Roy gave okay to cut trees RCV |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 1 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-12-08 | Yes | 62 | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  | 2021-12-18 | 2021-12-18 | 62 | 2022-01-25 |  | 2022-01-20 | 2022-01-27 | 2022-01-27 | 2022-01-27 | ROY CORTOPASSI | 916-383-7521 |  | Septic | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6413 | -120.5332 | Caldor | DR-4619 | Residential | No | 2021-09-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
347 | 041-652-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4966 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3938.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2021-12-21 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 |  |  | 2021-12-08 | 12.4 NO ANS LEFT FOR TREE REMOVAL. JC 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & TEXT. JC 12.08 Roy gave okay to cut trees RCV | [27 empty] | 2021-11-13 | Yes | 47 | 2021-12-21 |  | 2021-12-22 | 2021-12-22 |  | 2021-12-23 | 2021-12-23 | 47 |  |  | 2022-01-15 |  | 2022-01-15 | 2022-01-17 | CORTOPASSI ROY | 916-383-7521 |  |  |  | 38.6411 | -120.5329 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
348 | 041-734-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5360 | Wood View Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3734.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2022-01-26 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-08 | Yes | 2022-04-01 | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-26 | 2022-01-27 | 2022-04-08 | 01/27/22 SPOKE WITH MRS. SALAZAR SHE SAID OK. VNEDOR HANDLING PROPANE TANK. JC 4.8 SPOKE TO MRS SALAZAR AND SHE SAID OK. PF |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-03-21 | Yes | 31 | [14 empty] | Richard Salazar | 530-626-6909 | isacujo.anaya@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 502 | 38.6304 | -120.5337 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-08T18:44:40Z | FALSE
349 | 041-830-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4767 | Wild Bee Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3576.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 3 |  |  | 3 |  | No |  |  | 2021-12-23 | Yes | 2021-12-23 | 2021-12-29 | POSITIVE | 2022-01-21 | 2022-01-21 | 18 | 2021-12-04 | Bio Monitoring Needed for Debris AND Trees | 2022-01-22 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-14 | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-17 | 2022-01-22 | 2022-01-25 | 2022-03-24 | 01/25/22 NO ANS LEFT VM & TEXT JC 01/25/22 SPOKE RICK HE SAID OK AND THERE IS NO LARGE PROPANE TANK ON PROPERTY. PLEASE CALL IN ADVANCE. JC 03/23/22 NO ANS LEFT VM & TEXT. JC 03/24/22 Spoke with Rick he said ok for tree removal. jc |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Re-scrape | 2022-03-11 | 2022-03-21 | Approved |  |  |  | 2022-03-23 | 2021-12-20 | Yes | 85 | [14 empty] | Rick & Nicole Craine | 916-416-3165 | rlcraine@comcast.net | Safety Concerns Septic Vehicles Onsite | Debris Crew Leader/Crew# Crystal Egan/ #505 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 505 | 38.6444 | -120.5392 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
350 | 041-850-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10300 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3846.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 |  |  |  | TRUE | No |  |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | POSITIVE | 2021-10-22 | 2021-10-22 | 9 | 2021-10-13 | Bio Monitoring Needed for Debris AND Trees | 2021-11-04 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-04 | 2021-11-06 | 2022-01-20 | 11.5 NO ANS LEFT VM. JC 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH MICHAEL, HE SAID OK. PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/20/22 SPOKE WITH MICHAEL HE SAID OK. JC |  |  |  | 2021-11-10 |  | 2021-11-13 | 2021-11-13 |  |  | 1 | 2021-11-15 | 2021-11-23 | 7 | Soil Boring | 2021-12-04 | 2021-12-13 | Approved | [9 empty] | 2021-12-14 | 2021-11-01 | Yes | 44 | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  | 2022-02-02 | 2022-02-03 | 44 | 2022-02-10 |  | 2022-02-08 | 2022-02-16 | 2022-02-16 | 2022-02-16 | MICHAEL W. KRUSCHKE | 916-798-3144 | MIKE.KRUSCHKE@GMAIL.COM |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 501 | 38.6358 | -120.5284 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
351 | 028-261-056 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 19131 | State Highway 174 |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2315.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 10 |  |  | 14 |  | No |  |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-18 | No Bio Monitoring Needed for Debris or Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-11 | No |  | TRUE |  | Class III | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-26 | 2021-10-21 | 2021-11-04 |  | 10.27 NO ANS LINE BUSY 10.28 NO ANS AND LINE BUSY 11.4 SPOKE WITH ROBINETTE. SHE SAID OK. JC |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 6 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-11-19 | Yes | 3 | [14 empty] | Robinette and Michael Jewell | (530) 913-4861 or (530) 913-4862 | robinette.jewell@gmail.com | Other Vehicles Onsite | Debris Crew Leader/Crew# Carla Herbs/#301 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 301 | 39.1439 | -120.9681 | River Fire | DR-4601 | Residential | No | 2021-09-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
352 | 028-261-060 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 15834 | Ladera Lane |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2262.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-18 | Bio Monitoring Needed for Debris, not Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-10-20 | 2021-10-26 |  | 10.27 Spoke with Justine that debris removal can begin. Would like to be called before. RCV |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 6 | 2021-11-08 | 2021-11-17 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-10 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Bruce and Justine Fairey | (415) 264-6643 or (415) 264-6853 | jrfairey@gmail.com and bjfairey@gmail.com | Other Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Jared Kemp/301 Debris Crew WO# Refer to IAP 10/30 to 11/3 Crew 301" | 39.1391 | -120.9698 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
353 | 028-270-004 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20214 | Meyer Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2109.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | Yes |  | 2021-11-09 | No | TRUE | No | No | Yes | No | No | No | FALSE | TRUE | 4 | 4 | 0 | 4 | 6 | 1 | 2 | 21 |  |  | 7 | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | POSITIVE | 2021-11-02 | 2021-11-02 | 8 | 2021-10-21 | Bio Monitoring Needed for Debris, not Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-11-02 | 2021-11-03 |  | 11.3 SPOKE WITH MISTY. SHE SAID OK. PLEASE CALL IN ADVANCE. JC 02/15/22 SPOKE WITH MISTY SHE SAID PLEASE CALL LANDLINE 530 675-9274 IF SHE CANNOT BE REACHED ON CELL 702 281-2593. JC 02/15/22 SPOKE WITH HO ABT EROSION CONTROL WAIVER. SHE SAID SHE WOULD MOVE THE TRAILER SO EROSION CONTROL CAME BE COMPETED. JC 02/22/22 SPOKE WITH MISTY TO LET HER KNOW CREW WILL BE THERE FOR EROSION CONTROL ONCE SNOW CLEARS. JC |  |  |  | 2021-11-08 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-03-02 |  |  | 2022-03-02 | 2022-03-02 | 2022-03-02 | Misty Quabner | (702) 281-2593 OR (530) 675-9274 | mistyquabner7@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gary /#302 Debris Crew WO# Refer to IAP 11/24 to 12/2 Crew 302 | 39.1355 | -120.976 | River Fire | DR-4601 | Residential | No | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
354 | 028-270-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 15578 | Woodruff Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2250.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | Yes | No | No | Yes | FALSE | TRUE | 1 | 2 | 0 | 3 | 2 | 5 | 0 | 13 |  |  | 6 |  | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | POSITIVE | 2021-11-03 | 2021-11-03 | 10 | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-17 | Active Nest | 75 | [10 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-02-04 | 2022-02-04 |  | 11.3 SPOKE WITH MARK SAID OK. PLEASE CALL IN ADVANCE. HE HAS CONTACTED THE VENDOR ABT TANK. JC 02/04/22 contacted HO placing old truck on plastic and rented conex box. he said ok to old truck and to leave rented Conex. jc |  |  |  | 2022-02-08 |  | 2022-02-11 | 2022-02-11 |  |  | 14 | 2022-03-02 | 2022-03-10 | 7 | Re-scrape |  |  |  | 2022-03-18 | 2022-03-28 | Approved | [6 empty] | 2022-03-30 | 2021-11-19 | No | 0 | [14 empty] | Mark Guzman | (530) 205-5266 | tundratuff@live.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Ashanti Broussard / #301 Debris Crew WO# Refer to IAP 02/09 to 02/122 Crew 301 | 39.1354 | -120.9744 | River Fire | DR-4601 | Residential | No | 2021-09-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
355 | 028-270-008 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 15502 | Woodruff Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2227.25 |  | 2021-11-29 | Debris heavily disturbed/moved from footprint | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | Yes |  |  | No | TRUE | Yes | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-10 | Yes | 2021-11-11 | 2021-11-19 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-03 |  |  |  | 11.20 NO ANS LEFT VM. JC | [27 empty] | 2021-11-17 | Do Not Assess | 0 | [14 empty] | Trevor Juvinall | (530) 798-9093 | TJuvinall@icloud.com | Keep Items Other Septic Well |  | 39.135 | -120.9753 | River Fire | DR-4601 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
356 | 028-270-009 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19735 | Mountain Lion Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2143.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 |  |  | 2 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-16 | No Bio Monitoring Needed for Debris or Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-10-21 | 2021-11-01 |  | "10.27 MAILBOX FULL NO LONGER ACCEPTING MESS. PF 10.29 NO ANS LEFT MESS PF. 11.1 MR BREWER C/B AND SAID OK PF " |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-08 |  |  | 3 | 2021-11-10 | 2021-11-18 | 7 | Soil Boring | 2021-12-01 | 2021-12-09 | Re-scrape | 2022-01-19 | 2022-01-27 | Approved | [6 empty] | 2022-01-29 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Robert and Gabriela Brewer | (530) 408-6765 | falcon4@digitalpath.net | Other Septic Well | "Debris Crew Leader/Crew# Jared Kemp /#301 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 301" | 39.1355 | -120.9779 | River Fire | DR-4601 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
357 | 028-270-010 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19819 | Mountain Lion Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2176.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | Yes |  | 2021-11-09 | Yes | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | POSITIVE | 2021-11-02 | 2021-11-02 | 9 | 2021-10-16 | No Bio Monitoring Needed for Debris or Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | 2021-11-09 | 2021-10-27 |  | 10.27 NO ANS LEFT MESS PF10.27 SPOKE TO MR GEOTZ SAID OK PF |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 3 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-12-03 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-10 | 2021-12-10 | 2021-12-11 | Samuel and Miki Wood | (650) 279-4440 or (213) 926-0790 | iamsamwood@gmail.com and mhuber2009@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 301 | 39.135 | -120.98 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
358 | 028-270-026 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 19828 | Meyer Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2255.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 2 | 0 | 1 | 2 | 0 | 2 | 1 | 8 |  |  |  | TRUE | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | 2021-11-22 | 2021-11-24 |  | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM SENT EMAIL JC 11.24 SPOKE MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 3 | 2021-12-09 | 2021-12-17 | 7 | Approved | [12 empty] | 2021-12-20 | 2021-12-04 | Do Not Assess | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-14 | 2022-01-14 | 2022-01-14 | Michael Allen Gardner | (530) 305-8954 | michaelg283@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew403 | 39.1383 | -120.9693 | River Fire | DR-4601 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
359 | 028-270-039 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20228 | Meyer Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2210.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | Yes |  | 2021-11-09 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 9 | 7 | 8 | 1 | 3 | 11 | 1 | 40 |  |  |  | TRUE | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | POSITIVE | 2021-11-04 | 2021-11-04 | 10 | 2021-10-28 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-01-18 | 2022-01-18 |  | 11.10 NO ANS LEFT VM JC 11.11 SPOKE TO PATRICIA SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/18/22 NO ANS LEFT VM & TEXT. JC 01/18/22 SPOKE WITH JESSE HE SAID OK. JC |  |  |  | 2022-01-20 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-07 | 6 | Re-scrape |  |  |  | 2022-02-16 | 2022-02-24 | Approved | [6 empty] | 2022-02-25 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-02 | 2022-03-02 | 2022-03-02 | Jesse and Patricia Hernandez | (916) 955-3354 or (916) 955-3421 | bobtailpatty@gmail.com or jesse.autotech@gmail.com | Other Septic Vehicles Onsite Well |  | 39.1334 | -120.9756 | River Fire | DR-4601 | Residential | Yes | 2021-10-04 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
360 | 028-270-040 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20100 | Rumford Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2228.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 5 | 2 | 1 | 0 | 0 | 0 | 3 | 11 |  |  | 8 | TRUE | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-11-01 | 2021-11-03 |  | 11.3 SPOKE WITH MARK. HE SAID OK PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-12 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-10 | 2021-12-10 | 2021-12-11 | Mark and Laura Kendall | (530) 277-1646 or (530)263-4572 | kendalllaura1958@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 302 | 39.1332 | -120.9733 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
361 | 028-270-041 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20380 | Meyer Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2223.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | No |  | Yes | Yes | Yes | Yes | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Undamaged |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-26 | 2021-11-18 | 2021-11-19 |  | 11.19 NO ANS LEFT VM. JC 11.19 SPOKE WITH DAVID HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 |  |  | 2 | 2021-12-09 | 2021-12-17 | 7 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-25 | 2022-02-25 | 2022-02-25 | David L and Francine P. Busby Trustees | (760) 716-8176 | david@busby.us.com | Other Septic Well | Debris Crew Leader/Crew# Joshua Dragon /#301 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew301 | 39.1315 | -120.9757 | River Fire | DR-4601 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
362 | 028-270-042 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 20250 | Rumford Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2158.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | Yes | Yes | No | No | Yes | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 4 |  |  | 3 | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | POSITIVE | 2021-10-30 | 2021-10-30 | 9 | 2021-10-21 | Bio Monitoring Needed for Trees, not Debris | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-26 | 2021-10-30 | 2021-11-06 |  | 11.3 NO ANS LEFT MESS. JC 11.6 SPOKE WITH GERALD HE SAID OK. PLEASE CALL IN ADVANCE. ALSO, PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 5 | 2021-11-22 | 2021-12-02 | 7 | Re-scrape |  |  |  | 2021-12-08 | 2021-12-16 | Approved | [6 empty] | 2021-12-17 | 2021-11-12 | Do Not Assess | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-14 | 2022-01-14 | 2022-01-14 | Gerald and Marjorie Dolezal | (530) 913-3391 and (530) 615-9516 | margiedolezal@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Carla Herbst /#302 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 302 | 39.1314 | -120.9733 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
363 | 028-270-043 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 20228 | Meyer Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2060 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-18 | No | [6 empty] | 2021-10-28 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | [32 empty] | Do Not Assess | 0 | [14 empty] | Jesse and Patricia Hernadez | (916) 955-3354 or (916) 955-3421 | bobtailpatty@gmail.com or jesse.autotech@gmail.com | Vehicles Onsite |  | 39.1331 | -120.9776 | River Fire | DR-4601 | Residential | Yes | 2021-10-04 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
364 | 028-270-044 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20300 | Meyer Road |  | Grass Valley | Nevada |  | Commercial | [5 empty] | 2048.59 |  |  |  |  | FALSE |  |  | N/A |  |  |  | TRUE | Bridge | No |  | TRUE | 2022-01-28 | 2022-01-28 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2022-01-28 | Yes | 2022-01-28 | 2022-02-02 | NEGATIVE |  |  |  | 2022-01-28 | Bio Monitoring Needed for Debris, not Trees | 2022-01-29 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-30 | No Activity/Nest Building Removed | [11 empty] | FALSE |  |  |  | Yes | 2022-02-03 | 2022-03-30 |  |  | TRUE | 2022-03-03 | 2022-02-02 | 2022-02-02 |  | 02/02/22 NO ANS LEFT VM & TEXT. JC 02/02/22 HO GAVE CONSENT VIA TEXT. DAVID C/B HE SAID OWNS PROPANE TANK AND PLEASE REMOVE. JC |  |  |  | 2022-02-07 |  | 2022-02-08 | 2022-02-08 |  |  | 3 | 2022-02-10 | 2022-02-18 | 7 | Approved | [12 empty] | 2022-02-21 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-02 | 2022-03-02 | 2022-03-02 | David and Francine Busby | (760) 716-8176 | david@busby.us.com | Septic Well | Debris Crew Leader/Crew# Birdie Bell / #301 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 301 | 39.1321 | -120.9795 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
365 | 028-270-047 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 19907 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2176.13 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | Yes |  | No | No | Yes | No | No | No | FALSE | TRUE | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 6 |  |  |  | TRUE | No |  |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | Arch Monitoring Needed for Debris, not Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | 2021-12-03 | 2021-12-06 |  | 12.06 SPOKE WITH KEVIN HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-08 |  | 2021-12-10 | 2021-12-10 |  |  | 8 | 2021-12-21 | 2021-12-30 | 7 | Re-scrape | 2022-02-02 | 2022-02-10 | Approved | 2022-01-19 | 2022-01-27 | Soil Boring | [6 empty] | 2022-02-11 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Trust Under The LaVern Jacob Neu and Arleen Ann Neu Trust, Sharon Amaya and Nancy Joan Neu Lober Co-Trustees | (831) 706-1632 | kevinstewneu@hotmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Joshua Dragon/#301 Debris Crew WO# Refer to IAP -12/08/2021 to12/11/2021 Crew 301 | 39.134 | -120.9835 | River Fire | DR-4601 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
366 | 028-270-048 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20241 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2145.56 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Code: BEAR |  |  | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-30 | Bio Monitoring Needed for Debris AND Trees | 2021-12-23 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | 2021-12-09 | 2021-12-09 |  | 12.08 SPOKE WITH MICHAEL HE SAID TO PLEASE CALL IN ADVANCE BECAUSE HE WOULD LIKE TO BE ON SITE DURING THE DEBRIS REMOVAL. VENDOR HANDLED PROPANE TANK. JC Gate Combination is FROG. UPDATED GATE CODE PER KAI: BEAR 02/04/22 HO C/B HE SAID THE TEMP GATE CODE 1257. |  |  |  | 2021-12-10 |  | 2021-12-10 | 2021-12-10 |  |  | 8 | 2021-12-21 | 2021-12-30 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Re-scrape | 2022-02-14 | 2022-02-22 | Approved |  |  |  | 2022-02-24 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-02-28 |  |  | 2022-03-03 | 2022-03-03 | 2022-03-03 | Michael and Monika Allmon (owners) Nicholas Schaut (Agent) | Michael cell: (310-683-9885) Nicholas cell: (707) 355-2805 | mike@mbacpas.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Joshua Dragon/#301 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 301 | 39.131 | -120.9822 | River Fire | DR-4601 | Residential | Yes | 2021-09-16 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
367 | 028-310-024 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20809 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2012.37 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Gate Combination is FROG. | TRUE | Bridge | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-29 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed | [11 empty] | FALSE |  |  |  | Yes | 2022-01-18 | 2022-03-23 |  |  | TRUE | 2022-03-03 | 2021-11-01 | 2021-12-09 |  | 12.09 SPOKE WITH DORA SHE SAI OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC Gate Combination is FROG. |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 2 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-23 | 2022-02-23 | 2022-02-23 | Dora Hermansen (Weir) | (530) 575-1463 or (530) 320-8586 | dora.weir8@gmail.com | Other Septic Well |  | 39.1216 | -120.9819 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
368 | 028-310-028 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20582 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2055 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | Yes | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Trees, not Debris | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE |  | 2021-11-04 | [6 empty] | TRUE | 2022-01-12 | 2021-11-01 | 2021-10-28 |  | "10.28 NO ANS. NO ANS LEFT MESS PF 10.28 SPOKE TO KAREN SHEE SAID OK BUT PLEASE CALL FIRST. PF" 028-310-028 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/25/22 HO TEXT BACK TO SAY VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 5 | 2021-11-24 | 2021-12-06 | 7 | Soil Boring | 2022-01-19 | 2022-01-27 | Re-scrape | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-02-28 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Karen Corrie Daniels | (530) 386-4939 | corrie8657@hotmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 302 | 39.1256 | -120.9841 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
369 | 028-310-045 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 15402 | Sams Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2202.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-22 | POSITIVE | 2021-11-01 | 2021-11-01 | 7 | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-26 | 2021-11-01 | 2021-11-12 |  | 10.27 MAILBOX FULL PF 10.28. MAILBOX IS FULL PF 10.29 MAILBOX IS FULL PF﻿ 11.1 GAVE TO RICHARD FOR IMT 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 HO C/B HE SAID PROPANE IS WORKING AND DO NOT REMOVE. JC | 3 | Kendall Wilson |  | 2021-11-17 |  | 2021-11-19 | 2021-11-19 |  |  | 3 | 2021-11-23 | 2021-12-03 | 7 | Re-scrape | 2022-01-07 | 2022-01-17 | Re-scrape | 2021-12-08 | 2021-12-16 | Soil Boring | 2022-01-27 | 2022-02-04 | Approved |  |  |  | 2022-02-24 | 2021-11-12 | Do Not Assess | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Theodore Wunderlich and Carol Meer | (707) 592-1705 or (707) 529-3509 | ted_one@yahoo.com and carolmeer@ymail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jared Kemp/#301 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 301 | 39.1299 | -120.9762 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
370 | 037-211-001 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Needs Assessment | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Needed | 19812 | US Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6847.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | Yes |  | 2021-12-06 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-26 | POSITIVE | 2021-12-01 | 2021-12-01 | 3 | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | 2021-12-06 | 2021-12-03 |  | 12.03 SPOKE WITH HO SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 86 | 2022-04-07 |  | 2 | [15 empty] | Ok to Assess | [15 empty] | REDDING LARRY M TR & SHARON KAY TR - Lynn Roldan Agent | 707-310-0176 | beijaflors@yahoo.com | Septic | Debris Crew Leader/Crew# Zara Armani/ #511 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 511 | 38.8167 | -120.0807 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
371 | 037-211-004 | Full Program ROE (debris + trees) | Debris Removal in Progress | No Hazard Trees | Next Step: N/A | Twin Bridges Ready | Tree Assessment Needed | 2010 | Aspen Avenue |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6808.37 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | POSITIVE | 2021-12-01 | 2021-12-01 | 9 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-04-21 | 2021-12-01 | 2022-04-08 |  | 11.18 NO ANS LEFT VM. JC 11.18 CHARLES CALLED BACK AND SAID OK BUT SAID PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK﻿. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 SPOKE WITH CHARLES HE SAID OK. JC 4.8 NO ANS. LEFT MESS-VM AND SENT TEXT. ﻿PF4.8 CHARLES C/B AND SAID OK PF |  |  |  | 2021-12-08 | [23 empty] | 2022-04-01 | No | 0 | [14 empty] | CHARLES WATTERS | 916-825-5803 | 7MILE@COMCAST.NET | SEPTIC |  | 38.8159 | -120.0807 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-08T23:44:28Z | FALSE
372 | 037-212-001 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Needs Assessment | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Needed | 19826 | Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6849.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | POSITIVE | 2021-12-03 | 2021-12-03 | 6 | 2021-11-19 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-03 | 2021-12-03 |  | 12.03 SPOKE WITH KATHLEEN SHE SAID OK BUT PLEASE CALL ADVANCE. THEY WANT TO BE THERE FOR REMOVAL. WANTS TO DISCUSS WITH CREW LEADER ABT REMOVING PROPANE TANK. JC 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/15/22 TRIED CALLING SEVERAL TIMES BUT CALL KEPT DROPPING. SENT TEXT AND EMAIL. JC 02/15/22 KATHLEEN C/B SHE SAID THE PROPANE TANK WAS REMOVED. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 87 | 2022-04-07 |  | 2 | [15 empty] | Ok to Assess | [15 empty] | Scott and Kathleen Buchanan | 916-686-1378 /PLEASE CALL 415 309-8740 | karabuchanan@me.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 511 | 38.8169 | -120.0801 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
373 | 037-212-002 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 19830 | US Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6847.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-11-30 | Bio Monitoring Needed for Debris AND Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | [32 empty] | Ok to Assess | [15 empty] | Scott and Kathleen Buchanan | 916 686 1378 | karabuchanan@me.com |  |  | 38.8169 | -120.0799 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
374 | 037-212-005 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 19848 | Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6857.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-19 | 2021-11-19 | 4 | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH MARTIN HE OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANKS. JC |  |  |  | 2021-12-04 |  | 2021-12-04 | 2021-12-04 |  |  | 88 | 2022-04-07 |  | 2 | [14 empty] | 2022-03-19 | Yes | 13 | [14 empty] | MARTIN VETTER & LYNN SANCHEZ | 650-714-0923 | vetter17@pacbell.net | Septic | Debris Crew Leader/Crew# Zara Armani#511 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 511 | 38.8173 | -120.0792 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
375 | 037-212-007 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 19866 | Highway 50 |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6868.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-18 |  | 11.18 SPOKE WITH STEVEN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-06 |  | 2021-12-06 | 2021-12-06 |  |  | 87 | 2022-04-06 |  | 3 | [14 empty] | 2022-03-14 | Yes | 19 | [14 empty] | STEVEN & VICTORIA STONE | 702-497-2106 | stone3dv@yahoo.com | SEPTIC | Debris Crew Leader/Crew# Zara Armani /#511 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 511 | 38.8175 | -120.0784 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
376 | 037-212-008 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 19878 | US Highway 50 |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6870.98 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-22 | Yes | TRUE | No | Yes | Yes | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-19 | 2021-11-19 | 4 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH SUSAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/25/22 SPOKE WITH SUSAN SHE SAID LEAVE PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 85 | 2022-04-06 |  | 3 | [14 empty] | 2022-03-18 | Yes | 133 | [14 empty] | SUSAN & SARA LAMB | 530-666-2798 |  | SEPTIC | Debris Crew Leader/Crew# Zara Armani #511 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 511 | 38.8176 | -120.0779 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
377 | 037-212-009 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 19862 | Highway 50 |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6867.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | POSITIVE | 2021-12-03 | 2021-12-03 | 11 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-03 | 2021-11-18 |  | 11.18 SPOKE WITH WARREN HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 02/12/22 WARREN SAID TO PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 87 | 2022-04-06 |  | 3 | [14 empty] | 2022-03-14 | Yes | 27 | [14 empty] | WARREN & KRISTEN MERCER | 916-521-8387 | mercerkw@sbcglobal.net | SEPTIC | Debris Crew Leader/Crew# Zara Armani/ #511 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 511 | 38.8174 | -120.0785 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
378 | 037-212-010 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | TWB Pending | 19852 | Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6861.71 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | POSITIVE | 2021-11-20 | 2021-11-20 | 3 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-30 | 2021-11-18 |  | 11.18 SPOKE WITH ERIC HE SAID OK AND DOES NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-04 |  | 2021-12-04 | 2021-12-04 |  |  | 88 | 2022-04-07 |  | 2 | [14 empty] | 2021-12-08 | Yes | 17 | [14 empty] | ERIC KIM | 510-557-7998 | ekim@oaklandca.gov |  | Debris Crew Leader/Crew# Zara Armani /#511 Debris Crew WO# Refer to IAP 12/04/ to 12/08 Crew 511 | 38.8173 | -120.079 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
379 | 037-212-011 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 19858 | Highway 50 |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6862.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-12 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | [14 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-23 | [32 empty] | Ok to Assess | [15 empty] | ARTHUR ANDERSON & HERRINGER TR | 916-521-8587 | mercerkw@sbcglobal.net |  |  | 38.8174 | -120.0788 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
380 | 037-213-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7829 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6819.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | Class I | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-11 | 2021-11-16 |  | 11.11 NO ANS LEFT VM. JC 11.12 NO ANS LEFT VM. JC 11.13 SENT EMAIL. JC 11.15 Left a voicemail RCV 11.16 Contacted homeowner, they consented to the start of debris removal RCV |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-01 | Yes | 2 | [14 empty] | ROBERT & GAYLE MCKINLAY | 559-307-3268 | robert@mckinlay.com | Vehicles on site Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 511 | 38.8162 | -120.08 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
381 | 037-213-002 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7837 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6835.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-12 | POSITIVE | 2021-11-18 | 2021-11-18 | 5 | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | Class I | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-04-12 | 2021-11-19 | 2021-11-18 |  | 11.15 NO PHONE # ON FILE. JC 11.18 SPOKE WITH MELODY SHE SAID OK BUT PLEASE CALL IN ADVANCE. SHE DO NOT NEED TO BE THERE. PLEASE REMOVE PROPANE TANKS. |  |  |  | 2021-11-24 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | [13 empty] | 2021-11-23 | Yes | 18 | [14 empty] | MELODY PAGEE | 415 269-1628 | pageem@hdcco.com | Septic | Debris Crew Leader/Crew# Zara Armani /#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8164 | -120.0798 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
382 | 037-213-003 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Ready for Tree Felling | Next Step: N/A | Soil Borings | TWB Pending | 7845 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6838.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes |  |  |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-13 | 2021-11-15 |  | 11.15 SPOKE WITH LARRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Soil Boring | 2022-04-07 | [12 empty] | 2021-11-23 | Yes | 24 | [14 empty] | LARRY CASTELANELLI | 209-747-7727 | larry@castelanelli.net | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/20 to 11/24Crew 511 | 38.8165 | -120.0795 | Caldor | DR-4619 | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:04:29Z | FALSE
383 | 037-213-005 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | TWB Pending | 7875 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6858.72 |  |  |  |  | TRUE | Soil Sampling Issue |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-06 | 2021-11-06 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-19 | 2021-11-18 |  | "11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH CHARLES HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WOULD LIKE TO BE THERE. REMOVE PROPANE TANK. JC |  |  |  | 2021-11-23 |  | 2021-11-23 | 2021-11-23 |  |  | 5 | 2021-12-01 | 2021-12-09 | 7 | [14 empty] | 2021-11-30 | Yes | 63 | [14 empty] | Charles & Catherine Schoff | 916-524-8558 | cschoff@msn.com | Septic | Debris Crew Leader/Crew# Zara Armani /#511 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 511 | 38.8169 | -120.0783 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
384 | 037-213-006 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7881 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6875.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-04-12 | 2021-11-11 | 2021-11-12 |  | 11.12 SPOKE WITH THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape | [13 empty] | 2021-11-24 | Yes | 17 | [14 empty] | THOMAS ALLEN | 925-963-4065 | tandjallen@att.net | SEPTIC | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8169 | -120.0779 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-04T16:36:57Z | FALSE
385 | 037-213-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7887 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6872.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | POSITIVE | 2021-11-13 | 2021-11-13 | 1 | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | Class I | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-13 | 2021-11-15 |  | 11.15 SPOKE WITH CATHRINE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANKS. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Approved | [12 empty] | 2021-12-03 | 2021-11-29 | Yes | 8 | [14 empty] | Jerome & Cathrine Koewler | 916-559-4821, 916-161-0891 | jckoewler@comcast.net | Other | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 511 | 38.817 | -120.0777 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T23:19:07Z | FALSE
386 | 037-213-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7893 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6871.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | POSITIVE | 2021-11-19 | 2021-11-19 | 3 | 2021-11-17 | Bio Monitoring Needed for Trees, not Debris | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-23 | 2021-11-19 |  | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.19 SPOKE WITH JEREMY﻿ HE SAID OK BUT PLEASE CALL IN ADVANCE. UNSURE OF PROPANE TANK. JC 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/14/22 HO TEXT BACK. PLEASE REMOVE IF DAMAGED. JC |  |  |  | 2021-11-24 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-29 | Yes | 47 | [14 empty] | Jeremy Ahrens | 909-816-9260 | jeremy.ahrens@gmail.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 511 | 38.8171 | -120.0774 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-06T23:19:39Z | FALSE
387 | 041-651-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5019 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3868.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-26 | Bio Monitoring Needed for Trees, not Debris | 2021-11-03 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-04 | 2021-12-04 | 11.4 SPOKE WITH JAY. HE SAID OK. PLEASE CALL IN ADVANCE. JC 12.4 NO ANS LEFT VM. JC 12.4 SPOKE WITH JAY HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-29 | Yes | 45 | 2021-12-20 |  | 2021-12-21 | 2021-12-21 |  | 2021-12-23 | 2021-12-23 | 45 | 2022-01-31 |  | 2022-01-12 | 2022-02-02 | 2022-02-02 | 2022-02-02 | JAY EVANS | 510-516-9328 | jevans9089@aol.com |  | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 509 | 38.6407 | -120.5343 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
388 | 041-651-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5011 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3868.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 1 |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-28 | NEGATIVE |  |  |  | 2021-10-22 | Bio Monitoring Needed for Debris AND Trees | 2021-11-02 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | N/A | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-02 | 2021-11-06 | 2022-03-19 | 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH JOHN, HE SAID OK. PLEASE CALL IN ADVANCE. THERE IS NO PROPANE TANK. JC 12.4 SPOKE WITH JOHN HE SAID OK. JC 02/11/22 NO ANS LEFT VM & TEXT. JC 02/11/22 HO GAVE CONSENT VIA TEXT. JC 03/19/22 follow-up call NO ANS LEFT VM & TEXT. JC 3.19@1:40 SPOKE TO JOHN HE SAID OK TO PROCEED. PF |  |  |  | 2021-11-09 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Approved | [12 empty] | 2021-11-24 | 2021-11-29 | Yes | 38 | [14 empty] | John & Carrie Trujillo | 408-483-1987 | jjtrujillo81@gmail.com | Septic | Debris Crew Leader/Crew# Tony Ruiz/#509 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 509 | 38.641 | -120.5343 | Caldor | DR-4619 | Residential | Yes | 2021-10-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
389 | 041-651-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4914 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3923.74 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-03 | 2021-11-05 | 2022-03-25 | 11.5 SPOKE WITH SYRAH. SHE SAID OK BUT PLEASE CALL IN ADVANCE. THE VENDOR WILL HANDLE THE PROPANE TANK. JC 12.4 SPOKE WITH SYRAH SHE SAID OK. JC 01/22/22 SPOKE with SYRAH SHE SAID OK. JC 03/25/22 FOLLOW UP CALL. SPOKE WITH SYRAH SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-09 |  | 2021-11-09 | 2021-11-09 |  |  | 4 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2021-11-01 | Yes | 59 | [14 empty] | SYRAH BURCHETT | 530-556-0490 | syrahburchett@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP -11/06/21- to -11/10/21- Crew 509 | 38.6418 | -120.5331 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
390 | 041-651-009 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 4884 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3896.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-02-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-03-28 | "03/01/22 NO ANS LEFT VM & TEXT. JC 03/01/22 HO GAVE CONSENT VIA TEXT. JC" 03/28/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/28/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-01-06 | Yes | 51 | [14 empty] | Tal Greenberg | 415-290-3425 | talgreenberg76@gmail.com |  |  | 38.6428 | -120.5331 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
391 | 041-651-010 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 041-651-010 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3919.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-01-22 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | N/A | Yes | 2022-03-19 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-02-10 | 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-01-21 | Yes | 57 | [14 empty] | Tal Greenberg | 415-290-3425 | talgreenberg76@gmail.com |  |  | 38.6428 | -120.5324 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
392 | 041-651-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4897 | Rollingwood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3944.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | POSITIVE | 2021-11-03 | 2021-11-03 | 2 | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-08 | 2021-11-03 | 2022-03-17 | 11.3 NO ANS LEFT MESS. JC 11.17 No answer, could not leave a message, sent urgent email. 01/25/22 SPOKE WITH SUSAN SHE SAID OK. JC 3.17 Spoke to Susan and she said ok. PF |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 4 | 2021-11-24 | 2021-12-06 | 7 | Approved | [12 empty] | 2021-12-07 | 2022-03-17 | Yes | 38 | [14 empty] | FREDERICK & SUSAN GALLI | 530-296-8288 | s.galli8@yahoo.com | Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/24 To 12/01 Crew506 | 38.6426 | -120.532 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
393 | 041-651-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4965 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3957.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | N/A | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 | 2021-11-12 | 2021-11-15 | 2021-12-10 | 11.15 SPOKE WITH CARI SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 12.09 SPOKE WITH CARI SHE SAID SHE WANT TO HOLD OFF TREE REMOVAL. SHE IS WAITING TO HEAR FROM RESOLUTIONS ON COMPLAINT. JC |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-11-19 | Yes | 32 | 2022-01-04 |  | 2022-01-04 | 2022-01-04 |  | 2022-01-06 | 2022-01-06 | 32 | 2022-01-18 |  | 2022-01-12 | 2022-01-27 | 2022-01-27 | 2022-01-27 | David & Cari Dewolf | 530-919-3321 | ccdewolf1@gmail.com | Septic | Debris Crew Leader/Crew# Adam Hutchison/#504 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 504 | 38.6412 | -120.5322 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
394 | 041-712-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5133 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3795.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 |  | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2021-10-07 | No | [6 empty] | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-02-01 | 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 02/01/22 SPOKE WITH STEVEN HE SAID OK. DO NOT REMOVE PROPANE TANK. JC | [27 empty] | 2021-11-01 | Yes | 9 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-19 | 2022-03-21 | 9 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | STEVEN LOVEALL | 916-803-3115 | smloveall@aol.com |  |  | 38.6341 | -120.5347 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
395 | 041-721-006 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 5253 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3797.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-02 | 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 SPOKE WITH PAUL HE SAID OK BUT HE WANTS TO MEET CREW BEFORE TREES ARE REMOVED. PLEASE CALL IN ADVANCE. JC | [27 empty] | 2022-01-13 | Yes | 45 | [7 empty] | 2 | [6 empty] | Victoria L. Pike Bond Paul A. Bond | 510-787-6937, 415-488-7195 | dasbrusr@sonic.net |  |  | 38.6321 | -120.5348 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
396 | 041-721-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5263 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3802.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-14 | 2022-01-20 | 2022-03-01 | 01/20/22 SPOKE WITH PAUL HE SaiD OK BUT PLEASE CALL IN ADVANCE HE WOULD LIKE TO BE ON SITE DURING DEBRIS REMOVAL. DO NOT DRIVE HEAVY EQUIPMENT ON DRIVEWAY. PLEASE USE ENTRY FROM LOTS ON EITHER SIDE OF HOUSE OR LOGGING ROAD BEHIND THE HOUSE. DO NOT REMOVE PROPANE TANK. JC 03/01/22 SPOKE WITH PAUL HE SAID HE WANTS A PHONE CALL BEFORE TREE REMOVAL. PLEASE CALL IN ADVANCE. JC |  |  |  | 2022-01-26 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-14 | Yes | 56 | 2022-03-08 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-15 | 2022-03-17 | 56 | 2022-03-23 |  | 2022-03-19 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Paul Bond & Victoria Bond | 510-787-6937 , 415-488-7195 | dasbrusr@sonic.net | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 501 | 38.6319 | -120.5353 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T00:55:15Z | FALSE | 6
397 | 041-721-008 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5273 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3811.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [12 empty] | 2022-03-02 | 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 SPOKE WITH PAUL HE SAID OK BUT HE WANTS TO MEET CREW BEFORE TREES ARE REMOVED. PLEASE CALL IN ADVANCE. JC | [27 empty] | 2022-01-11 | Yes | 51 | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-14 | 2022-03-15 | 51 |  |  | 2022-03-17 |  | 2022-03-17 | 2022-03-17 | Victoria L. Pike Bond Paul A. Bond | 510-787-6937, 415-488-7196 | dasbrusr@sonic.net |  |  | 38.6317 | -120.5357 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
398 | 041-722-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5253 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3810.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 |  |  |  |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-26 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-10 | 2022-01-21 | 2022-03-21 | 12.09 SPOKE WITH KIMBERLY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 HOMEOWNER SAID OK. JC 3.21 SPOKE TO KIMBERLY AND SHE SAID OK PF |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-17 | Yes | 15 | [14 empty] | Kimberly Meader | 916-212-8522 | kimberlymeader@rocketmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 502 | 38.6332 | -120.5319 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-05T23:17:19Z | FALSE
399 | 041-423-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4734 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | NEGATIVE |  |  |  | 2021-10-13 | Bio Monitoring Needed for Debris AND Trees | 2021-11-04 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-04 | 2021-11-05 | 2022-01-14 | 11.5 SPOKE WITH ARTHUR, HE SAID OK. PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT PROPANE TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 01/14/22 NO ANS LEFT VM & TEXT. JC 01/14/22 SPOKE WITH ARTHUR HE SAID OK. JC |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-10-27 | Yes | 25 | 2022-01-18 |  | 2022-01-18 | 2022-01-18 |  | 2022-01-20 | 2022-01-22 | 25 | 2022-02-02 |  | 2022-01-24 | 2022-02-05 | 2022-02-05 | 2022-02-07 | ARTHUR SORENSEN | 323-304-3812 | ART.SORENSEN@GMAILCOM |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 501 | 38.6367 | -120.5362 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
400 | 041-423-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4708 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3796.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | Yes | Take | 2022-02-16 | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2022-01-17 | Bio Monitoring Needed for Trees, not Debris | 2021-11-04 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-04 | 2021-11-05 | 2022-01-24 | 11.5 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 12.4 SPOKE WITH MICHAEL HE SAID OK. JC 01/14/22 NO ANS LEFT VM & TEXT. JC 01/24/22 SPOKE WITH MICHAEL HE SAID OK .JC 02/10/22 SPOKE WITH MICHAEL SAID HE DOES NOT KNOW IF HE OWNS IT SO HE HAS TO FIND OUT AND CALL ME BACK. JC 02/12/22 NO ANS LEFT VM TO FOLLOW UP ON PROPANE TANK. JC 02/14/22 PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-10 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2021-11-05 | Yes | 36 | 2022-01-25 |  | 2022-01-27 | 2022-01-27 |  | 2022-01-28 | 2022-01-29 | 36 | 2022-02-10 |  | 2022-02-05 | 2022-02-17 | 2022-02-17 | 2022-02-17 | MICHAEL MIKLAUS | 916-712-4148 | mmiklaus@myintegritymortgage.com |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 501 | 38.6358 | -120.5362 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 1
401 | 041-431-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5087 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3888.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | POSITIVE | 2021-12-11 | 2021-12-11 | 4 | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-11 | 2022-01-14 | 2022-02-28 | 12.11 NO ANS LEFT VM & TEXT. JC 12.17 NO ANS LEFT VM & EMAIL . JC 12.18 GAVE TO RICHARD. JC 01/14/22 AIKO GAVE CONSENT VIA TEXT. JC 02/28/22 NO ANS LEFT VM & TEXT. JC 02/28/22 AIKO GAVE CONSENT FOR TREE REMOVAL VIA TEXT. ﻿JC |  |  |  | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Approved | [12 empty] | 2022-02-16 | 2022-01-15 | Yes | 44 | 2022-03-09 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-18 | 2022-03-19 | 44 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Aiko Sugimoto | 510-406-2482 | sugiaiko@aol.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/02 TO 02/06 Crew 504 | 38.6348 | -120.5394 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-09T00:18:31Z | FALSE | 4
402 | 041-431-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5155 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3845.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2022-01-24 | Bio Monitoring Needed for Trees, not Debris | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-13 | 2021-11-16 | 2022-01-21 | 11.15 WORNG NUMBER ON FILE. JC 11.16 Emailed county and got in contact with homeowner. Consented to removal RCV 01/20/22 NO ANS LEFT VM. JC 01/21/22 SPOKE WITH EVONNE SHE SAID OK. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/25/22 HO TEXT BACK TO SAY THEY WILL CALL VENDOR TO HANDLE PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 5 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-11-15 | Yes | 77 | 2022-01-22 |  | 2022-01-27 | 2022-01-27 |  | 2022-01-27 | 2022-01-28 | 77 | 2022-02-10 |  | 2022-02-02 | 2022-02-11 | 2022-02-11 | 2022-02-11 | JORGE & EVONNE PELAEZ | INS AGENT 530-676-8146/ HOMEOWNERS 916 801-9499 | sgandy@cfpnet.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 506 | 38.6349 | -120.5382 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
403 | 041-441-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10020 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3884.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-10 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-09 | 2021-11-10 | 2022-03-15 | 11.10 NO ANS UNABLE TO LEAVE MESS. JC 11.10 SPOKE WITH CLIFTON HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT PROPANE TANK. JC 03/15/22 CLIFTON HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Approved | [12 empty] | 2021-12-03 | 2021-11-01 | Yes | 15 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-25 | 2022-03-26 | 15 | 2022-03-30 |  | 2022-03-28 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Clifton Evans Jr | 916-586-9373 | cliftonevans61@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Adan Mattsson/#507 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 507 | 38.6325 | -120.5396 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
404 | 041-441-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10042 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3871.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-02 | 2021-12-03 | 2022-02-14 | 12.3 SPOKE WITH REBECA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/11/22 NO ANS LEFT VM & EMAIL. JC 02/12/22 NO ANS LEFT VM & SENT 2ND EMAIL. JC 02/14/22 SPOKE WITH REBECA. SHE SAID SHE WILL CALL ME BACK. JC 02/14/22 SPOKE WITH REBECA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-08 |  | 2021-12-10 | 2021-12-10 |  |  | 25 | 2022-01-15 | 2022-01-21 | 5 | Approved | [12 empty] | 2022-01-26 | 2022-01-08 | Yes | 10 | 2022-02-18 |  | 2022-02-18 | 2022-02-18 |  | 2022-02-25 | 2022-02-26 | 10 | 2022-03-10 |  | 2022-02-28 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Rebeca Marshall | 530-919-6497 | rebecamarahall@yahoo.com | Septic | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 509 | 38.6326 | -120.5387 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
405 | 041-441-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10064 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3865.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 6 |  |  | 6 | TRUE | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | POSITIVE | 2021-11-12 | 2021-11-12 | 3 | 2022-01-17 | Bio Monitoring Needed for Trees, not Debris | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-16 | 2021-11-17 | 2022-01-14 | 11.17 SPOKE WITH DEEDIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE TAKE SMALLER PROPANE TANKS BUT VENDOR WILL HANDLE LARGE PROPANE TANK. JC 01/14/22 SPOKE WITH DEEDIE SHE SAID OK. JC |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-11-06 | Yes | 10 | 2022-01-17 |  | 2022-01-17 | 2022-01-17 |  | 2022-01-21 | 2022-01-22 | 10 | 2022-01-27 |  | 2022-01-24 | 2022-01-28 | 2022-01-28 | 2022-01-28 | Keith & Deedie Cunningham | 916-802-4888 | deedie53@pacbell.net | Vehicle on site Keep items Septic | Debris Crew Leader/Crew# Adam, Mattson /#507 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 507 | 38.6326 | -120.5377 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 4
406 | 041-441-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10076 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3861.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-05 | 2021-11-06 | 2022-01-07 | 11.6 NO ANS LEFT VM. JC"11.6 NO ANS LEFT VM. JC 11.6 SPOKE TO MICHELE AND SHE SAID OK PLEASE TAKE THE SMALL PROPANE TANKS PF 01.07 Homeowner consented to tree removal start |  |  |  | 2021-11-10 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-01 | Yes | 11 | 2022-01-10 |  | 2022-01-10 | 2022-01-10 |  | 2022-01-13 | 2022-01-19 | 11 | 2022-01-27 |  | 2022-01-24 | 2022-01-28 | 2022-01-28 | 2022-01-28 | GREGORY & MICHELE EVEN | 719-338-8879 | micmarie39@gmail.com |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 505 | 38.6325 | -120.5373 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
407 | 041-441-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10088 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3853.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-06 | No | [6 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-13 | 2021-11-01 | 2022-01-07 | 10.29 Left and voicemail and text message RCV (homeowner did not believe I was with the removal program) 11.01 Homeowner contact made, acknowledged debris removal start RCV 01.07 ﻿Homeowner contact made, acknowledged hazard tree felling start. Lives on site and wants to be present RCV 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 HO TEXT BACK DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 7 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-08 | Yes | 26 | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  | 2022-01-17 | 2022-01-19 | 26 | 2022-01-27 |  | 2022-01-25 | 2022-02-04 | 2022-02-04 | 2022-02-04 | LYNN HANNBLOM | 916-367-3815 | lynnmh77@hotmail.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 506 | 38.6324 | -120.5368 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
408 | 041-450-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 5 | 041-450-008 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3645.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Trees, not Debris | 2021-11-13 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [10 empty] | 2021-12-01 | 2021-12-07 | 2022-04-04 | 12.06 NO ANS LEFT VM & TEXT. JC 12.07 NO ANS LEFT VM SENT EMAIL. JC 12.7 SPOKE WITH HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC 04/01/22 NO ANS LEFT VM & TEXT. JC 04/02/22 NO ANS LEFT VM & EMAIL. JC 04/04/22 NO ANS LEFT VM & 2ND EMAIL. JC 04/04/22 PHYLIS C/B SHE SAID OK FOR TREE REMOVAL. JC 04/08/22 No Ans left vm & text abt vehicles on property. jc |  |  |  | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-19 | Yes | 4 | [14 empty] | THOMAS KEVIN J & PHYLIS | 916-487-3134 | kt3odd6@gmail.com | Other | Debris Crew Leader/Crew# Antonio Ruiz /#501 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 501 | 38.6292 | -120.5324 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-08T22:14:25Z | FALSE
409 | 041-450-011 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4662 | String Canyon Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3783.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-21 | 2021-12-21 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | POSITIVE | 2022-01-22 | 2022-01-22 | 30 | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes |  | FALSE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-22 | 2022-01-24 | 2022-02-28 | 01/24/22 SPOKE WITH ALDEN HE SAID OK. NO NEED FOR CREW LEADER TO CALL JUST DO WHAT NEEDS TO BE DONE. PLEASE REMOVE PROPANE TANK. JC 02/28/22 N0 ANS LEFT VM & TEXT .JC 02/28/22 HO GAVE CONSENT VIA VOICEMAIL. JC |  |  |  | 2022-01-27 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2021-12-17 | Yes | 7 | 2022-04-02 |  | 2022-04-02 | 2022-04-02 |  | 2022-04-04 | 2022-04-05 | 7 |  |  | 2022-04-06 |  |  |  | Alden Pardew | 530-927-7925 | alden.pardew@gmail.com |  | Debris Crew Leader/Crew# Crystal Egan / #505 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 505 | 38.6422 | -120.5357 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T22:56:39Z | FALSE | 2
410 | 041-450-012 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4680 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3758.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Take |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | POSITIVE | 2021-12-01 | 2021-12-01 | 4 | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-12-01 | 2021-12-03 | 2022-03-18 | 12.03 SPOKE WITH GUADALUPE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 03/17/22 NO ANS LEFT VM & TEXT. JC 03/18/22 NO ANS LEFT VM & EMAIL. JC 03/18/22 GUADALUPE C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 33 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-13 | Yes | 22 | 2022-03-30 |  | 2022-03-31 | 2022-03-31 |  | 2022-04-04 | 2022-04-05 | 16 |  |  | 2022-04-06 |  |  |  | Guadalupe Rodriguez | 530-903-7037 | rodriguezguadalupe_12@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell /#504 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 504 | 38.6421 | -120.5363 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T18:45:07Z | FALSE | 4
411 | 041-450-017 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Rescrape Needed | Tree Assessment Complete | 4993 | Old Nail Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3840.49 |  |  |  |  | TRUE | DTSC Attn |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 2 | 0 | 2 | 1 | 8 |  |  | 2 |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2022-01-28 | Arch Monitoring Needed for Debris AND Trees | [12 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-28 | 2022-01-28 |  | 01/28/22 SPOKE WITH JOHN. HE SAID THEY WANT TO BE ON SITE DURING THE REMOVAL PROCESS. PLEASE CALL IN ADVANCE. THEY HAVE SEVERAL PROPANE TANKS, LEASE ON AND OWN THE OTHERS. THEY WOULD LIKE FOR THE OWNED PROPANE TANKS TO BE REMOVED AND VENDOR HANDLING LEASED PROPANE TANK. JC 04/08/22 Spoke with John abt vehicles on property. He said there were removed already. jc |  |  |  | 2022-02-01 |  | 2022-02-03 | 2022-02-03 |  |  | 7 | 2022-02-12 | 2022-02-22 | 7 | Re-scrape | [13 empty] | 2022-01-20 | Yes | 32 | [14 empty] | John & Constance Sanquinetti | 530-919-6449 , 530-919-6447 | jhsang_22@yahoo.com | Keep Items Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Tami Collins/ Terrence Harrison - #501/502 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 5071/502 | 38.6364 | -120.5322 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T20:14:40Z | FALSE
412 | 041-472-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7014 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 1 | TRUE | Yes | Take | 2022-02-16 | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2022-02-04 | Bio Monitoring Needed for Debris AND Trees | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-11-18 | 2021-11-19 | 2022-01-18 | 11.18 SPOKE WITH THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 01/18/22 SPOKE WITH THOMAS HE SAID OK. JC 01/29/22 TALKED WITH THOMAS TO LET HIM KNOW THE CREW COMING OUT. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Approved | [12 empty] | 2021-12-14 | 2021-11-30 | Yes | 28 | 2022-02-03 |  | 2022-02-04 | 2022-02-04 |  | 2022-02-07 | 2022-02-08 | 28 | 2022-02-11 |  | 2022-02-11 | 2022-02-17 | 2022-02-17 | 2022-02-17 | Thomas Hawley | 530-305-7433 | caldorefireROE@edcgov.us | Vehicles on site | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 502 | 38.6453 | -120.5226 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
413 | 041-472-007 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6988 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3981.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-04 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-02-04 | Bio Monitoring Needed for Trees, not Debris | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees | [12 empty] | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-01-24 | 12.4 NO ANS LEFT VM. JC 01/22/22 NO ANS LEFT VM & TEXT. JC 01/24/22 NO ANS LEFT VM & EMAIL. JC 01/24/22 HO GAVE CONSENT VIA EMAIL. JC 01/29/22 NO ANS LEFT VM TO INFORM HO THAT CREW COMING OUT NEXT WEEK. JC | [27 empty] | 2021-12-01 | Yes | 24 | 2022-02-04 |  | 2022-02-07 | 2022-02-07 |  | 2022-02-08 | 2022-02-09 | 24 |  |  | 2022-02-16 |  | 2022-02-16 | 2022-02-17 | Mark & Lisa Mallder | 916-316-3235 | markmallder@gmail.com |  |  | 38.6456 | -120.5219 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
414 | 041-472-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 6970 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3972.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-02-04 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-18 | TRUE |  | Class II | Covered under suspension | TRUE | [12 empty] | 2022-03-28 | 02/21/22 NO ANS LEFT VM & TEXT JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 SPOKE WITH MARK HE SAID OK FOR TREE REMOVAL. JC 03/02/22 Spoke with Mark, he said he wants all of the hazard trees cut and removed. Mark wants someone from county to contact him to discuss alternatives for removing trees from property. JC 3.28 NO ANS. LEFT MESS AND SENT TEXT PF | [27 empty] | 2021-11-12 | Yes | 45 | [14 empty] | MARK & SUSAN ALMER | 530-559-3774 | SUSANANDMARKALMER@GMAIL.COM |  |  | 38.6459 | -120.5224 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
415 | 041-472-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 1 | 6906 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3963.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No |  | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Take | 2022-02-16 | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-22 | 2021-11-22 | 3 | 2021-11-08 | Bio Monitoring Needed for Trees, not Debris | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-11-22 | 2021-11-29 | 2022-02-18 | "11.24 SPOKE WITH BREANNE SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/19/22 NO ANS LEFT VM, TEXT AND EMAIL. JC 01/20/22 NO ANS LEFT VM. GAVE TO RICHARD. JC 01/21/22 per Melissa clear to proceed. JC" 02/16/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 02/17/22 NO ANS LEFT VM & EMAIL JC 02/18/22 NO ANS LEFT VM & 2ND EMAIL. JC 02/18/22 CLEAR TO PROCEED PER MELISSA PERRY. JC | 3 | State Planner: Melissa Perry |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-13 | 7 | Re-scrape |  |  |  | 2022-01-21 | 2022-01-31 | Approved | [6 empty] | 2022-02-01 | 2021-11-11 | Yes | 45 | [14 empty] | James Holland-Crespo, Sloan Holland-Crespo | (916 470-1027 | jameshollandcrespo@yahoo.com | Vehicles on site Septic | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 502 | 38.6452 | -120.5234 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-08T20:13:41Z | FALSE
416 | 041-472-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 1 | 6900 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3978.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-11-16 | 2021-11-19 | 2022-02-18 | 11.16 NO ANS UNABLE TO LEAVE MESS. NO VM. SENT EMAIL JC 11.18 NO ANS UNABLE TO LEAVE MESS. NO VM. JC GAVE TO RCV 11.22 Attempted to call other phone numbers listed on insurance page to no success. Approval given to removal crews per Kendall Wilson. 02/16/22 PHONE NUMBER NOT IN SERVICE. SENT EMAIL. JC 02/17/22 SENT 2ND EMAIL. JC 02/18/22 CLEAR TO PROCEED PER MELISSA PERRY. | 2 | Kendall Wilson |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 3 | 2021-11-30 | 2021-12-08 | 7 | Re-scrape |  |  |  | 2022-01-22 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2021-11-10 | Yes | 31 | [14 empty] | Michael Nichols | 831-869-0203 | michael5cents@sbcglobal.net | Vehicles on site Septic | Debris Crew Leader/Crew# Justine Romero/#502 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 502 | 38.6448 | -120.5235 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-09T00:18:57Z | FALSE
417 | 041-482-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 1 | 6878 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3988.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Take | 2022-02-16 | 2021-11-09 | Yes | 2021-11-10 | 2021-11-16 | POSITIVE | 2021-11-19 | 2021-11-19 | 4 | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-14 | 2021-11-19 | 2021-11-19 | 2022-03-23 | 11.17 NO ANS UNABLE TO LEAVE MESS. SENT EMAIL. JC 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT. JC GAVE TO RICHARD 01/26/22 SPOKE WITH SEAN HE SAID PLEASE REMOVE PROPANE TANK IF DAMAGED. JC 02/11/22 SPOKE WITH SEAN HE SAID OK FOR TREE REMOVAL. PLEASE REMOVE THE PROPANE TANK. ﻿****DO NOT REMOVE GATE ON THE LEFT SIDE OF THE ENTRANCE. ****JC 03/22/22 NO ANS LEFT VM & TEXT. JC 03/23/22 HO GAVE CONSENT VIA TEXT. JC | 3 | Kendall Wilson |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape |  |  |  | 2022-02-01 | 2022-02-09 | Approved | [6 empty] | 2022-02-10 | 2022-03-22 | Yes | 11 | [14 empty] | Leslie & Sean Murphy | 760-576-7576 | sean_dakid99@hotmail.com | Vehicles on site | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 11/24 to 12/01Crew 502 | 38.6441 | -120.5242 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-08T01:12:11Z | FALSE
418 | 041-431-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10059 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3879.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 1 | 0 | 2 | 0 | 7 |  |  | 1 | TRUE | No |  |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | POSITIVE | 2021-12-03 | 2021-12-03 | 3 | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-03 | 2021-12-06 | 2022-03-03 | 12.04 NO ANS LEFT VM FOR DEBRIS REMOVAL. JC 12.06 NO ANS LEFT VM & TEXT. JC 12.06 LEE SAID OK TO PROCEED VIA TEXT. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 NO ANS LEFT VM & EMAIL. JC 03/03/22 SPOKE WITH LEE HE SAID OK HE SAID NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 26 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-01-08 | Yes | 40 | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-17 | 2022-03-18 | 40 | 2022-03-23 |  | 2022-03-19 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Lee Anders | 916-673-8715 | k100teebob@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison#509 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 509 | 38.6337 | -120.538 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 9
419 | 041-431-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10047 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3889.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | Yes | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-08 | 2021-11-03 | Yes | 2021-11-04 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-11 | Bio Monitoring Needed for Debris AND Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-18 | 2021-11-18 | 2022-02-01 | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH DALE HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE THE PROPANE TANK. JC 02/01/22 SPOKE WITH DALE HE SAID OK. JC |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Re-scrape |  |  |  | 2022-01-18 | 2022-01-26 | Approved | [6 empty] | 2022-01-27 | 2021-11-03 | Yes | 10 | 2022-02-11 |  | 2022-02-11 | 2022-02-11 |  | 2022-02-12 | 2022-02-14 | 10 | 2022-02-18 |  | 2022-02-15 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Dale Farias | 415-240-0305 | dstack743@gmail.com | Septic | Debris Crew Leader/Crew# Adam Mattson/#507 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 507 | 38.6337 | -120.5386 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
420 | 041-431-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5121 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3896.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 |  | FALSE |  |  |  |  | TRUE | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-01-20 | 01/20/22 SPOKE WITH JONATHAN HE SAID OK. JC | [27 empty] | 2021-12-21 | Yes | 24 | 2022-01-22 |  | 2022-01-22 | 2022-01-22 |  | 2022-01-24 | 2022-01-25 | 24 |  |  | 2022-01-26 |  | 2022-01-26 | 2022-01-26 | Jonathan & Shari Jochem | 916-767-2908 | jonjochem@gmail.com | Other Septic Vehicles Onsite |  | 38.6336 | -120.5392 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
421 | 041-431-005 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Crew ELD 7 | 5107 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3877.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-03-28 | 03/28/22 SPOKE WITH JONATHAN HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2021-12-21 | Yes | 34 | [7 empty] | 1 | [6 empty] | Jonathan & Shari Jochem | 916-767-2908 | jonjochem@gmail.com |  |  | 38.6341 | -120.5389 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-09T00:29:35Z | FALSE
422 | 041-431-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5099 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3875.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-02-09 | Bio Monitoring Needed for Trees, not Debris | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-02-01 | 02/01/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. HE SAID NO NEED TO CALL BEFORE CREW COMES. NO PROPANE TANK ON PROPERTY. JC | [27 empty] | 2021-12-22 | Yes | 33 | 2022-02-09 |  | 2022-02-10 | 2022-02-10 |  | 2022-02-16 | 2022-02-17 | 33 |  |  | 2022-02-19 |  | 2022-02-19 | 2022-02-19 | David Cafiero | 707-364-2338 | dave@kalabrand.com |  |  | 38.6345 | -120.5391 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
423 | 041-432-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 5184 | Mt Pleasant Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3818.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-03 |  | FALSE | [5 empty] | No | No | No | No | No |  |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-03-07 | Bio Monitoring Needed for Trees, not Debris | 2022-03-09 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-07 | No Activity/Nest Building Removed | [11 empty] | FALSE | [41 empty] | 2022-04-05 | Yes | 87 | [14 empty] | Robert Fischer | 408-898-0271 | rob.fischer@att.net |  |  | 38.6346 | -120.5364 | Caldor | DR-4619 | Residential | No | 2022-03-01 | ROE Verified | Central Division | 2022-04-05T18:11:56Z | FALSE
424 | 041-432-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5198 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3839.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-03 |  |  | No | None | FALSE | [12 empty] | 2022-03-04 | 03/04/22 SPOKE WITH DONALD HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-14 | Yes | 89 | 2022-03-08 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-18 | 2022-03-19 | 89 |  |  | 2022-03-21 |  | 2022-03-21 | 2022-03-22 | SCOTT, DONALD & DEBBIE | 530-409-8915 | scott719@sbcglobal.net |  |  | 38.634 | -120.5364 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
425 | 041-432-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 3 | 5210 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3851.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 5 |  |  |  |  | Yes | Take |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-09 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-21 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-15 | 2022-01-17 | 2022-03-16 | 01/17/22 PHONE BUSY SENT TEXT. JC 01/17/22 SPOKE WITH THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANKS. JC 03/16/22 SPOKE WITH THOMAS HE SAID OK FOR TREE REMOVAL. JC 04/08/22 Spoke with Thomas, he said all vehicles were removed from property. JC |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-15 | Yes | 36 | [14 empty] | Thomas & Gwendolyn Douglas | 530-663-6681 |  | Vehicle on site Septic | Debris Crew Leader/Crew# Eric Rocha / 504 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 504 | 38.6336 | -120.5364 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-08T20:25:43Z | FALSE
426 | 041-432-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 3 | 5218 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3853.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-10 | Yes | 2021-12-10 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-01-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-25 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-14 | 2022-01-18 | 2022-03-23 | 01/17/22 NO ANS LEFT VM & TEXT. JC 01/18/22 NO ANS LEFT VM & EMAIL. JC 01/18/22 WILLIAM CALLED BACK. HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/23/22 NO ANS LEFT VM & TEXT. JC 03/23/22 WILLIAM C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 3 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-01-14 | Yes | 39 | [14 empty] | William C. Bryant Tabita Bryant | 916-705-1268 | Tabitabryant@yahoo.com |  | Debris Crew Leader/Crew# Eric Rocha/ #504 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 504 | 38.6331 | -120.5364 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T17:17:26Z | FALSE
427 | 041-441-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10052 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3872.71 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 5 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-02 | 2021-12-03 | 2022-02-11 | 12.03 NO ANS LEFT VM. JC 12.03 SPOKE WITH HO DAUGHTER SHE SAID OK BUT PLEASE CALL 530 957-2679 IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/11/22 SPOKE WITH DAUGHTER SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 27 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-01-08 | Yes | 13 | 2022-02-18 |  | 2022-02-18 | 2022-02-18 |  | 2022-02-25 | 2022-02-26 | 13 | 2022-03-10 |  | 2022-02-28 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Kay M. Regan/ SHAWN RAGAN (DAUGHTER) | 510-523-5360/ 530 957-2679 | shawnregan12@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 509 | 38.6326 | -120.5382 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
428 | 041-441-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10100 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3844.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-11 | 2021-11-15 | 2022-02-10 | 11.15 SPOKE WITH LORENA SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT BURNED. JC 02/10/22 SPOKE WITH LORENA SHE SAID OK. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 3 | 2021-11-23 | 2021-12-03 | 7 | Re-scrape | 2022-01-15 | 2022-01-21 | Re-scrape | 2021-12-07 | 2021-12-15 | Soil Boring | 2022-01-31 | 2022-02-08 | Approved |  |  |  | 2022-02-09 | 2021-11-05 | Yes | 20 | 2022-02-18 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-28 | 2022-03-01 | 20 | 2022-03-09 |  | 2022-03-02 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Lorena Beaudion | 530-919-1191 | jumboshrimp4@yahoo.com | Vehicle on site Keep items Septic | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 507 | 38.6324 | -120.5363 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 9
429 | 041-450-009 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4710 | String Canyon Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3761.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 1 |  | Yes | Leave |  | 2021-10-23 | Yes | 2021-10-26 | 2021-10-29 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Complete | No |  |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-05 | 2021-11-09 | 2022-02-12 | 11.9 NO ANS LEFT VM. JC 11.9 SPOKE TO LORI SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED THE PROPANE TANK JC 02/11/22 NO ANS LEFT VM TEXT . JC 02/12/22 SPOKE LORI SHE SAID OK TREE REMOVAL. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-03 | Yes | 50 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-04-05 | 2022-04-05 | 50 |  |  | 2022-04-08 |  |  |  | FREDERICK & LORI COOPER | 916-334-0112 | fnl@gpagmac.com | Vehicle On Site Septic | Debris Crew Leader/Crew# Tony Ruiz/#510 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 510 | 38.6428 | -120.5367 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T19:41:46Z | FALSE | 7
430 | 041-450-010 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4664 | String Canyon Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3833.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes |  | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | POSITIVE | 2021-10-29 | 2021-10-29 | 9 | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-21 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-10-29 | 2021-11-05 |  | 11.3 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC 11.5 SPOKE WITH BENJAMIN. HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 02/11/22 NO ANS LEFT VM TEXT. JC 02/12/22 NO ANS LEFT VM & EMAIL.JC 02/12/22 HO SAID OK FOR TREE REMOVAL AND NOT PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-29 | Yes | 1 | 2022-03-30 |  | 2022-03-30 | 2022-03-30 |  | 2022-04-04 | 2022-04-05 | 1 |  |  | 2022-04-06 |  |  |  | BENJAMIN EDENS | 864-616-2777 | benedens@gmail.com |  | Debris Crew Leader/Crew# Tony Ruiz /#510 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 510 | 38.6428 | -120.5358 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T17:18:28Z | FALSE | 5
431 | 041-450-013 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 041-450-013 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3793.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-09 | Bio Monitoring Needed for Trees, not Debris | 2022-02-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-08 | No |  | TRUE |  | Class III | None | FALSE | [12 empty] | 2022-03-23 | 03/23/22 SPOKE WITH SHAUN HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-24 | Yes | 27 | [14 empty] | Shaun Kosnikowski | 916-410-1420 | icekoz@yahoo.com |  |  | 38.6397 | -120.5351 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
432 | 041-450-020 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10233 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3853.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-27 | 2022-01-27 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 6 | 5 | 0 | 6 | 1 | 4 | 2 | 24 |  |  | 19 | TRUE | Yes | Leave |  | 2021-12-10 | Yes | 2021-12-10 | 2021-12-15 | POSITIVE | 2022-01-20 | 2022-01-20 | 26 | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2022-01-28 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class IV | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2022-01-28 | 2022-02-01 | 2022-03-03 | 01/29/22 PHONE NUMBER ON FILE NOT IN SERVICE SENT EMAIL. JC 01/31/22 PHONE NUMBER STILL OUT OF SERVICE SENT EMAIL. JC 2/1/2022: Okay to proceed - MP 02/01/22 sent final email. JC 03/01/22 PHONE NUMBER NOT IN SERVICE SENT EMAIL. JC 03/02/22 PHONE STILL NOT IN SERVICE SENT 2ND EMAIL. JC 03/03/22 Cleared to proceed per Melissa. JC | 3 | State Planner: Melissa Perry |  | 2022-02-02 |  | 2022-02-04 | 2022-02-04 |  |  | 4 | 2022-02-09 | 2022-02-17 | 7 | Approved | [12 empty] | 2022-02-19 | 2022-03-10 | Yes | 19 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-21 | 2022-03-22 | 18 | 2022-03-24 |  | 2022-03-23 | 2022-03-25 | 2022-03-25 | 2022-03-25 | James Duncan | 590-306-3776 | jameseduncanlvn@icloud.com | Septic Well | Debris Crew Leader/Crew# Terrence Harrison/ #510 Debris Crew WO# Refer to IAP 02/02 To 02/06 Crew 510 | 38.6351 | -120.5313 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 10
433 | 041-450-023 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4630 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3807.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | No |  |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-02 | 2021-12-06 | 2022-02-11 | 12.06 SPOKE SHAUN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANKS. JC 02/10/22 NO ANS LEFT VM TEXT. JC 02/11/22 SPOKE WITH SHAUN HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 28 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2021-11-20 | Yes | 8 | 2022-03-25 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-31 | 2022-04-01 | 8 |  |  | 2022-04-04 |  |  |  | Shaun Kosnikowski | 916-410-1420 | icekoz@yahoo.com | Septic | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 504 | 38.6404 | -120.5351 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-04T20:25:12Z | FALSE | 6
434 | 041-450-024 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-450-024 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3816.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-02-14 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-08 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-15 | 3.15 Spoke to Shaun he said ok. PF | [27 empty] | 2022-02-21 | Yes | 64 | 2022-03-25 |  | 2022-03-28 | 2022-03-28 |  | 2022-04-01 | 2022-04-02 | 64 |  |  | 2022-04-05 |  | 2022-04-05 | 2022-04-05 | Shaun Kosnikowski | 916-410-1420 | icekoz@yahoo.com |  |  | 38.6411 | -120.5351 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-05T20:45:55Z | FALSE | 4
435 | 041-712-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5145 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3793.47 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | Yes | 2022-02-16 | No |  | TRUE |  | Class III | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-10-14 | 2021-11-06 | 2022-03-26 | 11.4 NO ANS. LEFT MESS. JC 11.5 NO ANS. LEFT VM. JC 11.6 (HO NEVER ANSWERED THE PHONE BUT REPLIEDTO AN EMAIL). 11.6 NO ANS LEFT MESS PF "Thank you for reaching out to me. I appreciate all of your current & future efforts. Do I need to do anything or is this just an fyi? Cheryl & Jeff Dooley" 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SPOKE WITH JEFF DOOLEY HE SAID OK. JC 01/20/22 SPOKE WITH JEFF HE SAID OK FOR TREES. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/25/22 JEFF C/B HE SAID PLEASE REMOVE PROPANE TANK IF DAMAGED. JC 03/26/22 FOLLOW-UP NO ANS LEFT VM & TEXT. JC 03/26/22 JEFF C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-08 |  | 2021-11-08 | 2021-11-08 |  |  | 5 | 2021-11-12 | 2021-11-19 | 6 | Approved | [12 empty] | 2021-11-22 | 2022-03-26 | Yes | 14 | [14 empty] | CHERYL DOOLEY | 530-919-5595 | grizzlyjeff@jeffreydooley.com |  | "Debris Crew Leader/Crew# Matthew Dorenzo/505 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 505" | 38.634 | -120.5341 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
436 | 041-721-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5225 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 3 |  |  | 1 | TRUE | No |  |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-04 | NEGATIVE |  |  |  | 2021-10-30 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-06 | 2021-11-08 | 2022-02-10 | 11.8 SPOKE WITH TAMI SHE SAID OK BUT PLEASE CALL IN ADVNACE. NO PROPANE TANK. JC 12.4 SPOKE WITH KRISTOFFER HE SAID OK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 SPOKE WITH TAMI SHE SAID OK. JC |  |  |  | 2021-11-10 |  | 2021-11-12 | 2021-11-12 |  |  | 1 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-05 | Yes | 8 | 2022-02-26 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-01 | 2022-03-02 | 8 | 2022-03-11 |  | 2022-03-02 | 2022-03-24 | 2022-03-24 | 2022-03-24 | KRISTOFFER & TAMI CHRISTNER | 530-391-2399, 530-903-7053 | tchristner7712@gmail.com | Septic Vehicle On Site | Debris Crew Leader/Crew# Robert Boyer#508 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 508 | 38.6327 | -120.5338 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 1
437 | 041-721-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5241 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3798.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | Yes | 2022-03-14 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-12 | 2022-01-20 | 2022-03-01 | 01/20/22 SPOKE WITH BRYON HE SAID OK. VENDOR HANDLING PROPANE. JC 03/01/22 SPOKE WITH BRYON SAID OK FOR TREE REMOVAL. JC 03/15/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/16/22 SPOKE WITH BRYON HE SAID OK FOR TREE REMOVAL. HE SAID NO NEED TO MAKE FOLLOW UP CALL. JC |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-27 | Yes | 43 | 2022-03-29 |  | 2022-03-31 | 2022-03-31 |  | 2022-04-02 | 2022-04-04 | 43 |  |  | 2022-04-05 |  |  |  | Bryon Vining | 530-919-2892 | None |  | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 501 | 38.6324 | -120.5344 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-05T19:42:10Z | FALSE | 2
438 | 041-722-008 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 5 | 5313 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3771.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-14 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-07 | 2022-02-22 | "12.07 NO ANS LEFT VM & TEXT. JC 12.07 DEBORAH GAVE CONSENT VIA TEXT. JC" 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 HO SAID OK VIA EMAIL. JC |  |  |  | 2022-01-13 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-15 | Yes | 39 | 2022-04-08 | [6 empty] | 9 | [6 empty] | Deborah Morales | 209-329-2874 | debbiesggl@gmail.com | Septic | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 01/12 To 01/15 Crew 516 | 38.6315 | -120.5325 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-08T23:38:39Z | FALSE
439 | 037-120-004 | Full Program ROE (debris + trees) | ROE Received | Needs Assessment | Next Step: N/A | Need Site Assessment | Tree Assessment Needed | 20712 | US HIGHWAY 50 |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 7214.55 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | No |  | TRUE |  |  | FALSE |  | FALSE |  |  | FALSE | [6 empty] | FALSE | FALSE | [7 empty] | 0 | [33 empty] | FALSE | [8 empty] | FALSE |  |  |  |  | 02/07/22 SPOKE WITH JAMES HE SAID NO BURNED STUCTURES OR DEBRIS. | [7 empty] | FALSE | [20 empty] | Ok to Assess | [15 empty] | James Adams | 510-209-7089 | james@firestop.us |  |  | 38.8237 | -120.0441 | Caldor | DR-4619 | Residential | Yes | 2021-12-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
440 | 037-140-002 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 037-140-002 | No Address |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 7112.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [32 empty] | Ok to Assess | [15 empty] | FEDANE, ROHIT | 408-242-6164 | rohitfedane@gmail.com |  |  | 38.823 | -120.0647 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
441 | 037-160-002 | Full Program ROE (debris + trees) | Site Assessment Complete | Needs Assessment | Next Step: N/A | Need ASB Assessment | Tree Assessment Needed | 20120 | US Highway 50 |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6923.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | [5 empty] | No | Yes | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No | [10 empty] | 2021-12-07 | Bio Monitoring Needed for Debris AND Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 |  |  |  | 02/12/22 PLEASE REMOVE PROPANE TANK. JC | [28 empty] | Ok to Assess | [15 empty] | George Allen Faris | 916-601-3728 | allen.faris@icloud.com |  |  | 38.8214 | -120.0687 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
442 | 037-160-027 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 037-160-027 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 6911.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-08 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [42 empty] | Ok to Assess | [15 empty] | George Allen Faris | 916-601-3728 | allen.faris@icloud.com |  |  | 38.8212 | -120.0695 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
443 | 037-160-028 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 037-160-028 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3727.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-11 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | [14 empty] | Class II |  | FALSE | [42 empty] | Ok to Assess | [15 empty] | YUSUFZAI SULTAN | 916-704-5898 | sultan.y@gmail.com |  |  | 38.8212 | -120.07 | Caldor | DR-4619 | Residential | No | 2021-10-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
444 | 037-180-001 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 19920 | Highway 50 |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6880.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-23 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-30 | 2021-11-18 |  | 11.18 SPOKE WITH JIM HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26﻿/22 JIM C/B HE SAID IF THERE IS A PROPANE TANK, PLEASE REMOVE. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 86 | 2022-04-06 |  | 3 | [14 empty] | 2022-03-18 | Yes | 43 | [14 empty] | Jim Moravec - 3zm Land & Cattle | 530-864-8956 | jmoravec@3zmland.com |  | Debris Crew Leader/Crew# Crystal Egan/#513 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 513 | 38.8182 | -120.0762 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
445 | 037-210-001 | Full Program ROE (debris + trees) | Pending Asbestos Results |  | Next Step: N/A | Twin Bridges Pending | Tree Assessment Complete | 2007 | Alpine Avenue |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6876.33 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2022-04-04 | 2022-04-04 | FALSE | No | FALSE |  | No | FALSE | No | Yes | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-04 | Yes | 2022-04-04 | 2022-04-07 |  |  |  |  | 2022-03-21 | Bio Monitoring Needed for Debris AND Trees | [16 empty] | FALSE | [8 empty] | FALSE |  |  |  |  | "02/07/22 NO ANS VOICEMAIL FULL SENT TEXT. ABT ELIGIBLE DEBRIS JC. 02/09/22 MAILBOX FULL SENT EMAIL. JC 02/09/22 HO C/B HE SAID BURNED STRUCTURES ON PROPERTY. JC" | [7 empty] | FALSE | [19 empty] | 2022-01-18 | Ok to Assess | 12 | [14 empty] | Bill Duran | 916-534-0406 | BillDuran@hotmail.com |  |  | 38.8173 | -120.077 | Caldor | DR-4619 | Residential | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-07T23:02:34Z | FALSE
446 | 037-210-002 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7911 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6875.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-12 | 2021-11-15 |  | 11.15 NO ANS LEFT VM. JC 11.15 SPOKE WITH JANET SHE SAI OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape | [13 empty] | 2021-12-02 | Yes | 45 | [14 empty] | JANET, DONALD & RICHARD SAMBUCETTI | 530-306-1948 | jsambucetti52@hotmail.com | SEPTIC | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 511 | 38.8174 | -120.0767 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-04T16:36:57Z | FALSE
447 | 037-210-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 2029 | Alpine Avenue |  | South Lake Tahoe | El Dorado |  | Residential | [5 empty] | 6889.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-22 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-21 | 2021-11-22 | 2021-11-18 |  | 11.18 PH# NOT IN SERVICE. SENT EMAIL. JC 11.18 NO ANS LEFT VM. JC 11.18 STEVEN RETURNED CALL AND SAID OK BUT WOULD LIKE TO BE THERE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-03 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2022-01-18 | Yes | 20 | [14 empty] | STEVEN & CHERI LOPEZ | 916-462-7671 | scutske@yahoo.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 511 | 38.8165 | -120.077 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
448 | 041-711-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5132 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3793.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 4 |  |  | 1 | TRUE | No |  |  | 2021-12-02 | No | [6 empty] | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-16 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-11 | 2022-01-14 |  | "01/14/22 NO ANS LEFT VM & TEXT. JC 01/14/22 HO GAVE CONSENT VIA TEXT for 5134 and 5124. JC" 3/19/22 - Sent a text advising of crew mobilization - MP 03/21/22 NO ANS LEFT VM & TEXT ABT, TREE REMOVAL. JC 3.21 3.21.22-JOSE C/B AND SAID OK PF |  |  |  | 2022-01-29 |  | 2022-01-29 | 2022-01-29 |  |  | 3 | 2022-02-02 | 2022-02-10 | 7 | Re-scrape |  |  |  | 2022-02-17 | 2022-02-25 | Approved | [6 empty] | 2022-03-01 | 2022-01-04 | Yes | 11 | 2022-03-21 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-24 | 2022-03-25 | 11 | 2022-03-30 |  | 2022-03-26 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Daniel Jose | 916-622-7030 | dcjose2014@gmail.com | Other Vehicles Onsite | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 501 | 38.6348 | -120.5346 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
449 | 041-711-013 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5146 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-02 | No | [6 empty] | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2021-12-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-03-16 | 3.16 Spoke to Tara she said ok PF | [27 empty] | 2022-01-06 | Yes | 24 | [14 empty] | Tara Young | 530-497-4639 | Taramisoo73@yahoo.com | Vehicles Onsite |  | 38.6346 | -120.534 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
450 | 041-711-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5154 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3799.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-15 | 2021-11-16 | 2022-03-31 | 11.16 NO ANS LEFT VM JC 11.16 SPOKE BRENNAN HE SAID OK BUT PLEASE CALL IN ADVNACE. VENDOR HANDLING PROPANE TANK. JC 3.31 SPOKE BRENNAN HE SAID OK PF |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-03 | Yes | 7 | [14 empty] | BRENNAN & YLOANDA WILLIAMS | 916-770-0928 | brennanw28@gmail.com | Septic | Debris Crew Leader/Crew# Crystal Egan #508 Debris Crew WO# Refer to IAP 11/20to 11/24 Crew 508 | 38.6346 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
451 | 041-711-016 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5164 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3804.05 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Take | 2022-02-17 | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-03-01 | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-05 | 2021-11-11 | 2022-01-27 | 11.6 NO ANS LEFT VM. JC 11.8 NO ANS LEFT VM. JC 11.8 SENT EMAIL. JC SENT TO RICHARD. 11.13 Contacted by son of owner who passed away. Acknowledged debris removal start. Can be reached at (541)727-8447 RCV 12.4 NO ANS LEFT VM AT PH# ABOVE FOR TREE REMOVAL. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 HO SAID PLEASE REMOVE PROPANE TANK AND GAVE CONSENT FOR TREE REMOVAL . JC 03/16/22 NO ANS LEFT VM & TEXT. JC 3.17No ans. Left VM 2nd email PF 03/18/22 SPOKE WITH SON MICHAEL. HE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. |  | Kendall Wilson |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-12-01 | Yes | 17 | [14 empty] | Warren Anderson (passed) Son's MICHAEL number listed | (541)727-8447 | wanderson558712@att.net |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 505 | 38.6344 | -120.533 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-05T23:16:53Z | FALSE
452 | 041-711-017 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5170 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3804.31 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 4 | 1 | 0 | 3 | 0 | 1 | 0 | 9 |  |  | 6 |  | No |  |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | POSITIVE | 2022-01-18 | 2022-01-18 | 28 | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-03 | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-18 | 2022-01-21 |  | 12.21 SPOKE WITH BRUCE HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 1.18 TFL spoke with homeowner, acknowledged start of debris removal RCV 04/08/22 Call abt vehicles. No ans left vm & text. jc 04/08/22 Bruce c/b he said to leave vehicles. JC |  |  | 2022-01-18 | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 7 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-26 | Yes | 7 | [14 empty] | Bruce & Britney Duncan | 530-919-9920 | iluvowienlilah27@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 515 | 38.6341 | -120.5328 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T21:16:57Z | FALSE
453 | 028-310-048 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 15512 | Sams Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2156.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2021-12-20 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | 2021-12-20 | 2021-12-27 |  | 12.23 NO ANS LEFT VM & TEXT. JC 12.27 SPOKE GERRY SHE SAID BE SAFE AND OK BUT PLEASE CALL IN ADVANCE. ﻿VENDOR HANDLING PROPANE. JC |  |  |  | 2022-01-12 |  | 2022-01-12 | 2022-01-12 |  |  | 2 | 2022-01-13 | 2022-01-21 | 7 | Approved | [12 empty] | 2022-01-26 | 2022-01-03 | No | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Gerry Schwede | (530) 558-5070 | no email | Septic Well | Debris Crew Leader/Crew# Glenn Adams / #403 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 403 | 39.1263 | -120.9792 | River Fire | DR-4601 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
454 | 028-310-049 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20196 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2124.39 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 4 |  |  | 3 | TRUE | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-10-28 | 2021-10-28 | 7 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-11-15 | Arch Monitoring Needed for Debris, not Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-15 | 2021-11-17 |  | 11.16 NO ANS LEFT VM. JC 11.17 NO ANS LEFT VM. SPOKE WITH BRENDA SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-05 |  | 2021-12-10 | 2021-12-10 |  |  | 8 | 2021-12-21 | 2021-12-30 | 7 | Soil Boring | 2022-01-08 | 2022-01-14 | Re-scrape | 2022-01-26 | 2022-02-03 | Approved | [6 empty] | 2022-02-04 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-02-16 |  |  | 2022-02-28 | 2022-02-28 | 2022-02-28 | Jeffrey and Brenda Bevilacqua (Bevilacqua Living Trust) | (805) 807-2008 or (805) 802-0366 | brendabbev@gmail.com or jlbevila@yahoo.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 403 | 39.1293 | -120.9843 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
455 | 028-350-009 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 20268 | Post Chaise Circle |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2277.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | Yes | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-10-25 | 2021-10-28 |  | "10.28 NO ANS PF 10.28 SPOKE TO JEFFREY AND HE SAID OK PROCEED NO NEED TO CALL. PF " |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 6 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Jeffrey Emery and Rebecca Laude | (916) 215-5474 | jeff463@icloud.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray /#302 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 302 | 39.1263 | -120.988 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
456 | 028-350-015 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 20154 | Post Chaise Circle |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2182.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 3 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-18 | No Bio Monitoring Needed for Debris or Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-10-21 | 2021-10-28 |  | 1 10.27 in contact with agent (Rick), owner to call later in day RCV 10.28 NO ANS LEFT MESS PF 10.28 SPOKE TO MR EWALD SAID OK BUT PLEASE CALL BEFORE GOING OUT.PF |  |  |  | 2021-11-02 |  | 2021-11-02 | 2021-11-02 |  |  | 6 | 2021-11-09 | 2021-11-18 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | David Zimmerman (owner) Rick Ewald (Agent for Owner) | Agent: (530) 575-1439; Owner: Lives in Australia (01161 400-821-919) or for messages (530)346-8438 | Agent: rick@dbspublicadjusters.com; Owner: support@fetivaldogs.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 302 | 39.124 | -120.9896 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
457 | 028-350-016 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 20926 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2012.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | TRUE | TRUE | 6 | 0 | 0 | 0 | 1 | 2 | 0 | 9 |  |  | 11 | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-24 | 2021-10-20 | 2021-10-28 |  | "10.28 NO ANS. LEFT MESS PF 10.28 SPOKE TO SEAN DOLBEE HE SAID OK AND PLEASE CALL BEFORE GOING OUT.PF" 01/25/22 SPOKE WITH SEAN HE SAID LEAVE PROPANE TANK. JC |  |  |  | 2022-01-17 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2021-11-17 | Do Not Assess | 0 | [8 empty] | 2022-02-28 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Sean Dolbee | (530) 315-7677 | dolbee555@yahoo.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Cynthia Sanderson / #301 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 301 | 39.1234 | -120.9874 | River Fire | DR-4601 | Residential | No | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
458 | 028-360-011 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 20976 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1907.69 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | POSITIVE | 2021-10-29 | 2021-10-29 | 9 | 2021-10-16 | Bio Monitoring Needed for Debris AND Trees | 2021-10-16 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE |  | 2021-11-04 | [6 empty] | TRUE | 2022-03-24 | 2021-10-29 | 2021-10-27 | 2021-10-27 | 10.27 SPOKE TO GARRETT AND he said ok PF NO ANS FOR TANK LEFT MESS PF 11.2﻿ TANK IS LEASED AND VENDOR IS PICKING IT UP. PF |  |  |  | 2021-11-05 |  | 2021-11-08 | 2021-11-08 |  |  | 4 | 2021-11-11 | 2021-11-18 | 6 | Re-scrape | 2021-12-20 | 2021-12-29 | Approved | 2021-12-02 | 2021-12-10 | Soil Boring | [6 empty] | 2021-12-30 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-14 | 2022-01-14 | 2022-01-14 | Garrett Stuessy | (530) 274-1293 or (415-503-8859 | dreamtime2013@yahoo.com |  | "Debris Crew Leader/Crew# Kelvin Gray /#302 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 402" | 39.122 | -120.9883 | River Fire | DR-4601 | Residential |  | 2021-09-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
459 | 028-360-016 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 21044 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2035.02 |  |  |  |  | FALSE |  |  | N/A |  |  |  | TRUE | Bridge | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | POSITIVE | 2021-10-29 | 2021-10-29 | 6 | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE |  |  |  | Yes | 2022-01-18 | 2022-03-23 |  |  | TRUE | 2022-03-24 | 2021-11-11 | 2021-12-09 |  | 12.09 SPOKE WITH JULIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE DID NOT BURN. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2022-02-28 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Julie Mason and Peter Lee | (510) 278-1326 | jmdscendo@yahoo.com | Other Septic Vehicles Onsite Well |  | 39.1206 | -120.989 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
460 | 028-360-017 | Full Program ROE (debris + trees) | Re-scrape Needed | No Hazard Trees | Next Step: N/A | Soil Borings | NO ELIGIBLE TREES | 20935 | Post Chaise Circle |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2109.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 4 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-11 | Bio Monitoring Needed for Trees, not Debris | 2021-12-07 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | [8 empty] | FALSE | [8 empty] | TRUE | 2022-04-21 | 2021-12-11 | 2021-12-11 |  | 12.11 SPOKE WITH SCOTT HE SAID OK BUT PLEASE CALL IN ADVANCE HE WOULD LIKE TO BE THERE DURING THE DEBRIS REMOVAL. DO NOT REMOVE PROPANE TANK. JC 04/08/22 Spoke with Scott abt vehicles on property. He said to leave vehicles on site. jc |  |  |  | 2022-01-12 |  | 2022-01-12 | 2022-01-12 |  |  | 2 | 2022-01-13 | 2022-01-21 | 7 | Re-scrape | 2022-03-11 | 2022-03-21 | Re-scrape | 2022-03-01 | 2022-03-09 | Re-scrape | 2022-03-29 | 2022-04-06 | Soil Boring | 2022-03-29 | 2022-04-06 | Soil Boring |  | 2022-01-03 | No | 0 | [14 empty] | Scott Dickson | (925) 595-2369 | mtzscott@aol.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Cynthia Sanderson /#301 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 301 | 39.1196 | -120.9919 | River Fire | DR-4601 | Residential | No | 2021-11-30 | ROE Verified | Central Division | 2022-04-08T20:42:42Z | FALSE
461 | 028-360-019 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 21168 | Post Chaise Circle |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1897.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 |  |  | 3 | TRUE | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-28 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-10-28 | 2021-10-27 |  | 10.27 SPOKE TO MARCELLA AND SHE SAID OK PF 11.2 NO ANS LEFT MESS FOR TANK 11.3 VM left mess. JC 11.3 MARCELLA SAID THE LARGE TANK IS LEASED AND THE VENDOR IS HANDLING THAT... BUT THERE'S 3 SMALL TANKS PLEASE TAKE THEM. PF |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 5 | 2021-11-11 | 2021-11-18 | 6 | Approved | [12 empty] | 2021-11-22 | 2021-11-09 | Do Not Assess | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Marcella Althea Snead | (530) 913-1904 | tropicsme@hotmail.com | Keep Items Other Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Kelvin Gray/302 Debris Crew WO# Refer to IAP 11/24 To 12/01 Crew 301 | 39.118 | -120.9904 | River Fire | DR-4601 | Residential | Yes | 2021-09-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
462 | 028-370-004_21275 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 21275 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1829.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-20 | 2021-12-23 | NEGATIVE |  |  |  | 2021-12-11 | Bio Monitoring Needed for Debris AND Trees | 2021-12-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-08 | Active Nest | 75 |  | On Hold | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | 2021-12-21 | 2022-01-12 |  | 01/11/22 NO ANS VM FULL LEFT TEXT. JC 01/12/22 NO ANS VM FULL & EMAIL. JC 01/12/22 SPOKE WITH JOAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. HO WANTS TO BE ON PROPERTY DURING DEBRIS REMOVAL PROCESS. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-13 |  | 2022-01-17 | 2022-01-17 |  |  | 10 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-04 | Yes | 55 | 2022-04-05 | [6 empty] | 4 | [6 empty] | Joan Bega | (530) 346-8909 | joanbega87@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Cynthia Sanderson /#301 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 301 | 39.1168 | -120.9886 | River Fire | DR-4601 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-09T00:16:24Z | FALSE
463 | 028-370-004_21285 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 21285 | Clydesdale Road |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1829.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 1 |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-20 | 2021-12-23 | POSITIVE | 2022-01-06 |  | 10 | 2021-12-21 | Bio Monitoring Needed for Debris AND Trees | 2021-12-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | Nest Building Not Removed |  |  | On Hold | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-28 | 2022-01-06 | 2022-01-12 |  | 01/11/22 NO ANS VM FULL LEFT TEXT. JC 01/12/22 NO ANS VM FULL & EMAIL. JC 01/12/22 SPOKE WITH JOAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. HO WANTS TO BE ON PROPERTY DURING DEBRIS REMOVAL PROCESS. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-13 |  | 2022-01-17 | 2022-01-17 |  |  | 10 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-04 | Yes | 42 | 2022-04-05 | [13 empty] | Joan Bega | (530) 346-8909 | joanbega87@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Cynthia Sanderson /#301 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 301 | 39.1168 | -120.9886 | River Fire | DR-4601 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-07T00:12:51Z | FALSE
464 | 028-370-008 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 21411 | Oxnard Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1964.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Phase 1 Revisit | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 |  | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-28 | Bio Monitoring Needed for Trees, not Debris | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-11 | No |  | TRUE |  |  |  | FALSE | Water Crossing/Bridge Needed, WLPZ Zone | 2022-01-05 | For HTR, water crossings necessary; bio, and arch surveys or monitoring recommended | Yes |  |  |  |  | TRUE | 2022-04-20 | 2021-11-01 | 2021-11-09 |  | 11.8 NO ANS LEFT VM JC. 11.9 NO ANS LEFT VM JC. 11.9 SPOKE WITH CINDY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2021-12-22 | Yes | 106 | 2022-04-05 | [6 empty] | 78 | [6 empty] | Cindy Lou Gray | (530) 615-4842 OR (916) 862-7013 | cindygray332@gmail.com | Other Septic Well | Debris Crew Leader/Crew# Kelvin Gray /#302 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew302 | 39.1162 | -120.9932 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-08T18:10:32Z | FALSE
465 | 028-370-009 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 21525 | Oxnard Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2082.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | Yes | Yes | Yes | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 5 |  |  | 9 | TRUE | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-20 | 2021-11-17 | 2021-11-20 |  | 10.27 left homeowner a voicemail RCV 11.18 NO ANS. NO VM. SENT EMAIL .JC 11.19 NO ANS LEFT VM. JC 11.20 SPOKE WITH CAROLEE SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Re-scrape | 2022-02-15 | 2022-02-23 | Approved |  |  |  | 2022-02-25 | 2021-11-10 | Do Not Assess | 0 | [8 empty] | 2022-02-28 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Carolee Taylor | 530-615-4779 | peaceandbalance@live.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray /#302 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 302 | 39.1152 | -120.9946 | River Fire | DR-4601 | Residential | Yes | 2021-10-08 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
466 | 028-370-010 | Full Program ROE (debris + trees) | Re-scrape Needed |  | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 21602 | Oxnard Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 2099.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 5 | 0 | 8 |  |  | 8 |  | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-29 | 2021-10-29 | 7 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-20 | 2021-11-01 | 2021-11-04 |  | 11.3 NO ANS LEFT MESS. JC 11.4 NO ANS LEFT MESS. JC 11.4 SPOKE WITH LINDA. SHE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-20 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape | 2022-03-03 | 2022-03-11 | Re-scrape | 2022-01-20 | 2022-01-28 | Re-scrape | 2022-02-16 | 2022-02-24 | Soil Boring | 2022-03-18 | 2022-03-28 | Approved | 2022-03-30 | 2021-11-18 |  | 0 | [14 empty] | Ron and Linda Sager | Ron: (530) 613-4839 or Linda (530) 277-0497 | gophyr@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Kelvin Gray/#302 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 302 | 39.1145 | -120.9948 | River Fire | DR-4601 | Residential | Yes | 2021-09-15 | ROE Verified | Central Division | 2022-04-05T16:03:10Z | FALSE
467 | 028-450-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew Nevada 1 (3/15) | 15070 | Tecolode Trail |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1953.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | POSITIVE | 2021-12-20 |  | 4 | 2021-12-11 | No Bio Monitoring Needed for Debris or Trees | 2021-12-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-11 | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-04-01 | 2021-12-21 | 2021-12-23 |  | 12.23 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Re-scrape |  |  |  | 2022-03-01 | 2022-03-09 | Approved | [6 empty] | 2022-03-11 | 2022-01-03 | Yes | 103 | [14 empty] | Robert Hatcher | (206) 741-4636 | no email | Septic Well | Debris Crew Leader/Crew# Crystal Steverson / #301 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 301 | 39.1126 | -120.9844 | River Fire | DR-4601 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-07T22:10:18Z | FALSE
468 | 028-450-006 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 15410 | Las Encinitas Court |  | Grass Valley | Nevada |  | Residential | [5 empty] | 1920.47 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1801 |  |  | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-17 | Bio Monitoring Needed for Debris AND Trees | 2021-11-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-26 | 2021-11-18 | 2021-11-22 |  | 11.20 NO ANS LEFT VM. JC 11.22 SPOKE WITH TERRY BROWN HE SAID OK BUT PLEASE CALL IN ADVANC. PLEASE REMOVE PROPANE TANKS. JC 02/22/22 SPOKE WITH TERRY HE SAID Small propane tanks are already removed. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-10 | 5 | Approved | [12 empty] | 2021-12-13 | 2021-11-18 | Do Not Assess | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-14 | 2022-01-14 | 2022-01-14 | Terry M and Karen H Brown Living Trust | (530) 273-1208 | terryb@cfnmail.com | Septic Well | Debris Crew Leader/Crew# Kelvin Gray /#302 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 302 | 39.1138 | -120.9826 | River Fire | DR-4601 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
469 | 041-632-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4829 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3846.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-30 | 2021-11-02 | 2021-12-04 | 11.2 SPOKE TO FELICIA AND SHE SAID OK BUT PLEASE CALL IN ADVANCE. 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC. 12.4 SPOKE WITH FELICIA SHE SAID OK. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 FELICIA SHE IS HAVING TANK TESTING DO NOT REMOVE PROPANE TANK UNTIL SHE CALLS US BACK. JC |  |  |  | 2021-11-08 |  | 2021-11-09 | 2021-11-09 |  |  | 4 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-06 | Yes | 52 | 2022-01-03 |  | 2022-01-05 | 2022-01-05 |  | 2022-01-07 | 2022-01-07 | 52 | 2022-01-31 |  | 2022-01-15 | 2022-02-05 | 2022-02-05 | 2022-02-07 | Felicia Moffat | 805-434-7216 | soto2d@yahoo.com | Septic | "Debris Crew Leader/Crew# Adam Hutcheson/504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6392 | -120.5388 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
470 | 041-471-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7100 | Pinehaven Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3977.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris, not Trees | [5 empty] | Survey Needed | Yes | 2022-03-29 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-11-30 | 2021-12-03 | 2022-04-07 | 12.03 Contacted homeowner RCV 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 SPOKE WITH BRUCE HE SAID VENDOR HANDLING ﻿PROPANE TANK. JC 04/07/22 SPOKE WITH BRUCE HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-26 | Yes | 37 | [14 empty] | Bruce Henry | 925-447-1261 | buckeysix@comcast.net |  | Debris Crew Leader/Crew# Carondlet / #509 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 509 | 38.6451 | -120.5253 | Caldor | DR-4619 | Residential | No | 2021-11-19 | ROE Verified | Central Division | 2022-04-07T17:44:44Z | FALSE
471 | 041-471-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7116 | Pinehaven Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3981.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-04 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-22 |  | "12.21 NO ANS LEFT VM & TEXT. JC 12.22 NO ANS LEFT VM & EMAIL. JC 12.22 SPOKE WITH HO SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. TANK. JC 03/17/22 NO ANS LEFT VM & TEXT. JC 03/17/22 GAO C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 7 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-27 | Yes | 52 | 2022-04-04 |  | 2022-04-05 | 2022-04-05 |  | 2022-04-06 | 2022-04-07 | 52 |  |  | 2022-04-08 |  |  |  | Chen Biyong & Hongwen Gao | 510-703-8181 | hongwen587@yahoo.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 504 | 38.6446 | -120.5246 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-08T22:57:07Z | FALSE | 1
472 | 041-471-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6901 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-04 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 |  |  | 2022-01-22 | 01/20/22 NO ANS LEFT VM & TEXT. JC 01/21/22 NO ANS LEFT VM & EMAIL. JC 01/22/22 NO ANS LEFT VM. JC GAVE TO IMT. JC 01/22/22 per Melissa clear for tree removal. jc | 3 | State Planner: Melissa Perry | [25 empty] | 2021-12-03 | Yes | 97 | 2022-03-04 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-10 | 2022-03-21 | 97 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | Chen Biyong & Hongwen Gao | 510-703-8181 | hongwen587@yahoo.com |  |  | 38.6449 | -120.5243 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T23:26:48Z | FALSE | 3
473 | 041-471-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6921 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3967.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Trees, not Debris | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-14 | Yes | 2022-02-15 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 | 2021-11-10 | 2021-11-13 | 2022-02-21 | 11.12 NO ANS LEFT VM. JC 11.12 SPOKE WITH EDWINA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE LARGE TANK. PLEASE REMOVE SMALLER PROPANE TANKS. JC 02/21/22 SPOKE WITH EDWINA SHE SAID OK FOR TREE REMOVAL. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Re-scrape |  |  |  | 2021-12-04 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2022-03-02 | Yes | 57 | 2022-03-02 |  | 2022-03-03 | 2022-03-03 |  | 2022-03-10 | 2022-03-11 | 57 | 2022-03-24 |  | 2022-03-16 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Scott & Edwina Gressheim | 530-503-7932 | flyinghawaiian84@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 503 | 38.6456 | -120.5249 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
474 | 041-471-008 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6935 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3932.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | POSITIVE | 2021-10-21 | 2021-10-21 | 8 | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-10-21 | 2021-10-26 |  | 10.25.21 Spoke with Kevin, acknowledged debris removal start, would like to be on site to point out septic system, call 24 hours in advance RCV |  |  |  | 2021-10-28 |  | 2021-10-28 | 2021-10-28 |  |  | 7 | 2021-11-06 | 2021-11-12 | 5 | Approved | [12 empty] | 2021-11-16 | 2021-10-26 | No | 0 | [8 empty] | 2021-12-10 |  |  | 2021-12-11 | 2021-12-11 | 2021-12-13 | KEVIN & CONNIE FORBEY | 408-202-7740 | kforbey@gmail.com |  | Debris Crew Leader/Crew# Cindy Sanderson/#503 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 503 | 38.6464 | -120.5241 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
475 | 041-471-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6943 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3941.71 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-18 | 2021-11-19 | 2022-01-11 | 11.18 NO ANS LEFT VM. JC 11.19 SPOKE WITH JOHN HE SAID TO CALL NEPHEW MICHAEL. NO ANS LEFT VM. JC 11.19 ﻿SPOKE WITH NEPHEW MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE. JC 1.11 Homeowner okayed start of hazard tree removal RCV |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Approved | [12 empty] | 2021-12-14 | 2022-01-10 | Yes | 6 | 2022-01-12 |  | 2022-01-12 | 2022-01-12 |  | 2022-01-13 | 2022-01-14 | 6 | 2022-02-11 |  | 2022-02-04 | 2022-02-12 | 2022-02-12 | 2022-02-12 | John F Ambrosini SR. call Michael Ambrosini | 925-778-2869/ 925 202-9752 | impalagold59@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Rome/#502 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 502 | 38.6465 | -120.5236 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
476 | 041-471-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6955 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3964.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | POSITIVE | 2021-10-26 | 2021-10-26 | 11 | 2021-10-14 | Bio Monitoring Needed for Debris AND Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-26 | 2021-11-03 | 2022-01-18 | 11.03 Contacted Homeowner, acknowledged /debris removal RCV ﻿01/18/22 SPOKE WITH CHARLENE SHE SAID OK. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/25/22 CHARLENE C/B SHE SAID SHE DOES NOT HAVE A LARGE PROPANE TANK ON HER PROPERTY. JC 02/07/22 HO CONTACTED 800# WANTED TO KNOW STATUS OF TREE REMOVAL. TRIED CALLING, NO ANS LEFT VM & TEXT. JC 02/17/22 SPOKE WITH CHARLENE TO GIVE STATUS. JC 02/18﻿/22 spoke with Charlene to give updated status. JC |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 5 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape |  |  |  | 2021-11-23 | 2021-12-03 | Approved | [6 empty] | 2021-12-06 | 2021-11-01 | Yes | 1 | 2022-02-07 |  | 2022-02-07 | 2022-02-07 |  | 2022-02-08 | 2022-02-09 | 1 | 2022-02-18 |  | 2022-02-11 | 2022-02-19 | 2022-02-19 | 2022-02-19 | CHARLENE ANK | 530-306-8964 | CHARSPETS@SBCGLOBAL.NET |  | "Debris Crew Leader/Crew# Sarah Mundt﻿/501 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 501" | 38.6464 | -120.5229 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
477 | 041-471-011 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 6969 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3971.94 |  | 2021-11-18 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | Complete | N/A | [7 empty] | FALSE | [41 empty] | 2021-11-18 | No | 0 | [14 empty] | MARK & SUSAN ALMER | 530-559-3774 | SUSANANDMARKALMER@GMAIL.COM |  |  | 38.6464 | -120.5222 |  |  | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
478 | 041-471-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 6987 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3988.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Debris AND Trees | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No |  | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-15 | 2021-11-16 | 2022-03-25 | 11.16 SPOKE WITH VICTOR HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/07/22 VICTOR CALLED FOR STATUS. JC 03/25/22 VICTOR CALLED FOR STATUS. VICTOR PER APPROVED FOR TREE REMOVAL. HE SAID PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-18 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Soil Boring | 2022-01-17 | 2022-01-25 | Approved | [9 empty] | 2022-01-27 | 2021-12-01 | Yes | 12 | [14 empty] | Victor J. Diaz | 530-417-1377 | vicsafdizk@hotmail.com | Septic | Debris Crew Leader/Crew# Cynthia Sanderson /#503 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 503 | 38.6458 | -120.5214 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
479 | 041-471-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 6995 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3991.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-15 | 2022-01-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2022-01-21 | Yes | 2022-01-21 | 2022-01-26 | NEGATIVE |  |  |  | 2021-12-23 | No Bio Monitoring Needed for Debris or Trees | 2022-02-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-02-01 | 2022-02-03 |  | 02/02/22 NO ANS LEFT & TEXT. JC 02/03/22 NO ANS LEFT & EMAIL. JC 02/03/22 SPOKE WITH ASHLEY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 3.25 NO ANS LEFT MESS AND SENT TEXT PF |  |  |  | 2022-02-08 |  | 2022-02-09 | 2022-02-09 |  |  | 3 | 2022-02-11 | 2022-02-21 | 7 | Approved | [12 empty] | 2022-02-24 | 2022-03-05 | Yes | 27 | [14 empty] | Ryan Gripp and Ashley Morgan | 530 786-8609 | Tomboytaylor87@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha / #503 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 503 | 38.6454 | -120.5214 | Caldor | DR-4619 | Residential | No | 2021-12-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
480 | 041-471-015 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7003 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3988.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-08 | 2021-11-10 | 2022-01-20 | 11.9 NO ANS LEFT VM. JC 11.10 SPOKE WITH ANGELA SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT BURNED DO NOT REMOVE. JC 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-15 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape |  |  |  | 2021-12-04 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-11-02 | Yes | 45 | 2022-01-29 |  | 2022-02-02 | 2022-02-02 |  | 2022-02-03 | 2022-02-08 | 45 | 2022-02-18 |  | 2022-02-11 | 2022-02-19 | 2022-02-19 | 2022-02-19 | GREGORY & ANGELA DeARTE | 916-217-4975 | SOUTHERNDUO@ATT.NET |  | Debris Crew Leader/Crew# Cynthia Sanderson /#503 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 503 | 38.645 | -120.5215 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
481 | 041-471-016 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7011 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3992.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-13 | NEGATIVE |  |  |  | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-17 | 2022-01-20 | 2022-03-29 | 01/20/22 SPOKE WITH RAY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/15/22 NEW OWNER. Mario 808-397-4611 3.29 Spoke to Mario he said ok to proceed PF |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-02-04 | Yes | 28 | [14 empty] | Mario B. Butay | 925-687-4168/808-397-4611 | kimalizzy@aol.com |  | Debris Crew Leader/Crew# Carondlet Dunbar / #509 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 509 | 38.6448 | -120.5218 | Caldor | DR-4619 | Residential | Yes | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
482 | 041-471-018 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7106 | Quietwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3990.37 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 |  |  | 3 |  | Yes | Take | 2022-02-16 | 2021-11-22 | Yes | 2021-11-22 | 2021-11-26 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-03 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-11-30 | 2021-12-03 | 2022-03-07 | 12.03 SPOKE WITH VICKI SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLESE NOTE SHE IS WORKING OUT OF TOWN AND HER TIME IS 1 HOUR AHEAD. PLEASE REMOVE BOTH PROPANE TANKS. JC 03/04/22 NO ANS LEFT VM & TEXT JC 03/05/22 NO ANS LEFT VM & EMAIL. JC 03/07/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/07/22 SPOKE WITH ﻿VICKI SHE SAID OK FOR TREE REMOVAL AND CREW DO NOT NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 35 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-29 | Yes | 33 | [14 empty] | Vicki Inferrera | 707-364-3632 | performancesleds@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz /#510 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 510 | 38.6444 | -120.5226 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
483 | 041-471-020 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7120 | Quietwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3998.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-22 | Yes | 2021-11-22 | 2021-11-26 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-26 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-01 | 2021-12-03 | 2022-03-28 | 12.03 NO ANS LEFT VM. JC 12.03 SPOKE WITH MARK HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. HO TEXT BACK. HE SAID TAKE PROPANE TANK. JC `"`3.26 NO ANS. LEFT MESS- TEXT PF 3.28 SPOKE TO MARK AND HE SAID OK TO PROCEED PF" |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 33 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-03-28 | Yes | 31 | [14 empty] | Mark Rogers | 916-317-9401 | 123markrogers@gmail.com | Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz Jr /#510 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 510 | 38.6443 | -120.5216 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
484 | 041-471-022 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6981 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-04 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-08 | Bio Monitoring Needed for Trees, not Debris | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class II | Covered under suspension | FALSE | [12 empty] | 2022-01-22 | 12.04 NO ANS LEFT VM . JC 01/22/22 SPOKE WITH MARK HE SAID OK. JC | [27 empty] | 2021-12-01 | Yes | 3 | 2022-02-07 |  | 2022-02-07 | 2022-02-07 |  | 2022-02-08 | 2022-02-09 | 3 |  |  | 2022-02-11 |  | 2022-02-11 | 2022-02-11 | Mark & Susan Almer | 530-559-3774 | susanandmarkalmer@gmail.com |  |  | 38.6462 | -120.5212 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
485 | 041-940-010 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Ready for FSO | NO ELIGIBLE TREES | 5029 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3632.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-10-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-04-05 | 2021-10-07 | Yes | 2021-10-08 | 2021-11-01 | POSITIVE | 2021-11-08 | 2021-11-08 | 6 | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-14 | 2021-11-17 |  | 11.17 NO ANS LEFT VM. JC 11.17 SPOKE WITH CLIFFORD HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE THE PROPANE TANKS. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-16 | No | 0 | [8 empty] | 2022-04-05 | [5 empty] | COLETTE & CLIFFORD CASE | 408-234-3855 | CLIFF.CASE@GMAIL.COM |  | Debris Crew Leader/Crew# Tony Ruiz /#510 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 510 | 38.6384 | -120.5451 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T23:24:00Z | FALSE
486 | 041-734-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5356 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3725.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-14 | 2021-10-25 | 2021-12-04 | 10.25 Spoke with Kevin, acknowledged debris removal start, does not need to be on site RCV. 11.2 Spoke with Kevin, he contacted the vendor to remove the large tank. JC 12.4 SPOKE WITH KEVIN HE SAID OK. JC 01/29/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/10/22 VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 6 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2022-03-11 | Yes | 19 | 2022-01-08 |  | 2022-01-08 | 2022-01-08 |  | 2022-01-11 | 2022-01-14 | 19 | 2022-01-28 |  | 2022-01-17 | 2022-01-28 | 2022-01-28 | 2022-02-11 | KEVIN & REBECCA LEISHER | 916-990-4863 | leisherkp@sbcglobal.net |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 505 | 38.6288 | -120.5346 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
487 | 041-734-002 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5348 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3733.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-06 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 |  |  |  | TRUE |  |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 |  |  | 2022-01-26 | 01/26/22 NO ANS LEFT VM & TEXT. JC 01/26/22 HO GAVE CONSENT VIA TEXT. NO PROPANE TANK ON PROPERTY. JC | [27 empty] | 2021-11-01 | Yes | 44 | 2022-03-02 |  | 2022-03-03 | 2022-03-03 |  | 2022-03-10 | 2022-03-11 | 44 |  |  | 2022-03-14 |  | 2022-03-14 | 2022-03-14 | MICHELLE VENABLES | 530-417-2161 | m.venables@att.net |  |  | 38.629 | -120.535 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
488 | 041-734-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5414 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3758.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | Yes |  | 2022-01-26 | No | TRUE | No | No | No | No | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 5 |  |  | 4 | TRUE | No |  |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-13 | POSITIVE | 2022-01-19 | 2022-01-19 | 27 | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2022-01-26 | 2022-01-28 | 2022-03-01 | 12.15 NO ANS LEFT VM. JC 12.15 SPOKE WITH BRICE HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/28/22 SPOKE WITH BRICE HE SAID OK. NO PROPANE TANK ON PROPERTY. JC 03/01/22 SPOKE WITH BRICE HE SAID OK. JC |  |  |  | 2022-02-04 |  | 2022-02-04 | 2022-02-04 |  |  | 4 | 2022-02-09 | 2022-02-17 | 7 | Approved | [12 empty] | 2022-02-19 | 2021-11-01 | Yes | 18 | 2022-03-05 |  | 2022-03-05 | 2022-03-05 |  | 2022-03-11 | 2022-03-14 | 18 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | BRICE & MICHELLE VENABLES | 530-417-2164 | m.venables@att.net | Vehicles on site Septic | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 502 | 38.6292 | -120.5351 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
489 | 041-734-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5398 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3736.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2022-01-13 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | Yes | 2022-03-17 | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  |  | 2022-03-19 | 03/01/22 NO ANS NO VOICEMAIL SENT EMAIL. JC 03/02/22 NO ANS NO VOICEMAIL. SENT 2ND EMAIL. JC 03/02/22 SPOKE WITH ROBERT HE SAID OK FOR TREE REMOVAL. JC 3.19 3.19 Spoke to Robert he said ok PF | [27 empty] | 2021-12-04 | Yes | 36 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-29 | 2022-03-30 | 36 |  |  | 2022-04-04 |  | 2022-04-04 | 2022-04-04 | Robert Ericksen | 916-397-1899 | bobericksen@comcast.net |  |  | 38.6295 | -120.5343 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-04T18:17:52Z | FALSE | 4
490 | 041-734-007 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1b | 5380 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3728.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-20 | Bio Monitoring Needed for Debris AND Trees | 2021-12-04 | Arch Monitoring Needed for Trees, not Debris |  | 2022-04-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-28 | Yes | 2022-03-02 | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-12-07 | 2021-12-08 | 2022-03-21 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 SPOKE WITH KELLY SHE SAID OK BUT PLEASE CALL IN ADVANCE VENDOR HANDLED PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 3.21 SPOKE TO GREGORY AND HE SAID OK BUT CALL KELLY. 408-981-5712 PF 3.21 SPOKE TO KELLY AND SHE SAID OK PF |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-03-02 | Yes | 80 | 2022-04-01 | [6 empty] | 80 | [6 empty] | Kelly Yamanishi, Gregory Yamanishi | 408-858-2842 Greg 408-981-5712﻿ Kelly | kayamanishi@comcast.net | Septic | Debris Crew Leader/Crew# Carondlet Dundar / #509 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 509 | 38.6302 | -120.5341 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-08T18:14:22Z | FALSE
491 | 041-734-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5363 | Woodview Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3700.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 2 | 3 | 1 | 0 | 5 | 2 | 14 |  |  | 6 |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | POSITIVE | 2022-01-24 | 2022-01-24 | 31 | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-10 | Yes |  | FALSE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-24 | 2022-01-28 |  | "12.21 NO ANS LEFT VM & TEXT. JC 12.21 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/25/22 NO ANS LEFT VM & TEXT. JC 01/28/22 HO TEXT BACK CONSENT. SHE WILL CALL BACK TO LET US KNOW ABOUT PROPANE TANK. JC |  |  |  | 2022-02-01 |  | 2022-02-03 | 2022-02-03 |  |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Approved | [12 empty] | 2022-02-17 | 2022-02-07 | Yes | 24 | [14 empty] | Elizabeth & Robert Freitas | 916-952-7338 | lizfreitas@sbcglobal.net | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Herrison /#502 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 502 | 38.6299 | -120.5328 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-07T00:04:01Z | FALSE
492 | 041-734-013 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5359 | Wood View Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3751.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-26 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-11 | 2022-01-21 | 2022-03-24 | 12.14 SPOKE WITH JEFF HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/21/22 HO SAID OK. JC 3.24 NO ANS LEFT VM -CLOSED TIL 3.25 SENT TEXT PF 3.24 JEFF REPLIED BY TEXT (3.24 8:00 AM )SAYING WE HAVE HIS CONSENT |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Re-scrape |  |  |  | 2022-02-11 | 2022-02-21 | Approved | [6 empty] | 2022-02-24 | 2022-03-23 | Yes | 65 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-04-01 | 2022-04-02 | 65 |  |  | 2022-04-05 |  |  |  | CORNETT JEFF | 530-748-8337 | bluemountainrvrpr@sbcglobal.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 502 | 38.6304 | -120.5323 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T19:57:58Z | FALSE | 3
493 | 041-734-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5328 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3756.98 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2021-12-20 | 2021-12-20 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-12-23 | Yes | 2021-12-23 | 2021-12-29 | NEGATIVE |  |  |  | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-18 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-25 | Yes | 2022-04-06 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-18 | 2022-01-20 | 2022-04-07 | 01/19/22 NO ANS LEFT VM & TEXT. JC 01/20/22 NO ANS LEFT VM & EMAIL. JC 01/20/22 ROBERT C/B HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/23/22 NO ANS LEFT VM & TEXT. JC 03/23/22 HO GAVE CONSENT VIA TEXT. JC 04/01/22 ROBERT CALLED FOR STATUS. JC 04.07.22 SPOKE TO WIFE MIALE SHE SAID OK PF |  |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 | FALSE |  | 4 | 2022-01-29 | 2022-02-04 | 5 | Re-scrape | 2022-02-25 | 2022-03-07 | Re-scrape | 2022-02-10 | 2022-02-18 | Soil Boring | 2022-03-11 | 2022-03-21 | Approved |  |  |  | 2022-03-23 | 2022-01-14 | Yes | 55 | [14 empty] | CIULLO ROBERT | 530-903-7919 | tony.ciullo@yahoo.com |  | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 502 | 38.6308 | -120.5329 | Caldor | DR-4619 | Residential | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-08T18:39:18Z | FALSE
494 | 041-734-015 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5322 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3763.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-11 | 2022-01-21 | 2022-02-10 | 12.14 SPOKE WITH DEREK HE SAID OK BUT CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 01/21/22 SPOKE WITH DEREK HE SAID OK. JC 02/10/22 WIRELESS CUST NOT AVAILABLE AT THIS TIME. SENT TEXT. JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-07 | 6 | Approved | [12 empty] | 2022-02-09 | 2021-10-30 | Yes | 19 | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-16 | 2022-03-17 | 19 | 2022-03-23 |  | 2022-03-18 | 2022-03-24 | 2022-03-24 | 2022-03-24 | DEREK SHAVES | 530-391-5402 | shavesderek@gmail.com | Septic | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 502 | 38.6308 | -120.5324 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
495 | 041-740-018 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 1920 | Carolina Way |  | Somerset | El Dorado |  | Residential | [5 empty] | 3405.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | Yes | No | No | No | No | No | TRUE | TRUE | 19 | 1 | 0 | 0 | 7 | 3 | 3 | 33 |  |  | 12 |  | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-12-14 | POSITIVE | 2021-11-09 | 2021-11-09 | -24 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-02 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | [8 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | 2021-11-16 | 2022-01-24 |  | 11.17 NO ANS LEFT VM. JC 11.17 SPIKE WITH KEVIN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/24/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-02-18 |  | 2022-02-21 | 2022-02-21 |  |  | 8 | 2022-03-02 | 2022-03-10 | 7 | Approved | [12 empty] | 2022-03-11 | 2021-11-29 | No | 0 | [14 empty] | Kevin Jones | 408-667-2636 | donkevjulio@yahoo.com |  | Debris Crew Leader/Crew# Carla Herbit / #514 Debris Crew WO# Refer to IAP 02/19 to 02/23 Crew 6 | 38.6138 | -120.5839 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
496 | 041-740-020 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 041-740-020 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 3507.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-02 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-11 | 2022-01-21 | 2022-03-28 | 12.20 NO ANS LEFT VM & TEXT 12.20 SPOKE WITH LADONNA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO DAMAGE TO PROPANE DO NOT REMOVE. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC 03/28/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 03/28/22 LADONNA C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-03-02 |  | 2022-03-02 | 2022-03-02 |  |  | 2 | 2022-03-03 | 2022-03-11 | 7 | Approved | [12 empty] | 2022-03-15 | 2021-12-17 | Yes | 43 | [14 empty] | LaDonna & James Thompson | 707-799-7931 | ladonnathompson@yahoo.com |  | Debris Crew Leader/Crew# Carondlet Dunbar / #514 Debris Crew WO# Refer to IAP 03/02 to 03/05 Crew 514 | 38.6092 | -120.5868 | Caldor | DR-4619 | Residential | Yes | 2021-11-19 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
497 | 041-740-021 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 6441 | Caldor Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3355.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-21 | 2021-10-21 | FALSE | No |  |  | No |  | Yes | Yes | Yes | Yes | No | No | FALSE | TRUE | 8 | 1 | 1 | 3 | 0 | 0 | 0 | 13 |  |  | 22 |  | Yes | Take |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-21 | 2021-10-21 | 6 | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-02 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-02 | 2021-11-04 |  | 11.3 NO ANS LEFT MESS. JC 11.4 SPOKE WITH JOSEPH. HE SAID OK. PLEASE CALL IN ADVANCE. JC 01/28/22 PHONE NUMBER ON FILE NOT IN SERVICE. SENT EMAIL. JC 01/28/22 JOE EMAILED BACK. HE SAID TO REMOVE THE PROANE TANK. JC |  |  |  | 2021-11-06 |  | 2021-11-09 | 2021-11-09 |  |  | 4 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-12-07 | 2021-12-15 | Re-scrape | 2022-01-31 | 2022-02-08 | Approved |  |  |  | 2022-02-09 | 2021-11-29 | No | 0 | [14 empty] | JOSEPH WILDE | 903-495-5902 | joe.n.wilde@gmail.com |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 501 | 38.6141 | -120.5877 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
498 | 041-740-023 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | FSO Pending Vehicles | NO ELIGIBLE TREES | 7050 | Sheer Bliss Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3073.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | Arch Monitoring Needed for Debris, not Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-02-07 | 2022-02-07 |  | 02/07/22 SPOKE WITH KATHLEEN SHE SAID OK BUT PLEASE CALL IN ADVANCE BECAUSE THEY WILL HAVE TO OPEN GATE AND MOVE EXCAVATOR. VENDOR HANDLING PROPANE TANK. JC 03/16/22 KATHLEEN CALLED FOR STATUS |  |  |  | 2022-02-08 |  | 2022-02-10 | 2022-02-10 |  |  | 4 | 2022-02-15 | 2022-02-23 | 7 | Approved | [12 empty] | 2022-02-25 | 2021-12-17 | No | 0 | [8 empty] | 2022-03-30 | [5 empty] | William & Kathleen Vaden | 916-991-6869 , 916-806-1450 | kathleenvaden@comcast.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar / #505 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 505 | 38.616 | -120.597 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
499 | 041-740-026 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7104 | Sheer Bliss Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3172.25 |  | 2021-12-17 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2021-12-17 | No | 0 | [14 empty] | SLUTZ JONINE | 707-589-5026 | drslutz@msn.com |  |  | 38.612 | -120.5973 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
500 | 041-740-035 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7116 | Sheer Bliss Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3228.76 |  | 2021-12-17 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2021-12-17 | No | 0 | [14 empty] | Donald Slutz | 707-589-5026 | sdslutz@msn.com |  |  | 38.6111 | -120.5967 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
501 | 041-740-039 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Planning Hold | NO ELIGIBLE TREES | 7090 | Sheer Bliss Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3138.51 |  |  |  |  | TRUE | New Owner |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | Bio Monitoring Needed for Debris, not Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-01 | 2021-12-07 |  | 12.07 SPOKE WITH JOSH HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK BUT DO NOT REMOVE. JC 3.31.22 THIS PROPERTY HAS BEEN SOLD. NEW OWNER GLEN GILMORE 907-444-9128 NO ANS . LEFT MESS AND SENT TEXT PF |  |  |  | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-09 | 2022-02-17 | Approved | [6 empty] | 2022-02-19 | 2022-02-01 | No | 0 | [8 empty] | 2022-03-30 | [5 empty] | Josh Moran | 530-313-0814 | josh.p.moran24@gmail.com | Septic Vehicles on site | Debris Crew Leader/Crew# Carondlet Dunbar / #509 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 509 | 38.6135 | -120.5973 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
502 | 041-771-007 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5407 | Pine Ridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.06 |  | 2021-11-02 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-09 |  | FALSE |  |  |  | No |  | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2021-11-02 | No | 0 | [14 empty] | ALISON SHARKEY | 916-501-5832 | alison.sharkey.music@gmail.com |  |  | 38.6293 | -120.5524 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
503 | 041-771-008 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5417 | Pine Ridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3837.83 |  | 2021-11-02 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-09 |  | FALSE |  |  |  | No |  | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2021-11-02 | No | 0 | [14 empty] | ALISON SHARKEY | 916-501-5831 | alison.sharkey.music@gmail.com |  |  | 38.6292 | -120.5527 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
504 | 041-802-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5388 | Blue Mountain Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3898.74 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-28 | 2021-10-28 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-18 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-06 | 2021-11-08 | 2022-02-21 | 11.8 NO ANS LEFT VM. JC 11.8 SPOKE WITH RUSSELL HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR TO HANDLE PROPANE TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.04 RUSSELL SAID OK TO PROCEED VIA TEXT. JC 01/13/22 spoke with Russell. He said okay. JC 02/21/22 RUSSELL SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 1 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-04 | Yes | 13 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-04 | 2022-03-05 | 13 | 2022-03-10 |  | 2022-03-08 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Russell and Mary Tuttle | 916-997-1082 | russtuttle1@sbcglobal.net | Vehicles on site Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 505 | 38.6298 | -120.5479 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
505 | 041-803-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5391 | Blue Mountain Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3893.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 4 |  |  |  | TRUE | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-18 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-11 | 2021-12-11 | 2022-02-22 | 12.11 SPOKE WITH DANIEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE THE PROPANE TANK. JC 02/21/22 NO ANS LEFT VM & TEXT JC 02/22/22 SPOKE WITH DANIEL HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 7 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2021-12-02 | Yes | 4 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-04 | 2022-03-05 | 4 | 2022-03-10 |  | 2022-03-08 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Daniel Burnor | 916-834-5740 | burnoroutdoorservices@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison /#502 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 502 | 38.6294 | -120.548 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 3
506 | 041-803-011 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5415 | Blue Mountain Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3904.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-03 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-04 | 2022-01-14 | 11.4 SPOKE WITH OWNER, SAID OK. PLEASE CALL IN ADVANCE. JC 12.4 SPOKE TERRI SHE SAID OK. JC 01/14/22 NO ANS LEFT VM. JC 01/14/22 HO TERRIE CALLED BACK AND SHE SAID OK. JC |  |  |  | 2021-11-09 |  | 2021-11-09 | 2021-11-09 |  |  | 4 | 2021-11-12 | 2021-11-18 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-04 | No | 0 | [8 empty] | 2022-02-01 |  |  | 2022-02-05 | 2022-02-05 | 2022-02-07 | Terri Dollar-Mills | 925-876-7206 | tuppermom46@gmail.com |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/06/21-- to 11/10/21 -- Crew 505 | 38.6293 | -120.549 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
507 | 041-840-005 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4781 | Huggy Bear Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3839.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-11 | 2022-01-14 |  | 01/14/22 SPOKE CLINTON HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 6 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2021-12-01 | No | 0 | [8 empty] | 2022-02-10 |  |  | 2022-02-10 | 2022-02-10 | 2022-02-10 | Clinton S. Bowman Melissa D. Bowman | 209-483-3931 209-275-3764 | melissabowman09@outlook.com | Keep Items Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/19 To 01/22 Crew 502 | 38.625 | -120.5463 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
508 | 041-840-006 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-840-006 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3750.29 |  | 2022-01-21 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [41 empty] | 2022-01-21 | No | 0 | [14 empty] | Lawarence Watson & Ann Seymour | 916-765-5576 | larry.watson@comcast.net |  |  | 38.6229 | -120.5467 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
509 | 041-840-007 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-840-007 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3676.67 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [42 empty] | Do Not Assess | 0 | [14 empty] | Lawarence Watson & Ann Seymour | 916-765-5577 | larry.watson@comcast.net |  |  | 38.6199 | -120.5477 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
510 | 041-840-009 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4651 | Huggy Bear Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3891.47 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-04 | 2021-10-04 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-04 | Yes | 2021-10-06 | 2021-10-11 | POSITIVE | 2021-10-21 | 2021-10-21 | 9 | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-11-03 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-17 |  | 11.17 SPOKE WITH MARK HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape | 2022-02-07 | 2022-02-15 | Approved | 2022-01-24 | 2022-02-01 | Soil Boring | [6 empty] | 2022-02-16 | 2021-12-01 | No | 0 | [8 empty] | 2022-02-18 |  |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | MARK & VANESSA BOSTON | 916-807-0640 | MARK@GBRREALESTATE.COM |  | Debris Crew Leader/Crew# Crystal Egan/#508 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 508 | 38.6289 | -120.5447 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
511 | 041-850-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-850-001 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3869.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-04 | No | [6 empty] | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-01-27 | 01/27/22 NO ANS LEFT VM & TEXT. JC 01/27/22 JACOB C/B HE SAID OK. NO PROPANE TANK ON PROPERTY. JC | [27 empty] | 2022-01-21 | Yes | 19 | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  | 2022-02-08 | 2022-02-09 | 19 |  |  | 2022-02-11 |  | 2022-02-11 | 2022-02-12 | HOUT JACOB & PICKETT KERITH | 510-333-5806 | jake.hout@yahoo.com | Other |  | 38.6358 | -120.5289 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
512 | 041-850-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 10340 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 2 |  | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-20 | POSITIVE | 2021-10-26 | 2021-10-26 | 5 | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-19 | 2021-11-22 | 2022-02-28 | 11.22 NO ANS LEFT VM. JC 11.22 SPOKE FRANCIS HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE ﻿PROPANE TANK. JC 02/28/22 SPOKE WITH FRANCIS HE SAID OK. JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape |  |  |  | 2022-01-19 | 2022-01-27 | Re-scrape | 2022-02-08 | 2022-02-16 | Approved |  |  |  | 2022-02-17 | 2021-11-15 | Yes | 33 | 2022-03-23 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-29 | 2022-03-30 | 33 |  |  | 2022-03-31 |  |  |  | FRANCIS & MARIA SOUZA | 530-414-0515 | FSS@CATKYLA.COM |  | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 505 | 38.6357 | -120.5271 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
513 | 041-861-007 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 5325 | Blue Mountain Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3888.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-07 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  |  |  | FALSE | [58 empty] | james & Rebecca Wischnowski | 530-903-3169 | wish_now_ski@att.net |  |  | 38.6308 | -120.5458 | Caldor | DR-4619 | Residential | Yes | 2022-02-15 | ROE Verified | Central Division | 2022-04-08T21:57:05Z | FALSE
514 | 041-861-010 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4658 | Huggy Bear Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3875.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | TRUE | TRUE | 3 | 5 | 0 | 0 | 1 | 3 | 0 | 12 |  |  |  | TRUE | No |  |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-12-04 | 2021-12-06 |  | 12.06 SPOKE HO WITH SAID OK BUT PLEASE CALL WHEN CREW IS ON THE WAY. NO PROPANE TANK. JC |  |  | 2021-12-04 | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 34 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2021-12-01 | No | 0 | [8 empty] | 2022-02-10 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Johnathan Walker | 530-295-1113 | grizzlygirl5600@gmail.com | Vehicle on site Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#501 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 501 | 38.6292 | -120.5462 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
515 | 041-871-014 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5497 | Pine Ridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3844.75 |  | 2022-01-21 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [17 empty] | 2022-01-21 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [41 empty] | 2022-01-21 | No | 0 | [14 empty] | Thomas Wilson | 321-633-0161 | wilsontf2020@gmail.com |  |  | 38.6272 | -120.5554 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
516 | 041-882-024 | Full Program ROE (debris + trees) | Re-scrape Needed | No Hazard Trees | Next Step: N/A | ELD Grizzly Rescrapes | NO ELIGIBLE TREES | 5396 | Wildberry Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3710.19 |  |  |  |  | FALSE |  |  | N/A |  | TRUE |  | TRUE | Locked gate | No |  | TRUE | 2022-03-04 | 2022-03-04 | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 | [7 empty] | 2022-03-04 | Yes | 2022-03-04 | 2022-03-09 | NEGATIVE |  |  |  | 2022-03-04 | Bio Monitoring Needed for Trees, not Debris | 2022-03-02 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-11 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-14 | Yes | 2022-03-16 | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-03-09 | 2022-03-09 |  | Abatement Site - No contact Needed | 0 | Melissa Perry |  | 2022-03-17 |  | 2022-03-17 | 2022-03-17 |  |  | 2 | 2022-03-19 | 2022-03-25 | 5 | Soil Boring | 2022-03-29 | 2022-04-06 | Re-scrape | [10 empty] | 2022-03-16 | No | 0 | [18 empty] | Debris Crew Leader/Crew# Antonio Ruiz / #519 Debris Crew WO# Refer to IAP 03/16 to 03/19 Crew 519 | 38.6217 | -120.5536 | Caldor | DR-4619 | Residential |  | 2022-02-28 | Abatement | Central Division | 2022-04-08T15:00:15Z | FALSE
517 | 041-722-022 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5231 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3783.4 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | POSITIVE | 2021-12-11 | 2021-12-11 | 3 | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2021-12-10 |  | 12.10 NO ANS LEFT VM. JC 12.10 SPOKE WITH ROY HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 02/10/22 SPOKE WITH ROY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-25 |  | 2022-01-26 | 2022-01-26 |  |  | 4 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-05 | Yes | 42 | 2022-02-25 |  | 2022-02-25 | 2022-02-25 |  | 2022-03-01 | 2022-03-02 | 42 | 2022-03-11 |  | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Roy Barnes | 510-610-1006/ 510-366-9775 | rbarnes42@sbcglobal.net | Septic | Debris Crew Leader/Crew# Tami Collins / #501 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 501 | 38.6323 | -120.5326 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
518 | 041-722-023 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 041-722-023 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3787.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | POSITIVE | 2022-01-18 | 2022-01-18 | 26 | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | No | None | FALSE | [10 empty] | 2022-01-14 | 2022-01-21 | 2022-03-16 | 12.14 NO ANS LEFT VM & TEXT. JC 12.14 SPOKE WITH TIME HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC 03/15/22 FOLLOW UP CALL NO ANS LEFT VM. JC 03/16/22 SPOKE WITH TOM HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 |  |  | 4 | 2022-01-29 | 2022-02-07 | 6 | Approved | [12 empty] | 2022-02-09 | 2022-01-26 | Yes | 26 | [14 empty] | Tom Aragon | 916-539-1381 | tomaplastic@yahoo.com | Septic | Debris Crew Leader/Crew# Tami Collins / # 501 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 501 | 38.6324 | -120.533 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
519 | 041-722-024 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5206 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3787.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-12 | 2022-01-17 | 2022-03-04 | 12.20 NO ANS LEFT VM. JC 01/17/22 NO ANS LEFT VM & TEXT. JC 01/17/22 SPOKE WITH APRIL SHE SAID OK. PLEASE CALL IN ADVANCE. JC 03/04/22 SPOKE WITH APRIL SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-17 | Yes | 15 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-17 | 2022-03-18 | 15 | 2022-03-23 |  | 2022-03-19 | 2022-03-24 | 2022-03-24 | 2022-03-24 | John Perez & April Bacchi-agent | 813-335-7111 , 916-903-6626 | auto5880@yahoo.com, april.soldwithcare@gmail.com |  | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 515 | 38.6326 | -120.5327 | Caldor | DR-4619 | Residential | Yes | 2021-11-23 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
520 | 041-722-025 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5202 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3793.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 |  |  | 1 | TRUE | [11 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-12 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  |  |  | No | None | FALSE | [12 empty] | 2022-02-21 | 01/19/22 SPOKE WITH APRIL SHE SAID OK. JC 02/21/22 HO SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-15 | Yes | 21 | 2022-03-10 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-17 | 2022-03-18 | 21 |  |  | 2022-03-19 |  | 2022-03-19 | 2022-03-19 | John Perez & April Bacchi-agent | 813-335-7111 , 916-903-6626 | auto5880@yahoo.com, april.soldwithcare@gmail.com |  |  | 38.6328 | -120.5325 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
521 | 041-722-026 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5198 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3796.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-13 | 2022-01-13 | FALSE | Yes |  | 2022-01-26 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-12-23 | Yes | 2021-12-23 | 2021-12-29 | POSITIVE | 2022-01-18 | 2022-01-18 | 15 | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-18 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-02 | Yes | 2022-03-17 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-26 | 2022-01-28 | 2022-03-17 | 01/28/22 SENT TEXT. JC 01/28/22 HO GAVE CONSENT VIA TEXT. JC 03/17/22 SENT TEXT. JC 03/17/22 SANDRA GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-29 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-15 | Yes | 19 | [14 empty] | Sandra Gay Olvera | 209-403-4076(Text no hearing) | olverasg@att.net |  | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 501 | 38.633 | -120.5324 | Caldor | DR-4619 | Residential | No | 2021-12-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
522 | 041-723-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5207 | Leoni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3834.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2022-01-20 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 |  |  | 2022-02-21 | 02/21/22 SPOKE WITH MICHAEL SHE SAID OK. JC | [27 empty] | 2022-02-12 | Yes | 15 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-18 | 2022-03-19 | 15 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | April & Michael Sayer | 303-854-7865, 530-391-0650 | mike.w.sayer@gmail.com, april.ra.sayer@gmail.com | Vehicle on site |  | 38.6337 | -120.5312 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
523 | 041-724-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 5 | 5294 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3763.74 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-11 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-10 | 2022-01-18 | 2022-03-15 | 12.11 NO ANS LEFT VM & EMAIL. JC 12.11 SPOKE WITH KIM SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/18/22 SPOKE WITH KIM SHE SAID OK. JC 03/15/22 SPOKE WITH KIM SHE OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 5 | 2022-01-26 | 2022-02-03 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2022-02-02 | Yes | 28 | [14 empty] | Kim Gustafson | 408-674-2914 | Kimrieg@aol.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 01/19 To 01/22 Crew516 | 38.6317 | -120.5314 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-09T00:29:35Z | FALSE
524 | 041-724-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5260 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3811.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | POSITIVE | 2021-12-11 | 2021-12-11 | 2 | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2021-12-20 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Survey Needed | Yes | 2022-03-04 | No |  | TRUE | Operational |  |  | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-20 | 2022-01-21 |  | 12.21 NO ANS LEFT VM & TEXT. JC 12.22 NO ANS LEFT VM & EMAIL. JC 12.23 SPOKE WITH KATHLEEN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/21/22 SPOKE WITH KATHLEEN SHE SAID OK BUT STILL WANTS SOMEONE TO CALL HER IN ADVANCE. JC |  |  |  | 2022-01-26 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-01-29 | Yes | 15 | [14 empty] | Kathleen Melvin | 530-317-8514 | karonmel@att.net |  | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 502 | 38.633 | -120.5313 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-02T03:12:09Z | FALSE
525 | 041-731-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5287 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3808.25 |  |  |  |  | TRUE | New Owner |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | On Hold | Yes | 2022-03-21 | Yes | 2022-04-02 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2022-01-19 |  | 12.18 NO ANS LEFT VM & TEXT. JC 12.20 PHONE OUT OF SERVICE. JC 01/19/22 NO ANS LEFT VM TEXT & EMAIL. JC 01/19/22 DOUG C/B HE SAID OK. NO PROPANE TANK. JC 04/04/22 I spoke with Susan. She said the property was sold, and she will call me back tomorrow with the new owners contact information. JC 04/05/22 No ans left vm and text for new owners or realtor contact info. JC 04/06/22 HO c/b to provide us with Realtor information: Allison Vonrae 209 283-4010. JC |  |  |  | 2022-01-22 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-04-04 | Yes | 22 | [14 empty] | Douglas & Susan Woolley | 530-305-7301 | suecatburg@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Enedith Montiel / #501 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 501 | 38.631 | -120.5359 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-07T15:21:20Z | FALSE
526 | 041-731-002 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5293 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3802.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-11 | No | [6 empty] | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2022-01-20 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-16 | 02/16/22 Spoke with Scot he gave pre approval for 5293 Golden Aspen. said ok. RE CREW CALLS HIM. HE WANTS TO BE THERE DURNING REMOVAL. REMOVE PROPANE TANK. 3.16 Spoke to Scot he said ok PF | [27 empty] | 2022-01-17 | Yes | 27 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-03-31 | 2022-04-01 | 27 |  |  | 2022-04-02 |  | 2022-04-02 | 2022-04-04 | Scot Allison Campbell Kyle Myra Campbell | 510 385 4565 | scot@baypowerllc.com |  |  | 38.6307 | -120.5359 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-04T16:22:18Z | FALSE | 2
527 | 041-731-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5317 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3775.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 3 |  |  |  | TRUE |  |  |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 |  |  | 2022-02-16 | 02/16/22 SPOKE WITH SCOT HE SAID OK. DO NOT COME UNTIL OWNERS IS CALLED. NO PROPANE TANK . JC | [27 empty] | 2022-01-05 | Yes | 22 | 2022-03-02 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-08 | 2022-03-10 | 22 |  |  | 2022-03-11 |  | 2022-03-11 | 2022-03-14 | Scot Allison Campbell Kyle Myra Campbell | 510 385 4565 | scot@baypowerllc.com |  |  | 38.63 | -120.5359 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
528 | 041-731-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5323 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3772.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 2 | 0 | 3 | 1 | 2 | 1 | 10 |  |  | 6 | TRUE | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2022-01-19 | 2022-03-02 | 12.16 NO ANS LEFT VM & TEXT. JC 12.16 SPOKE WITH TIM HE SAID OK BUT PLEASE CAL LIN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/19/22 NO ANS LEFT VM & TEXT. JC 01/19/22 TIM C/B SAID OK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 SPOKE WITH TIM HE SAID OK. JC |  |  |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 |  |  | 6 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-04 | Yes | 33 | 2022-03-05 |  | 2022-03-05 | 2022-03-05 |  | 2022-03-11 | 2022-03-14 | 33 | 2022-03-17 |  | 2022-03-16 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Tim & Heather Padgett | 916-768-5498, 916-715-6787 | datp2000@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Enedith Montiel / #501 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 501 | 38.6297 | -120.5359 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
529 | 041-731-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5309 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3792.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 0 | 2 | 1 | 2 | 1 | 0 | 1 | 7 |  |  |  | TRUE | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 |  |  |  | Complete | Yes | 2022-02-17 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-11 | 2021-12-16 | 2022-02-26 | 12.16 SPOKE WITH SCOT HE SAID OK BUT PLEASE CALL IN ADVANCE BECAUSE HE WANTS BE ON ONSITE DURING DEBRIS REMOVAL. VENDOR WILL HANDLE PROPANE TANK. JC 02/26/22 SPOKE WITH SCOTT HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2021-10-27 | Yes | 33 | 2022-03-01 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-07 | 2022-03-08 | 33 | 2022-03-11 |  | 2022-03-10 | 2022-03-17 | 2022-03-17 | 2022-03-17 | Scot Allison Campbell Kyle Myra Campbell | 5103854565 | scot@baypowerllc.com |  | Debris Crew Leader/Crew# Brandon Riley/ #501 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 501 | 38.6304 | -120.5359 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 5
530 | 041-732-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5300 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791.79 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-11 | 2022-01-21 | 2022-03-05 | 12.14 NO ANS NO VM SENT TEXT. JC 12.14 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE BECAUSE HE DO NOT WANT WOOD STOVE REMOVED. VENDOR HANDLING PROPANE TANK. JC 01/21/22 NO ANS VOICEMAIL FULL SENT TEXT. JC 01/21/22 SPOKE WITH JOHN HE SAID OK BUT HAVE CREW LEADER CALL HIM. JC "03/04/22 NO ANS LEFT VM & TEXT JC 03/05/22 NO ANS LEFT VM & EMAIL. JC 03/05/22 JOHN C/B HE SAID OK FOR TREE REMOVAL. JC" |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-17 | Yes | 21 | 2022-03-25 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-31 | 2022-04-01 | 21 |  |  | 2022-04-02 |  |  |  | PAPER JOHN | 530-295-7808 | cpaper@comcast |  | Debris Crew Leader/Crew# Enedith Montiel / #501 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 601 | 38.6305 | -120.5352 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-02T20:27:02Z | FALSE | 3
531 | 041-732-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5308 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3788.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-06 | 2021-11-08 | 2022-01-20 | 11.8 SPOKE WITH RICK HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT. PROPANE TANK. JC 01/20/22 SPOKE WITH RICK HE SAID OK. JC |  |  |  | 2021-11-15 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-02 | Yes | 22 | 2022-03-02 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-09 | 2022-03-10 | 22 | 2022-03-23 |  | 2022-03-11 | 2022-03-24 | 2022-03-24 | 2022-03-24 | RICK & MELINDA FROST-HURZEL | 530-503-5411 | rhurzel@saber.net | Vehicles on site Septic | Debris Crew Leader/Crew# Crystal Egan/#508 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 508 | 38.6302 | -120.5353 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
532 | 041-491-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6763 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4019.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-07 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-04 | 2021-11-05 | 2022-03-09 | 11.5 SPOKE BARBARA SHE SAID OK. PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/10/22 SPOKE WIT BARBARA SHE SAID OK TO TREE REMOVAL. JC 03/09/22 SPOKE WITH BARBARA TO UPDATE ON TREE REMOVAL. SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-10 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2021-11-03 | Yes | 23 | 2022-03-23 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-26 | 2022-03-28 | 23 | 2022-04-05 |  | 2022-03-30 | 2022-04-08 | 2022-04-08 | 2022-04-08 | WILLIAM & BARBARA BROWN | 530-717-0558 | thebusybs45@gmail.com | Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 503 | 38.6403 | -120.5257 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T21:16:16Z | FALSE | 2
533 | 041-492-002 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6786 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4019.37 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-02-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-02-15 | 02/10/22 TRIED CALLING BUT PHONE HAS CALLING RESTRICTIONS. SENT TEXT. JC 02/11/22 CALL RESTRICTION TO RECEIVE CALLS. SENT EMAIL. JC 02/12/22VSENT 2ND EMAIL JC 02/14/22 phone still has restrictions sent to IMT. JC | 4 | State Planner: Melissa Perry | [25 empty] | 2021-12-06 | Yes | 6 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-08 | 2022-03-09 | 6 |  |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | JAMES & BARBARA KELLY | 916-206-3477 | jkelly@surewest.net |  |  | 38.6413 | -120.5253 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
534 | 042-378-060 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16461 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1380.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 3 | TRUE | No |  |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [10 empty] | 2021-12-01 | 2021-12-03 | 2021-12-16 | 12.03.2021 SPOKE WITH LOLA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC 12.16 SPOKE WITH LOLA SHE DOES NOT WANT ANYMORE OF HER TREES REMOVED. JC |  |  |  | 2021-12-16 |  | 2021-12-17 | 2021-12-17 |  |  | 2 | 2021-12-20 | 2021-12-29 | 7 | Approved | [12 empty] | 2022-01-04 | 2021-12-16 | Yes | 4 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 |  | 2021-12-28 | 2021-12-28 | 4 | 2022-02-03 |  | 2021-12-29 | 2022-02-16 | 2022-02-16 | 2022-02-17 | Gordon/Lola Dennler | (707) 533-6241 | dennlerlola@gmail.com | Keep Items Vehicles Onsite | Debris Crew Leader/Crew# Crystal Eqan / #202 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 202 | 38.9252 | -122.6044 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
535 | 042-378-140 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16471 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 6 | 5 | 0 | 2 | 3 | 7 | 0 | 23 |  |  | 12 | TRUE | No |  |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-10-26 | 2021-10-26 | 5 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-23 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [10 empty] | 2021-10-26 | 2021-10-25 | 2021-12-16 | 10.25 SPOKE TO LOLA AND SHE SAID OK PLEASE CALL IN ADVANCE. 12.16 SPOKE WITH LOLA SHE DOES NOT WANT ANYMORE OF HER TREES REMOVED. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 7 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape | 2022-01-07 | 2022-01-17 | Approved | 2021-11-29 | 2021-12-07 | Re-scrape | 2021-12-17 | 2021-12-28 | Soil Boring |  |  |  | 2022-01-18 | 2021-11-10 | Yes | 5 | 2021-12-17 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-21 | 2021-12-21 | 5 | 2022-02-03 |  | 2021-12-29 | 2022-02-02 | 2022-02-02 | 2022-02-07 | Lola Dennler | (707) 533-6241 | dennlerlola@gmail.com | Septic | "Debris Crew Leader/Crew# Birdie Bell /#201 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 201" | 38.9253 | -122.6041 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
536 | 077-184-002 | Tree Only ROE (no qualifying debris) | Withdrawn | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5737 | Sugar Bush Circle |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3511.8 | 2022-02-25 |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2022-02-02 | No | 0 | [14 empty] | Karl Reichmuth | 916-824-9946 | kmreich1@icloud.com | Septic |  | 38.7053 | -120.6013 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
537 | 079-210-024 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5340 | Overland Way |  | Placerville | El Dorado |  | Residential | [5 empty] | 3199.11 |  | 2022-01-22 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-09 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [41 empty] | 2022-01-22 | No | 0 | [14 empty] | Joy & Mark Henderson | 530-663-3676 | joy.henderson@edcgov.us |  |  | 38.6894 | -120.6079 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
538 | 079-210-042 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5431 | Overland Way |  | Placerville | El Dorado |  | Residential | [5 empty] | 2946.53 |  | 2022-01-22 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | [7 empty] | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2022-01-22 | No | 0 | [14 empty] | Erin Evans | 530-644-2428 | erine6169@gmail.com | Septic Vehicles Onsite |  | 38.6864 | -120.6049 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
539 | 079-220-029 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5236 | Merritt Lane |  | Placerville | El Dorado |  | Residential | [5 empty] | 3327.26 |  | 2022-01-22 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-08 | No | [6 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2022-01-22 | No | 0 | [14 empty] | KEVIN GARDEPIE | 831-238-7447 | kgardepie@gmail.com |  |  | 38.6908 | -120.6053 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
540 | 041-485-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7123 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3 |  |  | 4 | TRUE | Yes | Take | 2022-02-17 | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-12-01 | 2021-12-03 |  | 12.03 NO ANS LEFT VM. JC 12.03 Sent Text, Homeowner okayed debris removal start RCV 01/26/22 SPOKE WITH KRYSTAL SHE SAID PLEASE REMOVE PROPANE TANK ONLY IF IT IS DAMAGED. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-30 | Yes | 11 | 2022-01-15 |  | 2022-01-19 | 2022-01-19 |  | 2022-01-21 | 2022-01-22 | 11 | 2022-01-28 |  | 2022-01-25 | 2022-01-29 | 2022-01-29 | 2022-02-17 | Krystal Burgess | 916-952-9913 | kandystar02@aol.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Christie Richter/#503 Debris Crew WO# Refer to IAP 12/01 to 12/08 Crew 503 | 38.6419 | -120.5229 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
541 | 041-051-004 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-051-004 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3609.4 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-08 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [42 empty] | Do Not Assess | 0 | [14 empty] | Lou Heimrich | 916-870-9171 | louisheimrich@gmail.com |  |  | 38.6064 | -120.5554 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
542 | 041-051-041 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 041-051-041 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3657.94 |  |  |  |  | FALSE |  |  | N/A |  |  |  | FALSE |  | Yes |  | TRUE | 2022-01-25 | 2022-01-25 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2022-01-25 | Yes | 2022-01-25 | 2022-01-28 | POSITIVE | 2022-02-14 | 2022-02-14 | 12 | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2022-02-19 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-29 | Yes |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-19 | 2022-02-19 | 2022-02-21 |  | 01/31/22 NO ANS AND NO VM SENT TEXT ABT TREES BLOCKING DIRT ROAD ONTO PROPERTY. JC 01/31/22 SPOKE WITH MR. HAMMOND. He said he did not authorize any trees to be cut down on his property. He want to put a hold on account until he contacts county to find out who cut down the trees on his property. JC 02/21/22 SPOKE WITH MR. HAMMOND. HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2022-03-02 |  | 2022-03-02 | 2022-03-02 |  |  | 3 | 2022-03-04 | 2022-03-14 | 7 | Approved | [12 empty] | 2022-03-15 | 2022-03-28 | Yes | 137 | [14 empty] | Louis Hammond | 510-579-6112 | wadehammond@yahoo.com |  | Debris Crew Leader/Crew# Carondlet Dunbar / #514 Debris Crew WO# Refer to IAP 03/02 to 03/05 Crew 514 | 38.6038 | -120.556 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
543 | 041-632-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 4855 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3859.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-28 | 2022-01-28 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2022-01-27 | Yes | 2022-01-27 |  | NEGATIVE |  |  |  | 2022-01-28 | No Bio Monitoring Needed for Debris or Trees | 2022-02-02 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | No |  | No |  | TRUE |  |  |  | FALSE | [10 empty] | 2022-02-02 | 2022-02-02 |  | 02/02/22 SPOKE WITH KENT HE SAID OK. BUT PLEASE CALL IN ADVANCE. HE WILL CHECK TO SEE IF PROPANE TANK IS LEASED. JC |  |  |  | 2022-02-09 |  | 2022-02-09 | 2022-02-09 |  |  | 3 | 2022-02-11 | 2022-02-21 | 7 | Approved | [12 empty] | 2022-02-24 | 2022-04-05 | Yes | 19 | [14 empty] | Fannie Mae, Kent Sutton | 916-317-7275 | kentsuttonre@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 02/05 to 02/12 Crew 502 | 38.6401 | -120.5393 | Caldor | DR-4619 | Residential | No | 2022-01-25 | ROE Verified | Central Division | 2022-04-08T21:57:05Z | FALSE
544 | 041-632-005 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1b | 4895 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3862.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-03 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-03 | 2021-12-06 | 2022-03-31 | 12.06 SPOKE WITH CAROL SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 3.31 SPOKE TO CAROL SHE SAID OK. PF |  |  |  | 2021-12-08 |  | 2021-12-10 | 2021-12-10 |  |  | 27 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-01-25 | Yes | 31 | 2022-04-07 |  | 2022-04-07 | 2022-04-07 |  |  |  | 20 | [6 empty] | Daniel Phillip Aguirre Carol Louise Potter | 530-383-2611 | Carolsquiltstudio@sbcglobal.net | Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#501 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 501 | 38.6403 | -120.5399 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-09T00:04:01Z | FALSE
545 | 041-632-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4913 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3862.89 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-23 | 2021-11-18 | 2022-01-20 | 11.17 NO ANS LEFT VM. JC 11.18 SPOKE WITH CAROL SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING LARGE PROPANE TANK PLEASE REMOVE SMALLER TANK. JC 01/20/22 SPOKE WITH CAROL SHE SAID OK. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2021-11-08 | Yes | 4 | 2022-01-22 |  | 2022-01-22 | 2022-01-22 |  | 2022-01-24 | 2022-01-25 | 4 | 2022-02-01 |  | 2022-01-26 | 2022-02-03 | 2022-02-03 | 2022-02-03 | Carol Azzarito | 916-502-0334 | cazzarito@sbcglobal.net |  | "Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 12/01 To 12/04 Crew 504 | 38.6399 | -120.5397 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
546 | 041-632-007 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4927 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3839 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | Yes |  | 2021-12-10 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-10 | 2021-12-11 | 2022-03-05 | 12.11 NO ANS LEFT MAILBOX FULL SENT TEXT & EMAIL. JC 12.11 HO GAVE CONSENT VIA TEXT. JC 03/04/22 NO ANS LEFT & TEXT. JC 03/05/22 Spoke with Rebecca she said ok for tree removal. jc |  |  |  | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  |  | 6 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-26 | Yes | 23 | 2022-03-23 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-25 | 2022-03-26 | 23 |  |  | 2022-03-29 |  |  |  | Rebecca & Michael Gruber | 530-306-8038 | rebecca4927g@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison /#502 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 502 | 38.6395 | -120.5396 | Caldor | DR-4619 | Residential | Yes | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
547 | 041-632-008 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Ready for Tree Felling | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 4937 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3847.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-01 | 2022-03-01 | FALSE | No |  |  | Yes |  | No | Yes | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-02 | Yes | 2022-03-02 | 2022-03-07 | NEGATIVE |  |  |  | 2022-03-01 | No Bio Monitoring Needed for Debris or Trees | 2022-03-01 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-29 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-04-21 | 2022-03-07 | 2022-03-08 |  | Abatement Site - No contact Needed | 0 | Melissa Perry |  | 2022-03-09 |  | 2022-03-10 | 2022-03-10 |  |  | 2 | 2022-03-11 | 2022-03-21 | 7 | Re-scrape |  |  |  | 2022-03-31 | 2022-04-08 | [8 empty] | 2022-03-08 | Yes | 39 | [18 empty] | Debris Crew Leader/Crew# Fernando Montealegre / #519 Debris Crew WO# Refer to IAP 03/09 to 03/12 Crew 519 | 38.6391 | -120.5395 | Caldor | DR-4619 | Residential |  | 2022-02-28 | Abatement | Central Division | 2022-04-09T00:03:09Z | FALSE
548 | 041-641-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4970 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3889.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 |  | FALSE | No |  |  | No |  | No | No | No | No | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-05 | No | [6 empty] | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 |  |  | 2022-01-11 | 12.4 NO ANS LEFT VM. JC 1.11 Homeowner ﻿acknowledged start of hazard tree removal RCV | [27 empty] | 2021-11-08 | Yes | 28 | 2022-01-13 |  | 2022-01-13 | 2022-01-13 |  | 2022-01-14 | 2022-01-20 | 28 |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 | SEAN AND CORTNEY LLORET | 916-271-2786 | CHIVA1804@GMAIL.COM | Keep items Safety concerns |  | 38.6376 | -120.5401 | Caldor | DR-4619 | Residential | Yes | 2021-10-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
549 | 041-482-018 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 7054 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3991.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-13 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-14 | Yes | 2022-03-15 | TRUE |  | Class III | Covered under suspension | TRUE | [12 empty] | 2022-03-19 | 02/01/22 SPOKE WITH SHERRON SHE GAVE PRE APPROVAL. . NO PROPANE TANKS ON PROPERTY. JC "3.19 NO ANS. LEFT MESS PF SENT TEXT. 3.19 SHERRON C/B AND SAID OK PF" | [27 empty] | 2021-12-06 | Yes | 7 | [14 empty] | Sherron Burleson Patricia Girvin | 530-417-7728 | burlesonsherron@yahoo.com |  |  | 38.644 | -120.5236 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
550 | 041-484-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7134 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4029.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-06 | 2021-10-06 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | POSITIVE | 2021-10-23 | 2021-10-23 | 4 | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-23 | 2021-11-05 | 2022-01-20 | 11.3 NO ANS LEFT MESS. JC 11.4 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC 11.5 SPOKE WITH OWNERS. SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL TAKE CARE OF TANK. JC 12.4 SPOKE WITH DEBRA SHE SAID OK. JC 01/20/22 SPOKE WITH DEBRA SHE SAID OK. JC |  |  |  | 2021-11-09 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-04 | Yes | 25 | 2022-02-10 |  | 2022-02-11 | 2022-02-11 |  | 2022-02-16 | 2022-02-17 | 25 | 2022-02-21 |  | 2022-02-18 | 2022-02-28 | 2022-02-28 | 2022-02-28 | ERNIE & DEBRA CUMBRA | 916-799-4870 | dcumbra@yahoo.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 506 | 38.6428 | -120.5215 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 5
551 | 041-485-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7121 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4005.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 5 |  |  | 7 | TRUE | Yes | Take | 2022-03-07 | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-11-23 | 2021-11-24 | 2022-02-22 | 11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SEND EMAIL JC 11.24 SPOKE WITH CHAD HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK BUT DOES NOT KNOW IF BURNED. HE WANTS REMOVED IF DESTROYED BY FIRE. JC 02/22/22 NO ANS LEFT VM & TEXT. JC 02/22/22 SPOKE WITH CHAD HE OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-18 | Yes | 17 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-22 | 2022-03-23 | 17 | 2022-03-25 |  | 2022-03-24 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Chad & Amberly Seccombe | 530-919-6055 | chadseccombe1992@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 505 | 38.6422 | -120.5221 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
552 | 041-485-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7115 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4003.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2022-01-18 | Yes | 2022-01-18 | 2022-01-21 | NEGATIVE |  |  |  | 2022-03-09 | Bio Monitoring Needed for Debris AND Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2022-01-21 | 2022-01-21 | 2022-03-08 | 01/21/22 SPOKE WITH PAVEL HE SAID OK. PLEASE REMOVE PROPANE TANK IF DAMAGED. JC 03/08/2022 - Contacted owner - good to go - MP |  |  |  | 2022-01-29 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-10 | Yes | 34 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-18 | 2022-03-21 | 34 | 2022-03-25 |  | 2022-03-22 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Pavel Kasyanchuk | 916-826-9860 | Pavel.jpbdesigns@gmail.com |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #509 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 509 | 38.6422 | -120.5225 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
553 | 041-513-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4944 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3998.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2022-01-18 | Yes | 2022-01-18 | 2022-01-21 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | On Hold | Yes | 2022-03-29 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-21 | 2022-01-22 | 2022-03-31 | 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 SPOKE WITH WILLIAM HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE ALL TANKS. JC 03/31/22 SPOKE WITH WILLIAM HE SAID OF FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-04 | 2022-02-04 |  |  | 4 | 2022-02-09 | 2022-02-17 | 7 | Approved | [12 empty] | 2022-02-19 | 2021-12-04 | Yes | 12 | [14 empty] | William Haddock | 916-342-4047 | wgatley@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha/ #503 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 503 | 38.641 | -120.5201 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
554 | 041-514-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7195 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4043.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-10-22 | 2021-11-01 | 2022-01-28 | 11.1 SPOKE TO MARSHALL AND HE SAID OK BUT PLEASE CALL BEFORE COMING OUT . PF 11.2 SPOKE TO MARSHALL SAID HE OWNS THE TANK . IF IT'S BURNED TAKE IT, IF NOT PLEASE LEAVE IT. PF 01/28/22 SPOKE WITH MARSHALL HE SAID OK. JC |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 4 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Re-scrape | 2022-01-17 | 2022-01-25 | Approved |  |  |  | 2022-01-27 | 2021-11-11 | Yes | 28 | 2022-02-03 |  | 2022-02-08 | 2022-02-08 |  | 2022-02-08 | 2022-02-11 | 28 | 2022-02-18 |  | 2022-02-14 | 2022-03-08 | 2022-03-08 | 2022-03-08 | MARSHALL STONE | 530-919-7843 | stonicus@att.net |  | "Debris Crew Leader/Crew# Max Patterson﻿/506 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 506" | 38.642 | -120.5189 | Caldor | DR-4619 | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
555 | 041-514-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7207 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4042.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-05 | 2021-11-18 | 2022-01-31 | 11.18 NO ANS LEFT VM .JC 11.18 SPOKE WITH TIMOTHY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE. JC 01/28/22 PHONE NUMBER NO LONGER IN SERVICE SENT EMAIL. JC 01/31/22 PHONE NUMBER IS BACK IN SERVICE. SPOKE WITH TIMOTHY. HE SAID OK. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 5 | 2021-12-03 | 2021-12-10 | 6 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-11-09 | Yes | 15 | 2022-02-02 |  | 2022-02-08 | 2022-02-08 |  | 2022-02-08 | 2022-02-11 | 15 | 2022-02-18 |  | 2022-02-14 | 2022-02-19 | 2022-02-19 | 2022-02-19 | Timothy C Rios | 925-436-8826 | timothycrios@yahoo.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 506 | 38.6422 | -120.5185 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
556 | 041-514-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7223 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4023.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Take | 2022-02-16 | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-11-23 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-23 | 2021-11-29 | 2022-02-10 | 11.22 NO ANS LEFET VM JC 11.24 UNABLE TO LEAVE MESS, PHONE BUSY. SENT EMAIL JC 11.29 SPOKE WITH TRAVIS SAID OK BUT PLEASE CALL IN ADVANCE. OWNS PROPANE TANK PLEASE REMOVE. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-12-02 | Yes | 12 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-19 | 2022-02-21 | 12 | 2022-03-09 |  | 2022-02-26 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Travis Myers | 530-798-1250 | travis13myers@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz /#510 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 510 | 38.6425 | -120.5179 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
557 | 041-522-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4958 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3975.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave | 2022-02-18 | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | Bio Monitoring Needed for Debris, not Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-10-16 | 2021-10-26 | 2022-01-26 | 10.26 SPOKE TO MR O'BYRON HE SAID OK PF 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.10 SPOKE WITH JAMES HE GAVE PRE APPROVAL FOR TREE REMOVAL. JC 01/25/22 NO ANS LEFT VM & TEXT. JC 01/26/22 ﻿HO GAVE CONSENT VIA TEXT. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-01 |  | 2021-11-03 | 2021-11-03 |  |  | 7 | 2021-11-11 | 2021-11-18 | 6 | Approved | [12 empty] | 2021-11-20 | 2021-11-13 | Yes | 23 | 2022-02-07 |  | 2022-02-08 | 2022-02-08 |  | 2022-02-12 | 2022-02-14 | 23 | 2022-02-18 |  | 2022-02-15 | 2022-02-19 | 2022-02-19 | 2022-02-19 | JAMES & MARCELA O'BRYON | 916-717-9044 | bigbluehunter@protonmail.com |  | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 503 | 38.6405 | -120.5217 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
558 | 041-522-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4962 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-18 | 2021-11-19 | 2022-03-07 | 11.19 NO ANS LEFT VM. JC 11.19 SPOKE WITH RAY HE SAID OK BUT PLEASE CALL IN ADVANCE. NO TANK. JC 02/21/22 SPOKE WITH RAY HE SAID HE HOLD ON TREE REMOVAL UNTIL HE SPEAKS WITH COUNTY ABOUT KEEPING THE CEDAR TREES. JC 03/02/22 Spoke with HO. Raymond ok to move forward but leave cedar trees after cutting them down and take all the others away. JC 03/07/22 HO cleared to proceed. per Melissa Perry JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 3 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-12-03 | Yes | 10 | [14 empty] | NUTTING RAYMOND & JENNIFER | 530-644-1728 | nuttingranch@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to 11/24 IAP 12/01 Crew 507 | 38.6403 | -120.5214 | Caldor | DR-4619 | Residential | Yes | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
559 | 041-523-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7184 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3916.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2022-03-02 | Bio Monitoring Needed for Trees, not Debris | 2021-11-22 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  |  |  | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-22 | 2021-11-24 |  | 11.23 NO ANS LEFT VM . JC 11.24 NO ANS LEFT VM. SENT EMAIL. JC 11.24 SPOKE WITH DANIEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC "02/10/11 NO ANS LEFT VM & TEXT. JC 02/10/11 SPOKE WITH DANIEL HE SAID OK. JC 3.16 Spoke to Daniel and he said ok PF" |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 5 | 2021-12-07 | 2021-12-15 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2021-11-05 | Yes | 39 | [14 empty] | DANIEL & CHERYL CUEVA | 707-999-0668 | DANIELCUEVA399@GMAIL.COM |  | Debris Crew Leader/Crew# Glenn Adams/#501 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 501 | 38.6396 | -120.5223 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
560 | 041-523-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 5001 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3871.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-02-03 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | N/A | Yes | 2022-03-14 | Yes |  | FALSE |  | Class II | Covered under suspension | TRUE | [12 empty] | 2022-02-11 | 02/11/22 NO ANS LEFT VM & TEXT. JC 02/11/22 GERARDO C/B HE SAID OK TO TREE REMOVAL. NO PROPANE TANKS ON PROPERTY. JC | [27 empty] | 2021-12-06 | Yes | 12 | [14 empty] | GERARDO LOPEZ-MAZARIEGOS | 916-833-2237 | gerardo.110@yahoo.com |  |  | 38.639 | -120.5224 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
561 | 041-523-009 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 7197 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3877.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-04 | No | [6 empty] | 2021-12-02 | Bio Monitoring Needed for Trees, not Debris | 2022-02-01 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-02 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-17 |  |  | 2022-03-30 | "02/10/22 NO ANS LEFT VM & TEXT JC 02/11/22 NO ANS LEFT VM AND EMAIL. JC 02/11/22 GERARDO C/B HE SAID OK TO TREE REMOVAL NO PROPANE ON PROPERTY. JC 03/25/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/26/22 GERARDO WANTS TO SPEAK WITH COUNTY REP BEFORE GIVING CONSENT. JC 03/30/22 NO ANS LEFT VM & SENT EMAIL. JC 03/30/22 SPOKE WITH GERARDO HE SAID HE WILL CALL BACK TODAY AFTER SPEAKING WITH COUNTY REP. JC 03/30/22 GERARDO C/B HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-04 | Yes | 17 | [14 empty] | GERARDO LOPEZ-MAZARIEGOS | 916-833-2236 | gerardo.110@yahoo.com |  |  | 38.6391 | -120.522 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
562 | 041-523-010 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7203 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3880.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2022-01-17 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2022-01-17 | 2022-01-18 | 2022-02-16 | 01/18/22 NO ANS LEFT VM & TEXT. JC 01/18/22 SPOKE WITH ROBIN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/16/22 SPOKE WITH ROBIN SHE SAID OK TO TREE REMOVAL. JC |  |  |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-04 | Yes | 15 | 2022-03-31 |  | 2022-03-31 | 2022-03-31 |  | 2022-04-02 | 2022-04-04 | 15 |  |  | 2022-04-05 |  |  |  | FECKNER BRIAN & DUNNE ROBIN | 530-391-4235 | robinrae22@yahoo.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 504 | 38.6389 | -120.5216 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-06T16:00:34Z | FALSE | 2
563 | 041-523-014 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 7235 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3870.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-11 |  |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-02-15 | ""02/10/22 SPOKE WITH MAUREEN SHE SAID OK. VENDOR WILL HANDLE PROPANE. JC 3.15 No Ans. left mess PF 3.15 Spoke to Maureen and she said ok PF" | [27 empty] | 2022-01-15 | Yes | 11 | [14 empty] | Maureen Flores | 530-957-8768 | moefrancesflores@gmail.com |  |  | 38.6387 | -120.5201 | Caldor | DR-4619 | Residential | No | 2021-11-02 | ROE Verified | Central Division | 2022-04-07T20:41:11Z | FALSE
564 | 041-531-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7281 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3934.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-11 | POSITIVE | 2021-11-16 | 2021-11-16 | 4 | 2021-11-11 | Bio Monitoring Needed for Trees, not Debris | 2022-02-02 | No Arch Monitoring Needed for Debris or Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-03-01 | TRUE |  | No | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-18 | 2021-11-19 | 2022-03-03 | 11.16 NO ANS LEFT VM JC 11.16 SPOKE WITH DIANA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 02/01/22 NO ANS LEFT TEXT AND VM ABT SCHEDULING APPOINTMENT FOR TEAM SURVEYING. JC 02/01/22 HO TEXT BACK THAT DOGS ARE REMOVED AND CREW CAN GO WHENEVER THEY ARE READY. JC 02/12/22 LEFT VM TO SCHEDULE TIME FOR TEAM TO COME OUT TO PROPERTY. JC 02/14/22 HO SAID WED. THE 16TH IS A GOOD TIME TO COME TO PROPERTY. THEY PUT THE DOGS AWAY. JC 02/23/22 HO CALLED TO SEE IF CREW VISTED THE PROPERTY FOR ASSESSMENT. SENT EMAIL TO MELISSA. JC 02/26/22 Notified HO that crew will be there on March 1st between 11am-3pm. Homeowner said ok. jc 03/03/22 NO ANS LEFT VM & TEXT. JC 03/03/22 HO GAVE CONSENT VIA TEXT. JC 3.05 CALLED NO ANS. LEFT MESS ABOUT THE PERSON LIVING ON THE PARCEL WHERE TREES NEED TO FELL. LEFT A DETAIL MESS REQUESTED A C/B PF 3.19@6:37 Diana c/b and said the person living on her parcel has moved off. PF 03/25/22 follow-up No Ans. left vm & text. JC 03/25/22 DIANA SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-11-12 | Yes | 23 | [14 empty] | Diana & James Roark | 510-685-0897 | roarkjd@netscape.net | Septic | Debris Crew Leader/Crew# Sara Mundt /#501 Debris Crew WO# Refer to IAP 11/20 to 11/24Crew 501 | 38.6403 | -120.5185 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
565 | 041-531-013 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7309 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3925.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 7 |  |  | 5 |  | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Debris AND Trees | 2021-11-15 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No |  |  |  | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-16 | 2021-11-17 | 2022-03-17 | 11.17 NO ANS LEFT VM. JC 11.17 HOMEOWNER CALL BACK AND SAID OK. PF 01/25/22 SPOKE WITH KELLY VENDOR WILL HANDLE PROPANE TANK. JC 02/10/11 SPOKE WITH KELLY SHE SAID OK. JC 3.17.22 Spoke to Kelly and she said ok PF |  |  |  | 2021-11-19 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2022-02-19 | Yes | 56 | [14 empty] | Kelly Disalvi | 530-391-7743 | kellydisalvi@icloud.com | Septic Vehicles on site | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 501 | 38.6405 | -120.517 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
566 | 099-100-075 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 26715 | Highway 174 |  | Colfax | Placer |  | Residential | [5 empty] | 1985 |  | 2021-11-12 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A |  | TRUE | 2141 | TRUE | Bridge | No |  | TRUE | 2021-10-19 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-18 | No | [6 empty] | 2021-10-28 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-30 | [31 empty] | 2021-11-12 | No | 0 | [14 empty] | Susette Ghilotti | (530) 346-2528, (530) 575-0166 | Sueg@colfaxnet.com | Other Septic Vehicles Onsite |  | 39.1276 | -120.9631 | River | DR-4610 | Residential | Yes | 2021-10-01 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
567 | 099-120-022 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1441 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2324.8 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | Yes |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 5 |  |  | 4 | TRUE | No |  |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 |  | 2021-11-18 |  | 11.17 NO ANS LEFT VM. 2ND PH# NOT WORKING. JC 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC GAVE TO RICHARD. 11.18 Homeowner contact made by Marcelo Benedicto. Accepted start of debris removal |  |  |  | 2021-11-20 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Approved | [6 empty] | 2022-01-27 | 2021-11-16 | No | 0 | [8 empty] | 2022-02-15 |  |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | Michael Nelson | (916) 956-5038, (530) 346-2301 | Nelson1@hughes.net | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP -11/24- to -12/01-- Crew 403 | 39.1205 | -120.9646 | River | DR-4610 | Residential | Yes | 2021-11-04 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
568 | 099-120-024 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1695 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2372.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |  |  |  | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-30 | 2021-11-01 |  | 11.1 Contacted Homeowner, confirmed debris removal start RCV |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 4 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Re-scrape | 2022-01-15 | 2022-01-21 | Approved |  |  |  | 2022-01-26 | 2021-11-12 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-16 | 2022-02-16 | 2022-02-16 | Daren Allbee, Oliva Allbee | (916) 662-3914 | ddallbee@gmail.com | Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Melanie Poole﻿/403 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 403" | 39.1178 | -120.9663 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
569 | 099-120-026 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1630 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2322.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 4 |  |  | 3 | TRUE | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | POSITIVE | 2021-11-04 | 2021-11-04 | 11 | 2021-10-28 | Bio Monitoring Needed for Trees, not Debris | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-18 | 2021-11-20 |  | 11.18 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.20 NO ANS LEFT VM & SENT EMAIL JC GAVE TO RCV |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Approved | [12 empty] | 2021-12-07 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-23 | Christine Marie Taylor Brown | (530) 368-1167 | Taylorbrownmft@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 403 | 39.1168 | -120.9674 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
570 | 099-120-027 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1530 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2308.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | Yes | No | No | Yes | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-09 | 2021-11-10 |  | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH DAIVD HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-13 |  | 2021-11-16 | 2021-11-16 |  |  | 3 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | David Dosen, Rona Dosen | (916) 316-3372 | dmdosen@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 403 | 39.1182 | -120.9676 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
571 | 099-120-028 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1466 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2200.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-27 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-27 | 2021-11-01 |  | 11.1 SPOKE TO DANIEL HAYES AND HE SAID OK PF |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 5 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-19 | 2021-12-11 | No | 0 | [8 empty] | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Daniel Hayes, Jessica Fratis | (916) 425-0097, (916) 871-5927 | None | Septic Well | "Debris Crew Leader/Crew# Melanie Pole/403 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 403" | 39.1197 | -120.9673 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
572 | 099-120-029 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1448 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2167.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Debris, not Trees | 2021-10-27 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-27 | 2021-11-01 |  | 11.1 SPOKE TO GEORGANN AND SHE SAID OK ALREADY WAS CALLED BY MARCELLO BENDITO. PF 11.2 SPOKE TO GEORGANN SHE WILL CALL VENDOR TO REMIND THEM TO P/U PROPANE TANK. PF |  |  |  | 2021-11-05 |  | 2021-11-08 | 2021-11-08 |  |  | 3 | 2021-11-10 | 2021-11-18 | 7 | Soil Boring | 2021-12-02 | 2021-12-10 | Approved | [9 empty] | 2021-12-13 | 2021-11-11 | No | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-23 | Georgann C. Chiozza, Allen Stutrud | (530) 210-6891, (530) 210-9599, (530) 346-8308 | leroy@stutrud.com | Keep Items Well | "Debris Crew Leader/Crew# Melanie Poole /#403 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 403" | 39.1206 | -120.9668 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
573 | 099-120-030 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1370 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2128.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-20 | POSITIVE | 2021-11-04 | 2021-11-04 | 12 | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-09 | 2021-11-10 |  | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH OWNER. SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK DID NOT BURN. PF |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Arthur Huber | (530) 613-3449 | meli_costa@yahoo.com | Septic | Debris Crew Leader/Crew# Dominic Uncango /#403 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 403 | 39.1215 | -120.9667 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
574 | 099-120-051 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1325 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2273.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-02 |  | 11.02 Contacted homeowner, acknowledged start of debris removal. wants to be on site to document RCV 11.3 called abt tank. Phone busy signal. JC 11.4 LEFT MESS ABT TANK. JC 12.03.21 left vm in reply to email dated 12.02.21. jc 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/27/22 Gave status to Elizabeth. She said vendor handled propane tank. JC |  |  |  | 2021-11-08 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Re-scrape | 2022-01-15 | 2022-01-21 | Approved |  |  |  | 2022-01-26 | 2021-11-22 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-21 | James Porter, Elizabeth Porter | (925) 383-9915 | lizz@morethanthursdays.com | Septic Well | Debris Crew Leader/Crew# Melanie Poole/#403 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 403 | 39.1215 | -120.9641 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
575 | 099-120-060 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1410 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2061.83 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Debris AND Trees | 2021-10-30 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-30 | 2021-11-01 |  | "11.1 NO ANS. LEFT MESS PF 11.1 SPOKE TO DONALD HE SAID OK AND CALL FIRST PLEASE PF" 11.2 Spoke w/Donald. He contacted vendor to remove tank. JC |  |  |  | 2021-11-10 |  | 2021-11-12 | 2021-11-12 |  |  | 4 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-01 | 2021-12-09 | Approved | [6 empty] | 2021-12-10 | 2021-11-22 | No | 0 | [8 empty] | 2022-01-12 |  |  | 2022-01-15 | 2022-01-15 | 2022-01-15 | Donald Axton, Cheryl Axton | (530) 388-0246 | djaxton@gmail.com | Keep Items Septic Well | Debris Crew Leader/Crew# Doming Uncangco/#401 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 401 | 39.1192 | -120.9706 | River | DR-4610 | Residential | No | 2021-10-06 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
576 | 099-120-063 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1395 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 1990.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-20 | POSITIVE | 2021-11-04 | 2021-11-04 | 12 | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-04 | 2021-11-04 |  | 11.3 SPOKE WITH LOUISE. SHE SAID OK. PLEASE CALL IN ADVANCE. SHE CONTACTED THE VENDOR ABT TANK. JC |  |  |  | 2021-11-08 |  | 2021-11-10 | 2021-11-10 |  |  | 2 | 2021-11-11 | 2021-11-18 | 6 | Re-scrape | 2022-02-02 | 2022-02-10 | Approved | 2021-12-01 | 2021-12-09 | Soil Boring | 2022-01-15 | 2022-01-21 | Soil Boring |  |  |  | 2022-02-11 | 2021-11-22 | No | 0 | [8 empty] | 2022-02-16 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Louise Loose | (530) 615-9426 | louise.a.loose@gmail.com | Septic Well | Debris Crew Leader/Crew# Dominic Uncango/#401 Debris Crew WO# Refer to IAP 11/10/2021 to 11/13/2021 Crew 401 | 39.1179 | -120.9717 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
577 | 099-120-064 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1400 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2201.17 |  | 2021-11-10 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 4 |  |  |  |  | Yes |  |  | 2021-10-12 | No | [6 empty] | 2021-10-19 | Bio Monitoring Needed for Debris, not Trees | 2021-10-30 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | [31 empty] | 2021-11-22 | No | 0 | [14 empty] | Amy Bazzoaroni | (530) 450-5251 | bazzarac@sutterhealth.org | Keep Items Septic Vehicles Onsite |  | 39.1175 | -120.9691 | River | DR-4610 | Residential | Yes | 2021-10-06 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
578 | 099-120-066 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1040 | Gladycon Road |  | Colfax | Placer |  | Residential | [5 empty] | 2372.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-05 | POSITIVE | 2021-11-10 | 2021-11-10 | 4 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-10 | 2021-11-11 |  | 11.11 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 |  |  | 4 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-17 | No | 0 | [8 empty] | 2022-01-14 |  |  | 2022-01-15 | 2022-01-15 | 2022-01-15 | Michael Sinor | (530)906-6527 | michael.sinor@gmail.com | Septic | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP -11/13/2021- to -11/17/2021- Crew 403 | 39.1184 | -120.9633 | River | DR-4610 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
579 | 099-120-068 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1480 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2119.08 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Debris, not Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-01 |  | "11.1 NO ANS. LEFT MESS PF 11.1 SPOKE TO DONALD HE SAID OK AND CALL FIRST PLEASE PF" 11.2 Spoke to Donald. He called the vendor to remove tank. JC |  |  |  | 2021-11-20 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Donald Axton, Cheryl Axton | (530) 388-0246 | djaxton@gmail.com | Septic Well | Debris Crew Leader/Crew# Dominic Uncongco /#401 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 401 | 39.1207 | -120.9684 | River | DR-4610 | Residential | No | 2021-10-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
580 | 099-120-070 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1440 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2092.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 2 | TRUE | No |  |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Debris AND Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-01 |  | "11.1 NO ANS LEFT MESS PF 11.2 Spoke w/Alan. He will like to have the tank removed. JC 11.1 SPOKE TO ALAN AND HE SAID OK BUT PLEASE CALL HE HAS A '57 CAR HE DOESN'T WANT TAKEN BECAUSE THE INSURANCE CO IS GOING TO PICK UP. PF 11.2 Spoke w/Alan. He will like to have the tank removed. JC" |  |  |  | 2021-11-17 |  | 2021-11-19 | 2021-11-19 |  |  | 3 | 2021-11-23 | 2021-12-03 | 7 | Re-scrape |  |  |  | 2022-01-15 | 2022-01-21 | Approved | [6 empty] | 2022-01-26 | 2021-11-22 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | Alan Shuttleworth, Dale Shuttleworth | (530) 277-3962, (530) 277-0478 | bigalcolfax@yahoo.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Dominic Uncangco/#401 Debris Crew WO# Refer to IAP 11/17 to 11/19 Crew 401 | 39.1193 | -120.9691 | River | DR-4610 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
581 | 100-010-017 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 100-010-017 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2049.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | Yes | No | Yes | Yes | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 3 |  |  | 2 | TRUE | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-11 | Bio Monitoring Needed for Trees, not Debris | 2021-12-11 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | On Hold | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-12-11 | 2021-12-10 |  | 12.09 NO ANS LEFT VM. JC 12.10 SPOKE WITH DAVID HE SAID OK. CAREGIVER ON PROPERTY WHO CAN DIRECT CREW LEADER. VENDOR HANDLING PROPANE. JC |  |  |  | 2022-01-12 |  | 2022-01-14 | 2022-01-14 |  |  | 6 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-03 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | Wayne Kaplan-Colman, Davis Mustelier | (916) 203-9379, (510) 551-8165 | mustelier@gmail.com, waynec@oregonveteranshome.com | Keep Items Other Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams /#403 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 403 | 39.0901 | -120.9815 | River | DR-4610 | Residential | No | 2021-10-19 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
582 | 100-030-001 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1490/1494 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2291.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-22 | POSITIVE | 2021-11-05 | 2021-11-05 | 11 | 2021-10-28 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-05 | 2021-11-06 |  | 11.6 SPOKE WITH JOSHUA, ﻿HE SAID OK. PLEASE CALL IN ADVANCE. THE VENDOR REMOVED THE PROPANE TANK. JC |  |  |  | 2021-11-08 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-12-02 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-11-12 | No | 0 | [8 empty] | 2021-12-20 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Anna Dehennis, Joshua Sanguinetti, Joden Sanguinetti | (916) 206-3635 | sangoconstruction@gmail.com | Septic | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 401 | 39.1088 | -120.9738 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
583 | 100-030-007 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1330 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2210.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | Yes |  | 2021-11-02 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 5 |  |  |  | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-21 | POSITIVE | 2021-11-01 | 2021-11-01 | 8 | 2021-10-18 | No Bio Monitoring Needed for Debris or Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-01 | 2021-11-06 |  | 11.5 NO ANS LEFT VM. JC 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH JAMES HE SAID OK. VENDOR HANDLED PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 |  |  | 2 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-12-03 | No | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | James Katches, Renee Katches | (530) 320-5855, (530) 320-3854 | katchman88@yahoo.com, rkatches@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Dominic Ungonco/#401 Debris Crew WO# Refer to IAP -11/13/2021- to -11/17/2021- Crew 401 | 39.1151 | -120.9704 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
584 | 100-030-008 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 25425 | Pineview Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2286.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | Yes | Yes | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 |  |  |  | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-03 |  | 11.3 PHONE IS OUT OF ORDER OR DISCONNECTED. PF 11.03﻿ Homeowner acknowledged debris removal start RCV |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 3 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-12-03 | No | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Raymond Asher | (916) 284-5075 | asherace@yahoo.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Dominic Unconco/#401 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 401 | 39.1151 | -120.9689 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
585 | 100-030-009 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 25405 | Pineview Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2316.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | Yes | No | Yes | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-11-01 | 2021-11-01 | 9 | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-01 | 2021-11-05 |  | 11.3 NO ANS LEFT MESS. JC 11.5 NO ANS LEFT VM. JC 11.5 SPOKE WITH RONALD HE SAID OK. PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-12-02 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-11-12 | No | 0 | [8 empty] | 2021-12-21 |  |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | Ronald Pucci, Lynelle Pucci | (530) 346-2314, (530) 320-7824 | rpucci44@gmail.com | Septic | Debris Crew Leader/Crew# Dominic Uncango/#401 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 401 | 39.1145 | -120.9686 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
586 | 100-030-010 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1270 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2214.47 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-12 | Bio Monitoring Needed for Debris AND Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-16 | 2021-11-17 |  | 11.17 NO ANS MAILBOX FULL. SENT EMAIL. JC 11.17 SPOKE WITH LISA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC |  |  |  | 2021-11-19 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Lisa Stager | (530) 334-3944 | lisastager@gmail.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 11/17 to 11/19 Crew 403 | 39.1142 | -120.9697 | River | DR-4610 | Residential | No | 2021-11-03 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
587 | 100-030-013 | Full Program ROE (debris + trees) | Withdrawn |  | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1240/1250 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2292.16 | 2021-11-23 |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | [48 empty] | Molly Pruyn, John Pruyn | (510) 303-9393, (510) 812-0754 | mollypruyn@comcast.net, mrclever59@gmail.com | Septic Vehicles Onsite |  | 39.1137 | -120.9689 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
588 | 100-030-014 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1270 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2156.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | No | No | Yes | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-19 | 2021-10-28 |  | "10.27 NO ANS LEFT MESS PF 10.28 NO ANS LEFT MESS. PF 10.28 SPOKE TO EDGAR AND HE SAID OK PF. PLEASE CALL IN ADVANCE. PF" 11.2 Left Mess on tank removal. JC 11.3 VM left mess abt tank. JC 11.4 VM LEFT MESS ABT TANK. JC |  |  |  | 2021-11-05 |  | 2021-11-06 | 2021-11-06 |  |  | 3 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-20 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Edgar Easton, Sharon Easton | (530) 320-6293, (530) 320-9002 | e_easton@outlook.com, s_easton@outlook.com | Septic Vehicles Onsite | "Debris Crew Leader/Crew# Dominic Uncango /#401 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 401" | 39.113 | -120.9701 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
589 | 100-030-018 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1345 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2173.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-11-22 | 2021-11-22 |  | 11.17 SPOKE WITH FRANKLIN HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK IS NOT BURNED DO NOT REMOVE. JC |  |  |  | 2021-11-30 |  | 2021-12-02 | 2021-12-02 |  |  | 5 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2021-11-16 | No | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-14 | 2022-01-14 | 2022-01-14 | Franklin Robinson, Dinah Robinson | (916) 764-9544 | fdrobin3@yahoo.com | Septic | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 403 | 39.1153 | -120.9714 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
590 | 100-030-019 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1313 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2163.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Undamaged |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-18 | No Bio Monitoring Needed for Debris or Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-18 | 2021-10-28 |  | "10.27 NO ANS LEFT MESS PF 10.28 Left voicemail RCV 10.28 SPOKE TO ALISON AND SHE SAID OK. PLS CALL FIRST. PF" 11.2 ALLISON SAID PLEASE TAKE ﻿PROPANE TANK. PF 02/22/22 SPOKE WITH ALLISON SHE SAID SHE WILL SEND EMAIL REQUEST TO HAVE PROPANE TANK REMOVED. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 6 | 2021-11-09 | 2021-11-17 | 7 | Approved | [12 empty] | 2021-11-19 | 2021-11-12 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Kenneth Brison, Alison Brison | (530) 272-5360, (775) 741-2426 | alison@colfaxnet.com | Septic Well | Debris Crew Leader/Crew# Doming Uncangco /401 Debris Crew WO# Refer to IAP 10/30 to 11/3 Crew 401 | 39.1145 | -120.9714 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
591 | 093-021-007 | Full Program ROE (debris + trees) | Pending Soil Sample Results | No Hazard Trees | Next Step: N/A | Pending Soil Sampling Results | NO ELIGIBLE TREES | 5361 | Butte Creek Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 2494.98 |  |  |  |  | FALSE |  |  | N/A |  |  |  | FALSE |  | Yes |  | TRUE | 2022-02-14 | 2022-02-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2022-02-14 | Yes | 2022-02-14 | 2022-03-07 | NEGATIVE |  |  |  | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2022-01-10 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-02 | No Activity/Nest Building Removed | [11 empty] | FALSE | Water Crossing/Bridge Needed |  |  | Yes | 2022-03-25 |  |  |  | TRUE | 2022-04-13 | 2022-03-25 | 2022-04-02 |  | 03/28/22 NO ANS MAILBOX FULL SENT TEXT. JC 3.29 NO ANS. MAILBOX FULL SENT TEXT- NO EMAIL ON FILE. PF 4.2 Spoke to Donald He said ok and he wants to be there when they do the debris removal.PF |  |  |  | 2022-04-04 |  | 2022-04-05 | 2022-04-05 |  |  | 2 | 2022-04-06 |  | 3 | [14 empty] | 2021-12-17 | No | 0 | [14 empty] | Donald Balthaser | 530-663-3249 (Old#) (530) 391-6518 New # |  | Septic Well |  | 38.6618 | -120.6189 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
592 | 093-021-013 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Not Eligible for Haz Tree Removal | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 5350 | Butte Creek Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 2225.17 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Key under rock next to pole with address on it | FALSE |  | Yes |  | TRUE | 2022-02-14 | 2022-02-14 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 0 | 1 | 1 | 0 | 6 |  |  |  |  | Yes |  |  | 2022-02-14 | Yes | 2022-02-14 | 2022-03-25 | POSITIVE | 2022-02-25 | 2022-02-25 | -21 | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-07 | Active Nest | 75 | [10 empty] | FALSE | Water Crossing/Bridge Needed |  |  | Yes | 2022-03-25 |  |  |  | TRUE | 2022-04-13 | 2022-03-25 | 2022-03-28 | 2022-04-01 | 03/28/22 NO ANS LEFT VM & TEXT. JC 03/28/22 Diana c/b she said ok for debris removal. BUT PLEASE CALL ﻿BOTH EDWARD @ 916 439-0752 & DIANA @ 530 317-7363 BEFORE ENTERING THE PROPERTY. VENDOR HANDLING PROPANE TANK. JC 04/01/22 FOLLOW-UP CALL B/C MONITOR WAS UNABLE TO MAKE CONTACT. NO ANS LEFT VM & TEXT. JC 04/01/22 SPOKE WITH DIANA SHE SAID KEY IS AT THE GATE BEHIND THE ROCK NEXT TO POLE WITH ADDRESS. IF NOT, SHE GIVES CONSENT FOR CREW TO CUT CHAIN TO GET ONTO THE PROPERY. SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-04-07 |  | 2022-04-08 | 2022-04-08 |  |  | 1 | [17 empty] | 2021-12-17 | Do Not Assess | 0 | [14 empty] | Diana Darrington | 530-317-7363 |  | Other Septic Vehicles Onsite Well |  | 38.6594 | -120.6234 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-08T17:27:04Z | FALSE
593 | 093-021-022 | Full Program ROE (debris + trees) | Ready for Soil Sampling | No Hazard Trees | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 7121 | Happy Valley Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 2201.61 |  |  |  |  | FALSE |  | Other - see comments | N/A |  | TRUE |  | FALSE | Water Crossing/Bridge | Yes |  | TRUE | 2022-02-15 | 2022-02-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2022-02-15 | Yes | 2022-02-15 | 2022-02-21 | POSITIVE | 2022-02-24 | 2022-02-24 | 4 | 2021-12-18 | No Bio Monitoring Needed for Debris or Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-04 | No Activity/Nest Building Removed | [11 empty] | FALSE | Water Crossing/Bridge Needed | [7 empty] | TRUE | 2022-04-13 | 2022-03-25 | 2022-03-28 |  | dogs on site. 02/23/22 No an. Left voicemail that crew is coming out tomorrow to complete asbestos abatement. HO c/b said he can be there at 9am to meet them. Gates will be unlocked and dogs will be in the house. JC Notified HO that crew will meet him at property @9am on ﻿02/24/22 per Kaiulani Watson. JC 02/24/22 HO c/b very upset b/c crew called him at 6:52 am saying they are at his property. I contacted State Planner: Melissa Perry immediately. Owner wants to be notified 48 hours prior to coming out to property. JC 03/28/22 SPOKE WITH WILLIAM HE SAID OK FOR DEBRIS REMOVAL. PLEASE CALL 48 HOURS PRIOR TO COMING OUT TO PROPERTY. JC |  |  |  | 2022-04-05 |  | 2022-04-06 | 2022-04-06 |  |  | 3 | [17 empty] | 2021-12-17 | No | 0 | [14 empty] | William Wendell | (530)363-6464 | billybraubillions@gmail.com |  |  | 38.6546 | -120.6229 | Caldor | DR-4619 | Residential | Yes | 2021-12-09 | ROE Verified | Central Division | 2022-04-08T22:12:52Z | FALSE
594 | 093-290-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 8200 | Grizzly Flat Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3045.17 |  |  |  |  | FALSE |  |  | N/A |  | TRUE |  | FALSE |  | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 5 | 2 | 0 | 1 | 2 | 3 | 5 | 18 |  |  |  |  | No |  |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | POSITIVE | 2022-01-26 | 2022-01-26 | 32 | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2022-01-26 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-15 | 2022-01-26 | 2022-01-27 |  | 01/21/22 Phone number on file is not correct for homeowner. No email on file. 01/27/22 APPROVED TO PROCEED PER MELISSA. JC | 1 | State Planner: Melissa Perry |  | 2022-02-03 |  | 2022-02-04 | 2022-02-04 |  |  | 5 | 2022-02-10 | 2022-02-18 | 7 | Approved | [12 empty] | 2022-02-21 | 2021-12-17 | No | 0 | [14 empty] | Larry & Virginia Anderson | 530-919-4984 |  | Vehicle on site Septic Well | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 510 | 38.6177 | -120.6012 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
595 | 093-290-011 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 8330 | Grizzly Flat Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3166.36 |  | 2021-12-17 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-17 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | [31 empty] | 2021-12-17 | No | 0 | [14 empty] | Jeffrey Paul Baldeston | 916-634-9092 | jeffpbalderston@aol.com |  |  | 38.6209 | -120.5978 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
596 | 095-011-006 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 6641 | Slug Gulch Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 2754.19 |  | 2022-01-24 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-18 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2022-01-24 | No | 0 | [14 empty] | Kimberly Morse | 510-862-8791 | Kimberlymorse@yahoo.com |  |  | 38.606 | -120.6351 | Caldor | DR-4619 | Residential | Yes | 2021-11-23 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
597 | 095-011-051 | Full Program ROE (debris + trees) | Asbestos Abatement Needed | No Hazard Trees | Next Step: N/A | ELD Ready -Access Issues | NO ELIGIBLE TREES | 095-011-051 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 2169.55 |  |  |  |  | TRUE | Access Issues | Aggressive Property Owner | N/A |  | TRUE |  | FALSE |  | Yes |  | TRUE | 2022-01-19 | 2022-01-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 |  |  |  |  | No |  |  | 2022-01-21 | Yes | 2022-01-21 | 2022-01-25 | POSITIVE |  |  | 54 | 2022-02-09 | Bio Monitoring Needed for Debris AND Trees | 2022-02-04 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [13 empty] | 01/31/22 NO ANS LEFT VM ABT GATE CODE. JC 02/02/22 NO ANS LEFT VM AND SENT EMAIL. JC 02/02/22 Yvonne emailed back. She said, The State/Bureau of Land Management are the ones who added the lock to the top of the road. You may want to check with that entity. JC 3.19 CALLED HO. NO ANS. LEFT MESS. PER NOTES ABOVE I CALLED BLM (EL DORADO COUNTY-916 941-3101) SPOKE TO MATT AND HE SAID HE WOULD PASS THE MESS ON TO LEE HEGGLESON WOULD CALL OR EMAIL ME BACK WITH INFO. PF | [27 empty] | 2021-12-17 | No | 0 | [14 empty] | Yvonne Smith | 317-979-9994 | yrsmith25@gmail.com |  |  | 38.6056 | -120.6075 | Caldor | DR-4619 | Residential | No | 2021-12-09 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
598 | 099-100-072 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1140 | White Oak Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2149.57 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 8861 |  |  | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-03 |  | 11.3 Spoke with Scott he said ok. He has contacted the vendor abt the tank. JC |  |  |  | 2021-11-10 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-12 | No | 0 | [8 empty] | 2021-12-07 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Scott Ishmael, Rebecca Ishmael | (530) 306-8495 | skishmael1912@att.net | Access Issues Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Melanie Poole/#403 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 403 | 39.1245 | -120.9655 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
599 | 041-724-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 5 | 5286 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3762.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | No |  |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-08 | POSITIVE | 2021-12-11 | 2021-12-11 | 3 | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-11 | 2021-12-15 | 2022-03-18 | 12.14 NO ANS LEFT VM. JC 12.15 SPOKE WITH DAVID HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 03/16/22 NO ANS LEFT VM & TEXT. JC 3.17 Left mess. no ans. PF (sent 2nd email) 03/18/22 SPOKE WITH DAVID HE SAID OK FOR TREE REMOVAL. JC 04/08/22 Called abt trailer on property. No ans left vm & text. JC |  |  |  | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  |  | 5 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-02-04 | Yes | 32 | [14 empty] | David J. Giver | 408-243-2256 | Lawgiver308@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 502 | 38.632 | -120.5314 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-09T00:29:35Z | FALSE
600 | 041-724-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5252 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3820.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 3 | 0 | 0 | 1 | 6 |  |  | 3 |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-11-22 | Bio Monitoring Needed for Debris AND Trees | 2021-12-20 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-12-20 | 2022-01-21 | 2022-03-22 | 12.21 NO ANS LEFT VM & TEXT. JC 12.22 ﻿NO ANS LEFT VM & EMAIL. JC 12.23 SPOKE WITH JOSHUA HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/21/22 JOSHUA SAID OK BUT CALL. JC 03/22/22 NO ANS LEFT VM & TEXT. JC 03/22/22 JOSHUA C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-17 | Yes | 28 | [14 empty] | Joshua Liebe | 530-417-2714 | joshliebe6@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 502 | 38.6333 | -120.5312 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
601 | 041-732-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5280 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3784.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-02-01 | 02/01/22 SPOKE WITH SHERRON SHE SAID OK. NO PROPANE TANKS ON PROPERTY. JC | [27 empty] | 2021-12-06 | Yes | 44 | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-04 | 2022-03-05 | 44 |  |  | 2022-03-08 |  | 2022-03-08 | 2022-03-08 | Sherron Burleson | 530-417-7728 | burlesonsherron@yahoo.com |  |  | 38.6311 | -120.5351 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
602 | 041-250-019 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 10315 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3875.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | POSITIVE | 2021-11-08 | 2021-11-08 | 3 | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-15 | 2021-11-19 | 2022-02-02 | 11.16 PHONE DISCONNECTED. JC 11.17 SENT EMAIL. JC 11.18 PHONE # ON FILE DISCONNECTED. GAVE TO RICHARD. JC 11.19 Reached out to county to attempt contact. 02/01/22 PHONE DISCONNECTED. SENT EMAIL. JC 02/202/22 SENT EMAIL. 02/02/22 OK TO PROCEED PER MELISSA. JC | 4 | Kendall Wilson |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Re-scrape |  |  |  | 2022-01-19 | 2022-01-27 | Approved | [6 empty] | 2022-01-29 | 2022-03-15 | Yes | 11 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-23 | 11 |  |  | 2022-03-29 |  |  |  | Williard Bunyan | 925-370-9311 | bbunyan@mindspring.com | Septic Safety Concern | Debris Crew Leader/Crew# Matthew Dorenson/#505 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 505 | 38.6365 | -120.5287 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
603 | 041-250-023 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 041-250-023 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3886.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-24 | POSITIVE | 2021-12-01 | 2021-12-01 | 4 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-11-22 | Arch Monitoring Needed for Debris AND Trees | [6 empty] | Yes | 2022-03-26 | Yes | [5 empty] | FALSE | [10 empty] | 2021-12-01 | 2021-12-02 |  | 11.29 NO ANS LEFT VM. JC 11:30 NO ANS LEFT VM. JC 12.01 SENT EMAIL. JC 12.02 Contacted homeowner, okayed debris removal start. 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/14/22 BRET SAID TO PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 37 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-03-22 | Yes | 12 | [14 empty] | Brett & Peggy Saum | 559-285-8948 | bsaum@comcast.net |  | Debris Crew Leader/Crew# Brandon Pilar /#505 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 505 | 38.636 | -120.5297 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
604 | 041-250-035 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 3723 | Nutting Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3882.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-22 | 2021-11-23 | 2022-03-03 | 11.23 Homeowner contacted, accepted start of debris removal. Had a question about driveway removal. RCV 01/25/22 NO ANS LEFT VM & TEXT. JC 01/27/22 SPOKE WITH RUTH SHE CALLING VENDOR AND WILL CALL US BACK. RUTH C/B VENDOR WILL HANDLE PROPANE TANK. JC 03/03/22 Ruth said ok but leave the cedar and doug fir trees at the top of the property where the other cut trees are stacked. |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape |  |  |  | 2022-01-25 | 2022-02-02 | Approved | [6 empty] | 2022-02-04 | 2022-01-19 | Yes | 7 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-19 | 2022-03-21 | 7 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | RUTH MILLER | 650-346-7804 | 7RUTHMILLER7@GMAIL.COM | Other Septic | Debris Crew Leader/Crew# Mathew Dorenzo /#505 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 505 | 38.6363 | -120.5293 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
605 | 041-250-036 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | NO ELIGIBLE TREES | 3717 | Nutting Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3882.85 |  | 2022-03-14 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-03-02 | 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 NO ANS LEFT VM & EMAIL JC 03/02/22 HO GAVE CONSENT VIA VOICEMAIL. JC | [27 empty] | 2021-12-01 | No | 0 | [14 empty] | Ruth Miller | 650-346-7805 | 7ruthmiller7@gmail.com |  |  | 38.6367 | -120.5293 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
606 | 041-250-038 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 3705 | Nutting Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3882.35 |  | 2021-12-01 | No qualifying debris; no hazard trees |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Debris AND Trees | 2021-11-10 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-14 | [31 empty] | 2021-12-01 | No | 0 | [14 empty] | Ruth Miller | 650-346-7804 | 7ruthmiller7@gmail.com |  |  | 38.6374 | -120.5291 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
607 | 041-250-042 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5015 | Old Nail Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3882.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | Yes | No | Yes | No | FALSE | TRUE | 7 | 0 | 8 | 0 | 1 | 4 | 0 | 20 |  |  | 11 |  | Yes | Leave |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-27 | 2021-10-27 | 10 | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | Arch Monitoring Needed for Trees, not Debris | [6 empty] | Yes | 2022-03-29 | Yes |  |  |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-15 | 2021-11-17 |  | 11.16 NO ANS LEFT VM JC 11.17 SPOKE RUSSELL HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE PROPANE TANKS. JC |  |  |  | 2021-11-18 |  | 2021-11-20 | 2021-11-20 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Re-scrape | 2022-02-04 | 2022-02-14 | Re-scrape | 2022-01-22 | 2022-01-28 | Soil Boring | 2022-02-19 | 2022-02-28 | Approved |  |  |  | 2022-03-02 | 2021-11-23 | Yes | 60 | [14 empty] | RUSSELL STARR | 530-748-8187 | RUSSELLSTARR54@GMAIL.COM |  | Debris Crew Leader/Crew# Mathew Dorerzo/#505 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 505 | 38.6373 | -120.5302 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
608 | 041-250-043 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4427 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3884.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | No |  |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-17 | POSITIVE | 2022-01-22 | 2022-01-22 | 25 | 2021-12-09 | Bio Monitoring Needed for Trees, not Debris | 2022-02-04 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-14 | No |  | TRUE |  | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-02-04 | 2022-02-07 | 2022-03-23 | 02/04/22 No ans left vm & text. JC 02/07/22 NO ANS LEFT VM AND EMAIL. JC 02/07/22 SPOKE WITH STACI SHE SAID OK. PLEASE CALL IN ADVANCE. NO PROPANE TANKS ON PROPERTY. JC 03/22/22 NO ANS LEFT VM & TEXT. PF 3.23 NO ANS. LEFT VM & SENT EMAIL PF 3.23 NO ANS. LEFT VM & SENT EMAIL PF Email returned undeliverable. SENT ANOTHER TEXT- STACI CALLED SAID OK AND SAID WE HAD THE WRONG EMAIL. CORRECTED ON SMART SHEETS PF |  |  |  | 2022-02-15 |  | 2022-02-16 | 2022-02-16 |  |  | 2 | 2022-02-17 | 2022-02-25 | 7 | Approved | [12 empty] | 2022-03-01 | 2022-02-04 | Yes | 156 | [14 empty] | Staci Jones | 619-850-9552 | sntjones@sbcglobal.net |  | Debris Crew Leader/Crew# Eric Rocha/ #503 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 503 | 38.6388 | -120.5299 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
609 | 041-260-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10385 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3838.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | POSITIVE | 2021-11-23 | 2021-11-23 | 26 | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-23 | 2021-11-23 | 2022-01-25 | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH SORIN HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT. JC 01/25/22 SPOKE WITH DANIELA SHE SAID OK BUT PLEASE CALL HER AT 916 288-7976﻿. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 4 | 2021-12-11 | 2021-12-17 | 5 | Approved | [12 empty] | 2021-12-20 | 2021-12-01 | Yes | 2 | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  | 2022-02-02 | 2022-02-03 | 2 | 2022-02-10 |  | 2022-02-04 | 2022-02-10 | 2022-02-10 | 2022-02-10 | SORIN & DANIELA SIGHETI | SORIN 916-273-0866 / DANIELA 916 288-7976 | dsigheti@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 509 | 38.6358 | -120.5249 | Caldor | DR-4619 | Residential | No | 2021-10-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
610 | 041-260-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10393 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3812.05 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Code is D-E-A-D |  |  | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 |  |  | 1 | TRUE | No |  |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | POSITIVE | 2021-10-27 | 2021-10-27 | 7 | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-10-27 | 2021-10-30 |  | 10.30 Spoke with homeowner, acknowledged beginning of debris removal. Homeowner requests to save bulldozer and for crews to avoid well RCV |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-03 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2021-11-20 | Yes | 3 | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  | 2022-01-17 | 2022-01-19 | 3 | 2022-01-27 |  | 2022-01-24 | 2022-02-16 | 2022-02-16 | 2022-02-16 | SORIN & DANIELA SIGHETI | 916-288-7976 | DSIGHETI@GMAIL.COM |  | Debris Crew Leader/Crew# Sarad Mundt/#501 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 501 | 38.6355 | -120.5243 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
611 | 041-260-012 | Full Program ROE (debris + trees) | ROE Received | Haz Trees Present | Next Step: N/A | Program Eligibility Determination | Tree Assessment Complete | 4991 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Commercial | [5 empty] | 4005.87 |  |  |  |  | TRUE | Inclusion Approval |  | N/A | Pending | FALSE |  | FALSE |  | Yes |  | TRUE |  |  | FALSE |  | FALSE |  |  | FALSE | [6 empty] | FALSE | FALSE | [7 empty] | 0 | [17 empty] | 2022-02-07 | Arch Monitoring Needed for Trees, not Debris | [12 empty] | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-03-17 | [11 empty] | FALSE | [19 empty] | 2022-01-19 | Yes | 85 | [14 empty] | Bryan Kroeker, Kelly Souza | 916-799-0202 | ken@westerntradingco.com |  |  | 38.6394 | -120.5255 | Caldor | DR-4619 | Commercial | No | 2021-12-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
612 | 041-260-022 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 3691 | Hidden Creek Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3784.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | NEGATIVE |  |  |  | 2021-11-09 | Bio Monitoring Needed for Trees, not Debris | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-09 | 2021-11-11 |  | 11.10 NOT ACCEPTING CALLS AT THIS TIME. SENT EMAIL. JC 11.11 SPOKE WITH RONNA SHE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT TAKE THE PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-19 | 2021-11-19 |  |  | 3 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-11-16 | No | 0 | [8 empty] | 2022-01-31 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | Ronna Wollcott | 530-417-0226 | ronnab02@sbcglobal.net | Vehicles on site Septic Keep items Safety concerns | Debris Crew Leader/Crew# Adam Hutcheson /#504 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 504 | 38.6326 | -120.5253 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
613 | 041-260-023 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 3679 | Hidden Creek Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3808.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | Yes | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-10 | 2021-11-11 |  | 11.11 SPOKE WITH OWNER, SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE. JC |  |  |  | 2021-11-12 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-20 | 2021-12-01 | 6 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Approved | [6 empty] | 2021-12-15 | 2021-11-29 | No | 0 | [8 empty] | 2022-01-31 |  |  | 2022-02-05 | 2022-02-05 | 2022-02-07 | TREZONA TOBY TYLER II | 530-363-5552 |  |  | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 504 | 38.6333 | -120.5243 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
614 | 041-260-024 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 3647 | Hidden Creek Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3801.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 4 |  |  | 4 | TRUE | No |  |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-06 | 2021-11-08 |  | 11.8 NO ANS LEFT VM. JC 11.8 SPOKE WITH RAYMOND HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Approved | [6 empty] | 2021-12-15 | 2021-11-16 | No | 0 | [8 empty] | 2022-02-11 |  |  | 2022-02-14 | 2022-02-14 | 2022-02-14 | RAYMOND & SANDRA DARE | 916-208-0000 | raydare@comcast.net | Vehicle On Site | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 501 | 38.6328 | -120.5234 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
615 | 041-260-028 | Full Program ROE (debris + trees) | Ready for Final Sign-off | Passed Tree Completion Check | Next Step: N/A | Punchlist | Ready for FSO | 10371 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3876.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | POSITIVE | 2021-11-11 | 2021-11-11 | 3 | 2022-01-29 | Bio Monitoring Needed for Trees, not Debris | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-23 | 2021-11-19 | 2022-01-22 | 11.19 SPOKE WITH MARY SHE SAID OK BUT PLEASE CALL IN ADVANCE OKAY. PLEASE REMOVE. JC 01/22/22 SPOKE WITH MARY SHE SAID OK. JC |  |  |  | 2021-12-03 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-02 | Yes | 67 | 2022-01-29 |  | 2022-02-01 | 2022-02-01 |  | 2022-02-07 | 2022-02-17 | 67 | 2022-03-14 |  | 2022-02-18 |  |  |  | Perry Phillis & Mary Runyan | 916-267-4822` | mvrunyan@icloud.com | Vehicle on site Septic Well Safety concerns | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/04to 12/08 Crew 509 | 38.6365 | -120.5254 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
616 | 041-290-001 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 4684 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4030.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 6 | 1 | 0 | 2 | 1 | 2 | 0 | 12 |  |  | 14 |  | Yes | Leave |  | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | POSITIVE | 2021-11-20 | 2021-11-20 | 9 | 2021-11-13 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | [6 empty] | Yes | 2022-03-26 | No |  | TRUE |  | Class II | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-20 | 2021-11-22 |  | 11.22 NO ANS LEFT VM JC 11.22 SPOKE WITH BOB HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Soil Boring | 2022-01-25 | 2022-02-02 | Re-scrape | 2022-02-09 | 2022-02-17 | Approved | [6 empty] | 2022-02-19 | 2022-01-31 | Yes | 160 | 2022-02-19 | [6 empty] | 1 | [6 empty] | Bob Meyer | 916-761-9047 | bobmyer2009@yahoo.com | Septic Vehicles on site | Debris Crew Leader/Crew# Antonio Ruiz #510 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 510 | 38.6474 | -120.5171 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
617 | 041-290-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4707 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4040.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 3 |  |  | 6 | TRUE | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-20 | 2021-11-20 | 2 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-20 | 2021-11-20 | 2022-02-18 | 11.17 NO ANS LEFT VM. JC 11.17 SPOKE WITH RANDY HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE THE PROPANE TANK OR WOOD STOVE. JC 02/16/22 I spoke with Randolph, and he said to hold off on hazard tree removal. He said he will call the county because he wants to cut the trees himself. JC 02/18/22 SPOKE WITH RANDY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 5 | 2021-12-07 | 2021-12-15 | 7 | Re-scrape |  |  |  | 2022-01-24 | 2022-02-01 | Approved | [6 empty] | 2022-02-03 | 2021-12-03 | Yes | 7 | 2022-02-26 |  | 2022-02-26 | 2022-02-26 |  | 2022-02-28 | 2022-03-02 | 7 | 2022-03-14 |  | 2022-03-10 | 2022-03-17 | 2022-03-17 | 2022-03-17 | Randolph Ank | 916-601-6138 | ank.randy@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Antonio Ruiz Jr/#510 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 510 | 38.6467 | -120.5171 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
618 | 041-290-007 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Ready for TFSW | 7084 | Pinehaven Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3986.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-24 | 2022-01-24 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 4 | 1 | 2 | 1 | 3 | 1 | 1 | 13 |  |  | 9 |  | Yes | Take |  | 2022-01-27 | Yes | 2022-01-27 | 2022-02-04 | POSITIVE | 2022-02-08 | 2022-02-08 | 3 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2022-02-07 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-01 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-21 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-02-08 | 2022-02-10 | 2022-03-24 | 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 HO GAVE CONSETN VIA TEXT AND ASKED THAT WE REMOVE THE PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 HO GAVE CONSETN VIA TEXT AND ASKED THAT WE REMOVE THE PROPANE TANK. JC 3.24 NO ANS LEFT MESS AND TEXT PF 3.24 DAUGHTER MARGARET C/B AND SAID OK. GAVE MOM'S # ALSO PF 04/08/22 Spoke with Maxine abt vehicles on property. She said there aren't any vehicles left on the property. JC |  |  |  | 2022-02-11 |  | 2022-02-16 | 2022-02-16 |  |  | 2 | 2022-02-17 | 2022-02-25 | 7 | Re-scrape |  |  |  | 2022-03-11 | 2022-03-21 | Approved | [6 empty] | 2022-03-23 | 2022-04-01 | Yes | 30 | 2022-04-01 |  | 2022-04-02 | 2022-04-02 |  | 2022-04-07 | 2022-04-08 | 30 | [6 empty] | Maxine Tyler | 916-517-3267 DAUGHTER MARGARET 530-626-5713 (MAXINE'S ) | Grossma95662@gmail.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 601 | 38.6449 | -120.5271 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-08T21:00:39Z | FALSE | 5
619 | 041-423-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5096 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3856.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-02 | No | [6 empty] | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-22 | 2021-12-07 | 2022-02-10 | 12.07 SPOKE WITH WENDY SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK IS NOT DAMAGED. JC 02/10/22 SPOKE WITH WENDY SHE SAID OK. JC |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 27 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2021-11-16 | Yes | 70 | 2022-02-14 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-21 | 2022-02-25 | 70 | 2022-03-10 |  | 2022-02-28 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Stephen & Wendy Auldridge | 530-845-2575 | grizgal06@gmail.com |  | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 504 | 38.6372 | -120.5389 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
620 | 041-423-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5120 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3831.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-17 | 2021-11-18 | 2022-02-21 | 11.18 SPOKE PAUL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE LARGE PROPANE TANK. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 PAUL GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-06 | Yes | 37 | 2022-03-08 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-17 | 2022-03-18 | 37 | 2022-03-23 |  | 2022-03-19 | 2022-03-24 | 2022-03-24 | 2022-03-24 | PAUL FLESHMAN | 530-663-3748 | katrinafleshman@yahoo.com | Vehicles on site Septic | "Debris Crew Leader/Crew# Adam Hutcheson /#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6366 | -120.5379 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 8
621 | 041-423-005 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 3 | 4685 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3818.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Milk Run | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Trees, not Debris | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | Yes | 2022-03-01 | TRUE |  | Class III | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-19 | 2021-11-19 | 2022-03-24 | 11.17 SPOKE WITH LILA SHE SAID OK BUT PLEASE CALL ADVANCE. PLEASE REMOVE PROPANE TANK. JC 01/19/22 NO ANS LEFT VM & TEXT. JC 01/19/22 LILA C/B SHE SAID OK. JC 3.24 SPOKE TO LILLA SHE SAID OK TO PROCEED. PF |  |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2022-03-01 | Yes | 65 | 2022-04-07 | [6 empty] | 31 | [6 empty] | Lila Rae Watson | 650-730-8713 | rush72912@gmail.com | SEPTIC | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 504 | 38.6353 | -120.5373 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-08T01:10:26Z | FALSE
622 | 041-423-007 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1b | 4729 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3814.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | POSITIVE | 2022-01-19 | 2022-01-19 | 37 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-21 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-19 | 2022-01-20 | 2022-03-26 | 01/19/22 NO ANS LEFT VM & TEXT. JC 01/20/22 SPOKE WITH HO THEY SAID OK. NO PROPANE TANKS ON PROPERTY. JC 03/25/22 NO ANS NO VM SENT TEXT. JC 3.26 SPOKE TO NONA AND SHE SAID HER FATHER DECEASED BUT ITS OK TO PROCEED. PF |  |  |  | 2022-01-29 |  | 2022-01-31 | 2022-01-31 |  |  | 5 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-02-02 | Yes | 22 | 2022-04-06 |  | 2022-04-06 | 2022-04-06 |  |  |  | 22 | [6 empty] | Norman Mactaggart Tr | 805-703-0195 | n.covington420@gmail.com |  | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 504 | 38.6363 | -120.5372 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T17:17:26Z | FALSE
623 | 041-423-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4700 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3800.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-23 | Yes | 2021-10-26 | 2021-10-29 | NEGATIVE |  |  |  | 2021-10-26 | Bio Monitoring Needed for Debris AND Trees | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-18 | 2021-11-19 | 2022-01-19 | 11.17 NO ANS LEFT VM. JC 11.17 SPOKE WITH ANISSA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/18/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL 01/19/22 NO ANS LEFT VM & EMAIL. JC 01/19/22 ANISSA C/B SHE SAID OK. JC |  |  |  | 2021-11-23 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2022-01-21 | Yes | 28 | 2022-01-21 |  | 2022-01-24 | 2022-01-24 |  | 2022-01-28 | 2022-01-29 | 28 | 2022-02-10 |  | 2022-02-02 | 2022-02-12 | 2022-02-12 | 2022-02-12 | Steven Starks Sr. and Anissa Williams | 916-768-0106 | dsp06@netzero.com | Septic | Debris Crew Leader/Crew# Adam Hutcheson /#504 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 504 | 38.6353 | -120.5363 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
624 | 041-424-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5147 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3847.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-20 | 2021-11-19 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-01-25 | 01/24/22 NO ANS LEFT VM & TEXT. JC 01/25/22 HO GAVE CONSENT VIA TEXT. JC 01/25/22 Robert c/b to confirm consent via text and said ok to tree removal. JC | [27 empty] | 2022-01-27 | Yes | 56 | 2022-01-27 |  | 2022-01-29 | 2022-01-29 |  | 2022-01-31 | 2022-02-01 | 56 |  |  | 2022-02-04 |  | 2022-02-04 | 2022-02-04 | Robert, Andy & Anne Kochendorfer | 925-784-5121 | bob_and_lea@yahoo.com |  |  | 38.6353 | -120.5385 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
625 | 041-424-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5067 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3896.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave | 2022-03-08 | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-18 | 2021-11-19 | 2022-01-19 | 11.19 NO ANS LEFT VM JC 11.19 SPOKE WITH SHARON SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/19/22 NO ANS LEFT VM, TEXT AND EMAIL. JC 01/19/22 SHARON C/B SHE SAID OK. JC |  |  |  | 2021-11-23 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2022-01-19 | Yes | 7 | 2022-02-09 |  | 2022-02-09 | 2022-02-09 |  | 2022-02-14 | 2022-02-15 | 7 | 2022-02-18 |  | 2022-02-16 | 2022-03-08 | 2022-03-08 | 2022-03-08 | Sharon Welch | 925-640-9934 | swelchca@aol.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6353 | -120.5392 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 5
626 | 041-424-005 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5031 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3883.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | Yes |  | 2021-12-10 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 1 |  | Yes | Leave |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-10 | 2021-12-11 |  | 12.11 NO ANS LEFT VM & TEXT. JC 12.11 SPOKE WITH TONY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 3.16 Spoke to Linda and she said ok PF |  |  |  | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  |  | 5 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-02-02 | Yes | 40 | 2022-03-22 |  | 2022-03-23 | 2022-03-23 |  | 2022-03-25 | 2022-03-26 | 40 |  |  | 2022-03-28 |  |  |  | Tony & Linda Iller | 530-558-5934 , 916-496-2705 | tonyillers@yahoo.com, linda.illers@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 504 | 38.6365 | -120.5389 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
627 | 041-090-015 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Not Eligible for Haz Tree Removal | Next Step: N/A | Pending Soil Sampling Results | NO ELIGIBLE TREES | 041-090-015 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3959.76 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2021-11-18 | 2022-03-07 |  | 11.19 SPOKE GREG HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 1/21/22 NO ANS LEFT VM & TEXT. JC 03/07/22 Greg said ok for debris removal. Please call in advance. jc 03/08/22 GREG CALLED REQUESTING DAMAGE CLAIM FORM. FORM EMAILED ON 03/08/22. jc |  |  |  | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  |  | 1 | 2022-03-08 | 2022-03-16 | 7 | Re-scrape |  |  |  | 2022-03-31 | 2022-04-08 | [9 empty] | Do Not Assess | 0 | [14 empty] | GREGORY & KELLY ADAMS | 510-952-1478 | kellya139@comcast.net |  | Debris Crew Leader/Crew# Cardonlet Dunbar/ #514 Debris Crew WO# Refer to IAP 03/05 to 03/09 Crew 514 | 38.6342 | -120.4457 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-09T00:02:16Z | FALSE
628 | 041-090-016 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-090-016 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4858.71 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-12 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-07 | Bio Monitoring Needed for Trees, not Debris | [16 empty] | FALSE | [42 empty] | Do Not Assess | 0 | [14 empty] | Frankie & Cindy Yoka | 916-494-2757 | butterflo1998@yahoo.com | Well |  | 38.6341 | -120.444 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
629 | 041-090-017 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Not Eligible for Haz Tree Removal | Next Step: N/A | Pending Soil Sampling Results | NO ELIGIBLE TREES | 041-090-017 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4675.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-18 | 2022-02-18 | FALSE | No |  |  | No |  | No | Yes | Yes | No | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2022-02-16 | Yes | 2022-02-16 | 2022-02-18 | POSITIVE | 2022-03-08 | 2022-03-08 | 13 | 2022-03-09 | Bio Monitoring Needed for Trees, not Debris | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-03-19 | 2022-03-09 | 2022-02-09 |  | 02/07/22 HO SAID BURNED STRUCTURES ON PROPERTY. JC 02/09/22 SPOKE WITH HO THEY SAID DO NOT REMOVE THE WINDMILL AND PUMP. JC |  |  |  | 2022-03-11 |  | 2022-03-14 | 2022-03-14 |  |  | 3 | 2022-03-16 | 2022-03-24 | 7 | Re-scrape |  |  |  | 2022-03-31 | 2022-04-08 | [9 empty] | Do Not Assess | 0 | [14 empty] | GARD, MICHAEL & ANDREA | 415-373-7048 , 415-756-0473 | andrea.lynn.gard@gmail.com, michael.c.gard@gmail.com |  | Debris Crew Leader/Crew# Carondlet Dunbar /#514 Debris Crew WO# Refer to IAP 03/12 to 03/16 Crew 514 | 38.634 | -120.4429 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-09T00:03:36Z | FALSE
630 | 041-160-007 | Full Program ROE (debris + trees) | ROE Received | Not Eligible for Haz Tree Removal | Next Step: N/A | Need Site Assessment | NO ELIGIBLE TREES | 041-160-007 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 7005.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [33 empty] | FALSE | [8 empty] | TRUE | 2022-03-19 |  |  |  | 02/07/22 HO SAID BURNED DEBRIS ON PROPERTY. JC | [28 empty] | Do Not Assess | 0 | [14 empty] | Alison Pillsbury | 209-267-5554 | acornhillsanimalcenter@gmail.com |  |  | 38.6345 | -120.2703 | Caldor | DR-4619 | Residential | No | 2021-12-06 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
631 | 041-200-007 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6011 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3895.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 |  |  | 3 | TRUE | No |  |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-24 | 2021-11-24 | 5 | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-20 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-24 | 2021-11-24 |  | 11.24 NO ANS LEFT VM. JC 11.24 SPOKE WITH SUSAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 4 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-12-17 | No | 0 | [8 empty] | 2022-02-21 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Susan Anderson | 916-212-2457 | jillesola@gmail.com | Vehicle on site Septic Well | Debris Crew Leader/Crew# Adam Mattson /#507 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 507 | 38.6519 | -120.5333 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
632 | 041-200-021 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6075 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3599.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 3 | 0 | 1 | 0 | 1 | 4 | 0 | 9 |  |  | 3 | TRUE | Yes | Take | 2022-02-17 | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | POSITIVE | 2021-12-03 | 2021-12-03 | 2 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-12-04 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-04 | 2022-01-21 |  | 12.07 SPOKE WITH LOUISE SHE SAID OK BUT PLEASE CALL IN ADVANCE. SHE OWNS PROPANE TANK AND WANTS REMOVED ONLY IF BEEN DESTROYED BY FIRE. JC 01/21/22 LOUISE SAID OK. JC |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-29 | 2022-02-04 | 5 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2021-12-17 | No | 0 | [8 empty] | 2022-03-17 |  |  | 2022-03-18 | 2022-03-18 | 2022-03-18 | TYLER JAMES RICHARD & LOUISE ROSE | 530-306-2402 | jalotyler@att.net |  | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/19 To 01/22 Crew507 | 38.6513 | -120.5281 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
633 | 041-200-022 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Rescrape Needed | Tree Assessment Complete | 6061 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3884.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-08 | 2022-02-08 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 35 | 6 | 0 | 10 | 5 | 17 | 5 | 78 |  |  | 20 |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-12-01 | 2021-12-01 | 6 | 2021-11-15 | Bio Monitoring Needed for Debris AND Trees | 2021-12-13 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-29 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-31 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-13 | 2022-01-22 |  | 12.14 NO ANS LEFT VM & TEXT. JC 12.15 NO ANS LEFT VM & EMAIIL. JC 12.16 NO ANS MAILBOX FULL. GAVE TO RICHARD. JC 12.17 SPOKE WITH SUSAN SHE SAID OK BUT SHE WANTS TO BE THERE DURING THE DEBRIS REMOVAL. NO PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-02-14 |  | 2022-02-17 | 2022-02-17 |  |  | 12 | 2022-03-04 | 2022-03-14 | 7 | Re-scrape | [13 empty] | 2021-12-18 | Yes | 30 | [14 empty] | Susan Tyler | 530 957-5583 | susantyler77@yahoo.com |  | Debris Crew Leader/Crew# Terrence Harrison/ #502 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 502 | 38.6553 | -120.5321 | Caldor | DR-4619 | Residential | No | 2021-10-12 | ROE Verified | Central Division | 2022-04-06T00:37:19Z | FALSE
634 | 041-230-006 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4595 | Huggy Bear Lane |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3907.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 4 |  |  | 3 | TRUE | Yes | Leave |  | 2021-11-18 | Yes | 2021-11-18 | 2021-11-24 | POSITIVE | 2021-12-02 | 2021-12-02 | 5 | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-24 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-02 | 2021-12-02 |  | 11.29 NO ANS LEFT VM. JC 11:30 NO ANS LEFT VM JC 12.02 Left voicemail, email, and text RCV 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 PHONE NUMBER OUT OF SERVICE SENT EMAIL. JC 02/10/22 PHONE NUMBER STILL OUT OF SERVICE SENT 2ND EMAIL ABT PROPANE TANK. JC | 3 | Kendall Wilson |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 |  |  | 3 | 2021-12-11 | 2021-12-17 | 5 | Soil Boring | 2022-01-12 | 2022-01-20 | Re-scrape | 2022-01-31 | 2022-02-08 | Approved | [6 empty] | 2022-02-09 | 2021-12-01 | No | 0 | [8 empty] | 2022-03-10 |  |  | 2022-03-17 | 2022-03-17 | 2022-03-17 | Claudine Howe Webb | 530-409-9208 | wwebbman@att.net | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Mattson Adam/#507 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 507 | 38.6309 | -120.5452 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
635 | 041-230-037 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 041-230-037 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3644.53 |  |  |  |  | TRUE | Property Owner Issue |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-09 | Bio Monitoring Needed for Debris, not Trees | 2022-02-17 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [41 empty] | 2022-03-15 | Yes | 53 | [14 empty] | Willy Cheng Ya Han | 510-585-7700 | wcyh@yahoo.com | Vehicles Onsite |  | 38.6344 | -120.5485 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
636 | 041-250-002 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 5061 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Commercial | No |  |  |  |  | 3943.21 |  |  |  |  | FALSE |  |  | N/A | Approved |  |  |  |  | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | Yes |  | 2022-03-28 | No | TRUE | No | Yes | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | POSITIVE | 2022-03-28 | 2022-03-28 | 86 | 2021-11-20 | Bio Monitoring Needed for Debris AND Trees | 2021-12-01 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-26 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-04-02 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2022-03-28 | 2022-03-30 |  | 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/15/22 NO ANS LEFT VM AND EMAIL. JC 02/16/22 NO ANS LEFT VM AND 2ND EMAIL ABT PROPANE TANK. JC 02/16/22 WILLIAM C/B VENDOR HANDLING PROPANCE TANK. JC 03/29/22 NO ANS LEFT VM SENT TEXT & EMAIL. JC 03/30/22 NO ANS LEFT VM & 2ND EMAIL JC 03/30/22 William c/b he said ok for debris removal. jc |  |  |  | 2022-03-30 |  | 2022-04-01 | 2022-04-01 |  |  | 1 | 2022-04-02 |  | 5 | [14 empty] | 2022-04-05 | Yes | 61 | [14 empty] | William Brown | 530-622-4538 | gfcc@att.net | Septic | "Debris Crew Leader/Crew# Stephanie Fairlee / 518 Debris Crew WO# Refer to IAP 03.30 to 04.02 Crew 518 | 38.6377 | -120.5264 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
637 | 041-250-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10331 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3878.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-22 | 2021-11-22 | 5 | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-22 | 2021-11-19 | 2022-01-28 | 11.19 SPOOKE WITH LARRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/28/22 SPOKE WITH LARRYHE SAID. JC |  |  |  | 2021-12-03 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Soil Boring | 2022-01-15 | 2022-01-21 | Approved | [9 empty] | 2022-01-26 | 2021-12-01 | Yes | 9 | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  | 2022-02-04 | 2022-02-07 | 9 | 2022-03-11 |  | 2022-02-17 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Larry Lodge | 530-363-4586 |  | Septic Vehicles Onsite | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 509 | 38.6365 | -120.527 | Caldor | DR-4619 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
638 | 041-250-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10345 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3893.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-09 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 |  |  | 2022-01-19 | 1/19: spoke with Jay about tree removal. Ok to proceed. Dogs in kennel next to cabin. (MP) | [27 empty] | 2021-12-01 | Yes | 3 | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  | 2022-01-21 | 2022-01-22 | 3 |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 | JAY C CARLON | 916-296-5016 | j.cc222@yahoo.com |  |  | 38.6364 | -120.5266 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
639 | 041-250-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10353 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3883.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | POSITIVE | 2021-11-11 | 2021-11-11 | 3 | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-19 | 2021-11-22 | 2022-01-18 | 11.20 NO ANS LEFT VM. JC 11.22 SPOKE WITH JAY HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK AND DOES NOT WANT IT REMOVED. JC 01/18/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 01/18/22 SPOKE WITH JAY HE SAID OK. JC 01/31/22 SPOKE WITH JAY. HE SAID HE DOES NOT HAVE A LOCKED GATE. JC |  |  |  | 2021-12-01 |  | 2021-12-03 | 2021-12-03 |  |  | 4 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-20 | 2021-12-03 | Yes | 10 | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  | 2022-01-24 | 2022-01-25 | 10 | 2022-01-28 |  | 2022-01-25 | 2022-02-05 | 2022-02-05 | 2022-02-07 | JAY C CARLON | 916-296-5016 | j.cc222@yahoo.com |  | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 509 | 38.6364 | -120.5262 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
640 | 041-011-035 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5275 | String Canyon Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3483.54 |  | 2021-12-17 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-11 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [41 empty] | 2021-12-17 | No | 0 | [14 empty] | Michael Logan & Alta Verdugo | 530-621-1186 | rosey2@hughes.net |  |  | 38.6454 | -120.5513 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
641 | 041-021-005 | Full Program ROE (debris + trees) | Ready for Soil Sampling | No Hazard Trees | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 4241 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3804.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 31 | 20 | 15 | 3 | 5 | 22 | 4 | 100 |  |  |  |  | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-29 | 2021-10-29 | 12 | 2021-10-29 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-17 | No Activity/Nest Building Removed |  |  | Complete | [8 empty] | FALSE | [8 empty] | TRUE | 2022-04-13 | 2021-11-17 | 2022-01-22 |  | 11.17 SPOKE WITH DAVID HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE THE PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 NO ANS LEFT VM & EMAIL. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC 01/24/22 DAVID CALLED AND SAID HE IS GOING UP TO PROPERTY ON WED OF THIS WEEK TO MARK ITEMS HE DOES NOT WANT REMOVED. ﻿JC |  |  |  | 2022-03-31 |  | 2022-04-05 | 2022-04-05 |  |  | 4 | [17 empty] | 2021-11-10 | No | 0 | [14 empty] | DAVID LYNCH | 408-472-4326 | aupanner@att.net |  |  | 38.6592 | -120.5257 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-08T22:12:52Z | FALSE
642 | 041-021-008 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 4245 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4054.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | Yes | TRUE | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 4 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | Bio Monitoring Needed for Trees, not Debris | 2021-11-04 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-11-04 | 2021-11-05 |  | 11.5 NO ANS. LEFT MESS PF 11.5 SPOKE TO RYAN AND HE SAID OK. HIS TANK IS BEING HANDLED BY VENDOR. PLEASE CALL BEFORE GOING TO PROPERTY. PF |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-29 | Do Not Assess | 0 | [8 empty] | 2022-01-18 |  |  | 2022-01-27 | 2022-01-27 | 2022-01-27 | RYAN RODRIGUEZ | 530-391-5963 | SARA_RAE86@YAHOO.COM |  | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 507 | 38.6581 | -120.5215 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
643 | 041-021-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4251 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4053.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | No |  | No | No | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-22 | 2021-10-26 | 2022-02-03 | 10.26 NO ANS LEFT MESS PF 10.26 MR NELSON C/B AND SAID OK. PF 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 01/24/22 SPOKE WITH JOHN SAID OK. JC 02/03/22 NO ANS LEFT VM AND TEXT ABT CREW MOBILIZING EITHER THIS AFTERNOON OR TOMORROW MORNING. JC 02/03/22 HO C/B AND SAID THEY WANT TO BE ON SITE. IF THE CREW IS ON SITE TODAY HE WANTS THEM TO STAND DOWN. HE SAID HE WILL BE ON PROPERTY TOMORROW. HE IS OKAY WITH CREW MOBILIZING TOMORROW. JC |  |  |  | 2021-10-30 |  | 2021-11-01 | 2021-11-01 |  |  | 6 | 2021-11-08 | 2021-11-17 | 8 | Approved | [12 empty] | 2021-11-19 | 2022-02-03 | Yes | 125 | 2022-02-04 |  | 2022-02-10 | 2022-02-10 |  | 2022-02-12 | 2022-02-14 | 125 | 2022-03-23 |  | 2022-03-21 | 2022-03-24 | 2022-03-24 | 2022-03-24 | JOHN & DONNA NELSON | 530-677-7274 | NelsonOutWest@att.net |  | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 503 | 38.6551 | -120.522 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
644 | 041-021-013 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4461 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4027.41 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 2 | 2 | 3 | 0 | 0 | 1 | 0 | 8 |  |  | 6 | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-20 | Bio Monitoring Needed for Debris AND Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-04 | 2021-11-05 |  | 11.5 SPOKE WITH RICHARD. HE SAID OK. PLEASE CALL IN ADVANCE. HE OWNS TANKS AND WOULD LIKE TO KEEP THEM. JC |  |  |  | 2021-11-10 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Re-scrape | 2022-02-09 | 2022-02-17 | Approved | 2021-12-03 | 2021-12-13 | Re-scrape | 2022-01-25 | 2022-02-02 | Soil Boring |  |  |  | 2022-02-19 | 2021-12-03 | Do Not Assess | 0 | [8 empty] | 2022-03-14 |  |  | 2022-03-16 | 2022-03-16 | 2022-03-16 | RICHARD LOWER & MARY COOK | 530-350-0999 | SCOOTER1956@GMAIL.COM |  | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 507 | 38.6529 | -120.5173 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
645 | 041-021-018 | Tree Only ROE (no qualifying debris) | Withdrawn | Needs Assessment | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 041-021-018 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4120.72 | 2022-02-28 |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | [7 empty] | 2021-12-11 | No | [6 empty] | 2021-12-07 | Bio Monitoring Needed for Debris AND Trees | 2022-02-15 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | FALSE | [33 empty] | Ok to Assess | [15 empty] | Douglas Cope | 707-628-1639 | drc2@aol.com |  |  | 38.648 | -120.513 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
646 | 041-021-022 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 8580 | Big Canyon Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4211.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2022-03-08 | POSITIVE | 2021-10-30 | 2021-10-30 | -89 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-01-10 | 2021-11-18 | 2021-11-19 |  | 11.19 NO ANS LEFT VM JC 11.19 SPOKE WITH DON HER SAID OK BUT PLEASE CALL IN ADVANCE. OWNS PROPANE TANK, PLEASE REMOVE TANKS. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 4 | 2021-12-06 | 2021-12-14 | 7 | Re-scrape |  |  |  | 2022-01-31 | 2022-02-08 | Approved | [6 empty] | 2022-02-09 | 2022-01-19 | No | 0 | [8 empty] | 2022-03-14 |  |  | 2022-03-17 | 2022-03-17 | 2022-03-17 | DON & DANA ELLIS | 530-409-4884 | don-ellis@comcast.net | Access Issues Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 506 | 38.6522 | -120.5052 | Caldor | DR-4619 | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
647 | 041-021-023 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 2075 | Backwoods Trail |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4015.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | Yes | No | Yes | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-12-11 | 2021-12-11 | 13 | 2021-11-18 | Bio Monitoring Needed for Trees, not Debris | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I |  | FALSE | [10 empty] | 2021-12-11 | 2022-01-21 |  | 12.11 SPOKE WITH STEVE HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 KIMBERLY SIAD OK. JC |  |  |  | 2022-01-25 |  | 2022-01-26 | 2022-01-26 |  |  | 4 | 2022-01-31 | 2022-02-08 | 7 | Re-scrape |  |  |  | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 |  | Do Not Assess | 0 | [8 empty] | 2022-03-23 |  |  | 2022-03-24 | 2022-03-24 | 2022-03-24 | STEVE AND KIMBERLY GUGGIANA | 925-784-3412 | gugg3476@yahoo.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 510 | 38.6525 | -120.5097 | Caldor | DR-4619 | Residential | No | 2021-10-23 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
648 | 041-021-024 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4631 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4093.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Milk Run | TRUE | 2021-12-07 | 2021-12-07 | FALSE | No |  |  | No |  | No | Yes | Yes | No | Yes | No | FALSE | TRUE | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 7 |  |  | 4 | TRUE | No |  |  | 2022-01-20 | Yes | 2022-01-20 | 2022-01-25 | NEGATIVE |  |  |  | 2021-12-10 | No Bio Monitoring Needed for Debris or Trees | 2022-01-27 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-02-01 | 2022-02-02 |  | 02/02/22 SPOKE WITH STEFAN HE SAID OK. PLEASE CALL IN ADVANCE. REMOVE ALL PROPANE TANKS. JC 02/18/22 NO ANS KEFT VM AND TEXT ABT CONEX BOX ON PROPERTY. JC |  |  |  | 2022-02-09 |  | 2022-02-11 | 2022-02-11 |  |  | 3 | 2022-02-15 | 2022-02-23 | 7 | Approved | [12 empty] | 2022-02-25 |  | Do Not Assess | 0 | [8 empty] | 2022-03-14 |  |  | 2022-03-17 | 2022-03-17 | 2022-03-17 | Stefan Stafford | 916-716-4517 | stefan_satafford@hotmail.com |  | Debris Crew Leader/Crew# Eric Rocha / #503 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 503 | 38.6505 | -120.5096 | Caldor | DR-4619 | Residential | No | 2021-11-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
649 | 041-021-025 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 2125 | Backwoods Trail |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4089.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | Yes | No | No | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-06 | 2022-01-21 |  | 12.07 SPOKE WITH MICHAEL HE SAID OK. BUT HE WOULD LIKE TO BE CALLED BEFORE ANYONE GOES TO HIS PROPERTY. HE OWNS THE PROPANE TANK AND DOES NOT WANT IT REMOVED. JC 01/21/22 MICHAEL SAID OKAY. JC |  |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 |  |  | 4 | 2022-01-29 | 2022-02-07 | 6 | Re-scrape |  |  |  | 2022-02-14 | 2022-02-22 | Approved | [6 empty] | 2022-02-24 | 2022-01-19 | No | 0 | [8 empty] | 2022-03-23 |  |  | 2022-03-24 | 2022-03-24 | 2022-03-24 | Michael Leach | 510-207-8630 | mwleach75@gmail.com | Septic Well | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 510 | 38.6486 | -120.5097 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
650 | 041-532-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 7280 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3904.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-21 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-21 | No Activity/Nest Building Removed |  |  | Complete | No |  | Yes | 2022-03-04 | TRUE |  | Class III | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-21 | 2022-01-21 | 2022-03-09 | 12.22 SPOKE REBECCA SHE SAID OK BUT PLEASE CALL IN ADVANCE. THEY OWN PROPANE TANK PLEASE REMOVE. JC 01/21/22 REBECCA SAID OK. JC 03/09/22 SPOKE WITH REBECCA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Approved | [12 empty] | 2022-02-17 | 2022-01-25 | Yes | 22 | [14 empty] | GARCIA MARCIAL C JR & REBECCA | 408-489-6837 | BECCA.GARCIA72@GMAIL.COM | Other | Debris Crew Leader/Crew# Birdie Bell /#504 Debris Crew WO# Refer to IAP 02/02 TO 02/06 Crew 501 | 38.6397 | -120.5183 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-07T20:41:28Z | FALSE
651 | 041-532-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 7281 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3869.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 3 | 1 | 2 | 4 | 14 |  |  | 5 |  | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-30 | Bio Monitoring Needed for Debris AND Trees | 2021-12-21 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Survey Needed | Yes | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-21 | 2022-01-06 |  | "12.23 LINE BUSY. SENT TEXT JC 12.28 PHONE OUT OF SERVICE SENT EMAIL. JC 01/06/22 Paul called with updated phone number and said ok for debris removal. Please call 414 308-3353 in advance JC" |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 6 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-25 | Yes | 19 | [14 empty] | Paul Lorenz | 510-688-2954 updated number 414 308-3353 | ratzcycles@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 503 | 38.6392 | -120.5184 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-07T20:43:08Z | FALSE
652 | 041-532-015 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7238 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3882.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-15 | Bio Monitoring Needed for Trees, not Debris | 2021-10-15 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-28 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-26 | 2022-02-08 | 10.26 SPOKE TO STEVEN AND HE SAID OK PF 01/26/22 SPOKE WITH STEVEN HE SAID OK. VENDOR WILL HANDLE PROPANE. JC 02/08/22 HO C/B AND SAID IF CREW CALLS AND CANNOT REACH HIM, TO CONTINUE OPERATIONS WITHOUT CONTACT. ﻿JC |  |  |  | 2021-10-29 |  | 2021-11-01 | 2021-11-01 |  |  | 7 | 2021-11-09 | 2021-11-17 | 7 | Approved | [12 empty] | 2021-11-18 | 2021-10-27 | Yes | 66 | 2022-02-26 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-05 | 2022-03-07 | 66 | 2022-03-10 |  | 2022-03-08 | 2022-03-11 | 2022-03-11 | 2022-03-11 | STEVEN PUCCI | 916-718-3817 | STEVENPUCCI@YAHOO.COM |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 502 | 38.6391 | -120.52 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
653 | 041-533-001 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 5180 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3879.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | [5 empty] | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-02-21 | 02/21/22 NO ANS LEFT V. & TEXT. JC 02/21/22 ANTHONY C/B HE SAID OK FOR TREE REMOVAL, ANS NO NEED TO CALL BEFORE GOING OUT. JC 03/09/22 HO TEXT SAYING OK FOR TREE REMOVAL AND NO NEED TO CALL ANYMORE. JC | [27 empty] | 2022-01-22 | Yes | 6 | [14 empty] | CUELLAR ANTHONY & CHERIE | 925-285-6081/925-963-3512 | tony545@comcast.net, cschaeffer4603@gmail.com |  |  | 38.6393 | -120.517 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:41:56Z | FALSE
654 | 041-533-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5166 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3857.84 |  |  |  |  | FALSE |  |  | N/A |  |  |  |  | Bridge | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-20 | Bio Monitoring Needed for Debris AND Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-04 | 2021-11-06 | 2022-01-18 | 11.5 NO ANS LEFT VM. JC 11.6 SPOKE WITH ANTHONY, HE SAID OK. BUT PLEASE CALL IN ADVANCE. THE VENDOR REMOVED THE PROPANE TANK. JC 01/18/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 01/18/22 ANTHONY C/B HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Approved | [12 empty] | 2021-11-24 | 2021-12-04 | Yes | 44 | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  | 2022-01-24 | 2022-01-25 | 44 | 2022-01-31 |  | 2022-01-25 | 2022-02-16 | 2022-02-16 | 2022-02-17 | CHERIE & ANTHONY CUELLAR | 925-285-6081 | cschaeffer4603@gmail.com |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 502 | 38.639 | -120.5169 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 3
655 | 041-533-003 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 5156 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3874.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-02-09 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-03-01 | 03/01/22 NO ANS LEFT VM & TEXT. JC 03/01/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2021-12-07 | Yes | 76 | [14 empty] | Stephen & Elizabeth Ryan | 530-919-0590 | lcryan362@gmail.com |  |  | 38.6386 | -120.517 | Caldor | DR-4619 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-07T20:42:14Z | FALSE
656 | 041-533-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5144 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3889.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 2 | 0 | 0 | 1 | 5 |  |  | 5 |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-01 | Yes | 2022-03-03 | TRUE |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-03 | 2021-12-06 | 2022-03-09 | 12.06 NO ANS LEFT VM AND TEXT. JC 12.06 SPOKE WITH ROBERT HE SAID OK BUT CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 03/09/22 NO ANS LEFT VM & TEXT JC. 03/09/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-18 |  | 2022-01-18 | 2022-01-18 |  |  | 6 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-20 | Yes | 29 | [14 empty] | Robert Liebe | 209-781-5659 | robertcharlesl66@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 515 | 38.6383 | -120.517 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T20:42:31Z | FALSE
657 | 041-541-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 7266 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3832.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | [7 empty] | 2021-12-06 | No | [6 empty] | 2021-12-06 | Bio Monitoring Needed for Debris AND Trees | 2022-02-01 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No |  |  |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-16 |  |  | 2022-02-21 | 02/21/22 SPOKE WITH BRADLEY HE SAID OK BUT PLEASE CALL IN ADVANCE. JC | [27 empty] | 2022-01-18 | Yes | 5 | [14 empty] | Bradley Withington | 916-633-4834 | bradwithington@att.net | Vehicles Onsite |  | 38.6385 | -120.5187 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:42:45Z | FALSE
658 | 041-541-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 7258 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3830.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 4 |  |  | 4 |  | Yes | Take |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2021-12-08 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-11 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-08 | 2021-12-09 | 2022-03-08 | 12.09 CALLER NOT TAKING CALLS AT THIS TIME. SENT TEXT AND EMAIL. JC 12.09 SPOKE WITH BRADLEY HE SAID OK BUT PLEASE CALL IN ADVANCE. REMOVE PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 SPOKE WITH BRADLEY HE IS GOT A PHONE CALL FROM CREW LEADER (BIRDIE) AND WAITING TO BACK ABT 5TH WHEEL. JC 03/15/22 SPOKE WITH BRADLEY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-18 | Yes | 13 | [14 empty] | Bradley Withington | 916-633-4834 | bradwithington@att.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson / #507 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 507 | 38.6383 | -120.519 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:42:58Z | FALSE
659 | 041-541-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7250 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3828.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | TRUE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2021-12-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-26 | Active Nest | 650 | 2022-06-08 | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-12-08 | 2022-01-21 | 2022-03-16 | "12.09 NO ANS & NO VM SENT EMAIL & TEXT. JC 12.09 SPOKE WITH JANISE SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 JANISE SAID OKAY. JC" 03/15/22 EMAIL FROM JANISE INQUIRING STATUS. I CALLED JANISE WITH UPDATED STATUS REPORT. SHE WAS VERY UPSET AND BECAME RUDE OFFENSIVE STATEMENTS. SHE INFORMED ME THAT SHE CALLED STATE TO BE PRIORITIZED FOR COMPLETION BECAUSE SHE IS CURRENTLY LIVING IN AN UNSAFE AREA. JC 3/16/2022﻿ - Dave Teeter spoke with owner. She would like parcel returned in 3 weeks as she is returning to live on the parcel. |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Re-scrape |  |  |  | 2022-02-17 | 2022-02-25 | Approved | [6 empty] | 2022-03-01 | 2022-03-16 | Yes | 16 | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  | 2022-03-26 | 2022-03-28 | 16 | 2022-04-07 |  | 2022-03-30 | 2022-04-07 | 2022-04-07 | 2022-04-07 | Janise Twomey | 530 663-6901 NEW NUMBER | grizzlygirltwoyou@gmail.com | Septic | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 507 | 38.6381 | -120.5193 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T23:48:44Z | FALSE | 0
660 | 041-541-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 7240 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3838.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  |  |  | FALSE |  | Class III | None | TRUE | [12 empty] | 2022-02-01 | 02/01/22 NO ANS LEFT VM & TEXT. JC 02/01/22 NANCY C/B SHE SAID OK. NO PROPANE TANK ON PROPERTY. JC | [27 empty] | 2021-12-07 | Yes | 5 | [14 empty] | Robert & Nancy Bishop | 925-899-2443 | nsbishop@gmail.com |  |  | 38.638 | -120.52 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:43:36Z | FALSE
661 | 041-541-012 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 7200 | Grizzly Creek Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3859.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 | 2021-12-06 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 |  |  |  |  | Yes |  |  | 2021-12-07 | No | [6 empty] | 2021-12-06 | Bio Monitoring Needed for Debris AND Trees | 2022-02-01 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No |  | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-03-26 | 11.18 SPOKE WITH STEPHEN HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 02/02/22 NO ANS LEFT VE & TEXT. JC 02/02/22 SPOKE WITH STEPHEN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 03/23/22 VERINA CALLED FOR STATUS. JC 03/36/22 SPOKE WITH STEPHEN HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-07 | Yes | 20 | [14 empty] | STEPHEN C. & VERINA K. PIETRZYK | 530-417-6333 | STEVENPIETRZYK@ROCKETMAIL.COM |  |  | 38.6383 | -120.5216 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
662 | 041-541-018 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5085 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3797.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-12-14 | NEGATIVE |  |  |  | 2021-11-11 | Bio Monitoring Needed for Debris AND Trees | 2021-11-22 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-26 | Yes | 2022-03-29 | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-11-22 | 2021-11-17 |  | 11.17 SPOKE WITH TIFFANY SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Approved | [12 empty] | 2021-12-14 | 2021-12-01 | Yes | 11 | [14 empty] | TIFFANY A. DEVOS | 530-503-5163 | TRICH7283@YAHOO.COM |  | Debris Crew Leader/Crew# Glenn Adams/#501 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 501 | 38.6376 | -120.5196 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:44:03Z | FALSE
663 | 041-541-022 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 5129 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3817.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2022-01-25 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-02-16 | No |  | FALSE |  | Class II | Covered under suspension | TRUE | [12 empty] | 2022-02-01 | 02/01/22 SPOKE WITH SHERRON SHE GAVE PRE APPROVAL. NO PROPANE TANKS ON PROPERTY. JC | [27 empty] | 2022-01-21 | Yes | 61 | [7 empty] | 3 | [6 empty] | Sherron Patricia Burleson | 530-417-7728 | burlesonsherron@yahoo.com |  |  | 38.6382 | -120.5182 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T20:44:17Z | FALSE
664 | 041-561-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 4987 | Parkside Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3797.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Debris AND Trees | 2021-12-07 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-07 | 2022-01-22 | 2022-03-01 | 12.08 NO ANS LEFT VM & TEXT. JC 12.08 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE, VENDOR WILL HANDLE PROPANE TANK. JC 01/22/22 NO ANS LEFT VM & TEXT. JC 01/22/22 MICHAEL GAVE CONSENT VIA TEXT. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/01/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-02-11 |  | 2022-02-12 | 2022-02-12 |  |  | 1 | 2022-02-14 | 2022-02-22 | 7 | Approved | [12 empty] | 2022-02-24 | 2021-12-01 | Yes | 12 | [14 empty] | Michael Griffith | 530-409-6021 | mikegriffith903@gmail.com |  | Debris Crew Leader/Crew# Zara Armani/ #507 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 507 | 38.6369 | -120.5196 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T20:44:31Z | FALSE
665 | 041-562-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Hold | 4990 | Parkside Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3854.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-03-02 | Yes | 2022-03-03 | TRUE |  | No | None | TRUE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-03-09 | 03/09/22 NO ANS LEFT VM & TEXT. JC 03/09/22 MIKE GAVE CONSET VIA TEXT. JC | [27 empty] | 2022-01-18 | Yes | 66 | [14 empty] | Michael Griffith | 530-409-6021 | mikegriffith903@gmail.com | Septic |  | 38.6368 | -120.5188 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:44:46Z | FALSE
666 | 041-562-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 4995 | Storybook Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3888.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2022-02-02 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-28 | Yes | 2022-03-29 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2022-02-02 | 2022-02-04 |  | 02/04/22 TRIED CALL PHONE NUMBER ON FILE. PHONE NUMBER OUT OF SERVICE. SENT EMAIL. JC 02/04/2022 - Left Voicemail for Kenny @ 9:48 AM AND SENT TEXT- MP 02/04/2021: Owner approved mobilization via text - MP 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 02/14/22 KENNETH TEXT BACK. HE SAID REMOVE PROPANE TANK. JC |  |  |  | 2022-02-04 |  | 2022-02-08 | 2022-02-08 |  |  | 3 | 2022-02-10 | 2022-02-18 | 7 | Approved | [12 empty] | 2022-02-21 | 2022-01-21 | Yes | 33 | [14 empty] | Kenneth Hooley | 530-417-2148 | khooleyrok@gmail.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 504 | 38.637 | -120.5178 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-07T20:45:00Z | FALSE
667 | 012-036-020_24 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 24 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-02 | 2021-11-02 | 7 | 2021-10-23 | Bio Monitoring Needed for Debris AND Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-11-02 | 2021-10-29 |  | 10.29 Homeowner acknowledged debris removal (owns #2) RCV |  |  |  | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
668 | 012-036-020_25 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 25 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-23 | NEGATIVE |  |  |  | 2021-10-21 | Bio Monitoring Needed for Debris AND Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-23 | 2021-11-06 |  | 10.29 voicemail left RCV 11.5 NO ANS. LEFT VM. JC 11.6 NO ANS LEFT VM JC NO EMAIL ON FILE. JC SENT TO RICHARD. JC | 3 | Kendall Wilson | 2021-11-06 | 2021-11-06 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Janice F. Daniels Reyes | (707) 337-2038 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
669 | 012-036-020_26_27 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 26_27 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | FALSE | [10 empty] | 2021-10-25 | 2021-10-29 |  | 10.29 Contacted Homeowner, acknowledged debris removal start RCV |  |  |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Becky J. Halsch | (707) 295-6648 | cahalschs@comcast.net |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
670 | 012-036-020_28 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 28 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-02 | 2021-11-02 | 7 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-02 | 2021-11-05 |  | 11.5 SPOKE WITH DAVID. HE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | David Johnson | 707 350 3633 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-10-21 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
671 | 012-036-020_29 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 29 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-03 | 2021-11-03 | 8 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-03 | 2021-11-08 |  | 11.5 NO ANS. MAILBOX FULL. JC 11.6 NO ANS. MAILBOX FULL. JC 11.8 NO ANS. MAILBOX FULL. JC 11.8 SENT EMAIL. JC EMAIL REJECTED. SENT TO RICHARD. JC | 4 | Kendall Wilson |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Michael/Ruth Irwin | (707) 480-6542 | mdgsb@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
672 | 012-036-020_30 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 30 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-02 | 2021-11-02 | 7 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-02 | 2021-11-09 |  | 11.9 NO ANS LEFT VM. JC 11.9 SPOKE WITH JOHN HE SAID PROPERTY IS CLEARED. JC |  |  |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
673 | 012-036-020_31 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 31 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-03 | 2021-11-03 | 8 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-03 | 2021-11-05 |  | 11.5 SPOKE WITH CHRISTINA SHE SAID OK. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2021-12-21 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Gust/Christina Jordan | (559) 563-2950 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
674 | 012-036-020_32 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 32 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-27 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-27 | 2021-11-06 |  | 11.5 NO ANS. LEFT VM. JC 11.6 SPOKE WITH TODD HE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Todd/Janna Black | (707) 296-0691 | toddwilliamblack@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
675 | 012-036-020_33 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 33 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-25 | 2021-10-29 |  | 10.29 Contacted homeowner via text message, acknowledged debris removal start RCV |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Tom/Linda Reedy | (707) 350-2671 | reedy97@att.net | Vehicles Onsite | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
676 | 012-036-020_34 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 34 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-19 | 2021-10-23 | POSITIVE | 2021-11-05 | 2021-11-05 | 10 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-05 | 2021-11-08 |  | 11.5 The phone is disconnected. Sent email to Richard. JC 11.8 Will proceed under the overall APN per Kendall Wilson | 2 | Kendall Wilson |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Robert Swim | (707) 994-1753 |  | Other Vehicles Onsite | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-21 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
677 | 012-036-020_35 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 35 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-04 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-04 | 2021-11-03 |  | 11.03 Contacted overall owner of the MHP who claims ownership over the bay. Acknowledged debris removal |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Re-scrape | 2022-01-06 | 2022-01-14 | Approved |  |  |  | 2022-01-17 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-02-18 | 2022-02-18 | 2022-03-07 |  |  |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
678 | 012-036-020_36 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 36 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-03 | 2021-11-03 | 8 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-03 | 2021-11-04 |  | 11.4 SPOKE WITH OWNER, SAID OK. PLEASE CALL IN ADVANCE. JF |  |  |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2021-11-30 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Dillon Family Trust | (650) 867-2504 | mottly1@yahoo.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
679 | 012-036-020_37 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 37 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-04 | 2021-11-04 | 9 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-11-06 | 2021-11-10 |  | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH ﻿VIVIAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. PF |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2021-12-21 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Vivian Ferreira | (707) 938-8070 |  | Other Septic | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
680 | 012-036-020_38 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 38 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-04 | 2021-11-04 | 9 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-11-04 | 2021-11-09 |  | 11.9 NO ANS LEFT VM. JC 11.9 Spoke with bay owners brother, acknowledged debris removal start RCV |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Margaret Capolungo | 925 354-6477 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
681 | 012-036-020_39 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 39 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-09 | 2021-11-09 | 12 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-09 | 2021-11-09 |  | 11.6 SPOKE WITH ROBERT HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Approved | [12 empty] | 2022-02-14 | 2021-11-09 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-03 | 2022-03-03 | 2022-03-07 | Robert Stinson | 360 620-1434 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-12-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
682 | 012-036-020_40 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 40 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-10-21 | Yes | 2021-10-22 | 2021-10-28 | POSITIVE | 2021-11-08 | 2021-11-08 | 8 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-08 | 2021-11-09 |  | 11.9 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2022-02-14 | 2021-11-09 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-03 | 2022-03-03 | 2022-03-07 | James A. Flint | (208) 506-0422 | jaflint9231@gmail.com |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
683 | 012-036-020_42 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 42 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-26 | NEGATIVE |  |  |  | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-10-26 | 2021-11-09 |  | 11.9 Mail box full RCV GREENLIGHT PER RVC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Johnny Self | 707-496-6168 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | No | 2021-11-08 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
684 | 012-036-020_43 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 43 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 5 |  |  |  | TRUE | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-25 | POSITIVE | 2021-11-06 | 2021-11-06 | 10 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-06 | 2021-11-08 |  | 11.8 NO ANS LEFT VM. JC 11.8 SPOKE WITH DEREK LEWIS HE SAID OK. PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Derek Lewis | 707 461-9025 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-12-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
685 | 012-036-020_45 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 45 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-06 | 2021-11-06 | 10 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-06 | 2021-11-10 |  | 11.10 SPOKE WITH RONALD HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE TAKE PROPANE TANKS. JC |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Ronald/Gael Thornton | (707) 530-6994 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
686 | 012-036-020_46 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 46 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-11-06 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | POSITIVE | 2021-11-06 | 2021-11-06 | 10 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-06 | 2021-11-10 |  | 11.10 PHONE BUSY. JC 11.10 SPOKE WITH DEBORAH SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-03-07 | Deborah Havstad | (707) 494-1944 | dhavstad@yahoo.com | Other | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential | Yes | 2021-10-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
687 | 012-036-020_47 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 47 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-23 | POSITIVE | 2021-11-08 | 2021-11-08 | 11 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-08 | 2021-11-08 |  | 11.8 Made contact with the owner and approved of removal. Would like to be called RCV |  |  |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-09 | 2021-12-17 | Approved | [6 empty] | 2021-12-20 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-30 |  |  | 2021-12-30 | 2021-12-30 | 2022-03-07 | Mark Sanchez | (559) 899-6407 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
688 | 012-036-020_48 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16425 | Dam Road | 48 | Clearlake | Lake |  | Mobile Home Park | [5 empty] | 1387.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-23 | POSITIVE | 2021-11-09 | 2021-11-09 | 12 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-10-22 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [10 empty] | 2021-11-09 | 2021-11-09 |  | 11.9 SPOKE WITH ELIZABETH SHE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-09 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2022-03-07 | Elizabeth A. Turner | 760 774-5053 |  |  | "Debris Crew Leader/Crew# Birdie Bell /#201-202 Debris Crew WO# Refer to IAP 11/15 to 11/17 Crew 201-202 | 38.9236 | -122.6052 | Cache |  | Residential |  | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
689 | 041-682-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5124 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3795.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-22 | 2022-01-22 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 5 |  |  |  | TRUE | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-17 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2022-01-22 | 2022-01-14 | 2022-03-01 | "01/14/22 NO ANS LEFT VM & TEXT. JC 01/14/22 HO GAVE CONSENT VIA TEXT for 5134 and 5124. JC" 03/01/22 SPOKE WITH DAN HE SAID OK. JC |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 13 | 2022-02-16 | 2022-02-24 | 7 | Approved | [12 empty] | 2022-02-25 | 2021-11-18 | Yes | 7 | 2022-03-21 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-25 | 2022-03-26 | 7 | 2022-03-30 |  | 2022-03-28 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Daniel C. Jose | 916-622-7030 | dcjose2010@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 501 | 38.6348 | -120.535 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
690 | 041-021-017 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4621 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4036.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | POSITIVE | 2021-11-15 | 2021-11-15 | 5 | 2021-11-12 | Bio Monitoring Needed for Trees, not Debris | 2021-11-15 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No |  | No |  |  |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-15 | 2021-11-17 | 2022-01-29 | 11.16 NO ANS LEFT VM JC 11.17 NO ANS. UNABLE TO LEAVE MESS. SENT EMAIL. JC 11.17 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JAMES C/B SAID VENDOR WILL HANDLE PROPANE. JC 01/28/22 NO ANS LEFT VM & TEXT. JC 01/29/22 NO AND LEFT VM & EMAIL. JC 01/29/22 HO C/B SAID DO NOT CUT THE HUGH OAK TREE AT THE HOUSE/GATE. ON THE RIGHT SIDE AS YOU WALK UP TO THE YARD. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-18 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Soil Boring | 2022-01-11 | 2022-01-19 | Approved | [9 empty] | 2022-01-20 | 2021-11-30 | Yes | 972 | 2022-02-09 |  | 2022-02-26 | 2022-02-26 |  | 2022-03-19 | 2022-03-21 | 972 | 2022-03-30 |  | 2022-03-25 | 2022-03-31 | 2022-03-31 | 2022-03-31 | JAMES E & LORRI A STRINGFIELD | 530-903-6120 | YOGADAD@SBCGLOBAL.NET | Vehicle on site Septic | "Debris Crew Leader/Crew# Justin Romero /#502 Debris Crew WO# Refer to IAP 11/20/2021to 11/24/2021 Crew 502 | 38.6482 | -120.5153 | Caldor | DR-4619 | Residential | No | 2021-09-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 21
691 | 041-021-036 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Tree Removal in Progress | Next Step: N/A | TREE ONLY ROEs | ELDT 1a | 041-021-036 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4170.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-02-24 | 02/22/22 NO ANS LEFT VM & TEXT. JC 02/23/22 NO ANS LEFT VM & EMAIL. JC 02/24/22 SPOKE WITH LAURIE SHE SAID OK. JC | [27 empty] | 2022-03-24 | Yes | 208 | 2022-03-30 |  | 2022-04-06 | 2022-04-06 |  |  |  | 208 | [6 empty] | Laurie Ann Brady | 530-622-0952 | lauriebscraps@yahoo.com |  |  | 38.6445 | -120.5083 | Caldor | DR-4619 | Residential | No | 2021-11-23 | ROE Verified | Central Division | 2022-04-07T00:09:12Z | FALSE
692 | 041-040-042 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Tree Felling in Progress | Next Step: N/A | TREE ONLY ROEs | Tree Crew ELD 6 | 041-040-042 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3805.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-27 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-15 | Yes | 2022-03-15 | TRUE |  | Class II | Covered under suspension | TRUE | [12 empty] | 2022-03-29 | "3.25 NOT AVILABLE NO V/M. SENT TEXT PF 3.26 NOT AVAILABLE NO V/M SENT ANOTHER TEXT. THERE'S NO EMAIL ON FILE PF 3.28 Spoke to Charles and he's concerned about the process of how his trees was determined hazard and wants a representative to call him before he consents to proceed. PF Sent email to MP." (Pending Rep) 3.29 Sent text to HO per his suggestion if the rep couldn't reach him, since he's having phone issues. He has no email. PF 3.29 Ho c/b and said he spoke to the Rep and all's good. Its ok to proceed. PF | [27 empty] | 2022-04-08 | Yes | 1591 | 2022-03-30 | [6 empty] | 772 | [6 empty] | Charles Vidmar | 916-221-2194 | none |  |  | 38.6338 | -120.5285 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-08T18:11:52Z | FALSE
693 | 041-641-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4960 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3859 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-19 | Yes | 2021-10-20 | 2021-10-25 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-30 | 2021-11-03 | 2022-01-11 | 11.02 Homeowner contacted by TFL, acknowledged start of debris removal RCV 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 1.11 Homeowner ﻿acknowledged start of hazard tree removal RCV |  |  |  | 2021-11-04 |  | 2021-11-06 | 2021-11-06 |  |  | 3 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-06 | Yes | 26 | 2022-01-12 |  | 2022-01-12 | 2022-01-12 |  | 2022-01-15 | 2022-01-21 | 26 | 2022-02-01 |  | 2022-01-22 | 2022-02-04 | 2022-02-04 | 2022-02-04 | Sean and Cortney Lloret | 916-271-2786 | chiva1804@gmail.com | Septic Safety Concerns | "Debris Crew Leader/Crew# Matthew Dorenzo/505 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 505" | 38.638 | -120.5405 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
694 | 041-642-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4777 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3835.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-18 | 2021-11-17 |  | 11.17 SPOKE WITH MARILYN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANKS. JC |  |  |  | 2021-11-24 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape |  |  |  | 2022-01-18 | 2022-01-26 | Approved | [6 empty] | 2022-01-27 | 2022-02-12 | Yes | 39 | 2022-02-12 |  | 2022-02-14 | 2022-02-14 |  | 2022-02-17 | 2022-02-18 | 39 | 2022-02-21 |  | 2022-02-19 | 2022-03-01 | 2022-03-01 | 2022-03-01 | William & Marilyn Brown | 530-919-3187 | marlbrown@hotmail.com | Safety Concerns Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 509 | 38.6376 | -120.5383 | Caldor | DR-4619 | Residential | Yes | 2021-11-04 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
695 | 041-642-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4945 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3839.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 5 |  |  | 2 |  | No |  |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-12 | Bio Monitoring Needed for Debris AND Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-21 | No |  | TRUE |  | Class III | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-12 | 2021-11-16 | 2022-04-07 | 11.15 NO ANS LEFT VM. JC 11.16 NO ANS LEFT VM. JC 11.16 SENT EMAIL JC 11.16 SPOKE WITH MRS. BAUMER SHE SAID OK PLEASE CALL IN ADVANCE. PLEASE REMOVE SMALL PROPANE TANKS. JC 4.7 NO ANS. NO V/M. RECORDING- VERIZON SAYING PLS.CHK #- SENT A TEXT AND EMAIL PF 4.7 @1.11 rec'd a text back from DEREK BAUMER SAYING I ACKNOWLEDGE. PF |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | 2022-02-07 | 2022-02-15 | Approved | 2022-01-19 | 2022-01-27 | Soil Boring | [6 empty] | 2022-02-16 | 2021-11-08 | Yes | 15 | [14 empty] | DEREK BAUMER | 707-564-5876 | CHRISTINETEFFT@ATT.NET | Vehicles on site Septic | Debris Crew Leader/Crew# Tony Ruiz/#507510 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 510 | 38.6387 | -120.5394 | Caldor | DR-4619 | Residential | Yes | 2021-10-23 | ROE Verified | Central Division | 2022-04-07T20:14:42Z | FALSE
696 | 041-642-007 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4981 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3854.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [12 empty] | 2022-01-22 | 01/22/22/NO ANS LEFT VM & TEXT. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-01-27 | Yes | 39 | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  | 2022-01-31 | 2022-02-01 | 39 |  |  | 2022-02-04 |  | 2022-02-04 | 2022-02-04 | Charles & Chau Sherwood | 530-499-0522 , 530-499-0521 | charlessherwoody@gmail.com |  |  | 38.6378 | -120.5392 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
697 | 041-643-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Tree Removal in Progress | Next Step: N/A | TREE ONLY ROEs | ELDT 1b | 4810 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3801.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-07 | Bio Monitoring Needed for Trees, not Debris | 2022-02-09 | Arch Monitoring Needed for Trees, not Debris |  | 2022-04-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-03 | TRUE |  | Class I | Covered under suspension | FALSE | [12 empty] | 2022-03-26 | 03/25/22 NO ANS LEFT VM & TEXT JC 03/26/22 NO ANS LEFT VM & EMAIL. JC 03/26/22 BETTY C/B SHE SAID OK FOR TREE REMOVAL. NO NEED TO CALL IN ADVANCE. JC | [27 empty] | 2022-01-14 | Yes | 61 | 2022-04-05 |  | 2022-04-07 | 2022-04-07 |  |  |  | 61 | [6 empty] | Betty J Benefield | 626-797-6435 | chanteebenefield@gmail.com |  |  | 38.6389 | -120.5375 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
698 | 100-060-035 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 25390 | Pineview Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2365.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 4 |  |  |  | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-20 | 2021-10-28 |  | "10.27 LINE BUSY NO ANS.PF 10.28 Line 'temporarily unavailable' RCV 10.28 SPOKE TO DAVE AND HE SAID OK BUT BE SURE TO CALL BEFORE GOING OUT HE WANTS TO BE THERE . PF" |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 8 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-20 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Marilyn Wardlow, Dave Del Porto | (530) 847-5668, (209) 470-1925(BEST #) | drdelporto@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Melanie Poole﻿/401 Debris Crew WO# Refer to IAP 10/28 to 10/30 Crew 401 | 39.1156 | -120.9677 | River | DR-4610 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
699 | 100-060-037 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 25360 | Pineview Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2371.08 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-16 | 2021-11-17 |  | "11.17 NO ANS LEFT VM. JC 11.17 SPOKE WITH DAN HE SAID OK BUT PLEASE CALL IN ADVANCE. PF" |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Approved | [12 empty] | 2021-12-06 | 2021-12-03 | No | 0 | [8 empty] | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Dan Zendner, Carol Zendner | (530) 263-4331 | Dzendner@yahoo.com | Septic | Debris Crew Leader/Crew# Dominic Uncangco /#401 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 401 | 39.1156 | -120.9663 | River | DR-4610 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
700 | 100-180-011 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 23685 | Milk Ranch Road |  | Colfax | Placer |  | Residential | [5 empty] | 2174.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 6 |  |  |  | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | POSITIVE | 2021-10-30 | 2021-10-30 | 8 | 2021-10-19 | Bio Monitoring Needed for Trees, not Debris | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2020-03-30 | 2021-10-30 | 2021-11-08 |  | 11.8 SPOKE WITH DENNIS HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT PROPANE TANK. JC |  |  |  | 2021-11-10 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-02 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Dennis Acmoody | (530) 913-8881 | Acmoodyranch@colfaxnet.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 402 | 39.0926 | -120.9805 | River | DR-4610 | Residential | Yes | 2021-10-01 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
701 | 100-180-013 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 23405 | Spring Valley Road |  | Colfax | Placer |  | Residential | [5 empty] | 1994.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 5 |  |  | 2 | TRUE | Yes | Leave |  | 2021-11-13 | Yes | 2021-11-13 | 2021-11-17 | NEGATIVE |  |  |  | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2021-11-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-18 | 2021-11-20 |  | 11.17 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.20 NO ANS LEFT VM. SENT EMAIL. JC GAVE TO RCV 11.20 WENDY RETURNED CALL SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK IS NOT BURNED AND DO NOT REMOVE. JC |  |  |  | 2021-12-03 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2021-11-16 | No | 0 | [8 empty] | 2022-01-14 |  |  | 2022-01-25 | 2022-01-25 | 2022-01-25 | Wendy Dion, Jesse Bandy | (530) 263-7342 | wendydion64@gmail.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 403 | 39.0874 | -120.9864 | River | DR-4610 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
702 | 100-180-014 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 100-180-014 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2086.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 |  |  | 2 | TRUE | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | POSITIVE | 2021-12-08 | 2021-12-08 | 2 | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | Arch Monitoring Needed for Trees, not Debris | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-12-09 | 2021-12-09 |  | 12.09 SPOKE WITH DONNA SHE SAID OK AND ADDRESS IS 23515 SPRING VALLEY ROAD. PLEASE CALL IN ADVANCE. 01/25/22 SPOKE WITH DONNA ABT PROPANE TANK SHE SAID SHE HAS TO CHECK WITH HER HUSBAND AND WILL CALL ME BACK. JC 02/14/22 NO ANS LEFT VM AND TEXT ABT PROPANE TANK. JC 02/14/22 HO C/B DONNA SAID TO LEAVE PROPANE TANK. JC |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 6 | 2021-12-20 | 2021-12-29 | 7 | Re-scrape |  |  |  | 2022-01-14 | 2022-01-24 | Approved | [6 empty] | 2022-01-26 | 2021-11-16 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | James Dion, Donna Dion | (530) 537-5404 | donnadion235@gmail.com | Keep Items Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Carla Herbst#403 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 403 | 39.0874 | -120.9845 | River | DR-4610 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
703 | 100-180-016 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 23515 | Spring Valley Road |  | Colfax | Placer |  | Residential | [5 empty] | 2147 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | Yes | No | FALSE | TRUE | 5 | 2 | 2 | 0 | 0 | 2 | 0 | 11 |  |  | 6 | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-18 | 2021-11-20 |  | 11.17 NO ANS LEFT VM. JC 11.18 NO ANS LEFT VM. JC 11.18 Sent an email RCV 11.20 UNABLE TO MAKE CONTACT VIA PH# ON FILE. JC GAVE TO RCV. 01/25/22 SPOKE WITH DONNA ABT PROPANE TANK SHE SAID SHE HAS TO CHECK WITH HER HUSBAND AND WILL CALL ME BACK. JC 01/26/22 SPOKE WITH JAMES HE SAID DO NOT REMOVE PROPANE TANK. JC | 2 | Kendall Wilson |  | 2021-11-22 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-09 | 6 | Re-scrape |  |  |  | 2022-01-14 | 2022-01-24 | Approved | [6 empty] | 2022-01-26 | 2021-11-22 | No | 0 | [8 empty] | 2022-02-14 |  |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | James Dion, Donna Dion | (530) 537-5404 | donnadion235@gmail.com | Keep Items Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Dominic Uncongco/#401 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 401 | 39.0902 | -120.9848 | River | DR-4610 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
704 | 100-180-017 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 23560 | Spring Valley Road |  | Colfax | Placer |  | Residential | [5 empty] | 2238.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | Yes | No | Yes | No | FALSE | TRUE | 3 | 2 | 0 | 2 | 1 | 4 | 0 | 12 |  |  |  | TRUE | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-30 | 2021-10-30 | 7 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-30 | 2021-11-03 |  | 11.03 Homeowner confirmed start of debris RCV |  |  |  | 2021-11-05 |  | 2021-11-06 | 2021-11-06 |  |  | 4 | 2021-11-11 | 2021-11-18 | 6 | Approved | [12 empty] | 2021-11-20 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-02 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | James Dion, Robert Dion | (530) 388-6567, (530) 263-4921 | Bob.Dion.123@gmail.com | Other Septic Vehicles Onsite | "Debris Crew Leader/Crew# Jason Lowe /#402 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 402" | 39.0914 | -120.9845 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
705 | 100-180-019 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 23780 | Spring Valley Road |  | Colfax | Placer |  | Residential | [5 empty] | 2083.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | Yes | Yes | Yes | Yes | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-02 |  | 11.2 SPOKE TO TOM AND HE SAID OK PF 11.2 Leased tank. He will contact vendor to have removed. JC |  |  |  | 2021-11-03 |  | 2021-11-05 | 2021-11-05 |  |  | 3 | 2021-11-09 | 2021-11-18 | 8 | Approved | [12 empty] | 2021-11-20 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-02 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Thomas Dunipace, Deborah Dunipace | (520) 305-8003 | tdunipace@gmail.com | Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Jason Lowe/402 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 402" | 39.0944 | -120.9831 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
706 | 100-180-023 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1720 | River View Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2380.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | Yes | No | Yes | No | No | Yes | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-09 | 2021-11-11 |  | 11.10 NO ANS LEFT VM JC 11.11 SPOKE WITH ALECIA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 3 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 2021-12-11 | Alecia Weisman, Russell Weisman | (530) 615-1720, (904) 509-7234 | alecia@yubariver.org, aleciabrantley@gmail.com | Keep Items Septic Well | Debris Crew Leader/Crew# Jason Lowe/#403 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 403 | 39.0961 | -120.981 | River | DR-4610 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
707 | 100-180-025 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 23854 | Spring Valley Road |  | Colfax | Placer |  | Residential | [5 empty] | 2018.42 |  | 2021-11-29 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | [31 empty] | 2021-11-16 | No | 0 | [14 empty] | Mike Basich, Donna Basich | (530) 401-7822 | Donnabasich@aol.com |  |  | 39.0938 | -120.9776 | River | DR-4610 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
708 | 100-190-001 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100-190-001 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 1797.33 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2021-12-20 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | FALSE |  |  |  |  | 12.14 NO ANS LEFT VM. JC 12.15SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL 530 320-9301 IN ADVANCE. JC | [27 empty] | 2022-01-03 | No | 0 | [14 empty] | James Wegman, Kathleen Dutra, Frank Dutra | 530-888-0608 | nanak@ssctv.net | Septic Vehicles Onsite |  | 39.1004 | -120.9874 | River | DR-4610 | Residential | No | 2021-12-07 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
709 | 100-190-002 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100-190-002 | No Address |  | Colfax | Placer |  | Residential | [5 empty] | 2022.64 |  | 2022-01-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-07 | No | [6 empty] | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | 2021-12-20 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 | [31 empty] | 2022-01-03 | No | 0 | [15 empty] | (650) 387-4268 | csg@guenzer.com |  |  | 39.1005 | -120.9849 | River | DR-4610 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
710 | 100-190-003 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1565 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2335.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | Yes | No | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2020-03-30 | 2021-10-29 | 2021-11-02 |  | "11.1 NO ANS LEFT MESS PF 11.2 DOUGLAS C/B AND SAID OK. PLEASE CALL IN ADVANCE. PF" 11.2 Left mess abt. tank removal. JC﻿ 11.3 VM left mess abt tank removal. JC 11.4 LEFT MESS ABT TANK. JC 11.9 VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-11 |  | 2021-11-13 | 2021-11-13 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Re-scrape |  |  |  | 2021-12-02 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-20 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | Douglas Thorley, Elizabeth Miller, Douglas Thorley | (530) 400-8815, (530) 401-1662 | dougthor@infostations.com | Septic | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 402 | 39.101 | -120.9813 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
711 | 041-483-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7127 | Quietwood Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4001.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | Yes |  | 2021-11-01 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-18 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-16 | 2021-11-03 | 2022-02-10 | 11.3 SPOKE WITH DANIEL HE SAID OK. PLEASE CALL IN ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 SPOKE WITH DANIEL HE SAID LEAVE PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC ﻿02/10/22 SPOKE WITH DANIEL HE SAID OK. JC |  |  |  | 2021-11-09 |  | 2021-11-09 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-12-06 | Yes | 21 | 2022-02-18 |  | 2022-02-18 | 2022-02-18 |  | 2022-02-25 | 2022-02-26 | 21 | 2022-03-09 |  | 2022-02-28 | 2022-03-17 | 2022-03-17 | 2022-03-17 | DANIEL & CINDY FEIS | 602-463-8774 | dteis@cox.net |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/24 To 12/01 Crew 506 | 38.6438 | -120.5222 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
712 | 041-483-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7053 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3999.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-15 | 2021-11-24 | 2021-11-29 | 2022-03-25 | 11.29 NO ANS LEFT VM. JC 11.29 SPOKE WITH VICKY SHE SAID OK BUT PLEASE CALL IN ADVANCE BECAUSE SHE WOULD LIKE TO BE THERE FOR THE REMOVAL. PLEASE REMOVE PROPANE TANKS. JC 01/18/22 NO ANS LEFT VM. JC 01/18/22 VICKY C/B SHE SAID OK. JC 03/25/22 FOLLOW UP CALL. NO ANS LEFT VM & TEXT. JC 03/25/22 SPOKE WITH VICKY SAID OK FOR TREE REMOVAL. JC |  |  | 2021-12-02 | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 4 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2021-11-10 | Yes | 50 | [14 empty] | Vicky Wallace | 530-919-1828 | vdw415@gmail.com | Septic Vehicles on site | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 502 | 38.6437 | -120.5229 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
713 | 041-484-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4837 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Commercial | [5 empty] | 4027.89 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2021-12-23 | 2021-12-23 | FALSE | No | FALSE |  | No | FALSE | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2022-01-25 | Yes | 2022-01-25 | 2022-01-28 | NEGATIVE |  |  |  | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-27 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-28 | 2022-01-29 | 2022-03-24 | 01/28/22 NO ANS LEFT VM. JC 01/29/22 NO ANS LEFT VM & EMAIL. JC 01/29/22 TALKED WITH LYNETTE SHE SAID OK. BUT PLEASE CALL HER CELL PHONE 925 381-7291 IN ADVANCE. 02/14/22 SPOKE WITH LYNETTE SHE WILL HAVE TO CHECK TO SEE IF OWNED OR RENTED. SHE WILL CALL BACK. JC 02/15/22 SPOKE WITH LYNETTE SHE SAID VENDOR HANDLING PROPANE TANK. JC 3.24 3.24 SPOKE TO DAN. THE PROPERTY USED TO BE DTATION #35. HE SAID OK PF |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 | FALSE |  | 3 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-20 | Yes | 2 | [14 empty] | Dan Dwyer & Lynette Dwyer | 530-620-4444 Dan home530 295-0566 Cell 925 381-7291 | admin@pioneerfire.org |  | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 504 | 38.6433 | -120.5215 | Caldor | DR-4619 | Commercial | Yes | 2021-12-15 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
714 | 041-484-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4847 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4019.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Yes | Take |  | 2021-11-03 | Yes | 2021-11-04 | 2021-11-09 | POSITIVE | 2021-11-15 | 2021-11-15 | 5 | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-16 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-17 | 2021-11-19 | 2022-03-31 | 11.18 NO ANS LEFT VM. JC 11.19 SPOKE WITH STEVEN HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE TAKE PROPANE TANK. JC 01/19/22 NO ANS LEFT VM & TEXT AND EMAIL. JC 01/19/22 STEVE C/B SAID OK. JC"3.31 NO ANS. LEFT MESS AND SENT TEXT PF 3.31 MR SWENSON C/B AND SAID OK TO PROCEED. PF" |  |  |  | 2021-11-22 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2022-01-19 | Yes | 12 | [14 empty] | Steven Swenson | 408-390-3048 | Stevenr.swensonlaw@yahoo.com | Vehicle on site Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/20 to 11/24Crew 506 | 38.6431 | -120.5219 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
715 | 041-484-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7126 | Capps Crossing Rd |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4022.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-14 | Bio Monitoring Needed for Debris AND Trees | 2022-02-12 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-02-26 | 02/26/22 NO ANS LEFT VM & TEXT JC 02/26/22 DEBBIE C/B SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-28 | Yes | 40 | 2022-03-15 |  | 2022-03-16 | 2022-03-16 |  | 2022-03-22 | 2022-03-23 | 40 |  |  | 2022-03-25 |  | 2022-03-25 | 2022-03-24 | Ernie Lynn Cumbra. Tr & Debra Lynn Havey-Cumbra Tr | 916-799-4870 | dcumbra@yahoo.com |  |  | 38.6428 | -120.5218 | Caldor | DR-4619 | Residential | No | 2022-01-21 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
716 | 041-485-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4889 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3994.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-24 | No |  | TRUE |  | No | None | FALSE | [13 empty] | 03/15/22 NO AND LEFT VM & TEXT PF | [27 empty] | 2021-12-18 | Yes | 4 | 2022-03-29 |  | 2022-03-29 | 2022-03-29 |  | 2022-03-31 | 2022-04-01 | 4 |  |  | 2022-04-02 |  | 2022-04-02 | 2022-04-04 | Michael Rodriguez | 530-919-5495 | irirod714@gmail.com |  |  | 38.6424 | -120.5235 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-04T16:26:39Z | FALSE | 2
717 | 041-485-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7117 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3990.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-20 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-12 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-24 | 2021-11-29 | 2022-01-13 | 11.29 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 1.13.22 Spoke to Mr. LaCoste and he said ok. Not happy that the trees weren't discussed with him but ok go ahead and do it. PF |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-11-30 | Yes | 6 | 2022-02-10 |  | 2022-02-10 | 2022-02-10 |  | 2022-02-11 | 2022-02-12 | 6 | 2022-02-18 |  | 2022-02-14 | 2022-02-19 | 2022-02-19 | 2022-02-19 | John & Patricia LaCoste | 925-229-4244 | lacostejohn@gmail.com | Other Septic | Debris Crew Leader/Crew# Christine Richter/#501 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 501 | 38.6421 | -120.5232 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
718 | 041-485-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7109 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3997.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-07 | 2021-12-08 | 2022-02-28 | 12.07 NO ANS LEFT VM &TEXT JC 12.08 NO ANS LEFT VM & SENT EMAIL JC 12.08 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/26/22 NO ANS LEFT VM & TEXT. JC 02/28/22 HO SAID OK. JC |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 6 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2021-12-02 | Yes | 36 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-19 | 2022-03-21 | 36 | 2022-03-25 |  | 2022-03-23 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Michael & Irina Rodriguez | 530-417-5687 | irirod714@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 515 | 38.6424 | -120.523 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 9
719 | 041-486-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7090 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3990.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-11-01 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-05 | 2021-11-06 | 2021-12-04 | 11.6 SPOKE DANIEL, HE SAID OK. PLEASE CALL IN ADVANCE. THE VENDOR REMOVING THE TANK. JC 12.04 SPOKE WITH DANIEL HE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 2 | 2021-11-15 | 2021-11-23 | 7 | Approved | [12 empty] | 2021-11-24 | 2021-11-04 | Yes | 17 | 2022-01-04 |  | 2022-01-08 | 2022-01-08 |  | 2022-01-08 | 2022-01-08 | 17 | 2022-01-25 |  | 2022-01-17 | 2022-01-28 | 2022-01-28 | 2022-01-28 | DANIEL & AMY TRIPP | 530-957-2224 | dtripp702@gmail.com | Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 503 | 38.6421 | -120.5239 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
720 | 041-486-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7120 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-10 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-15 | 2021-11-16 |  | 11.8 NO ANS LEFT VM. JC 11.16 SPOKE WITH LAURA HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK, VENDOR PICKED UP. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Approved | [6 empty] | 2021-12-15 | 2021-11-12 | Yes | 20 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-04 | 20 | 2022-03-10 |  | 2022-03-05 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Paul & Laura Simpson | 209-815-1170 | psimpson@comcast.net | Septic | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 501 | 38.6418 | -120.5237 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
721 | 041-491-003 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 6781 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4031.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | Yes | No | Yes | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 3 |  |  | 3 |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | POSITIVE | 2021-11-29 | 2021-11-29 | 2 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-30 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-07 | 2021-12-06 | 2022-03-31 | 12.06 ANS LEFT VM. JC 12.06 SPOKE WITH JIMMY HE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/25/22 SPOKE WITH JIMMY HE SAID HE WILL CALL VENDOR AND CALL US BACK. HE SAID HE TALKED WITH CREW ABOUT REMOVING OUT BULDING, BUT THEY WERE NOT REMOVED. JC 03/31/22 SPOKE WITH JAMMIE HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 29 | 2022-01-21 | 2022-01-31 | 7 | Soil Boring | 2022-02-04 | 2022-02-14 | Re-scrape | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-26 | Yes | 1 | 2022-04-07 |  | 2022-04-07 | 2022-04-07 |  | 2022-04-08 | 2022-04-08 | 1 | [6 empty] | Jimmie Allen | 916-430-6664 | 19jka66@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Romero/#501 Debris Crew WO# Refer to IAP 12/11to 12/15 Crew 501 | 38.6412 | -120.5258 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-09T00:27:00Z | FALSE | 1
722 | 041-402-002 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5263 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3933.71 |  | 2021-12-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | [7 empty] | Complete | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-23 | [31 empty] | 2021-12-03 | No | 0 | [14 empty] | Kevin Fedor | 408-775-2795 | kevin.fedor@aol.com |  |  | 38.6316 | -120.5445 | Caldor | DR-4619 | Residential | No | 2021-11-02 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
723 | 041-403-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5308 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3971.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-14 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-02-22 | 02/22/22 NO AND LEFT VM & TEXT. JC 02/22/22 DEAN C/B HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2021-12-07 | Yes | 69 | 2022-03-03 |  | 2022-03-05 | 2022-03-05 |  | 2022-03-11 | 2022-03-14 | 69 |  |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 | Dean & Catherine Welch | 925-428-0461 | welchcatherine@outlook.com |  |  | 38.6306 | -120.5433 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
724 | 041-403-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5286 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3966.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-03 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-04 | 2022-01-14 | 11.4 SPOKE WITH OWNER. SHE SAID OK. PLEASE CALL IN ADVANCE. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL JC 12.06 NO ANS LEFT VM AND TEXT. JC 12.06 SENT EMAIL. JC 12.07 NO ANS LEFT VM. GAVE TO RICHARD. JC 01/14/22 NO ANS LEFT VM & TEXT ABT. TREE REMOVAL. JC 01/14/22 SPOKE WITH JEAN SHE SAID OK. JC 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK JC 01/26/22 HO TEXT BACK SAID DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2021-11-09 |  | 2021-11-09 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-02 | Yes | 24 | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  | 2022-01-18 | 2022-01-19 | 24 | 2022-02-01 |  | 2022-01-25 | 2022-02-05 | 2022-02-05 | 2022-02-07 | JEAN LIM | 650-603-1254 | jeanannlim@gmail.com |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 505 | 38.6307 | -120.5438 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
725 | 041-403-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5268 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3969.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-29 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-03-22 | No |  | TRUE |  |  |  | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-02 | 2021-12-06 |  | 12.06 SPOKE WITH OSCAR HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-10 |  | 2021-12-10 | 2021-12-10 |  |  | 27 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-03-04 | Yes | 13 | [14 empty] | Oscar Espinosa | 916-595-8378 | ncsk916@gmail.com | Vehicles Onsite | Debris Crew Leader/Crew# Cynthia Sanderson /#501 Debris Crew WO# Refer to IAP 12/08 to 12/11 Crew 501 | 38.6312 | -120.5434 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
726 | 041-403-007 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5254 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3961.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-09 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Trees, not Debris | 2022-02-03 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-02-16 |  |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-02-10 | 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 SPOKE WITH CYNTHIA SHE SAID OK. NO PAROPANE TANK ON PROPERTY. JC | [27 empty] | 2021-11-29 | Yes | 1 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-19 | 2022-02-21 | 1 |  |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 | Ronald & Cynthia Tjeerdema | 707-266-4211 | thecindysue@aol.com | Septic |  | 38.6316 | -120.5433 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
727 | 041-403-009 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 9952 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3953.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | Yes | 2022-02-17 | TRUE |  | No | None | FALSE | [12 empty] | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/21 SPOKE WITH FRANK HE SAID OK FOR TREE REMOVAL. CHAIN ON GATE IS NOT LOCKED. JC | [27 empty] | 2021-11-04 | Yes | 28 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-23 | 28 |  |  | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-03-26 | FRANK SHORTT | 408-207-5556 | SHORTTFRANK42@GMAIL.COM | Other |  | 38.6321 | -120.5424 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
728 | 041-403-011 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4890 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3971.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-09 | 2021-11-10 | 2022-03-01 | 11.10 SPOKE WITH PAUL HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE SMALL PROPANE TANK BUT VENDOR WILL HANDLE LARGER TANK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/01/22 PAUL C/B HE SAID OK FOR TREE REMOVAL JC |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 52 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-16 | 2021-11-22 | No | 0 | [8 empty] | 2022-03-10 |  |  | 2022-03-11 | 2022-03-11 | 2022-03-11 | JOHNSON PAUL | 650-793-2172 | pej12378@yahoo.com | Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 506 | 38.6311 | -120.5423 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
729 | 041-404-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 7 | 10000 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3908.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-29 | Yes | 2022-04-01 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-08 | 2022-01-21 | 2022-04-04 | 12.09 SPOKE WITH DAVID HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC 4.04 SPOKE TO DAVID AND HE SAD OK PF |  |  |  | 2022-02-01 |  | 2022-02-01 | 2022-02-01 |  |  | 5 | 2022-02-07 | 2022-02-15 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-01-06 | Yes | 26 | [14 empty] | USELTON, DAVID & THOMAS | 209-602-5477 | daveuselton@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell/ #504 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 504 | 38.6325 | -120.5406 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
730 | 041-404-010 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-404-010 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3919.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-01-27 | 01/26/22 NO ANS LEFT VM & TEXT. JC 01/27/22 SPOKE WITH JEFFREY HE SAID OK BUT PLEASE CALL IN ADVANCE. ALSO PLEASE REMOVE THE DRIVEWAY THAT IS DAMAGED. VENDOR HANDLING PROPANE TANK. JC | [27 empty] | 2022-01-17 | Yes | 5 | 2022-02-04 |  | 2022-02-04 | 2022-02-04 |  | 2022-02-08 | 2022-02-09 | 5 |  |  | 2022-02-10 |  | 2022-02-10 | 2022-02-14 | Jeffrey & Sharon Messner | 209-296-4330 | jeffmessner@att.net |  |  | 38.6309 | -120.5412 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
731 | 041-404-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4893 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3926.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | POSITIVE | 2021-11-12 | 2021-11-12 | 5 | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-12 | 2021-11-12 | 2021-12-06 | 11.12 Contacted property owner, acknowledged start. Wants a call before start RCV 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.06 SPOKE WITH SHARON SHE SAID OK BUT PLEASE CALL IN ADVANCE. JC 01/14/22 NO ANS LEFT VM. JC 01/15/22 SHARON SAID OK. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-23 | Yes | 6 | 2022-01-13 |  | 2022-01-14 | 2022-01-14 |  | 2022-01-15 | 2022-01-18 | 6 | 2022-01-25 |  | 2022-01-19 | 2022-01-27 | 2022-01-27 | 2022-01-27 | Jeffrey J Messner and Sharon A Messner | 209-296-4330 | jeffmessner@att.net | Vehicle on site Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 506 | 38.6314 | -120.5412 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 1
732 | 041-404-012 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-404-012 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3906.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-01-27 | 01/26/22 NO ANS LEFT VM & TEXT. JC 01/27/22 SPOKE WITH JEFFREY HE SAID OK BUT PLEASE CALL IN ADVANCE. ALSO PLEASE REMOVE THE DRIVEWAY THAT IS DAMAGED. VENDOR HANDLING PROPANE TANK. JC | [27 empty] | 2022-01-15 | Yes | 11 | 2022-02-04 |  | 2022-02-04 | 2022-02-04 |  | 2022-02-08 | 2022-02-09 | 11 |  |  | 2022-02-10 |  | 2022-02-10 | 2022-02-10 | Jeffrey & Sharon Messner | 209-296-4330 | jeffmessner@att.net |  |  | 38.6318 | -120.5412 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
733 | 041-411-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5293 | Forest View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3918.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-09 |  | FALSE | [5 empty] | No | Yes | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | [10 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-02-21 | 02/21/22 SPOKE WITH MRS FAURE SHE SAID OK FOR TREE REMOVAL. 3.8 Spoke to HO(wife) got permission to send ROE ACCESS she agreed emailed it 3.9.PF | [27 empty] | 2022-03-02 | Yes | 37 | 2022-03-02 |  | 2022-03-04 | 2022-03-04 |  | 2022-03-19 | 2022-03-21 | 37 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | Paul Faure | 925 447 5022 | cvbanderson@gmail.com | Septic |  | 38.6302 | -120.5447 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 15
734 | 041-411-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4826 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3910.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 5 |  |  | 2 | TRUE | Yes | Take | 2022-03-07 | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | NEGATIVE |  |  |  | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-13 | 2021-10-25 | 2021-12-04 | 10.25 Spoke with Tamara, acknowledged start of debris removal, would like to be present for removal RCV 12.4 SPOKE TAMRA WITH SHE OK. JC 02/14/22 PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 5 | 2021-11-08 | 2021-11-17 | 8 | Approved | [12 empty] | 2021-11-19 | 2021-11-05 | Yes | 15 | 2022-01-05 |  | 2022-01-06 | 2022-01-06 |  | 2022-01-07 | 2022-01-08 | 15 | 2022-01-27 |  | 2022-01-17 | 2022-03-08 | 2022-03-08 | 2022-03-08 | TAMRA MCVAY | 530-363-4850 | tami.mcvay@yahoo.com |  | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 505 | 38.6292 | -120.5429 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 1
735 | 041-411-007 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4814 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3894.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  |  | 2022-01-12 | 1.12 Contacted homeowner who gave approval for tree removal to start RCV | [27 empty] | 2021-12-21 | Yes | 42 | 2022-01-12 |  | 2022-01-12 | 2022-01-12 |  | 2022-01-14 | 2022-01-21 | 42 |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 | Dale & Marlene Aaron | 530-622-1502 | djamea@sbcglobal.net |  |  | 38.6287 | -120.5431 | Caldor | DR-4619 | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
736 | 041-412-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4817 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3870.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-23 | Yes | 2021-10-26 | 2021-10-29 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-05 | 2021-11-08 | 2021-12-06 | 11.6 NO ANS LEFT VM. JC 11.8 NO ANS LEFT VM. JC 11.8 SENT EMAIL. JC SPOKE WITH PATRICK SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. PF 12.4 NO ANS LEFT VM FOR TREE REMOVAL .JC 12.4 PATRICK GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2021-11-06 | Yes | 4 | 2022-01-05 |  | 2022-01-05 | 2022-01-05 |  | 2022-01-06 | 2022-01-06 | 4 | 2022-01-18 |  | 2022-01-14 | 2022-01-27 | 2022-01-27 | 2022-01-27 | PATRICK & KATHLEEN HALEY | 415-215-9351 | pathaleyhci@gmail.com | Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 505 | 38.6286 | -120.5416 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
737 | 041-412-002 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4829 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3875.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-08 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 |  |  | 2021-12-04 | "12.4 NO ANS LEFT VM FOR TREE REMOVAL .JC 12.4 SENT TEXT MESS. JC 12.4 PATRICK GAVE CONSENT VIA TEXT. JC" | [27 empty] | 2022-01-05 | Yes | 4 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 | 4 |  |  | 2022-01-15 |  | 2022-01-15 | 2022-01-17 | PATRICK & KATHLEEN HALEY | 415-215-9350 | pathaleyhci@gmail.com |  |  | 38.629 | -120.5415 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
738 | 041-412-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4841 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3890.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  |  | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/21 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2021-11-29 | Yes | 15 | 2022-03-03 |  | 2022-03-03 | 2022-03-03 |  | 2022-03-09 | 2022-03-11 | 15 |  |  | 2022-03-14 |  | 2022-03-14 | 2022-03-14 | Mary Allison & Chad Edward Morgan | 858-568-0428 & 916-390-1128 | originalalicat@gmail.com |  |  | 38.6294 | -120.5414 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
739 | 041-412-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4861 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3909.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-09 | 2021-11-10 | 2022-01-11 | 11.10 SPOKE WITH ANDREW HE SAID OK BUT PLEASE CALL IN ADVANCE. THE INSURANCE COMPANY WILL PICK UP THE THE 1968 CHEVY VAN. VENDOR WILL HANDLE PROPANE TANK. JC 12.4 NO ANS LEFT VM AND TEXT MESS FOR TREE REMOVAL. JC 1.11 Homeowner ﻿acknowledged start of hazard tree removal RCV |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 3 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-11-22 | Yes | 16 | 2022-01-13 |  | 2022-01-13 | 2022-01-13 |  | 2022-01-15 | 2022-01-17 | 16 | 2022-01-31 |  | 2022-01-18 | 2022-02-03 | 2022-02-03 | 2022-02-07 | Denise & Andrew Fisher | 916-505-4544, 916-223-0083 | cmt4relief@yahoo.com, fordmanfisher@gmail.com | Vehicle on site Keep item Septic | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 506 | 38.6301 | -120.5413 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
740 | 041-421-001 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 5068 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3892.23 |  | 2021-11-02 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-06 |  | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | Yes |  |  | 2021-10-05 | No | [6 empty] | 2021-10-13 | No Bio Monitoring Needed for Debris or Trees | 2021-10-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | N/A | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 |  |  | 2021-12-04 | 12.4 SPOKE WITH JOHN HE SAID OK. JC | [27 empty] | 2021-11-02 | No | 0 | [14 empty] | JOHN R. & CHRISTINA A. ROGERS | 530-558-0762 | JRROGER99@GMAIL.COM |  |  | 38.6371 | -120.5405 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
741 | 041-421-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5082 | Mount Pleasant Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3892.38 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-19 | 2021-11-19 | 4 | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-19 | 2021-11-23 |  | 11.23 SPOKE WITH JAMES HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-04 | 2021-12-04 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2022-01-10 | Yes | 16 | 2022-01-14 |  | 2022-01-14 | 2022-01-14 |  | 2022-01-15 | 2022-01-18 | 16 | 2022-01-28 |  | 2022-01-19 | 2022-02-03 | 2022-02-03 | 2022-02-03 | PADILLA JAMES R & DORIS S | 530-317-7595 / 530-957-9799 | sierradweller@gmail.com | Other Septic | Debris Crew Leader/Crew# Berdre Bell/#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6372 | -120.5398 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
742 | 041-422-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5048 | Woodridge Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3912.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-18 | 2021-11-19 | 2022-02-22 | 11.19 NO ANS & NO VM SENT EMAIL. JC 11.19 SPOKE WITH HO HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 02/21/22 PHONE NUMBER CHANGED OR OUT OF SERVICE SENT EMAIL. JC 02/21/22 HO GAVE CONSENT VIA EMAIL. HE ASKED THAT THE WIRE FENCE AND ELECTRIC POLE NOT BE DAMAGED. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2022-03-05 | Yes | 14 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 14 | 2022-03-30 |  | 2022-03-22 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Ho & Su Kim | 408-828-8552 or 925 519-6624 | hkk1191@hotmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 504 | 38.6359 | -120.54 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
743 | 041-482-009 | Full Program ROE (debris + trees) | Ready for Final Sign-off | Passed Tree Completion Check | Next Step: N/A | FSO Pending Vehicles | Ready for FSO | 6802 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4016.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-11-30 | 2021-12-03 |  | 12.03 NO ANS LEFT VM. JC ﻿12.03 Contacted owner, okayed debris removal RCV 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE. JC 01/27/22 VENDOR HANDLING PROPANE. JC 03/16/22 NO ANS LEFT VM & TEXT. JC 3.17 3.17 Gerald c/b and said ok to proceed. PF |  |  |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 |  |  | 37 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-03-08 | Yes | 11 | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  | 2022-03-31 | 2022-04-01 | 11 | 2022-04-05 |  | 2022-04-02 |  |  |  | Gerald Flaherty | 916-485-7194 | flair-t@outlook.com | Septic | Debris Crew Leader/Crew# Justin Romero /#502 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 502 | 38.6419 | -120.5252 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T00:15:01Z | FALSE | 5
744 | 041-482-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4908 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3998.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 2 | 1 | 5 |  |  | 5 | TRUE | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-24 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-24 | 2021-11-29 | 2022-01-19 | 11.17 NO ANS LEFT VM. JC 11.19 NO ANS LEFT VM. JC 11.29 NO ANS VM FULL SENT EMAIL JC 11.29 SPOKE WITH TERRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/19/22 SPOKE WITH TERRY HE SAID OK. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2022-01-19 | Yes | 9 | 2022-02-10 |  | 2022-02-10 | 2022-02-10 |  | 2022-02-11 | 2022-02-12 | 9 | 2022-02-21 |  | 2022-02-14 | 2022-03-01 | 2022-03-01 | 2022-03-01 | terry smith caudle and lynette gaye newman | 916-468-8688 | terryc4113@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Romero /#502 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 502 | 38.6421 | -120.5246 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 1
745 | 041-482-012 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4900 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3996.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-16 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-01 | Yes | 2021-11-02 | 2021-11-05 | NEGATIVE |  |  |  | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-16 | 2021-11-17 | 2022-02-28 | 11.17 NO ANS LEFT VM. JC 11.17 SPOKE WITH ANTHONY HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CALL VENDOR TO HANDLE THE PROPANE TANK. JC 02/28/22 SPOKE WITH ANTHONY HE SAID OK. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Re-scrape |  |  |  | 2021-12-04 | 2021-12-10 | Re-scrape | 2022-01-20 | 2022-01-28 | Re-scrape | 2022-02-07 | 2022-02-15 | Approved | 2022-02-16 | 2021-11-15 | Yes | 10 | 2022-03-08 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-16 | 2022-03-17 | 10 | 2022-03-23 |  | 2022-03-18 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Anthony & Linda Bolen | 530-320-1529, 916-207-6619 | ton_bolen@sbcglobal.net, llbolen@sbcglobal.net | Vehicle on site Septic | Debris Crew Leader/Crew# Terrance Harrison#509 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 509 | 38.6424 | -120.5245 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
746 | 041-482-015 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7078 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3995.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-02-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 |  |  | 2022-02-18 | 02/17/22 NO ANS LEFT VM & TEXT. JC 02/18/22 NO ANS LEFT VM & EMAIL. JC 02/18/22 Joseph emailed back ok for tree removal. JC | [27 empty] | 2022-01-20 | Yes | 17 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-07 | 2022-03-08 | 17 |  |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 | Joseph Gilmete | 041-482-015 | joegilmete1@gmail.com | Vehicles Onsite |  | 38.6433 | -120.5245 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
747 | 041-603-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7634 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3991.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-04 | 2021-12-07 | 2022-02-16 | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 HO GAVE CONSENT VIA TEXT. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/25/22 HO SAID VENDOR HANDLING PROPANE TANK. JC 02/16/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 02/16/22 JEANETTE GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-12-10 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2021-11-23 | Yes | 32 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-26 | 2022-03-02 | 32 | 2022-03-09 |  | 2022-03-05 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Jeanette West | 530-306-9338 | Sarahsmommywest@netscape.net | Other Septic | Debris Crew Leader/Crew# Robert Berry/ #508 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 508 | 38.641 | -120.5105 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
748 | 041-611-019 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 2 | 7463 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.92 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-07 | 2022-02-07 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 |  | No |  |  | 2022-02-07 | Yes | 2022-02-07 | 2022-02-09 | NEGATIVE |  |  |  | 2022-02-04 | Bio Monitoring Needed for Debris AND Trees | 2022-02-08 | Arch Monitoring Needed for Debris AND Trees | [6 empty] | No |  | No |  | TRUE |  | Class I | Covered under suspension | FALSE | [10 empty] | 2022-02-09 | 2022-02-10 | 2022-03-28 | "02/07/22 NO ANS LEFT VM AND TEXT ABT ELIGIBLE DEBRIS. JC 02/07/22 SPOKE WITH JACK HE SAID BURNED STRUCTURES AND DEBRIS. JC" 02/10/22 SPOKE WITH JACK HE SAID OK. PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 02/12/22 3.28 Spoke to Mr Brush he said ok PF |  |  |  | 2022-02-16 |  | 2022-02-17 | 2022-02-17 |  |  | 2 | 2022-02-18 | 2022-02-28 | 7 | Approved | [12 empty] | 2022-03-02 | 2022-03-16 | Yes | 14 | [14 empty] | Jack L Brush | 408-394-3157 | jack101007@gmail.com |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 601 | 38.6396 | -120.5105 | Caldor | DR-4619 | Residential | Yes | 2022-01-31 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
749 | 041-612-002 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7418 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3965.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-12-03 | 2022-01-21 |  | 12.07 SPOKE WITH NICHOLE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT BURNED DO NOT REMOVE. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-12-10 |  | 2022-02-16 | 2022-02-16 |  |  | 2 | 2022-02-17 | 2022-02-25 | 7 | Approved | [12 empty] | 2022-03-01 | 2021-11-15 | No | 0 | [8 empty] | 2022-03-09 |  |  | 2022-03-10 | 2022-03-10 | 2022-03-10 | Nichole Estrada | 714-222-2622 | Nichole_estrada@yahoo.co | Septic | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/16 to 02/19 Crew 504 | 38.6391 | -120.5125 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
750 | 041-612-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7426 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3978.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-30 | 2021-11-03 | 2022-02-10 | 11.3 No Answer Left Mess. JC 11.3 SPOKE WITH STACY SHE SAID OK. PLEASE CALL IN ADVANCE. JC 02/10/11 NO ANS LEFT VM & TEXT. JC 02/10/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-05 |  | 2021-11-05 | 2021-11-05 |  |  | 4 | 2021-11-10 | 2021-11-18 | 7 | Re-scrape | 2022-01-17 | 2022-01-25 | Approved | 2021-11-23 | 2021-12-03 | Soil Boring | [6 empty] | 2022-01-26 | 2021-11-15 | Yes | 7 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-26 | 2022-02-28 | 7 | 2022-03-09 |  | 2022-03-01 | 2022-03-10 | 2022-03-10 | 2022-03-10 | STACY EBESEK | 530-312-2546 | stacy_1250@msn.com |  | "Debris Crew Leader/Crew# Stephanie Fairlee/502 Debris Crew WO# Refer to IAP 11/03 to 11-06 Crew 502" | 38.6391 | -120.5121 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
751 | 041-613-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7450 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4001.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 6 |  |  | 1 | TRUE | No |  |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-10-16 | 2021-10-25 | 2022-01-24 | 10.25 Spoke with Nina, acknowledged start of debris removal. Would like a call before start. RCV 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 01/24/22 SPOKE WITH NINA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 5 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-10-27 | Yes | 2 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-26 | 2022-02-28 | 2 | 2022-03-09 |  | 2022-03-01 | 2022-03-17 | 2022-03-17 | 2022-03-17 | NINA ZHIGADLO & YAHOR ARLOU | 916-595-2318 | ninazhigadlo@gmail.com |  | "Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/03 to 11/04 Crew 502" | 38.639 | -120.5111 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
752 | 041-613-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7484 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4050.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 6 | 0 | 0 | 0 | 8 |  |  |  | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-20 | POSITIVE | 2021-11-02 | 2021-11-02 | 10 | 2021-10-22 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 | TRUE |  |  |  | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-02 | 2021-11-04 | 2022-02-21 | 11.3 NO ANS. LEFT MESS. JC 11.4 SPOKE WITH JANICE. SHE SAID OK. PLEASE CALL IN ADVANCE. JC 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE. JC 01/27/22 VENDOR HANDLING PROPANE. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 JANICE GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-08 |  | 2021-11-09 | 2021-11-09 |  |  | 3 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-12-03 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2021-10-30 | Yes | 24 | 2022-03-04 |  | 2022-03-04 | 2022-03-04 |  | 2022-03-11 | 2022-03-14 | 24 | 2022-03-23 |  | 2022-03-16 | 2022-03-24 | 2022-03-24 | 2022-03-24 | EDWARD & JANICE FARRIS | 209-362-8459 | janiceafarris@gmail.com |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/6-11/10/ Crew 502 | 38.6389 | -120.5095 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
753 | 041-613-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7502 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4059.72 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | Yes | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-04 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-30 | Yes | 2022-04-02 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-22 | 2021-12-07 | 2022-04-04 | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH GREG HE SAID OK BUT HE WANTS A CALL IN ADVANCE BECASUE HE WANTS TO BE ON SITE WHEN REMOVAL HAPPENS. NO PROPANE TANKS. JC 01/21/NO ANS LEFT VM & TEXT. JC 01/22/22 HO SAID OK. BUT PLEASE CALL BEFORE GOING TO PROPERTY. HE WANTS TO BE THERE WHEN DEBRIS REMOVAL. JC 4.4.22 GREG RESPONDED BY TEXT TO PROCEED. PF |  |  |  | 2022-01-28 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-29 | Yes | 38 | [14 empty] | Greg & Jennifer Ingram | 415-225-5274 | gregorydavidingram | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando M / #515 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 515 | 38.6389 | -120.5088 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-05T18:13:40Z | FALSE
754 | 041-613-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7506 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4063.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Take | 2022-03-07 | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-25 |  | 10.25 Spoke with Curtis, acknowledged start of debris removal RCV 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 SPOKE WITH CURTIS HE SAID TO REMOVE PROPANE TANK. JC |  |  |  | 2021-10-27 |  | 2021-10-28 | 2021-10-28 |  |  | 64 | 2022-01-28 | 2022-02-07 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2021-10-28 | Yes | 39 | [14 empty] | CURTIS JEFFERSON | 916-878-8716 | crutsy@gmail.com |  | Debris Crew Leader/Crew# Stefanie Fairlee/#502 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 502 | 38.6389 | -120.5083 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
755 | 041-613-016 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7542 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4046.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | Yes | 2022-03-03 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-12-07 | 2022-01-21 | 2022-03-04 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 SPOKE WITH GRAY HE SAID HE WANTS TO BE ON SITE DURING DEBRIS REMOVAL. PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 GARY GAVE CONSENT VIA TEXT. JC 03/﻿04/22 SPOKE WITH GARY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-29 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-25 | Yes | 31 | 2022-03-05 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-16 | 2022-03-17 | 31 | 2022-03-23 |  | 2022-03-18 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Gray McCombs | 916-761-2545 | gray.arvid.mccombs@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Fernando Montealegre / #515 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 4515 | 38.6405 | -120.5078 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
756 | 041-482-016 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7070 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3993.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-06 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-02-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-01 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 |  |  | 2022-02-21 | 02/21/22 SPOKE WITH JOSEPH HE SAID OK. JC | [27 empty] | 2022-01-20 | Yes | 12 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-07 | 2022-03-08 | 12 |  |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 | Joseph Gilmete | cell 510-292-5000 | joegilmete1@gmail.com | Vehicles Onsite |  | 38.6436 | -120.5243 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
757 | 100-030-023 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1506 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2296.89 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Trees, not Debris | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-19 | 2021-10-28 |  | "10.27 NO ANS. LEFT MESS PF 10.28 SPOKE TO ROSEMARY AND SHE SAID OK PF" 11.2 left mess abt. tank removal. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 6 | 2021-11-09 | 2021-11-18 | 8 | Approved | [12 empty] | 2021-11-20 | 2021-11-18 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Harry Palmer, Rosemary Palmer | (831) 594-1466 | hpalmer655@aol.com | Septic Well | Debris Crew Leader/Crew# Jason Lowe /402 Debris Crew WO# Refer to IAP 10/30 to 11/3 Crew 402 | 39.1075 | -120.9741 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
758 | 100-030-030 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1330 | Bear View Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2122.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 5 | 0 | 0 | 0 | 1 | 0 | 8 |  |  |  | TRUE | Yes | Leave |  | 2021-11-02 | Yes | 2021-11-03 | 2021-11-08 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-09 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-22 | 2021-11-09 | 2021-11-10 |  | 11.10 Mr. Miler informed the Call center he's leaving town on 11/19-11/29. But its a must that he's there when they are on his property cleaning so he wants to be delayed until after he returns. Then he wants to be called 12-24 hours prior to coming out to his property. |  |  |  | 2021-11-17 |  | 2021-11-17 | 2021-11-17 |  |  | 9 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-11-22 | No | 0 | [8 empty] | 2021-12-20 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | A. Daniel Miller, Robin L. Miller | (530) 305-0391 | wolfgong@aol.com | Keep Items Septic | Debris Crew Leader/Crew# Dominic Unconco/#401 Debris Crew WO# Refer to IAP 11/17 to 11/19 Crew 401 | 39.1137 | -120.9715 | River | DR-4610 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
759 | 100-030-031 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1281 | Wildwood Lane |  | Colfax | Placer |  | Residential | [5 empty] | 2185.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-13 | 2021-10-13 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-18 | Bio Monitoring Needed for Debris AND Trees | 2021-10-18 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-18 | 2021-10-28 |  | ""10.27 LINE BUSY NO ANS. PF 10.28 NO ANS. LEFT MESS PF 10.28 SPOKE TO MICHAEL HE SAID OK BUT PLEASE CALL. PF" 11.2 SPOKE TO MICHAEL LEASING HIS TANK. DEBRIS CREW THERE TODAY AND SAID ITS OK AND OUT OF THE WAY. IT WAS NOT BURNED. PF |  |  |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 |  |  | 5 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-20 | 2021-11-16 | No | 0 | [8 empty] | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2021-12-11 | Michael Mazikowski, Susan Mazikowski | (530) 392-5023 | mmazikom@gmail.com | Septic | "Debris Crew Leader/Crew# Dominic Uncango﻿/401 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 401" | 39.1139 | -120.9706 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
760 | 100-030-032 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 1502 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2335.54 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class III | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-29 | 2021-10-29 | 2021-11-06 | 2022-01-26 | 11.6 SPOKE TO CHRIS AND HE SAID OK PF (NOTANKS) 12.06 SPOKE WITH CHRISTOPHER HE SAID OK. JC 01/26/22 SPOKE WITH CHRIS HE SAID DO NOT REMOVE PROPANE TANK. HE GIVE PRE APPROVAL FOR TREE REMOVAL. JC |  |  |  | 2021-11-10 |  | 2021-11-10 | 2021-11-10 |  |  | 2 | 2021-11-11 | 2021-11-18 | 6 | Approved | [12 empty] | 2021-11-20 | 2021-11-17 | Yes | 1 | 2022-02-03 |  | 2022-02-03 | 2022-02-03 |  | 2022-02-04 | 2022-02-04 | 1 | 2022-02-16 |  | 2022-02-11 | 2022-02-17 | 2022-02-17 | 2022-02-17 | Christopher Arteaga, Marcie Arteaga | (530) 263-8897, (530) 613-0776 | chris.arteaga@gmail.com, mrsart@gmail.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 11/10/2021 to 11/13/2021 Crew 402 | 39.1072 | -120.9733 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
761 | 100-030-037 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 1500 | Hillcrest Boulevard |  | Colfax | Placer |  | Residential | [5 empty] | 2302.95 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | Yes | Yes | Yes | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-19 | Bio Monitoring Needed for Debris, not Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-10-21 | 2021-10-28 |  | 10.28 SPOKE TO STEVE HE SAID OK. PF 11.2 Spoke with Laurie. They do not want the tank removed. JC |  |  |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 |  |  | 8 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-12-02 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2021-11-12 | No | 0 | [8 empty] | 2021-12-20 |  |  | 2021-12-22 | 2021-12-22 | 2021-12-23 | Steven Sanders, Laurie Sanders | (530) 205-6382, (530) 906-0718 | slsanders@wavecable.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Jason Lowe/#402 Debris Crew WO# Refer to IAP 10/30 to 11/03/ Crew 402 | 39.1081 | -120.9735 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
762 | 100-040-012 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 1151 | Monte Vista Court |  | Colfax | Placer |  | Residential | [5 empty] | 2351.49 |  | 2021-12-03 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-16 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-10-16 | No | [6 empty] | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | FALSE | [32 empty] | 2021-12-03 | No | 0 | [14 empty] | Lisa Walukones, Kasey Walukones, Steele Walukones | (916) 342-6567 | Kaseywalukones@gmail.com | Septic |  | 39.1098 | -120.9703 | River | DR-4610 | Residential | Yes | 2021-10-01 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
763 | 100-060-030 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 25397 | Pineview Drive |  | Colfax | Placer |  | Residential | [5 empty] | 2335.97 |  |  |  |  | FALSE |  |  | N/A |  |  | 9119# |  |  | Yes |  | TRUE | 2021-10-12 | 2021-10-12 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-19 | No Bio Monitoring Needed for Debris or Trees | 2021-10-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-29 | 2021-12-02 | 2021-11-23 |  | 11.23 NO ANS LEFT VM. JC 11.23 SPOKE WITH FRED HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANKS. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 4 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2021-12-03 | No | 0 | [8 empty] | 2022-01-13 |  |  | 2022-01-25 | 2022-01-25 | 2022-01-25 | Fred Osmond, Lori Osmond | (916) 764-0926, (916) 747-4559 | fosmond21@gmail.com | Keep Items Septic | Debris Crew Leader/Crew# Terrence Harrison/#403 Jason Lowe WO# Refer to IAP 12/01 to 12/04 Crew 403 | 39.114 | -120.9673 | River | DR-4610 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
764 | 041-541-029 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5071 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3824.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-09 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-15 | 2021-11-16 | 2022-01-18 | 11.16 SPOKE WITH MICHAEL HE SAID OKAY BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 01/18/22 SPOKE WITH MICHAEL HE SAID OK. JC 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 SPOKE WITH MICHAEL HE SAID DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 |  |  | 4 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-01 | Yes | 7 | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  | 2022-01-21 | 2022-01-22 | 7 | 2022-01-28 |  | 2022-01-25 | 2022-02-04 | 2022-02-04 | 2022-02-04 | GEORGE MICHAEL D & NANCY | 530-391-5332 | michaelgeorge7883@att.net | SEPTIC | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 509 | 38.6377 | -120.5203 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
765 | 041-551-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 5035 | Merrywood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3879.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-08 | Bio Monitoring Needed for Trees, not Debris | 2022-02-07 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | No |  | No |  | TRUE | Operational | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-14 | [31 empty] | 2021-12-07 | Yes | 103 | [14 empty] | Pat or Donna Hamer | 925-360-1936 | homesculptor@yahoo.com |  |  | 38.637 | -120.5246 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
766 | 041-551-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5021 | Merrywood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3890.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | Yes |  | 2021-12-07 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-23 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-31 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-11-30 |  | 11.24 NO ANS LEFT VM. JC 11.29 NO ANS LEFT VM. JC 11.29 SENT EMAIL JC 11:30 RECEIVED CONFIRMATION VIA EMAIL FROM Dan Widemann, BUT HE DOES NOT WANT THE WOOD STOVE REMOVED. DO NOT REMOVE WOOD BURNING STOVE. JC "01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE. JC 4.04 NO ANS. LEFT MESS ON BOTH PHONES AND SENT TEXTS ON BOTH. PF"﻿ 4.4 SENT EMAILS TO BOTH EMAIL ADDRESSES. PF | 3 | Kendall Wilson |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 35 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-25 | Yes | 59 | [14 empty] | Daniel & Leticia Widemann | 707-301-8869 / 707-580-9731 | dpweedie@gmail.com, letyweed@gmail.com | Septic | Debris Crew Leader/Crew# Christer Richter #503 Debris Crew WO# Refer to IAP 12/08 to 12/11Crew 503 | 38.6379 | -120.5239 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-05T01:29:07Z | FALSE
767 | 041-551-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5006 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3864.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Take | 2022-02-17 | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-01 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-03 | 2021-12-07 | 2022-04-04 | 12.06 NO ANS LEFT VM & TEXT. JC 12.06 SENT EMAIL. GAVE TO RICHARD. JC 12.07 SPOKE WITH DENISE SHE SAID OK BUT PLEASE CALL IN ADVANCE. REMOVE PROPANE TANK. JC 03/31/22 NO ANS LEFT VM & Text. JC 04/01/22 NO ANS LEFT VM & EMAIL. JC 04/02/22 NO ANS LEFT VM & 2ND EMAIL. JC 04/04/22 NO ANS LEFT VM. OK TO PROCEED PER MELISSA PERRY. JC | 4 | State Planner: Melissa Perry |  | 2021-12-10 |  | 2021-12-11 | 2021-12-11 |  |  | 30 | 2022-01-24 | 2022-02-01 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2022-01-21 | Yes | 15 | [14 empty] | Russell & Denise Howell | 916-470-0275 | russhowell24@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Melanie Poole#515 Debris Crew WO# Refer to IAP 12/11 to 12/15 Crew 515 | 38.6383 | -120.5228 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-04T18:57:16Z | FALSE
768 | 041-722-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5269 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3800.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-09 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-01 | Yes | 2022-03-01 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-21 | 2022-01-21 | 2022-04-01 | 12.09 SPOKE WITH MELAINE SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 MELAINE SAID OK. JC 3.18 SPOKE TO MELANIE AND SHE SAID OK AND WHEN ARE THE TREES COMING DOWN. SHE'S ALSO CONCERNED ABOUT THE PROPERTY NEXT TO HERS TREES ARE VERY TALL AND DANGEROUS AND HER PROPERTY IS BEING PUT IN JEOPARDY WITH THEM. 04/01/22 SPOKE WITH MELANIE SHE SAID OK FOR TREE REMOVAL. JC 04/06/22 MELANIE CALLED FOR STATUS. JC |  |  |  | 2022-01-25 |  | 2022-01-26 | 2022-01-26 |  |  | 4 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-03-01 | Yes | 20 | [7 empty] | 4 | [6 empty] | Craig & Melanie Osmer | 209-404-3367 | melhasmail@gmail.com | Septic | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 502 | 38.6327 | -120.532 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T22:05:38Z | FALSE
769 | 041-722-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5279 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3789.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-02-09 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-03-16 | 03/15/22 NO ANS LEFT VM & TEXT. JC 03/16/22 NO ANS LEFT VM & EMAIL. JC 03/16/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-01-13 | Yes | 20 | [14 empty] | Drew Johnson | 650-430-0915 | drewjohnson03@comcast.net | Vehicles Onsite |  | 38.6325 | -120.5321 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
770 | 041-722-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5285 | Wooded Glen Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3783.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 |  |  |  |  | Yes | Leave |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-15 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-12-09 | 2021-12-10 | 2022-03-09 | 12.10 NO ANS LEFT VM & TEXT. JC 12.10 SPOKE WITH DREW HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/09/22 NO ANS LEFT VM & TEXT. JC 03/09/22 SPOKE DREW HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  |  | 6 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-13 | Yes | 19 | [14 empty] | Drew Johnson | 650-430-0915 | drewjohnson03@comcast.net | Vehicles on site Septic | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 505 | 38.6322 | -120.5321 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
771 | 041-722-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5293 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3776.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-03 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-10 | 2021-12-11 | 2022-03-07 | 12.10 NO ANS LEFT VM & TEXT. JC 12.11 NO ANS LEFT VM & SENT EMAIL JC 12.11 SPOKE WITH MIKE HE SAID OK BUT PLEASE CALL IN ADVANCE. ﻿ NO PROPANE TANK. JC 03/04/22 NO ANS LEFT VM & TEXT JC 03/05/22 NO ANS LEFT VM & EMAIL. JC 03/07/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/07/22 MIKE CALLED BACK. HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 6 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-03-09 | Yes | 43 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-17 | 2022-03-18 | 43 | 2022-03-23 |  | 2022-03-21 | 2022-03-24 | 2022-03-24 | 2022-03-24 | Michael Buckman | 541-324-2961 | mikebuckman65@icloud.com |  | Debris Crew Leader/Crew# Carondlet Dunbar / #509 Debris Crew WO# Refer to IAP 01/19to 01/22 Crew 509 | 38.632 | -120.5322 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
772 | 041-722-007 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Crew ELD 5 | 5303 | Wooded Glen Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3773.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-01-28 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-01-28 | No Bio Monitoring Needed for Debris or Trees | 2022-02-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-08 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  | Class III | None | FALSE | [12 empty] | 2022-03-28 | 03/28/22 SPOKE WITH DOUGLAS HE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-03-03 | Yes | 69 | [14 empty] | Douglas Robert Deakin | 916-652-6207, 916-764-7220 | dougjanet5562@gmail.com |  |  | 38.6317 | -120.5323 | Caldor | DR-4619 | Residential | No | 2022-01-25 | ROE Verified | Central Division | 2022-04-08T17:09:56Z | FALSE
773 | 041-722-009 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5323 | Wooded Glen Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3772.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | None | FALSE | [12 empty] | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 SPOKE WITH STEPSON (JAMES) HE SAID OK BUT PLEASE CONTACT HIM AT 925 997-2452. JC | [27 empty] | 2022-01-17 | Yes | 34 | 2022-03-08 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-17 | 2022-03-18 | 34 |  |  | 2022-03-19 |  | 2022-03-19 | 2022-03-19 | Kathrine Hawkins | 510-928-9012 , 925-997-2452 | jrhawkins01@gmail.com |  |  | 38.6314 | -120.5328 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
774 | 041-722-010 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5335 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3772.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-25 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-14 | Yes | 2022-03-17 | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 |  |  | 2022-03-19 | 01/20/22 NO ANS LEFT VM & TEXT JC 01/20/22 SON C/B AND SAID OK. JC 03/19/22 follow up call SPOKE JAMES HE SAID OK FOR TREE REMOVAL JC | [27 empty] | 2021-10-29 | Yes | 57 | 2022-03-25 |  | 2022-03-29 | 2022-03-29 |  | 2022-03-31 | 2022-04-01 | 57 |  |  | 2022-04-02 |  | 2022-04-02 | 2022-04-04 | KATHARINE HAWKINS/ JAMES HAWKINS (SON) POA | 510-928-9012--CALL JAMES @ 925 997-2452 | jrhawkins01@gmail.com |  |  | 38.6314 | -120.5332 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-04T22:53:50Z | FALSE | 2
775 | 041-722-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5343 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3768.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-19 | 2021-10-26 | 2021-12-04 | 10.26 NO ANS LEFT MESS PF 10.26 MR GARRETT SAID OK PF 12.4 SPOKE WITH DONALD HE SAID OK. JC ﻿01/27/22 SPOKE WITH DONALD HE SAID PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-01 |  | 2021-11-01 | 2021-11-01 |  |  | 6 | 2021-11-08 | 2021-11-17 | 8 | Approved | [12 empty] | 2021-11-19 | 2021-10-27 | Yes | 28 | 2022-01-03 |  | 2022-01-03 | 2022-01-03 |  | 2022-01-06 | 2022-01-06 | 28 | 2022-01-18 |  | 2022-01-12 | 2022-03-03 | 2022-03-03 | 2022-03-03 | DONALD GARRETT III | 530-957-8720 | kk6fnw@gmail.com |  | Debris Crew Leader/Crew Sarah Mundt/#501 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 501 | 38.6314 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
776 | 041-722-015 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5250 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3762.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-01 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | On Hold | Yes | 2022-04-01 | No |  | TRUE |  | Class II | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-15 | 2022-01-11 | 2022-01-14 | 2022-04-05 | 01/14/22 SPOKE COLLEEN SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK ON PROPERTY. JC 041-501-004 Anita & Mike Hibbard 530-417-4286 , 530-391-8964 6701 Tyler Drive "12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & SENT EMAIL. JC 12.09 NO ANS LEFT VM GAVE TO RICHARD. JC 12.09 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 4.5 NO ANS LEFT MESS AND SENT TEXT PF 041-513-009 Travis Taylor 530-409-4689 4936 Deerwood Drive "01/29/22 SPOKE WITH TRAVIS HE SAID OK. VENDOR HANDLING PROPANE TANK. JC 4.5 Robert sent text acknowledging mobilization. PF |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-07 | 6 | Re-scrape |  |  |  | 2022-02-18 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-03-18 | Yes | 31 | [14 empty] | Robert & Colleen Jolson | 530-633-2933 | jolsonwelding@aol.com |  | Debris Crew Leader/Crew# Tami Collins / #501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 511 | 38.6316 | -120.5345 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T15:04:07Z | FALSE
777 | 041-722-017 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5222 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3783.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-08 | 2021-12-09 | 2022-02-10 | 12.09 SPOKE WITH JOANN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/10/22 SPOKE WITH JOANN SHE SAID OK. JC |  |  |  | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  |  | 5 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-01-06 | Yes | 3 | 2022-02-26 |  | 2022-02-26 | 2022-02-26 |  | 2022-03-01 | 2022-03-02 | 3 | 2022-03-11 |  | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Warren & Joann Mecham | 530 957-6885, 530 240-5533 | gpark7244@att.net | Vehicles on site Septic | Debris Crew Leader/Crew# Crystal Egan /#507 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 507 | 38.6323 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
778 | 041-722-018 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5230 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3777.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-11 | 2022-01-14 | 2022-02-10 | 01/14/22 SPOKE WITH JOANN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/10/22 SPOKE WITH WARREN HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-25 |  | 2022-01-25 | 2022-01-25 |  |  | 4 | 2022-01-29 | 2022-02-07 | 6 | Approved | [12 empty] | 2022-02-09 | 2022-01-05 | Yes | 7 | 2022-02-26 |  | 2022-02-26 | 2022-02-26 |  | 2022-03-01 | 2022-03-02 | 7 | 2022-03-11 |  | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | Warren & Joann Mecham | 530 957-6885, 530240-5533 | gpark7244@att.net | Septic | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP to Crew 501 | 38.632 | -120.5335 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 3
779 | 037-213-010 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7859 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6850.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | TRUE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-15 | POSITIVE | 2021-11-18 | 2021-11-18 | 4 | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-19 | 2021-11-16 |  | 11.16 NO ANS LEFT VM. JC 11.16 SPOKE WITH BRUCE HE SAID OK PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 5 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | [13 empty] | 2021-12-01 | Yes | 72 | [14 empty] | BRUCE PECCIANTI & CAROL CLINE | 209-267-9390 | brucepeccianti@hotmail.com |  | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8168 | -120.0788 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-02T02:56:28Z | FALSE
780 | 037-214-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7832 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6837.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-19 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 MR. MCKINTY CALLED BACK AND SAID OK THEY DO NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 3 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-12-03 | Yes | 5 | [14 empty] | BARBARA MCKINTY & SUSAN BUNTON | 916-412-1675 | MCKINTY@SBCGLOBAL.NET, KURAKASAMA@YAHOO.COM | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 511 | 38.8159 | -120.0796 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
781 | 037-214-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7842 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6852.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-10-21 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 | [31 empty] | 2021-12-03 | Yes | 24 | [14 empty] | JOHN W. & PATRICIA THOMSEN TRUST | 916-704-4841 | JTHOMSEN@SUREWEST.NET |  |  | 38.816 | -120.0793 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
782 | 037-214-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7850 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6869.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-11-13 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | POSITIVE | 2021-11-13 | 2021-11-13 | 1 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-19 | 2021-11-18 |  | 11.18 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. BUT HE DOES NOT NEED TO BE THERE. PLEASE REMOVE THE PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-02 | 2021-12-02 |  |  | 3 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2021-12-03 | Yes | 21 | [14 empty] | JOHN & PATRICIA THOMSEN | 916-704-4841 | JTHOMSEN@SUREWEST.NET | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 511 | 38.8161 | -120.079 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
783 | 037-214-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7845 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6878.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | [14 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 |  |  |  | 11.18 SPOKE WITH JOHN HE SAID OK BUT PLEASE CALL IN ADVANCE. BUT HE DOES NOT NEED TO BE THERE. PLEASE REMOVE THE PROPANE TANK. JC | [27 empty] | 2021-12-07 | Yes | 94 | [14 empty] | JOHN W. & PATRICIA THOMSEN TRUST | 916-704-4841 | JTHOMSEN@SUREWEST.NET |  |  | 38.8159 | -120.0788 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
784 | 037-214-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7855 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6884.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-29 | POSITIVE | 2021-11-06 | 2021-11-06 | 6 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-08 | 2021-11-10 |  | 11.10 SPOKE WITH DAVID HE SAID OK BUT CALL IN ADVANCE. PEALSE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-15 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Approved | [12 empty] | 2021-12-01 | 2021-12-02 | Yes | 28 | [14 empty] | DAVID & JODY BRANCHCOMB | 916-813-3879 | david.branchcomb@yahoo.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 511 | 38.816 | -120.0785 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
785 | 037-214-010 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7863 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6880 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-02 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-23 | [31 empty] | 2021-12-02 | Yes | 44 | [14 empty] | DAVID & JODY BRANCHCOMB | 916-813-3879 | david.branchcomb@yahoo.com |  |  | 38.8161 | -120.0782 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
786 | 037-214-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7869 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6885.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | Yes |  | 2021-11-13 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-20 | Yes | 2021-10-21 | 2021-10-26 | POSITIVE | 2021-11-06 | 2021-11-06 | 9 | 2021-10-23 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-13 | 2021-11-15 |  | 11.15 NO ANS LEFT VM. JC 11.15 SPOKE WITH GARRY HE SAID OK BUT PLEASE CALL IN ADVANCE. JC NO PROPANE TANK. JC |  |  |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 |  |  | 3 | 2021-11-19 | 2021-12-01 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-02 | Yes | 14 | [14 empty] | EUGENE, GARRY & SHELLY GERWER | 916-718-5165 | garrygerwer@comcast.net | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 511 | 38.8162 | -120.0779 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
787 | 037-214-013 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7873 | Hemlock Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6887.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 |  |  |  | 11.18 NO ANS LEFT VM. JC 11.18 WILLIAM CALLED BACK AND SAID OK AND HE DOES NOT NEED TO BE THERE. PLEASE CALL IN ADVANCE. NO PROPANE. JC | [27 empty] | 2021-12-06 | Yes | 26 | [14 empty] | William & Kara Swars | 916-802-1570 | Swarsb@hotmail.com | Other |  | 38.8162 | -120.0778 | Caldor | DR-4619 | Residential | No | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
788 | 037-214-018 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7856 | Tamarack Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6871.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-15 | POSITIVE | 2021-11-18 | 2021-11-18 | 4 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-18 |  | 11.18 Homeowner contact made, approved start of removal. Wants to save patio if possible RCV |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-03 | Yes | 1 | [14 empty] | JOHN & CHERYL COOK & TERESA BARBEAU | 916-761-8828 | jcook@eldoradosavings.com | SEPTIC | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 511 | 38.8162 | -120.0787 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
789 | 037-214-019 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7860 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6872.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-08 | 2021-11-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH JOHN HE SAID OK. JC |  |  |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 |  |  | 6 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-12-03 | Yes | 6 | [14 empty] | John & Cheryl Cook | 916-761-8828 | jcook@eldoradosavings.com |  | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 511 | 38.8163 | -120.0786 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
790 | 037-214-021 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7880 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6882.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-15 | 2021-11-17 |  | 11.16 NO ANS LEFT VM JC 11.17 NO ANS LEFT VM JC 11.17 SPOKE WITH RACHEL SHE SAID OK BUT PLAEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 4 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-12-02 | Yes | 10 | [14 empty] | GEORGE FEATHERS & RACHEL CARNES | 916-995-0973 | rcarnz@gmail.com | Vehicles On Site Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/24 to 12/01Crew 511 | 38.8165 | -120.0777 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
791 | 037-214-022 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 037-214-022 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 6884.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE |  |  |  | No |  |  | No | [7 empty] | FALSE | FALSE | [7 empty] | 0 | [7 empty] | 2021-12-08 | No | [6 empty] | 2021-12-10 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [42 empty] | Ok to Assess | [15 empty] | Feathers George M TR & Claudia A TR | 916-995-0973 | rcarnz@gmail.com |  |  | 38.8166 | -120.0775 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
792 | 037-214-026 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7876 | Tamarack Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6884.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-15 | POSITIVE | 2021-11-18 | 2021-11-18 | 4 | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-17 | 2021-11-18 | 2021-11-18 |  | 11.18 SPOKE WITH GEORGE HE SAID OK BUT PLEASE CALL IN ADVANCE. HE DOES NOT NEED TO BE THERE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 3 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-12-02 | Yes | 6 | [14 empty] | MARY & GEORGE PADOVAN | 916-709-0804 | gpadovan3@comcast.net | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 511 | 38.8165 | -120.0779 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
793 | 037-214-027 | Full Program ROE (debris + trees) | Asbestos Abatement Needed | Needs Assessment | Next Step: N/A | Twin Bridges Ready | Tree Assessment Needed | 7839 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6868.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | Yes |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | [7 empty] | 2022-04-04 | Yes | 2022-04-04 | 2022-04-07 | POSITIVE |  |  | 2 | 2021-12-07 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 |  |  |  | 04/08/22 SPOKE WITH LAURA SHE SAID OK. JC | [28 empty] | Ok to Assess | [15 empty] | Laura McKinty Kevin McKinty | 916-412-3903 | lauramckinty@gmail.com |  |  | 38.8158 | -120.0791 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-08T23:28:17Z | FALSE
794 | 037-214-028 | Full Program ROE (debris + trees) | Re-scrape Needed | Ready for Tree Felling | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7835 | Hemlock Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6864.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-18 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-11-05 | Yes | 2021-11-08 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-04-14 | 2021-11-18 | 2021-11-18 |  | 11.18 SPOKE WITH BAO HE SAID OK. BUT PLEASE CALL IN ADVANCE. HE DOES NOT HAVE TO BE THERE ANDHE OWNS TANK NOT SURE IF PROPANE TANK WAS BURNED. JC |  |  |  | 2021-11-19 |  | 2021-11-20 | 2021-11-20 |  |  | 2 | 2021-11-23 | 2021-12-03 | 7 | Re-scrape | [13 empty] | 2021-12-03 | Yes | 16 | [14 empty] | BAO NGUYEN | 510-364-7293 | bnguyen.2re@gmail.com | SEPTIC | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 511 | 38.8157 | -120.0792 | Caldor | DR-4619 | Residential | Yes | 2021-10-22 | ROE Verified | Central Division | 2022-04-02T03:04:16Z | FALSE
795 | 037-215-001 | Full Program ROE (debris + trees) | Asbestos Abatement Needed | Needs Assessment | Next Step: N/A | Twin Bridges Ready | Tree Assessment Needed | 037-215-001 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 6811 |  |  |  |  | FALSE |  |  | N/A |  |  |  | TRUE | Weather-related | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | POSITIVE |  |  | 87 | 2021-11-30 | Bio Monitoring Needed for Debris AND Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 |  |  |  | 12.09 NO ANS LEFT VM JC 12.10 SPOKE WITH WENDELL HE SAID OK BUT PLEASE CALL IN ADVANCE BECAUSE HE WANTS TO BE ON SITE DURING THE DEBRIS REMOVAL. PLEASE REMOVE PROPANE TANK. JC | [28 empty] | Ok to Assess | [15 empty] | WARD WENDELL | 916-761-7043 , 530-626-8033 | wward@papemh.com |  |  | 38.8157 | -120.0801 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
796 | 037-215-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 2036 | Pine Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6825.6 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-05 | 2021-11-05 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-11 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Trees, not Debris | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | [5 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-21 | 2021-11-19 | 2021-11-16 |  | 11.16 SPOKE WITH CHERI SHE SAID OK PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 2 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-12-01 | Yes | 4 | [14 empty] | KENT & CHERI FORTIN | 425-418-6556 | cherifortin@icloud.com | Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 511 | 38.8155 | -120.08 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
797 | 037-220-001 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 2036 | Pine Avenue |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6131.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | [5 empty] | No | No | No | Yes | No | No |  | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | [15 empty] | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | [14 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-23 |  |  |  | 11.16 SPOKE WITH CHERI SHE SAID OK PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC | [27 empty] | 2022-04-02 | Yes | 3 | [14 empty] | KENT & CHERI FORTIN | 425-418-6557 | cherifortin@icloud.com |  |  | 38.8153 | -120.0802 | Caldor | DR-4619 | Residential | No | 2021-10-25 | ROE Verified | Central Division | 2022-04-04T23:29:18Z | FALSE
798 | 037-221-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7833 | Phillips Heights Avenue |  | Echo Lake | El Dorado |  | Residential | [5 empty] | 6865.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-15 | POSITIVE | 2021-11-17 | 2021-11-17 | 3 | 2021-11-05 | Bio Monitoring Needed for Debris AND Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | [5 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-18 | 2021-11-19 | 2021-11-19 |  | 11.18 SPOKE WITH STACEY SHE SAID OK BUT PLEASE CALL IN ADVANCE . NO PROPANE TANK. JC |  |  |  | 2021-11-24 |  | 2021-11-24 | 2021-11-24 |  |  | 5 | 2021-12-02 | 2021-12-10 | 7 | Approved | [12 empty] | 2021-12-13 | 2021-11-30 | Yes | 17 | [14 empty] | STACEY PARKER & STEVEN PENNIMAN | 415-264-9979 | sparker@ucdavis.edu | Safety Concern | Debris Crew Leader/Crew# Robert Berry/#513 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 513 | 38.815 | -120.0796 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
799 | 041-561-001 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 5070 | Parkside Drive |  | Grizzly Flats | El Dorado |  | Other | [5 empty] | 3800.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-09 | Bio Monitoring Needed for Trees, not Debris | 2022-03-08 | Arch Monitoring Needed for Debris AND Trees | [73 empty] | Grizzly Flats Community Services District | 530-6629626 |  |  |  | 38.6368 | -120.5208 | Caldor | DR-4619 | Recreation |  | 2022-03-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
800 | 041-531-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 4956 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3976.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-02-01 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-14 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-03-25 | 03/25/22 NO ANS LEFT VM & TEXT. JC 03/25/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-02-16 | Yes | 47 | [14 empty] | Shannon Gordon | 916-410-0273 | shannonocean@gmail.com |  |  | 38.6408 | -120.5193 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
801 | 041-531-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 4996 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3970.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-08 | 2021-12-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-12-08 | 2022-01-21 |  | 12.09 NO ANS NO VOICEMAIL. SENT TEXT AND EMAIL. JC 12.09 SPOKE SHANNAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-02-01 |  | 2022-02-01 | 2022-02-01 |  |  | 4 | 2022-02-04 | 2022-02-14 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2021-12-22 | Yes | 41 | [14 empty] | Shannan Gordon | 916-410-0273 | shannanocean@gmail.com |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #509 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 509 | 38.6406 | -120.5195 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
802 | 041-531-005 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 4984 | Edgewood Cir |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3964.42 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-07 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed | [11 empty] | FALSE | [41 empty] | 2022-04-04 | Yes | 4 | [14 empty] | Lise Lebel | 530-647-6548 | liselebel237@gmail.com |  |  | 38.6403 | -120.5201 | Caldor | DR-4619 | Residential | No | 2022-02-15 | ROE Verified | Central Division | 2022-04-04T23:29:18Z | FALSE
803 | 041-531-006 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7245 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3928.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 SPOKE WITH HO SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-21 | Yes | 53 | 2022-03-02 |  | 2022-03-03 | 2022-03-03 |  | 2022-03-09 | 2022-03-10 | 53 |  |  | 2022-03-11 |  | 2022-03-11 | 2022-03-11 | Leslie Cox (Okano) | 650-349-5119 | okano4@aol.com |  |  | 38.6398 | -120.52 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
804 | 041-531-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4963 | Deertrack Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3920.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-14 | Yes | 2021-10-15 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-20 | 2021-10-26 | 2021-12-04 | 10.26 SPOKE TO JANET AND SHE SAID OK PF 11.2 left message abt tank removal. JC 11.3 Spoke to Janet she will call vendor. JC 12.4 SPOKE WITH JANET SHE SAID OK. JC |  |  |  | 2021-11-05 |  | 2021-11-06 | 2021-11-06 |  |  | 5 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-22 | 2022-01-06 | Yes | 15 | 2022-01-11 |  | 2022-01-11 | 2022-01-11 |  | 2022-01-13 | 2022-01-14 | 15 | 2022-01-25 |  | 2022-01-19 | 2022-01-27 | 2022-01-27 | 2022-02-16 | Janet Smith | 530-409-6014 | cjanet1958@yahoo.com |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 502 | 38.6401 | -120.5166 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
805 | 041-531-015 | Full Program ROE (debris + trees) | Withdrawn |  | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7255 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3929.33 | 2021-12-21 |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-09 | 2021-11-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2021-11-04 | Yes | 2021-11-05 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-10 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | N/A | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-17 | 2021-11-18 |  | 11.18 SPOKE WITH ROY HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WOULD LIKE TO BE THERE. VENDOR WILL HANDLE PROPANE TANK. PF | [27 empty] | 2021-12-01 | Ok to Assess | 16 | [14 empty] | Roy Carter | 530-622-5019, 919-5019 |  |  |  | 38.64 | -120.5195 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
806 | 041-532-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 7262 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3896.38 |  |  |  |  | TRUE | Nesting Birds |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-02 | 2022-03-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No |  | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2022-03-01 | Yes | 2022-03-01 | 2022-03-07 | POSITIVE | 2022-03-09 | 2022-03-09 | 3 | 2022-03-03 | No Bio Monitoring Needed for Debris or Trees | 2022-03-01 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-15 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-10 | Yes | 2022-03-16 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-03-09 | 2022-03-09 |  | 3.15 Per MP. Spoke to Juan and informed him crew was on premises He said ok PF |  |  |  | 2022-03-15 |  | 2022-03-17 | 2022-03-17 |  |  | 3 | 2022-03-21 | 2022-03-29 | 7 | Approved | [12 empty] | 2022-03-30 | 2022-03-16 | Yes | 21 | [14 empty] | Juan Manuel Canales Baltazar | 530-919-7258 | Baltazarjuan1979@gmail.com |  | Debris Crew Leader/Crew# Fernando Montealegre/ #519 Debris Crew WO# Refer to IAP 03/16 to 03/19 Crew 519 | 38.6395 | -120.5191 | Caldor | DR-4619 | Residential |  | 2022-02-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
807 | 042-376-190 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16428 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1370.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-12-04 | No | [6 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-12-06 | 2021-12-07 |  | 12.07 SPOKE WITH DOMINQUE, SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2022-01-06 |  | 2022-01-07 | 2022-01-07 |  |  | 2 | 2022-01-10 | 2022-01-18 | 7 | Re-scrape |  |  |  | 2022-02-11 | 2022-02-21 | Approved | [6 empty] | 2022-02-17 | 2021-12-16 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-09 | 2022-03-09 | 2022-03-10 | Tanom Domingue | (415)724-0076 | Tanomdomingue@hotmail.com |  | Debris Crew Leader/Crew# Glenn Adams/#202 Debris Crew WO# Refer to IAP 01/05/2022 to 01/08/2022 Crew 202 | 38.9257 | -122.6051 | Cache |  | Residential | No | 2021-12-02 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
808 | 042-377-050 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16417 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 11 | 0 | 4 | 0 | 0 | 1 | 0 | 16 |  |  | 12 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-22 | POSITIVE | 2021-10-27 | 2021-10-27 | 4 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  | 2021-10-27 | 2021-10-23 | 2021-12-07 | 10.23 Spoke to HO and he said yes. But wants to be called first for a walk thru PF 12.07 SPOKE WITH GARRETT HE SAID OK. BUT HE WANTS TO TALK TO CREW LEADER BEFORE GOING OUT TO REMOVE TREES. JC |  |  |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 |  |  | 7 | 2021-11-08 | 2021-11-17 | 8 | Re-scrape |  |  |  | 2021-11-23 | 2021-12-03 | Approved | [6 empty] | 2021-12-06 | 2021-11-10 | Yes | 3 | 2021-12-18 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-28 | 2021-12-28 | 3 | 2021-12-31 |  | 2021-12-29 | 2022-01-06 | 2022-01-06 | 2022-01-06 | Robert/Garrett Reed | (707) 350-0260 |  | Vehicles Onsite | Debris Crew Leader/Crew# BirdieBell/#202 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 202 | 38.9253 | -122.6053 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 10
809 | 042-377-110 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16390 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 12 |  |  | 8 | TRUE | No |  |  | 2021-10-14 | No | [6 empty] | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  | 2021-10-21 | 2021-10-23 | 2021-12-17 | Spoke to HO and he said yes. But wants to be called first for a walk thru PF 12.17 SPOKE WITH GARRETT HE SAID OK. BUT PLEASE CALL BEFORE GOING OUT TO REMOVE TREES. JC |  |  |  | 2021-10-27 |  | 2021-10-27 | 2021-10-27 |  |  | 9 | 2021-11-08 | 2021-11-17 | 8 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Re-scrape | 2021-12-17 | 2021-12-28 | Approved |  |  |  | 2022-01-04 | 2021-11-09 | Yes | 1 | 2021-12-18 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-22 | 2021-12-22 | 1 | 2022-02-03 |  | 2021-12-29 | 2022-02-02 | 2022-02-02 | 2022-02-07 | Robert/Garrett Reed | (707) 350-0260 |  | Vehicles Onsite | "Debris Crew Leader/Crew# TBD(Carla Herbst)/#201 Debris Crew WO# Refer to IAP 10/23 to 10/27 Crew 201" | 38.9251 | -122.6056 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 4
810 | 042-377-120 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16427 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-28 | 2021-10-28 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 14 | 2 | 4 | 0 | 1 | 2 | 0 | 23 |  |  | 20 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-20 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  | 2021-10-21 | 2021-10-23 | 2021-12-07 | 10.25 NO ANSWER 10.26 SPOKE TO MATT HE SAID OK AS LONG AS HE IS CALLED FIRST. PF 12.07 SPOKE WITH GARRETT HE SAID OK. BUT HE WANTS TO TALK TO CREW LEADER BEFORE GOING OUT TO REMOVE TREES. JC |  |  |  | 2021-10-29 |  | 2021-11-01 | 2021-11-01 |  |  | 5 | 2021-11-05 | 2021-11-15 | 7 | Re-scrape |  |  |  | 2021-11-30 | 2021-12-08 | Approved | [6 empty] | 2021-12-09 | 2021-11-10 | Yes | 4 | 2021-12-18 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-20 | 2021-12-20 | 4 | 2021-12-31 |  | 2021-12-29 | 2022-01-03 | 2022-01-03 | 2022-01-03 | Robert/Garrett Reed | (707) 350-0260 |  | Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell/#202 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 202 | 38.9254 | -122.605 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
811 | 042-377-160 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16397 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 12 |  |  | 14 | TRUE | No |  |  | 2021-10-15 | No | [6 empty] | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  | 2021-10-21 | 2021-10-25 | 2021-12-07 | 10.23@ 5:25 SPOKE TO HO AND HE WANTS TO BE CALLED IN ADVANCE TO DO A WLK THROUGH ABOUT HIS EQUIPMENT ON THE PARCEL. OK GOOD TO GO. PF 12.07 SPOKE WITH GARRETT HE SAID OK. BUT HE WANTS TO TALK TO CREW LEADER BEFORE GOING OUT TO REMOVE TREES. JC |  |  |  | 2021-10-27 |  | 2021-10-27 | 2021-10-27 |  |  | 10 | 2021-11-09 | 2021-11-17 | 7 | Re-scrape |  |  |  | 2021-11-23 | 2021-12-03 | Approved | [6 empty] | 2021-12-06 | 2021-11-09 | Yes | 2 | 2021-12-18 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-28 | 2021-12-28 | 2 | 2021-12-30 |  | 2021-12-29 | 2022-01-03 | 2022-01-03 | 2022-01-03 | Robert/Garrett Reed | (707) 350-0260 |  | Vehicles Onsite Well | "Debris Crew Leader/Crew# Birdie Bell/202 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 202" | 38.9253 | -122.6057 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 10
812 | 042-377-170 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16407 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | TRUE | TRUE | 4 | 1 | 0 | 0 | 2 | 3 | 0 | 10 |  |  | 8 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-22 | POSITIVE | 2021-10-29 | 2021-10-29 | 6 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [10 empty] | 2021-10-29 | 2021-10-25 | 2021-12-17 | 10.25 Spoke to HO and he said yes. But wants to be called first for a walk thru PF 12.17 SPOKE WITH GARRETT HE SAID OK. BUT PLEASE CALL BEFORE GOING OUT TO REMOVE TREES. JC |  |  | 2021-11-02 | 2021-11-03 |  | 2021-11-04 | 2021-11-04 |  |  | 7 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-12-10 | 2021-12-20 | Approved | [6 empty] | 2021-12-21 | 2021-11-09 | Yes | 1 | 2021-12-18 |  | 2021-12-18 | 2021-12-18 |  | 2021-12-20 | 2021-12-20 | 1 | 2021-12-27 |  | 2021-12-29 | 2022-01-03 | 2022-01-03 | 2022-01-03 | Robert/Garrett Reed | (707) 350-0260 |  | Septic Vehicles Onsite Well | "Debris Crew Leader/Crew# Birdie Bell/#202 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 202" | 38.9253 | -122.6055 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
813 | 042-377-180 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16377 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 4 | 2 | 5 | 0 | 0 | 1 | 2 | 14 |  |  | 8 | TRUE | No |  |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-20 | POSITIVE | 2021-10-26 | 2021-10-26 | 5 | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-21 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  | 2021-10-25 | 2021-12-07 | 10.25 NO ANS. LEFT MESS 10.25 SPOKE TO MS. CAIRES SAID OK BUT CALL FIRST. 12.07 NO ANS LEFT VM &TEXT. JC 12.07 SPOKE WITH MRS. CAIRES SHE SAID OK. JC |  |  |  | 2021-11-01 |  | 2021-11-02 | 2021-11-02 |  |  | 6 | 2021-11-09 | 2021-11-17 | 7 | Re-scrape |  |  |  | 2021-11-23 | 2021-12-03 | Approved | [6 empty] | 2021-12-06 | 2021-11-09 | Yes | 13 | 2021-12-17 |  | 2021-12-17 | 2021-12-17 |  | 2021-12-28 | 2021-12-28 | 13 | 2021-12-31 |  | 2021-12-29 | 2022-01-03 | 2022-01-03 | 2022-01-03 | Clifford Allan Caires | (707) 530-5702 | cairesbecky1@gmail.com | Keep Items Other Vehicles Onsite Well | "Debris Crew Leader/Crew# Birdie Bell /#201 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 201" | 38.9252 | -122.6059 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 11
814 | 041-882-027 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5691 | Wildrose Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3833.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-11 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-11 | No | [6 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-21 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 |  |  | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 HO SAID OK FOR TREE REMOVAL FOR 5691 & 5701. JC | [27 empty] | 2022-01-24 | Yes | 6 | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-04 | 2022-03-05 | 6 |  |  | 2022-03-08 |  | 2022-03-08 | 2022-03-08 | Andrew Chemistruck Victoria Chemistruck | 408-701-7948 | andrew.chemistruck@gmail.com |  |  | 38.6217 | -120.5551 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
815 | 041-891-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4795 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4042.22 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | Yes | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 4 |  |  |  |  | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-16 | Bio Monitoring Needed for Debris AND Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-02 | Yes | 2022-03-16 | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-17 | 2022-01-20 | 2022-03-26 | 11.17 SPOKE ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. OKAY TO REMOVE SMALL TANKS. JC 01/20/22 SPOKE WITH ROBERT HE SAID OK. 3.25 NO ANS LEFT MESS AND SENT TEXT. PF 3.25 ROBERT TEXTED BACK W/QUESTIONS ABOUT TREE SELECTIONS SIZE AND DISTANCE BEFORE HE SAYS OK. PER MP WE WIL HAVE A REP REACHOUT TO HIM. ALSO SENT HIM A COPY OF HIS TREE SURVEY. PF 3.26 State Rep spoke to Robert and its Ok to proceed. PF Per MP email. 04/08/22 Spoke with Robert and he said there is nothing left on his property. The ATV was there but they removed it when the cleaned the debris. |  |  |  | 2022-01-22 |  | 2022-01-26 | 2022-01-26 |  |  | 5 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-15 | 2022-02-23 | Approved | [6 empty] | 2022-02-25 | 2022-01-31 | Yes | 56 | [14 empty] | JANZEN ROBERT & AIMEE | 916-541-6325 | robjanzen50@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar / #509 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 509 | 38.6444 | -120.5196 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-08T19:30:45Z | FALSE
816 | 041-891-009 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7272 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4130.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-12 | Yes | 2021-10-13 | 2021-10-18 | NEGATIVE |  |  |  | 2021-10-20 | Bio Monitoring Needed for Trees, not Debris | 2021-11-04 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-04 | 2021-11-06 | 2022-01-19 | 11.5 CALLED #ON FILE BUT WAS TOLD CHARLES NO LONGER AT NUMBER. JC 11.5 Sent an email RCV 11.6 Contacted homeowner, approved start of debris removal. Asked to leave propane tanks on property. Requests call before mobilization RCV 01/18/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL . JC 01/19/22 NO ANS LEFT VM & EMAIL. JC 01/19/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-08 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-12-03 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2021-11-06 | Yes | 21 | 2022-01-28 |  | 2022-01-28 | 2022-01-28 |  | 2022-01-31 | 2022-02-01 | 21 | 2022-02-10 |  | 2022-02-02 | 2022-02-11 | 2022-02-11 | 2022-02-11 | Charles Makin | 1(530)957-2851 | rick@dbspublicadjusters.com/dcmakin9283@gmail.com |  | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 507 | 38.6453 | -120.516 | Caldor | DR-4619 | Residential | Yes | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
817 | 041-891-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7280 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4132.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-22 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-22 | 2022-01-18 | 2022-02-11 | "12.27 NO ANS LEFT VM & TEXT. JC 12.28 NO ANS LEFT VM & EMAIL. JC 12.28 GENE GAVE CONSENT VIA EMAIL. JC" 01/18/22 SPOKE WITH GENE HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK. PLEASE DO NOT REMOVE. JC 02/10/22 NO ANS LEFT VM & TEXT FOR TREES. JC 02/11/22 NO ANS LEFT VM & EMAIL. JC 02/11/22 GENE C/B HE SAID OK FOR TREE REMOVAL. JC 02/16/22 GENE TEXT FOR STATUS. JC 02/17/22 SPOKE WITH GENE ON TREE STATUS. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-27 | Yes | 15 | 2022-02-16 |  | 2022-02-16 | 2022-02-16 |  | 2022-02-21 | 2022-02-25 | 15 | 2022-03-09 |  | 2022-03-01 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Gene & Abbie Totten | 916-719-6089 | gdtotten@gmail.com | Septic | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 510 | 38.6456 | -120.5153 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
818 | 041-891-011 | Full Program ROE (debris + trees) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7318 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4123.56 |  | 2022-01-13 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2021-12-04 | No | [6 empty] | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-22 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | N/A | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-12-22 |  |  | 11.12 Spoke to David and he was wondering when his property would be cleared. he said ok to proceed but please call him first. PF | [27 empty] | 2021-11-15 | No | 0 | [14 empty] | DAVID & LAURIE MANSKE | 408-807-1325 | MACMANSKE@MAC.COM | Septic |  | 38.6457 | -120.5144 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
819 | 041-891-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7350 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4168.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-22 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-12-22 | 2021-12-27 | 2022-02-10 | 12.27 SPOKE WITH KATHLYNN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC. 01/21/22 KATHLNN SAID OK. JC 02/10/22 SPOKE WITH KATHLYNN SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-21 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2021-11-15 | Yes | 47 | 2022-02-15 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-21 | 2022-02-25 | 47 | 2022-03-09 |  | 2022-03-01 | 2022-03-17 | 2022-03-17 | 2022-03-17 | KATHLYNN LIVORSI | 530-313-3676 | KATHLYNN333@GMAIL.COM | Vehicles on site Septic | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 510 | 38.6453 | -120.5124 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
820 | 041-891-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 041-891-014 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4126.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | No |  |  | 2021-12-07 | Yes | 2021-12-07 | 2022-03-08 | POSITIVE | 2022-01-26 | 2022-01-26 | -30 | 2021-11-23 | Bio Monitoring Needed for Trees, not Debris | 2021-12-22 | Arch Monitoring Needed for Debris AND Trees | [6 empty] | Yes | 2022-03-08 | No |  | TRUE |  | No | None | FALSE | [10 empty] | 2022-01-26 | 2022-01-28 | 2022-03-26 | 01/28/22 NO ANS LEFT VM & TEXT. JC 01/28/22 SPOKE WITH WILLIAM HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK ON PROPERTY. JC 3.24 SPOKE TO WM. HE SAID OK AND GRANTED PERMISSION TO FELL TREES OF NEIGHBORS ONTO HIS PARCEL. GAVE HIM AN UPDATE THAT WE ARE WAITING FOR A PROPERTY LINE SURVEY TO SCHEDULE HIS. PF 03/26/22 SPOKE WITH WILLIAM HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-29 |  | 2022-01-31 | 2022-01-31 |  |  | 5 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-03-10 | Yes | 162 | [14 empty] | William Peters | 707-734-0918 | billsthrills@sbcglobal.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 02/02 to 02/05 Crew 510 | 38.6445 | -120.5133 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
821 | 041-891-015 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4841 | Cypress Point Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4088 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 5 |  |  |  |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-21 | Bio Monitoring Needed for Debris AND Trees | 2022-02-03 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-14 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-02-03 | 2022-02-04 | 2022-03-16 | 02/04/22 SPOKE WITH MICHAEL HE SAID OK. PLEASE CALL IN ADVANCE. PLEASE DO NOT REMOVE THE DRIVEWAY AND DO NOT REMOVE PROPANE TANK. JC 03/16/22 SPOKE WITH MICHAEL HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-08 |  | 2022-02-09 | 2022-02-09 |  |  | 3 | 2022-02-11 | 2022-02-21 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-02-03 | Yes | 114 | 2022-03-23 |  | 2022-03-25 | 2022-03-25 |  | 2022-04-01 | 2022-04-02 | 114 |  |  | 2022-04-05 |  |  |  | Michael J McBride | 530-748-7340 | mkbigmac1@aol.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 504 | 38.6438 | -120.5127 | Caldor | DR-4619 | Residential | Yes | 2021-12-09 | ROE Verified | Central Division | 2022-04-05T22:04:50Z | FALSE | 7
822 | 041-893-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7305 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4022.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 3 |  |  | 1 |  | Yes | Leave |  | 2022-01-18 | Yes | 2022-01-18 | 2022-01-21 | NEGATIVE |  |  |  | 2021-12-06 | Bio Monitoring Needed for Debris AND Trees | 2022-01-27 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-04 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-27 | 2022-01-31 | 2022-03-25 | 01/29/22 NO ANS LEFT VM & TEXT JC 01/31/22 WRONG NUMBER ON FILE. SENT EMAIL. JC 01/31/22 SPOKE WITH JON HE SAID OK. PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 03/25/22 SPOKE WITH JON. HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Approved | [12 empty] | 2022-02-16 | 2022-01-31 | Yes | 111 | [14 empty] | MARIA ALMEIDA & JON BUCK | 530-620-5180 | grizzlyjon@att.net |  | Debris Crew Leader/Crew# Crystal Egan / 505 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 505 | 38.6429 | -120.5151 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
823 | 041-893-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7261 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4010.11 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 |  |  | 1 |  | No |  |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-24 | Bio Monitoring Needed for Trees, not Debris | 2021-12-02 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Survey Needed | Yes | 2022-03-05 | No |  |  | Tree & Operational | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-01 | 2021-12-02 |  | 12.02 Contacted homeowner, but wants to keep foundation. Forwarded to Dale. Okayed debris start RCV |  |  |  | 2021-12-04 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape |  |  |  | 2022-01-17 | 2022-01-25 | Re-scrape | 2022-02-01 | 2022-02-09 | Approved |  |  |  | 2022-02-10 | 2022-01-28 | Yes | 107 | [14 empty] | Damon and Ericca Ciochetti | 916-955-6642 | eciochetti@yahoo.com | Septic | Debris Crew Leader/Crew# Antonio Ruiz/#510 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 510 | 38.6429 | -120.5162 | Caldor | DR-4619 | Residential | Yes | 2021-10-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
824 | 041-940-009 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 5026 | Old Mine Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3612.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 3 |  |  |  |  | Yes | Take |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | POSITIVE | 2021-12-11 | 2021-12-11 | 2 | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-10 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-22 | 2022-01-24 |  | 01/24/22 NO ANS LEFT VM & TEXT. JC 01/24/22 SPOKE WITH DAVID HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE ALL PROPANE TANKS. JC |  |  |  | 2022-02-14 |  | 2022-02-15 | 2022-02-15 |  |  | 4 | 2022-02-18 | 2022-02-28 | 7 | Re-scrape |  |  |  | 2022-03-11 | 2022-03-21 | Approved | [6 empty] | 2022-03-23 | 2022-01-27 | No | 0 | [14 empty] | David Mathis | 916-837-2251 | davidgarymathis@gmail.com |  | Debris Crew Leader/Crew# Adam Mattsson / #507 Debris Crew WO# Refer to IAP 02/16 To 02/19 Crew 507 | 38.639 | -120.5452 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
825 | 041-494-012 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7148 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3980.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-02-28 | Bio Monitoring Needed for Trees, not Debris | 2022-01-20 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 |  |  | 2022-02-21 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 KEVIN C/B HE SAID OK. JC | [27 empty] | 2022-01-21 | Yes | 16 | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-02 | 2022-03-04 | 16 |  |  | 2022-03-14 |  | 2022-03-14 | 2022-03-14 | Kevin Fedor | 408-775-2795 | kfedor34@gmail.com |  |  | 38.6409 | -120.5237 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
826 | 041-501-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6667 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3971.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2022-03-09 | Bio Monitoring Needed for Trees, not Debris | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-09 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-21 | No |  | TRUE |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-11-15 | 2021-11-19 | 2022-03-03 | 11.16 NO ANS LEFT VM. JC 11.17 NO ANS LEFT VM. SENT EMAIL JC 11.18 NO ANS LEFT VM. JC GAVE TO RCV 02/28/22 NO ANS LEFT VM & TEXT. JC 03/01/22 NO ANS LEFT VM & EMAIL. JC 03/02/22 ﻿NO ANS LEFT VM & 2ND EMAIL. JC 03/03/22 CLEARED TO PROCEEED PER MELISSA. JC | 3 | Kendall Wilson/ TREEs/ State planner: Melissa Perry |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2022-02-24 | 2022-01-10 | Yes | 13 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-26 | 14 | 2022-03-30 |  | 2022-03-28 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Jacob Sharp | 530 417-6028, 916-799-2347 | jesisharp3a@gmail.com | Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/17 to 11/20Crew 503 | 38.6386 | -120.5259 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:11:28Z | FALSE | 7
827 | 041-501-002 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6677 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3973.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Yes | Take | 2022-02-16 | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | POSITIVE | 2021-12-02 | 2021-12-02 | 2 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-21 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-12-02 | 2021-12-03 | 2022-03-02 | 12.03 SPOKE WITH ELIZABETH SHE SAID BUT PLEASE CALL PLEASE CALL IN ADVANCE. THEY OWN PROPANE TANK BUT UNSURE IF DAMAGED BY FIRE. WILL DISCUSS WITH CREW LEADER. JC 01/25/22 SPOKE WITH ELIZABETH SHE SAID IF DAMAGED REMOVE IF NOT LEAVE PROPANE TANK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 HO GAVE CONSENT VIA VOICEMAIL. JC |  |  |  | 2021-12-07 |  | 2021-12-07 | 2021-12-07 |  |  | 39 | 2022-01-31 | 2022-02-08 | 7 | Re-scrape |  |  |  | 2022-02-15 | 2022-02-23 | Approved | [6 empty] | 2022-02-25 | 2022-01-11 | Yes | 18 | 2022-03-29 |  | 2022-03-30 | 2022-03-30 |  | 2022-04-04 | 2022-04-05 | 16 |  |  | 2022-04-06 |  |  |  | NELSON KARL S & STATHOPOULOS ELIZABETH M | 530-391-5680 | liz.stathopoulos@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Cynthia Sanderson /#501 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 501 | 38.6386 | -120.5255 | Caldor | DR-4619 | Residential | Yes | 2021-11-09 | ROE Verified | Central Division | 2022-04-06T22:49:58Z | FALSE | 5
828 | 041-501-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6685 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3967.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 4 |  |  | 2 |  | No |  |  | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-21 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-01 | 2021-12-03 | 2022-02-22 | 12.03 NO ANS & NO VOICEMAIL. JC 12.03 SPOKE WITH HO SAID OK BUT PLEASE CALL IN ADVANCE﻿. NO PROPANE TANK. JC 02/22/22﻿ SPOKE WITH DARLEE SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 36 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-11 | Yes | 8 | 2022-03-21 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-22 | 2022-03-26 | 8 |  |  | 2022-03-28 |  |  |  | Darlee James | 530-388-8974 | daryleeroppelt@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Romero /#502 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 502 | 38.6386 | -120.5252 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
829 | 041-502-001 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1a | 6668 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3931.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 3 |  | Yes | Leave |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | Bio Monitoring Needed for Trees, not Debris | 2021-11-19 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-04 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-21 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-19 | 2021-11-23 | 2022-02-23 | 11.22 NO ANS LEFT VM JC. 11.23 NO ANS LEFT VM SENT EMAIL JC. 11.23 SPOKE WITH TAMARA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/22/22 NO ANS LEFT VM & TEXT. JC 02/23/22 NO ANS LEFT VM & EMAIL. JC 02/23/22 TAMARA C/B SHE SAID OK BUT PLEASE CALL IN ADVANC. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-13 | 7 | Re-scrape |  |  |  | 2022-01-19 | 2022-01-27 | Approved | [6 empty] | 2022-02-01 | 2022-01-11 | Yes | 68 | 2022-04-05 |  | 2022-04-07 | 2022-04-07 |  |  |  | 66 | [6 empty] | RURKA CHARLES D JR & TAMARA S | 530-409-4194 | tamarasue0586@gmail.com |  | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 503 | 38.6376 | -120.5257 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-08T16:19:12Z | FALSE
830 | 041-511-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7140 | Capps Crossing Rd |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4035.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-01-29 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | [11 empty] | 2022-01-28 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-15 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-02-26 | 02/26/22 NO ANS LEFT VM & TEXT JC 02/26/22 DEBBIE C/B SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-29 | Yes | 50 | 2022-03-18 |  | 2022-03-19 | 2022-03-19 |  | 2022-03-23 | 2022-03-30 | 50 |  |  | 2022-03-31 |  | 2022-03-31 | 2022-03-31 | Ernie Lynn Cumbra. Tr & Debra Lynn Havey-Cumbra Tr | 916-799-4871 | dcumbra@yahoo.com |  |  | 38.6428 | -120.5212 | Caldor | DR-4619 | Residential | No | 2022-01-21 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
831 | 041-512-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4926 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4003.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 3 |  |  | 1 |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-22 | No Arch Monitoring Needed for Debris or Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-17 | Yes | 2022-02-15 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-22 | 2021-11-24 | 2022-02-22 | "11.23 NO ANS LEFT VM. JC 11.24 NO ANS LEFT VM. SENT EMAIL. JC 11.24 SPOKE DEAN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC" 02/21/22 ﻿NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 SPOKE WITH DEAN HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 5 | 2021-12-06 | 2021-12-14 | 7 | Re-scrape |  |  |  | 2022-01-25 | 2022-02-02 | Approved | [6 empty] | 2022-02-04 | 2021-11-10 | Yes | 47 | [14 empty] | DEAN DUMITRESCU | 925-323-4334 | dean1co@yahoo.com | Vehicles on site Septic | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 505 | 38.6416 | -120.5222 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
832 | 041-696-003 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10204 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3818.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | TRUE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 6 |  |  | 7 | TRUE | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-06 | 2021-11-08 | 2022-01-14 | 11.8 SPOKE WITH AMANDA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC 12.4 SPOKE WITH AMANDA SHE SAID OK. JC 01/14/22 SPOKE WITH AMANDA OK. JC |  |  |  | 2021-11-12 |  | 2021-11-12 | 2021-11-12 |  |  | 3 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-11-02 | No | 0 | [8 empty] | 2022-01-27 |  |  | 2022-01-28 | 2022-01-28 | 2022-01-28 | Amanda Sooth | 530-957-4264 | amanda.sooth83@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 505 | 38.6335 | -120.5319 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
833 | 041-697-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5238 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3840.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-30 | 2021-10-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-08 | 2021-11-09 | 2021-12-04 | 11.9 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SPOKE WITH MICHAEL HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-13 | 2021-11-13 |  |  | 2 | 2021-11-16 | 2021-11-24 | 7 | Approved | [12 empty] | 2021-11-29 | 2021-10-30 | Yes | 2 | 2022-01-04 |  | 2022-01-04 | 2022-01-04 |  | 2022-01-06 | 2022-01-06 | 2 | 2022-01-25 |  | 2022-01-19 | 2022-01-27 | 2022-01-27 | 2022-01-27 | MICHAEL SAYER | 303-854-7865 | MIKE.W.SAYER@GMAIL.COM | Vehicles on site Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 505 | 38.6338 | -120.5314 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
834 | 041-701-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5150 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3802.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-05 | 2021-10-05 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | POSITIVE | 2021-10-22 | 2021-10-22 | 10 | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-22 | 2021-10-26 | 2022-02-11 | 10.25 SPOKE TO WENDI AND SHE SAID OK. PLEASE CALL FIRST. PF 12.4 SPOKE WITH WENDI SHE SAID OK. JC 01/26/22 SPOKE WITH WENDI SHE SAID VENDOR HANDLING PROPANE TANK AND SHE GIVE PRE APPROVAL FOR TREE REMOVAL. JC 02/11/22 SPOKE WITH WENDI SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-01 |  | 2021-11-01 | 2021-11-01 |  |  | 6 | 2021-11-08 | 2021-11-17 | 8 | Approved | [12 empty] | 2021-11-19 | 2021-10-29 | Yes | 35 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-19 | 2022-03-21 | 35 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | WENDI & LAWRENCE BARBA | 530-919-2131 | WENDIBARBA@YAHOO.COM |  | "Debris Crew Leader/Crew# Max Patterson/506 Debris Crew WO# Refer to IAP 10/30 to 11/3 Crew 506 | 38.6357 | -120.5338 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 9
835 | 041-701-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5164 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3804.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-11 | Yes | 2021-12-11 | 2021-12-15 | NEGATIVE |  |  |  | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-19 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-31 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-19 | 2022-01-20 |  | "01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO C/B SHE SAID OK. VENDOR HANDLING PROPANE TANK. JC" |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 3 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-17 | Yes | 20 | [14 empty] | Mitchell & Kaitlyn Dunn | 916-380-2722 | kaitlynmdunn5@gmail.com |  | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 503 | 38.6355 | -120.5336 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
836 | 041-701-010 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5180 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3815.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 1 | 1 | 2 | 0 | 1 | 0 | 9 | [7 empty] | 2021-12-01 | No | [6 empty] | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-02-16 | 02/16/22 SPOKE WITH ROBERT HE SAID OK FOR TREE REMOVAL. DO NOT REMOVE PROPANE TANKS. JC 3.15 SPOKE TO MR LOWERY ABOUT THE VEHICLES PER MP. HE AGREED FOR US TO GO AHEAD AND MOVE THEM AND CARRY THEM AWAY. PF | [27 empty] | 2021-12-22 | Yes | 28 | [14 empty] | Robert & Melissa Lowery | 530-503-7752 | melissa.lowery@att.net |  |  | 38.6354 | -120.533 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-05T23:16:01Z | FALSE
837 | 041-701-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5188 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3820.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 4 |  |  |  | TRUE | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Survey Needed | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-07 | 2021-12-07 | 2022-03-22 | 12.07 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK IS NOT DAMAGED DO NOT REMOVE. JC 3.22 SPOKE TO ROBERT AND HE SAID OK PF |  |  |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 |  |  | 35 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-17 | Yes | 19 | [14 empty] | Robert & Melissa Lowery | 530-503-7752 | melissa.lowery@att.net | Vehicles Onsite | Debris Crew Leader/Crew# Mattson Adams /#507 Debris Crew WO# Refer to IAP -- to --- Crew 507 | 38.6354 | -120.5326 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-06T18:41:13Z | FALSE
838 | 041-701-012 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5192 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3827.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-28 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2022-01-21 | 2022-03-28 | "12.11 NO ANS LEFT VM & TEXT. JC 12.11 HO GAVE CONSENT VIA TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC" 02/14/22 NO ANS LEFT VM & TEXT. JC 02/14/22 HO TEXT BACK. VENDOR HANDLING PROPANE TANK. JC 03/28/22 SPOKE WITH CONSTANCE SHE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2022-01-26 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-01-18 | Yes | 27 | [14 empty] | Roger & Constance Van Guilder | 707-477-1493 | Cvanguilder@sbcglobal.net |  | Debris Crew Leader/Crew# Zara Armani/ #503 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 503 | 38.6353 | -120.5323 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
839 | 041-701-016 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5218 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3832.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | Yes |  | 2021-12-10 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-02 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-10 | 2022-01-21 | 2022-03-03 | "12.10 NO ANS LEFT VM & TEXT. JC 12.10 HO GAVE CONSENT VIA TEXT. JC 01/21/22 MR. LEE SAID OK. JC" 03/03/22 NO ANS LEFT VM & TEXT. JC 03/03/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-24 |  | 2022-01-25 | 2022-01-25 |  |  | 5 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-20 | Yes | 9 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-19 | 2022-03-21 | 9 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | EDDIE LEE | 650-766-4553 | ampemployee1@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Collins/ # 503 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 503 | 38.6344 | -120.532 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
840 | 041-711-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5217 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3815.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-20 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-03-01 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-24 | 2021-11-18 | 2022-03-05 | 11.18 SPOKE WITH BRIAN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLE PROPANE TANK. JC 03/03/22 NO ANS LEFT VM & TEXT JC 03/04/22 NO ANS LEFT VM. NO EMAIL SENT 2ND TEXT. JC 03/05/22 NO ANS LEFT VM. JC 03/05/22 OK TO PROCEED PER MELISSA PERRY | 3 | State Planner: Melissa Perry |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Re-scrape |  |  |  | 2022-01-18 | 2022-01-26 | Approved | [6 empty] | 2022-01-27 | 2022-03-01 | Yes | 19 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-21 | 2022-03-22 | 19 | 2022-03-24 |  | 2022-03-23 | 2022-03-29 | 2022-03-29 | 2022-03-29 | DINSMORE, BRIAN | 408-379-3504 |  | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Justin Romero/#502 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 502 | 38.6342 | -120.5325 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
841 | 041-711-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5185 | Wooded Glen Dr |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3810.77 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-01-20 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-01-27 | No Bio Monitoring Needed for Debris or Trees | 2022-02-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-09 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-16 | 3.16 Spoke to Tricia. She said ok PF | [27 empty] | 2022-02-01 | Yes | 28 | [14 empty] | Tricia Milburn | 916-396-9842 | tmilburn@wkblaw.com |  |  | 38.6349 | -120.533 | Caldor | DR-4619 | Residential | No | 2022-01-10 | ROE Verified | Central Division | 2022-04-07T16:13:32Z | FALSE
842 | 041-711-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5163 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3796.74 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | 2022-04-06 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-14 | 2022-01-19 | 2022-03-03 | 12.11 NO ANS VOICEMAIL FULL SENT EMAIL. JC 12.13 SPOKE WITH GLORIA SHE SAID OK. BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE THANK. JC 01/19/22 NO ANS LEFT VM TEXT. JC 01/19/22 HO GAVE CONSENT VIA TEXT. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 NO ANS LEFT VM & EMAIL. JC 03/03/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/03/22 SPOKE WITH GLORIA SHE SAID OK. JC |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 4 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-06 | Yes | 20 | [14 empty] | Joseph & Gloria Lopez | 530-599-0322 , 530-391-6997 | gloria73lopez@gmail.com | Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 503 | 38.6351 | -120.534 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-08T18:39:18Z | FALSE
843 | 041-711-008 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5159 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-28 |  | FALSE | [5 empty] | No | Yes | No | No | No | No |  | TRUE | 1 | 2 | 0 | 0 | 0 | 0 | 3 | 6 |  |  |  | TRUE | Yes | [10 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | N/A | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-01-25 | 01/24/22 NO ANS MAILBOX IS FULL SENT EMAIL. JC 01/25/22 NO ANS LEFT VM & TEXT. JC 01/25/22 GLORIA C/B SHE SAID OK FOR TREE REMOVAL. JC 02/10/22 GLORIA SAID OK. JC | [27 empty] | 2021-12-22 | Yes | 23 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-19 | 2022-03-21 | 23 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 | Joseph & Gloria Lopez | 530-599-0322 , PLEASE CALL 530 391-4163 | gloria73lopez@gmail.com |  |  | 38.6353 | -120.5343 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 8
844 | 038-361-015 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7121 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6562.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-18 | 2021-11-18 | 3 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-13 | 2021-11-18 | 2021-11-24 |  | 11.18 BUSY SENT EMAIL. JC 11.19 BUSY. JC GAVE TO RCV 11.24 TFL contacted homeowner who consented to start of operations |  |  |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Re-scrape | [13 empty] | 2021-12-08 | Yes | 27 | [14 empty] | Suzanne Metzinger | 916-715-5044 | suzskate@yahoo.com | Septic | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 514 | 38.8069 | -120.1051 | Caldor | DR-4619 | Residential | No | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
845 | 038-361-016 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7125 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6570.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | Yes |  | 2021-11-23 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-13 | 2021-11-23 | 2021-11-18 |  | 11.18 SPOKE WITH JOHN HE SAID OK AND DOES NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Re-scrape | [13 empty] | 2021-12-08 | Yes | 12 | [14 empty] | John Graifemberg | 916-709-7575 | jrgraifemberg@gmail.com | Septic | Debris Crew Leader/Crew# Carla Herbest/#514 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 514 | 38.8069 | -120.1048 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
846 | 038-361-017 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7131 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6568.58 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-11-24 | 2021-11-24 | 3 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-24 | 2021-11-29 |  | 11.24 NO ANS LEFT VM. JC 11.29 NO ANS LEFT VM. JC 11.29 SENT EMAIL JC |  |  |  | 2021-11-30 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2021-12-08 | Yes | 25 | [14 empty] | Mike and Laura Hibbard | 415-990-1212 | mason.hibbard@compass.com | Septic | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 12/01 To 12/04 Crew 514 | 38.8069 | -120.1046 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
847 | 038-361-018 | Full Program ROE (debris + trees) | Re-scrape Needed | Haz Trees Present | Next Step: N/A | ELD Twin Bridges Rescrapes | TWB Pending | 7137 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6571.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 | 2021-10-22 | FALSE | Yes |  | 2021-11-19 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-04-12 | 2021-11-19 | 2021-11-24 |  | 11.19 NO ANS LEFT VM. JC 11.22 NO ANS LEFT VM. SENT EMAIL. JC 11.22 HO EMAILED BACK. DO NOT WANT TO BE CONTACTED EVER. JC |  |  |  | 2021-11-24 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Re-scrape | [13 empty] | 2021-12-04 | Yes | 26 | [14 empty] | EDWARD & ANNETTE KELLY | 916-606-1321 | edkelly50@gmail.com | Septic | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 514 | 38.8069 | -120.1044 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-02T01:00:48Z | FALSE
848 | 038-361-019 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7141 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6571.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-22 | 2021-12-01 |  | 12.01 contacted homeowner, okayed debris removal RCV |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-12-08 | Yes | 20 | [14 empty] | Roberta Sparkman & George Smith | 916-397-3445 | roberta.sparkman@att.net | Other Septic | Debris Crew Leader/Crew# Carla Herbst /#514 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 514 | 38.8069 | -120.1041 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
849 | 038-361-020 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7147 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6576.09 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 |  | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-10 | Yes | 2021-11-11 | 2021-11-16 | POSITIVE | 2021-11-18 | 2021-11-18 | 3 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-18 |  | 11.18 SPOKE WITH OWNER HE SAID OK AND HE DOES NOT NEED TO BE THERE. BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 3 | 2021-11-24 | 2021-12-06 | 7 | Approved | [12 empty] | 2021-12-07 | 2021-12-07 | Yes | 12 | [14 empty] | TYRONE BEEBY | 925-989-2840 | rwagles516@gmail.com |  | Debris Crew Leader/Crew# Carla Herost/#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8069 | -120.1039 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
850 | 038-361-021 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7151 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6573.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |  |  | 1 |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-19 |  | 11.19 SPOKE WITH DOUG HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 5 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-12-08 | Yes | 38 | [14 empty] | Timothy & Bela Kriner | 916-956-3161 | timkriner@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Carla Herost/#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8069 | -120.1037 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
851 | 038-361-024 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7163 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6575.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-11-24 | 2021-11-24 | 3 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 |  |  |  |  | No |  | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-30 | 2021-11-22 |  | 11.22 SPOKE WITH ROBERT HE SAID OK BUT CALL IN ADVANCE. DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 4 | 2021-12-06 | 2021-12-14 | 7 | Approved | [12 empty] | 2021-12-15 | 2022-03-31 | Yes | 21 | [14 empty] | HENCKEN ROBERT P & HAEFELE BRANDON TR | 650-380-1756 | rhencken@hdc-11c.net | Septic | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8067 | -120.103 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
852 | 038-361-025 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7167 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6573.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | [8 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-07 | Yes | 8 | [14 empty] | Kathleen Grace O'brien | 916-533-6227 | kobatwilton@gmail.com |  |  | 38.8065 | -120.1029 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
853 | 038-362-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7160 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6564.31 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-19 |  | 11.19 NO ANS NO VM SENT EMAIL. JC 11.19 SPOKE IWHT LEE HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR TAKING CARE OF PROPANE TANK. JC |  |  |  | 2021-11-22 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2022-03-31 | Yes | 8 | [14 empty] | Lee Grignon & Beverly Achterhof | 415-404-2619 | leegrignon@gmail.com, bev.achterhof@gmail.com | Septic | Debris Crew Leader/Crew# Carla Herost /#514 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 514 | 38.8064 | -120.1034 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
854 | 038-362-002 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Haz Trees Present | Next Step: N/A | Ready for Soil Sampling | TWB Pending | 7154 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6563.03 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-12-04 | 2021-12-04 | 8 | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-12-04 | 2021-12-06 |  | 12.06 NO ANS LEFT VM & TEXT FROM MY PERSONAL PHONE DUE TO INTERNET ISSUES. JC 12.06 SPOKE WITH GREG HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 88 | [17 empty] | 2021-12-08 | Yes | 5 | [14 empty] | Greg & Yvonne Conlin | 925-285-7864 | Conlin67@hotmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 514 | 38.8064 | -120.1036 | Caldor | DR-4619 | Residential | Yes | 2021-10-26 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
855 | 038-362-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7148 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6564.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-15 | 2021-11-18 | POSITIVE | 2021-11-22 | 2021-11-22 | 3 | 2021-11-06 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-22 |  | 11.22 NO ANS LEFT VM JC 11.22 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL ADVANCE. PLEASE REMOVE SMALL PROPANE TANKS. JC |  |  |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 |  |  | 3 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2022-03-31 | Yes | 11 | [14 empty] | MICHAEL CARBIN & CAROLYN CHANG | 916-296-1931 | carolynmkchang@gmail.com | Septic | "Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 514 | 38.8064 | -120.1039 | Caldor | DR-4619 | Residential | Yes | 2021-09-21 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
856 | 038-362-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 7142 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6562.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | POSITIVE | 2021-11-23 | 2021-11-23 | 2 | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-23 | 2021-11-23 |  | 11.23 SPOKE WITH WESLEY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. CJ |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2022-03-31 | Yes | 13 | [14 empty] | Wesley & Dawn Hardaker | 530-404-0099 | bills@hardakers.net | Other Septic | Debris Crew Leader/Crew# Carla Herbst /#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8064 | -120.1041 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
857 | 038-362-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7138 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6564.8 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-06 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-16 | 2021-11-18 | 2021-11-19 |  | 11.19 SPOKE WITH ADAM HE SAID OK BUT PLEASE CALL ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 |  |  | 4 | 2021-12-01 | 2021-12-09 | 7 | Approved | [12 empty] | 2021-12-10 | 2021-12-07 | Yes | 14 | [14 empty] | ADAM & ANDREA BROWN | 530-906-4545 | adambrown.d@gmail.com |  | Debris Crew Leader/Crew# Carla Herost/#514 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 514 | 38.8064 | -120.1043 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
858 | 038-362-006 | Full Program ROE (debris + trees) | Ready for Debris Removal | Haz Trees Present | Next Step: N/A | Twin Bridges Ready | Tree Assessment Complete | 7132 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6561.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-04-11 | 2021-12-08 | 2022-01-21 |  | 12.09 NO ANS MAILBOX FULL SENT TEXT. JC 12.09 HO GAVE CONSENT VIA TEXT. JC 01/21/22 NO ANS LEFT VM AND TEXT. HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-03-31 | Yes | 12 | [14 empty] | Michael & Cheryl Morris | 707-337-2904 | tiggersmanager@gmail.com |  |  | 38.8065 | -120.1046 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
859 | 038-362-007 | Full Program ROE (debris + trees) | Chimney Tip Needed | Haz Trees Present | Next Step: N/A | Twin Bridges Ready | TWB Pending | 7128 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6560.42 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-07 | 2021-12-07 | FALSE | Yes |  |  | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2021-12-07 | Bio Monitoring Needed for Trees, not Debris | [8 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-15 |  |  |  | 12.09 NO ANS LEFT VM. JC 12.10 NO ANS LEFT VM. JC | [27 empty] | 2021-12-07 | Yes | 18 | [14 empty] | HEISTER, CYNTHIA D | 831-338-1511 , 831-331-5038 | cynthiaheister@gmail.com |  |  | 38.8065 | -120.1048 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
860 | 038-362-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7120 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6558.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-11 | 2021-11-11 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-05 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2021-11-22 | 2021-11-30 |  | 11.23 NO ANS LEFT MESS. JC 11.29 NO ANS LEFT VM. JC 11.29 SENT EMAIL. JC 11:30 NO ANS MAILBOX FULL GAVE TO RICHARD. JC 01/25/22 NO ANS LEFT VM AND TEXT FOR PROPANE TANK. JC 01/27/22 VENDOR HANDLING PROPANETANK. JC | 4 | Kendall Wilson |  | 2021-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 3 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2021-12-07 | Yes | 10 | [14 empty] | MAGGIE & STEPHEN HOPKINS | 916-549-3131/916-717-2318 | maggiebhomes@gmail.com, swrhopkins@gmail.com | SEPTIC | Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 514 | 38.8065 | -120.105 | Caldor | DR-4619 | Residential | Yes | 2021-10-25 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
861 | 038-362-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7116 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6555.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-21 | 2021-12-01 | 2021-12-02 |  | carla Herbst: The owner requested to avoid the biological wetlands zone and keep the brick fire pit if possible. |  |  |  | 2021-12-02 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2021-12-07 | Yes | 21 | [14 empty] | WELCH LARRY D TR & LEONA J | 916-216-4788 | welchll@sbcglobal.net | Septic | "Debris Crew Leader/Crew# Carla Herbst/#514 Debris Crew WO# Refer to IAP 02/05 To 02/09 Crew 514 | 38.8065 | -120.1053 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
862 | 038-362-010 | Full Program ROE (debris + trees) | Withdrawn | Needs Assessment | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 7112 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6558.64 | 2021-11-30 |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-22 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-06 | Yes | 2021-11-08 | 2021-11-12 | NEGATIVE |  |  |  | 2021-11-05 | Bio Monitoring Needed for Trees, not Debris | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | [32 empty] | Ok to Assess | [15 empty] | CLYDE & SANDRA COOPER | 707-965-3819 | COOPER.CLYDE@ATT.NET | Septic |  | 38.8065 | -120.1055 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
863 | 038-362-011 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7104 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6555.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-06 | Bio Monitoring Needed for Trees, not Debris | [8 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-06 | Yes | 40 | [14 empty] | Brooke Davis, Bethany Berkowitz | 415-516-3141 | Lauryn@coastside.net |  |  | 38.8064 | -120.1057 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
864 | 038-362-012 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 7098 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6555.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-06 | Bio Monitoring Needed for Trees, not Debris | [8 empty] | Yes | 2022-04-06 | [6 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-06 | Yes | 17 | [14 empty] | Brooke Davis, Bethany Berkowitz | 415-516-3141 | Lauryn@coastside.net | Other Septic |  | 38.8064 | -120.106 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T00:18:45Z | FALSE
865 | 038-362-016 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | TWB Pending | 7092 | Mount Ralston Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6552.41 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-17 | 2021-11-17 | FALSE | Yes |  | 2021-11-30 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-16 | Yes | 2021-11-16 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-23 | Bio Monitoring Needed for Debris AND Trees | 2021-11-19 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | Yes | 2022-04-06 | Yes | [5 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-11-23 | 2021-11-29 |  | 11.29 SPOKE WITH HO SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-13 | 6 | Approved | [12 empty] | 2021-12-14 | 2021-12-07 | Yes | 22 | [14 empty] | Brooke Davis, Bethany Berkowitz | 415-516-3141 | Lauryn@coastside.net | Other Septic | Debris Crew Leader/Crew# Carla Herbst /#514 Debris Crew WO# Refer to IAP 12/01 to 12/04Crew 514 | 38.8063 | -120.1062 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T15:21:45Z | FALSE
866 | 038-382-004 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 205 | Margaret Drive |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 5942.13 |  | 2021-12-08 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-04-01 | [31 empty] | 2021-12-06 | No | 0 | [14 empty] | ESTEN JAMES M & RENEE | 916-801-2528 , 916-803-2528 | correctcon@aol.com |  |  | 38.8042 | -120.1435 | Caldor | DR-4619 | Residential | Yes | 2021-11-18 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
867 | 038-390-002 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 038-390-002 | No Address |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6649.56 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-03 | Bio Monitoring Needed for Trees, not Debris | [14 empty] | Class I |  | FALSE | [8 empty] | FALSE | [33 empty] | Ok to Assess | [15 empty] | COUPERUS JAMES J TR & CHERYL | 909-793-6944 | jjcouperus@yahoo.com |  |  | 38.8022 | -120.1039 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
868 | 038-390-003 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Needs Assessment | Next Step: N/A | Ready for Soil Sampling | Tree Assessment Needed | 7340 | Sayles Canyon Road |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 6566.67 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | POSITIVE | 2021-12-04 | 2021-12-04 | 5 | 2021-11-20 | Bio Monitoring Needed for Debris AND Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | 2021-12-04 | 2021-12-06 |  | 12.06 NO ANS LEFT VM & TEXT FROM MY PERSONAL PHONE DUE TO INTERNET ISSUES. JC 12.06 SPOKE WITH MARK HE SAID OK BUT PLEASE CALL IN ADVANCE. HE IS NOT SURE IF PROPANE TANK IS BURNED BUT WILL DISCUSS WITH CREW LEADER. JC |  |  |  | 2021-12-07 |  | 2021-12-07 | 2021-12-07 |  |  | 88 | [18 empty] | Ok to Assess | [15 empty] | Mark Harris | 714-273-9607 | MMGHARRIS1@AOL.COM |  | Debris Crew Leader/Crew# Melanie Poole /#512 Debris Crew WO# Refer to IAP 12/0 to 12/0 Crew 512 | 38.8038 | -120.1038 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
869 | 038-421-003 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | TWB Pending | 16261 | Strawberry Lane |  | TWIN BRIDGES | El Dorado |  | Residential | [5 empty] | 5761.24 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-18 | No | [6 empty] | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | No | Covered under suspension | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-03-28 | [31 empty] | 2021-12-04 | Yes | 1 | [14 empty] | Eric Knight & Christine Huffard | 510-708-2493 , 831-334-9308 | e-knight@hotmail.com, chuffard@gmail.com | Septic |  | 38.7971 | -120.1422 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
870 | 038-421-004 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 16263 | Strawberry Lane |  | Twin Bridges | El Dorado |  | Residential | [5 empty] | 5760.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-11-18 | No | [6 empty] | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | [7 empty] | FALSE | [8 empty] | TRUE | 2022-03-28 | [31 empty] | 2021-12-08 | Yes | 1 | [14 empty] | William & Robin Hopkins | 831-818-4959 , 831-566-8900 | hopper55@yahoo.com, rshopkins62@gmail.com | Septic |  | 38.7968 | -120.1423 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
871 | 041-850-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 041-850-003 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3842.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Take |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2022-01-27 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [10 empty] | 2022-01-27 | 2022-01-28 | 2022-03-02 | 01/28/22 SPOKE MICHAEL HE SAID OK. PLEASE REMOVE PROPANE TANK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 SPOKE WITH MICHAEL HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-04 |  | 2022-02-07 | 2022-02-07 |  |  | 4 | 2022-02-10 | 2022-02-18 | 7 | Approved | [12 empty] | 2022-02-21 | 2021-11-15 | Yes | 19 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-30 | 2022-03-31 | 19 |  |  | 2022-04-04 |  |  |  | KRUSCHKE, MICHAEL | 916-798-3144 | mike.kruschke@gmail.com |  | Debris Crew Leader/Crew# Terrence Harrison / #502 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 502 | 38.6358 | -120.5278 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-04T20:44:44Z | FALSE | 8
872 | 041-891-019 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-891-019 | No Address |  | Grizzly Flats | El Dorado |  | Other | [5 empty] | 4061.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [12 empty] | 2022-03-01 | 01/28/22 SPOKE WITH DIANA SHE OK ABT TREE REMOVAL. JC 03/01/22 SPOKE WITH DIANA SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-03-10 | Yes | 81 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-24 | 2022-03-30 | 81 |  |  | 2022-03-31 |  | 2022-03-31 | 2022-04-04 | GERALD & DIANA EDIE | 530-333-5770 | gerdee@sbcglobal.net |  |  | 38.6431 | -120.5189 | Caldor | DR-4619 |  | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-04T18:21:19Z | FALSE | 2
873 | 041-891-021 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7234 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4087.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-09 | 2021-10-09 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 0 | 2 | 0 | 6 |  |  |  | TRUE | Yes | Take | 2022-03-07 | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-15 | No Bio Monitoring Needed for Debris or Trees | 2021-10-15 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class I | Covered under suspension | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-16 | 2021-10-28 | 2022-01-20 | 10.28 SPOKE TO DIANA AND SHE SAID OK PF 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC 01/28/22 SPOKE WITH DIANA SHE SAID TO REMOVE PORPANE TANK ONLY IF DAMAGED. JC 02/16/22 Homeowner called with a concern of hazardous trees still standing around her building site on property. She said not all burned trees were cut down and removed.﻿ SENT EMAIL TO ED CLARK. JC 02/19/22 PER ED CLARK THIS HAS BEEN RESOLVED. JC |  |  |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 |  |  | 6 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Approved | [6 empty] | 2021-12-07 | 2021-11-16 | Yes | 50 | 2022-01-29 |  | 2022-01-29 | 2022-01-29 |  | 2022-02-01 | 2022-02-03 | 50 | 2022-02-10 |  | 2022-02-05 | 2022-03-16 | 2022-03-16 | 2022-03-16 | GERALD & DIANA EDIE | 530-333-5770 | gerdee@sbcglobal.net |  | "Debris Crew Leader/Crew# Max Patterson﻿/506 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 506" | 38.6438 | -120.5185 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 3
874 | 042-233-600 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16530 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1401.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-08 | 2022-03-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 |  |  | 2 | TRUE |  |  |  | 2022-03-08 | Yes | 2022-03-08 | 2022-03-11 | POSITIVE | 2022-03-14 | 2022-03-14 | 2 | 2022-03-08 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-02 | No Activity/Nest Building Removed | 30 | 2022-04-04 |  | Yes | 2022-03-30 | Yes | 2022-03-31 | TRUE | [14 empty] | 2022-03-14 | 2022-03-15 |  | 3.15 No Ans left mess. PF Sent Text 3.15@12:13 Spoke to Diana she said ok PF |  |  |  | 2022-03-16 |  | 2022-03-16 | 2022-03-16 |  |  | 3 | 2022-03-18 | 2022-03-28 | 7 | Approved | [12 empty] | 2022-03-31 | 2022-03-07 | Yes | 15 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 | 15 | 2022-04-04 |  | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-05 | Velma Loe/Diana Louise Tucker | (925) 207-9643 | dltucker@tuckersfrenchies.com |  | Debris Crew Leader/Crew# Carondlet Dunbar /#201 Debris Crew WO# Refer to IAP 03/16 to 03/19 Crew 201 | 38.9252 | -122.6028 | Cache |  | Residential | Yes | 2022-03-04 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 0
875 | 041-672-001 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4570 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3831.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  |  | 6 |  | Yes | Take | 2022-03-08 | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-06 | 2021-11-08 | 2022-02-16 | 11.8 SPOKE WITH THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. ALSO, PLEASE TAKE PROPANE TANK. JC 02/16/22 NO ANS LEFT VM & TEXT. JC 02/16/22 SPOKE WITH THOMAS HE SAID OK FOR TREE REMOVAL. 02/23/22 MR. Hicks called to see what happened to his farm tractor. Sent email to inform Melissa. jc |  |  |  | 2021-11-17 |  | 2021-11-20 | 2021-11-20 |  |  | 5 | 2021-11-30 | 2021-12-08 | 7 | Re-scrape |  |  |  | 2022-01-24 | 2022-02-01 | Approved | [6 empty] | 2022-02-03 | 2021-11-06 | Yes | 49 | 2022-03-23 |  | 2022-03-25 | 2022-03-25 |  | 2022-03-28 | 2022-03-29 | 49 |  |  | 2022-03-30 |  |  |  | THOMAS HICKS | 530-680-8757 | tchicks@me.com | Vehicles On Site Septic | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 502 | 38.6388 | -120.535 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
876 | 041-672-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4520 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3849.16 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | No |  |  | 2021-11-24 | Yes | 2021-11-24 | 2021-12-01 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-14 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-14 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-12-01 | 2021-12-03 | 2022-03-04 | 12.03 NO ANS. VOICEMAIL FULL. SENT EMAIL. JC 12.03 SPOKE WITH PAUL HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC "03/04/22 NO ANS MAILBOX FULL SENT TEXT. JC 03/04/22 Paul gave consent via email. JC" |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 3 | 2021-12-11 | 2021-12-17 | 5 | Approved | [12 empty] | 2021-12-20 | 2022-01-12 | Yes | 69 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-23 | 69 | 2022-03-25 |  | 2022-03-24 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Paul Baermann | 831-320-7023 | grizzlypaul@att.net | Septic | Debris Crew Leader/Crew# Birdie Bell/#504 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 504 | 38.6377 | -120.5339 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
877 | 041-672-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4508 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3854.15 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2021-12-22 | 2021-12-22 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 4 |  |  |  |  | No |  |  | 2021-12-23 | Yes | 2021-12-23 | 2022-01-24 | NEGATIVE |  |  |  | 2021-12-22 | Bio Monitoring Needed for Debris AND Trees | 2022-01-18 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-21 | Yes | 2022-03-31 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-18 | 2022-01-20 | 2022-04-04 | 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC 4.01.22 NO ANS. LEFT MESS & SENT TEXT PF 4.02.22 NO ANS. LEFT MESS & SENT TEXT & EMAIL PF 4.04.22 NO ANS. LEFT MESS , SENT TEXT AND 2nd EMAIL PF 4.4 PROCEED TO MOVE FORWARD PER MP | 3 | MP |  | 2022-01-25 |  | 2022-01-27 | 2022-01-27 | FALSE |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-15 | 2022-02-23 | Approved | [6 empty] | 2022-02-25 | 2022-01-12 | Yes | 44 | [14 empty] | Brandon Keeling | 530-363-6922 | brandonkeeling762@gmail.com |  | Debris Crew Leader/Crew# Crystal Egan/ #505 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 505 | 38.6377 | -120.5334 | Caldor | DR-4619 | Residential | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-04T20:19:09Z | FALSE
878 | 041-711-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5195 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3815.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | Bio Monitoring Needed for Debris AND Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-15 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-07 | 2021-12-07 |  | 12.07 SPOKE WITH ROBIN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 3.16 3.16 No Ans. Sent text. PF |  |  |  | 2021-12-11 |  | 2022-01-18 | 2022-01-18 |  |  | 6 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-19 | Yes | 13 | 2022-03-22 |  | 2022-03-23 | 2022-03-23 |  | 2022-03-25 | 2022-03-26 | 13 | 2022-03-30 |  | 2022-03-28 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Robin Meneely | 408-396-4120 | rmeneely61@gmail.com |  | Debris Crew Leader/Crew# Crystal Egan / #507 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 507 | 38.6348 | -120.5327 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
879 | 041-711-012 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5140 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3793.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2022-01-11 | 2022-01-14 | 2022-02-26 | 01/14/22 SPOKE TARA SHE SAID OK BUT PLEASE CALL ADVANCE. NO PROPANE TANK. JC 02/26/22 NO ANS NO VM SENT TEXT. JC 02/26/22 TARA C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-29 |  | 2022-01-29 | 2022-01-29 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-06 | Yes | 9 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-21 | 2022-03-22 | 9 | 2022-03-25 |  | 2022-03-23 | 2022-03-26 | 2022-03-26 | 2022-03-26 | Tara Young | 530-497-4639 | Taramisoo73@yahoo.com | Vehicles Onsite | Debris Crew Leader/Crew# Tami Collins/ #501 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 501 | 38.6347 | -120.5343 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
880 | 041-712-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5153 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.78 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | Yes |  | 2021-11-13 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-13 | 2021-11-16 | 2022-01-15 | 11.13 NO ANS LEFT VM. JC 11.15 NO ANS LEFT VM. JC 11.16 NO EMAIL ADDRESS. JC 11.16 Contact made with homeowner's son. Consented to debris removal. RCV 01/14/22 NO ANS LEFT VM & TEXT. JC 01/15/22 SPOKE WITH HO SON, FRANK, HE SAID OK. JC |  |  |  | 2021-11-20 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-11-19 | Yes | 13 | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  | 2022-01-22 | 2022-01-24 | 13 | 2022-02-01 |  | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2022-02-07 | MADEILINE GRAY | 530-344-7955 | N/A |  | Debris Crew Leader/Crew# Crystal Egan/#508 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 508 | 38.634 | -120.5337 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
881 | 041-671-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Pending PO Notification | 5087 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3786.49 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-08 | Yes | 2021-12-08 | 2021-12-13 | NEGATIVE |  |  |  | 2022-03-01 | Bio Monitoring Needed for Debris AND Trees | 2021-12-23 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-31 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-23 | 2022-01-12 |  | 01/11/22 NO ANS LEFT VM & TEXT. JC 01/12/22 SPOKE WITH BRONTE﻿ SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 04/07/22 NO ANS LEFT VM & TEXT. JC 04/08/22 NO ANS LEFT VM & SENT EMAIL FOR TREE REMOVAL. JC |  |  |  | 2022-01-24 |  | 2022-01-25 | 2022-01-25 |  |  | 4 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2022-02-21 | Yes | 64 | [14 empty] | Bronte Lukanish | 916-933-6401 | lukanish@piedmontcompany.com | Other Septic | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 505 | 38.6378 | -120.5355 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-08T15:19:10Z | FALSE
882 | 041-673-003 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4461 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3871.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-14 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-01 | 2021-12-03 |  | 12.03 NO ANS LEFT VM. JC 12.03 SPOKE WITH PETER HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE. JC 03/17/22 NO ANS LEFT VM & TEXT JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 28 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-01-10 | Yes | 54 | [14 empty] | KASHUBA ,PETER | 916-671-4345 | nastalgia2@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 505 | 38.6385 | -120.5315 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
883 | 041-673-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4469 | String Canyon Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3865.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-11-20 | Yes | 2021-11-20 | 2021-11-24 | POSITIVE | 2021-12-02 | 2021-12-02 | 5 | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-15 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-12-02 | 2021-12-02 | 2022-03-25 | 11.29 NO ANS LEFT VM. JC 11:30 NO ANS LEFT VM AND SENT EMAIL.JC 11:30 SPOKE WITH NORMAN HE SAID OK BUT PLEASE CALL CELL PHONE @(530)919-3959﻿. NO PROPANE. JC 02/21/22 SPOKE WITH NORMAN HE OK FOR TREE REMOVAL. JC 03/25/22 FOLLOW-UP CALL. SPOKE WITH NORMAN HE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-12-04 |  | 2021-12-06 | 2021-12-06 |  |  | 5 | 2021-12-10 | 2021-12-20 | 7 | Approved | [12 empty] | 2021-12-21 | 2022-03-25 | Yes | 31 | [14 empty] | Norman Anderson | 530 344-1966 cell (530)919-3959 | andersonii@sbcglobal.net | Septic | Debris Crew Leader/Crew# Birdie Bell /#504 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 504 | 38.6382 | -120.5317 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
884 | 041-673-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5142 | String Canyon Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3866.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 5 | 2 | 0 | 4 | 0 | 1 | 0 | 12 |  |  | 11 |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-03 | Bio Monitoring Needed for Debris AND Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-21 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-11 | 2021-12-16 |  | 12.16 NO ANS LEFT VM & TEXT. JC 12.16 SPOKE WITH HO ﻿SAID OK. BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 6 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-11 | Yes | 26 | [14 empty] | Brian Gustafson | 530-306-4042 | crownjwl@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 505 | 38.6382 | -120.5312 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
885 | 041-673-008 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5145 | String Canyon Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3861.05 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-09 | Bio Monitoring Needed for Trees, not Debris | 2022-01-27 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [12 empty] | 2022-03-25 | 02/10/22 SPOKE WITH EDWARD SHE SAID OK FOR TREE REMOVAL. JC 03/25/22 FOLLOW UP CALL. SPOKE WITH EDWARD HE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. JC | [27 empty] | 2022-03-25 | Yes | 35 | [14 empty] | Edward Hendrix | 408-981-9801 | elcjd@comcast.net |  |  | 38.6375 | -120.5312 | Caldor | DR-4619 | Residential | No | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
886 | 041-673-013 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4505 | String Canyon Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3839.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-09 | Bio Monitoring Needed for Trees, not Debris | 2022-01-24 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-15 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | Class I | None | TRUE | [12 empty] | 2022-02-10 | 02/10/22 SPOKE WITH RANDI SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-29 | Yes | 43 | 2022-03-15 |  | 2022-03-16 | 2022-03-16 |  | 2022-03-23 | 2022-03-25 | 43 |  |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 | Matthew & Randi Bruntmyer | 209-409-4452 | randibruntmyer@gmail.com |  |  | 38.6372 | -120.533 | Caldor | DR-4619 | Residential | No | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
887 | 041-682-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5136 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  | Bridge | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | Yes | TRUE | No | No | Yes | No | No | Yes | TRUE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 |  |  |  |  | No |  |  | 2021-10-05 | Yes | 2021-10-06 | 2021-10-11 | POSITIVE | 2021-10-28 | 2021-10-28 | 14 | 2021-10-13 | Bio Monitoring Needed for Debris AND Trees | 2021-11-24 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-03-31 | No |  | TRUE |  | Class II | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-12-03 | 2021-12-04 | 2022-04-05 | 12.4 SPOKE WITH SEAN HE SAID OK. BUT PLEASE CALL IN ADVANCE. NO PROPANE. JC 02/16/22 SPOKE WITH SEAN HE SAID OK FOR TREE REMOVAL. JC 04/05/22 FOLLOW-UP CALL. NO ANS LEFT VM & TEXT. JC 04/05/22 HO GAVE TEXT BACK OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 2 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-11-09 | Yes | 15 | [14 empty] | SEAN & MARY HOLTE | 209-479-2797 | HOLTESM@SBCGLOBAL.NET |  | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 507 | 38.6359 | -120.5349 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-06T15:17:28Z | FALSE
888 | 041-682-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5140 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-31 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-17 | 2021-12-10 | 2022-01-21 | 2022-04-08 | 12.16 NO ANS LEFT VM & TEXT. JC 12.17 NO ANS LEFT VM & EMAIL JC 12.18 GAVE TO RICHARD. JC 01/14/22 NO ANS LEFT VM & TEXT. JC 01/19/22 NO ANS LEFT VM & EMAIL. JC 01/20/22 NO ANS LEFT VM GAVE TO RICHARD. JC 01/21/22 per Melissa clear to proceed. JC 04/05/22 NO ANS LEFT VM & TEXT ABT TREE. JC 04/06/22 NO ANS LEFT VM & EMAIL. JC 04/07/22 NO ANS LEFT VM & 2ND EMAIL. JC 04/08/22 No Ans Left VM. JC 04/08/22 Clear to proceed per Melissa Perry. jc | 4 | State Planner: Melissa Perry |  | 2022-01-29 |  | 2022-01-31 | 2022-01-31 |  |  | 4 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-20 | Yes | 4 | [14 empty] | George & Carol Hill | 530-409-9882 | arianacory80@gmail.com |  | Debris Crew Leader/Crew# Eric Rachon / #503 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 503 | 38.6356 | -120.5349 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T17:01:10Z | FALSE
889 | 041-682-003 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5146 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3792.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 5 |  |  | 4 |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-06 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-02 | 2021-12-06 | 2022-03-15 | 12.4 NO ANS LEFT VM. JC 12.4 SPOKE WITH CHARLES HE SAID OK. JC 01/25/22 SPOKE WITH DOROTHY SHE SAID VENDOR WILL HANDLE PROPANE TANK. JC 03/15/22 NO ANS LEFT VM & TEXT. JC 03/15/22 SPOKE WITH DOROTHY SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  |  | 4 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-19 | Yes | 7 | 2022-04-02 | [6 empty] | 1 | [6 empty] | Charles & Dorothy Fiedler | 530-748-8130 | deedee_fiedler@sbcglobal.net | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson /#507 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 507 | 38.6353 | -120.5349 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-06T18:27:47Z | FALSE
890 | 041-682-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5154 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3794.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-19 | 2021-10-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 4 | 4 | 0 | 2 | 0 | 2 | 0 | 12 |  |  | 3 |  | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-28 | 2021-10-28 | 6 | 2021-10-22 | Bio Monitoring Needed for Debris AND Trees | 2021-11-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | N/A | No |  |  |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2021-11-02 | 2021-11-03 | 2022-02-16 | 11.3 NO ANS LEFT MESS. JC 01/26/22 SPOKE WITH NADINE SHE SAID VENDOR WILL HANDLE PROPANE TANK. JC 02/16/22 SPOKE WITH NADINE SHE SAID OF FOR TREE REMOVAL. JC |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 18 | 2021-12-02 | 2021-12-10 | 7 | Re-scrape |  |  |  | 2022-01-22 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2021-11-17 | Yes | 9 | 2022-03-21 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-23 | 2022-03-25 | 9 |  |  | 2022-03-26 |  |  |  | Daniel and Nadine DeBoard | 530-497-4446 | forestcritters@sbcglobal.net |  | "Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 501 | 38.6351 | -120.535 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
891 | 041-722-014 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 5264 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3762.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | Bio Monitoring Needed for Debris AND Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-15 | 2021-11-06 | 2021-11-08 | 2022-03-01 | 11.8 SPOKE WITH RICK HE SAID OK BUT PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT. PROPANE TANK. JC 03/01/22 SPOKE WITH COLLEEN. HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Re-scrape | 2022-01-18 | 2022-01-26 | Re-scrape |  |  | Approved | 2022-02-09 | 2022-01-05 | Yes | 11 | 2022-03-29 |  | 2022-03-29 | 2022-03-29 |  | 2022-04-01 | 2022-04-02 | 11 |  |  | 2022-04-05 |  |  |  | Robert & Colleen Jolson | 530-633-2933 | jolsonwelding@aol.com | Vehicle on site Septic | Debris Crew Leader/Crew# Crystal Eqan/#508 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 508 | 38.6314 | -120.5348 | Caldor | DR-4619 | Residential | Yes | 2021-10-28 | ROE Verified | Central Division | 2022-04-06T16:05:44Z | FALSE | 3
892 | 041-722-020 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5236 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3781.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-10-27 | Yes | 2021-10-28 | 2021-11-02 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-23 | 2021-11-02 | 2021-11-05 | 2022-01-24 | 11.3 NO ANS LEFT MESS. JC 11.4 NO ANS LEFT MESS. JC 11.5 Contacted homeowner's agent (Jim) and he okayed debris removal RCV 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 01/24/22 SPOKE WITH STEPSON JAMES. HE SAID OK. JC PLEASE CALL JAMES HAWKINS IN ADVANCE AT 925 997-2452 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-08 |  |  | 5 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2022-01-28 | Yes | 17 | 2022-02-21 |  | 2022-02-21 | 2022-02-21 |  | 2022-03-01 | 2022-03-02 | 17 | 2022-03-11 |  | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | KATHARINE HAWKINS AGENT JAMES HAWKINS | 510-928-9012/**CALL JAMES 925 997-2452 | jrhawkins01@gmail.com | Septic Vehicle On Site | "Debris Crew Leader/Crew# Matthew Dorenzo/505 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 505 | 38.6317 | -120.5329 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 8
893 | 041-722-021 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5235 | Golden Aspen Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3783.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | POSITIVE | 2021-11-05 | 2021-11-05 | 3 | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-06 | 2021-11-08 | 2022-01-24 | 11.8 SPOKE WITH DOUG HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 01/24/22 NO ANS LEFT VM & TEXT. JC 01/24/22 DOUG C/B HE SAID OK.JC |  |  |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 |  |  | 3 | 2021-11-12 | 2021-11-22 | 7 | Approved | [12 empty] | 2021-11-23 | 2021-11-04 | Yes | 23 | 2022-02-21 |  | 2022-02-21 | 2022-02-21 |  | 2022-03-01 | 2022-03-02 | 23 | 2022-03-11 |  | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | DOUG DEAKIN | 916-764-7220 | dougjanet5562@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Robert Boyer/#508 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 508 | 38.632 | -120.5327 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 8
894 | 042-260-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 9000 | Happy Valley Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 4156.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-02 | 2022-02-02 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2022-02-01 | Yes | 2022-02-01 | 2022-02-04 | NEGATIVE |  |  |  | 2022-02-17 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-16 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-04-02 | Yes | [5 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2022-02-17 | 2022-02-18 |  | 02/18/22 SPOKE WITH JULIE SHE SAID OK FOR DEBRIS REMOVAL. VENDOR HANDLING PROPANE. JC |  |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  |  | 2 | 2022-03-23 | 2022-03-31 | 7 | Approved | [12 empty] | 2022-04-01 | 2022-02-04 | Yes | 5 | [14 empty] | MICKEY VERNON | 530-391-2730 | mickey.vernon@protonmail.com | Other Well | Debris Crew Leader/Crew# Antonio Ruiz /#519 Debris Crew WO# Refer to IAP 03/19 to 03/22 Crew 519 | 38.6821 | -120.5338 | Caldor | DR-4619 | Residential | No | 2021-10-20 | ROE Verified | Central Division | 2022-04-04T23:29:18Z | FALSE
895 | 042-300-050 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 042-300-050 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3727.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-03 | No | [6 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-02-18 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-02 | Yes |  |  |  | Class III | Covered under suspension | FALSE | [12 empty] | 2022-03-18 | 03/18/22 DAVID CALLED FOR STATUS. HE GAVE PER APPROVAL FOR TREE REMOVAL. 04/04/22 DAVID CALLED FOR STATUS. HE WOULD LIKE FOR CREW LEADER TO CALL IN ADVANCE BECAUSE HE WANTS TO BE THERE DURING THE PROCESS. JC | [27 empty] | 2022-01-24 | Yes | 10 | [14 empty] | DAVID & CHRISTINE PIERSON | 916-724-9423 | info@davidpiersonphd.com |  |  | 38.714 | -120.5826 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-04T18:01:41Z | FALSE
896 | 042-300-052 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 042-300-052 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3727.76 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-07 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-03 | No | [6 empty] | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [13 empty] | 02/14/22 RETURNED CALL TO GIVE STATUS. INSTRUCTED PO TO CONTACT THE COUNTY. JC | [28 empty] | Do Not Assess | 0 | [14 empty] | DAVID & CHRISTINE PIERSON | 916-724-9423 | info@davidpiersonphd.com |  |  | 38.7127 | -120.5825 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
897 | 042-365-110 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16461 | 6th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1471.55 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | TRUE | No |  |  | 2021-12-15 | Yes | 2021-12-15 | 2021-12-20 | POSITIVE | 2021-12-21 | 2021-12-21 | 2 | 2021-12-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-15 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | FALSE |  | 2021-12-21 | 2021-12-23 |  | 12.20 NO ANS LEFT VM & TEXT. JC 12.23 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-07 |  | 2022-01-07 | 2022-01-07 | FALSE |  | 2 | 2022-01-10 | 2022-01-18 | 7 | Approved | [12 empty] | 2022-01-19 | 2021-12-20 | No | 0 | [8 empty] | 2022-02-03 |  |  | 2022-02-02 | 2022-02-02 | 2022-02-07 | Paul Quistgard | (425) 877-5123 | Paulquistgard@aol.com | Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#202 Debris Crew WO# Refer to IAP 01/05/2022 to 01/08/2022 Crew 202 | 38.928 | -122.6043 | Cache |  | Residential | No | 2021-12-14 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
898 | 042-374-040 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16347 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | TRUE |  | TRUE | Yes | Take | 2022-03-03 | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | POSITIVE | 2022-01-17 | 2022-01-17 | 3 | 2022-01-07 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-17 | 2022-01-19 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 |  |  | 1 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-01-11 | Yes | 1 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-17 | 2022-02-19 | 1 | 2022-03-03 |  | 2022-02-22 | 2022-03-03 | 2022-03-03 | 2022-03-03 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean / #202 Debris Crew WO# Refer to IAP --- to --- Crew 202 | 38.9253 | -122.6067 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-07T20:05:49Z | FALSE | 0
899 | 042-374-050 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16357 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | TRUE | 2 | TRUE | No |  |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | NEGATIVE |  |  |  | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-29 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-29 | 2021-10-23 |  | HO C/B AND SAID OK. PLEASE DONT REMOVE RED BLOCKS HE'S GONNA BUILD A MODULAR HOME WITH. PF 11.2 Matt would like to have Propane tank removed. JC 02/22/22 NO ANS LEFT VM ABT PROPANE TANK REMOVAL PROCESS. JC |  |  |  | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | 2 | 2022-01-07 | 2022-01-17 | 7 | Approved | [12 empty] | 2022-01-18 | 2021-11-09 | No | 0 | [8 empty] | 2022-02-04 |  |  | 2022-02-02 | 2022-02-02 | 2022-03-17 | Matt Reed | (707) 490-5665 |  | Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/#202 Debris Crew WO# Refer to IAP 01/05/2022 to 01/08/2022 Crew 202 | 38.9253 | -122.6065 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
900 | 042-374-060 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16367 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-01-08 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE |  |  |  | 2022-01-08 | No | [6 empty] | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2022-01-11 | Yes | 1 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-17 | 2022-02-19 | 1 |  |  | 2022-02-22 |  | 2022-02-22 | 2022-02-22 | ABATEMENT |  |  |  |  | 38.9253 | -122.6063 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-07T20:05:49Z | FALSE | 0
901 | 042-374-130 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16350 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1362.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-09 | 2021-11-10 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | No | None | FALSE | [10 empty] | 2021-11-13 | 2021-12-10 | 2021-12-17 | 11.16 NO ANS UNABLE TO LEAVE VM. JC GAVE TO RICHARD. JC 12.10 MELISSA SHE SAID OK ﻿BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 12.17 SPOKE WITH MELISSA SAID OK. JC |  |  |  | 2021-12-16 |  | 2021-12-16 | 2021-12-16 |  |  | 12 | 2022-01-03 | 2022-01-11 | 7 | Approved | [12 empty] | 2022-01-12 | 2021-11-10 | Yes | 1 | 2021-12-17 |  | 2021-12-17 | 2021-12-17 |  | 2021-12-21 | 2021-12-21 | 1 | 2022-02-04 |  | 2021-12-29 | 2022-02-02 | 2022-02-02 | 2022-02-17 | Melissa Fanning | (707) 533-3063 | mfanning1952@gmail.com |  | Debris Crew Leader/Crew# Crystal Eqan / #202 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 202 | 38.925 | -122.6065 | Cache |  | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE | 4
902 | 042-375-110 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 16479 | 4th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  | 2022-01-12 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-01-08 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-01-08 | No | [6 empty] | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | [31 empty] | 2022-01-12 | No | 0 | [14 empty] | ABATEMENT |  |  |  |  | 38.9267 | -122.6045 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-05T17:56:48Z | FALSE
903 | 042-375-150 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16374 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 5 |  | TRUE |  | TRUE | No |  |  | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | NEGATIVE |  |  |  | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-13 | 2022-01-13 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  |  | 2 | 2022-01-22 | 2022-01-28 | 5 | Re-scrape |  |  |  | 2022-02-11 | 2022-02-21 | Approved | [6 empty] | 2022-02-24 | 2022-02-14 | Yes | 3 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-17 | 2022-02-19 | 3 | 2022-03-03 |  | 2022-02-22 | 2022-03-03 | 2022-03-03 | 2022-03-03 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean/ #202 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 202 | 38.9264 | -122.606 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-07T20:05:49Z | FALSE | 0
904 | 042-375-170 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16394 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1395.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-24 | 2022-01-24 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | TRUE | 5 | TRUE | No |  |  | 2022-01-24 | Yes | 2022-01-24 | 2022-01-27 | POSITIVE | 2022-01-31 | 2022-01-31 | 3 | 2022-01-25 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | N/A | No | [5 empty] | No | None | FALSE | [10 empty] | 2022-01-31 | 2022-01-31 |  | 01/31/22 ABATEMENT. JC |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 2 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-24 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Carla Herbet/ # 202 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 202 | 38.9264 | -122.6057 | Cache |  | Residential |  | 2022-01-19 | Abatement | Central Division | 2022-04-06T18:52:41Z | FALSE
905 | 042-375-190 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16424 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1392.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-24 | 2022-01-24 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | TRUE | 4 | TRUE | No |  |  | 2022-01-24 | Yes | 2022-01-24 | 2022-01-27 | NEGATIVE | 2022-02-07 | 2022-02-07 |  | 2022-01-25 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | No Arch Monitoring Needed for Debris or Trees | Yes | [13 empty] | FALSE | [10 empty] | 2022-01-27 | 2022-01-29 |  | 01/28/22 NO ANS LEFT & TEXT. JC 01/29/22 SPOKE WITH KATIE SHE SAID OK. IF PROPANE TANK IS ON PROPERTY AND DAMAGED PLEASE REMOVE. JC |  |  |  | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  |  | 1 | 2022-03-01 | 2022-03-09 | 7 | Approved | [12 empty] | 2022-03-11 | 2022-01-24 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-19 | 2022-03-19 | 2022-03-19 | Katie Lewellen | (510) 965-3879 | slobber22@gmail.com |  |  | 38.9264 | -122.6052 | Cache |  | Residential | No | 2022-01-13 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
906 | 042-375-210 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16444 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | NEGATIVE |  |  |  | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-13 | 2022-01-13 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  |  | 2 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-01-11 | No | 0 | [8 empty] | 2022-02-04 |  |  | 2022-02-04 | 2022-02-04 | 2022-02-07 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean/ #202 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 202 | 38.9264 | -122.6048 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-01T22:00:05Z | FALSE
907 | 042-376-020 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16383 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1398.6 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | No |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE | [5 empty] | 2021-12-15 | No |  |  |  | 2021-12-21 |  |  | 2021-12-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-17 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [7 empty] | FALSE | [8 empty] | FALSE |  |  |  | 2021-12-17 |  | 12.16 NO ANS LEFT VM. JC 12.17 SPOKE WITH CHARLOTTE ﻿ SHE SAID OK. JC | [6 empty] | FALSE | [19 empty] | 2021-12-16 | Yes | 2 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 | 2 |  |  | 2021-12-29 |  | 2021-12-29 | 2021-12-29 | Xanders Charlotte Corinne Trustee | (530) 220-5935 | Xanders@csus.edu |  |  | 38.926 | -122.6058 | Cache |  | Residential | No | 2021-12-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
908 | 042-376-030 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16393 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1392.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | TRUE | No |  |  | 2021-12-15 | Yes | 2021-12-15 | 2021-12-20 | POSITIVE | 2021-12-21 | 2021-12-21 | 2 | 2022-01-25 | No Bio Monitoring Needed for Debris or Trees | 2022-01-24 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [10 empty] | 2022-01-25 | 2022-01-26 |  | 01/26/22 ABATEMENT NO CONTACT NEEDED. |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 2 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-02-15 | Yes | 6 | 2022-02-17 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-17 | 2022-02-19 | 6 | 2022-03-03 |  | 2022-02-22 | 2022-03-03 | 2022-03-03 | 2022-03-03 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Carla Herbt / #202 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 202 | 38.926 | -122.6057 | Cache |  | Residential |  | 2022-01-19 | Abatement | Central Division | 2022-04-06T18:52:41Z | FALSE | 0
909 | 042-376-060 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16423 | 3rd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1374.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Unk |  | TRUE | 2021-12-04 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE |  |  |  | 2021-12-04 | No | [6 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2021-12-16 | 12.16 SPOKE HO ABT TREE REMOVAL, SAID OK. JC | [27 empty] | 2021-12-16 | Yes | 2 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 | 2 |  |  | 2021-12-29 |  | 2021-12-29 | 2021-12-29 | Chris Wortman | (831) 479-3408 | cwexcavation@comcast.net |  |  | 38.926 | -122.6051 | Cache |  | Residential | No | 2021-12-03 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 0
910 | 042-376-180 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | NO ELIGIBLE TREES | 16418 | 2nd Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1373.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-20 | 2021-10-20 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 |  |  | 1 | TRUE | No |  |  | 2021-10-19 | No | [6 empty] | 2021-10-21 | No Bio Monitoring Needed for Debris or Trees | 2021-10-26 | Arch Monitoring Needed for Debris AND Trees | Yes | [11 empty] | No | None | FALSE | [10 empty] | 2021-10-26 | 2021-10-23 |  | 10.23 @ 5:25 SPOKE TO HO AND HE WANTS TO BE CALLED IN ADVANCE TO DO A WLK THROUGH ABOUT HIS EQUIPMENT ON THE PARCEL. OK GOOD TO GO. PF |  |  |  | 2021-11-04 |  | 2021-11-04 | 2021-11-04 |  |  | 6 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-11-29 | 2021-12-07 | Approved | [6 empty] | 2021-12-08 | 2021-11-10 | No | 0 | [8 empty] | 2021-12-17 |  |  | 2021-12-18 | 2021-12-18 | 2021-12-21 | Robert/Garrett Reed | (707) 350-0262 |  | Vehicles Onsite | "Debris Crew Leader/Crew# Birdie Bell/202 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 202" | 38.9257 | -122.6053 | Cache |  | Residential | No | 2021-10-07 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
911 | 041-701-013 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5198 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3832.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-22 | No Bio Monitoring Needed for Debris or Trees | 2021-12-14 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-15 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | Yes | 2022-03-01 | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-16 | 2021-12-14 | 2021-12-16 | 2022-03-02 | 12.16 NO ANS LEFT VM & TEXT. JC 12.16 SPOKE WITH JARED HE SAID BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE. TANK. JC 03/02/22 NO ANS LEFT VM & TEXT. JC 03/02/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-20 |  | 2022-01-20 | 2022-01-20 |  |  | 6 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-18 | Yes | 23 | 2022-03-15 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-26 | 23 | 2022-03-30 |  | 2022-03-28 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Jared & Kaitlyn McVey | 530-391-0932 | mcvey_jared@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 505 | 38.6352 | -120.532 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
912 | 041-701-015 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5208 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3833.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-18 | Bio Monitoring Needed for Debris AND Trees | 2021-12-11 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-12-11 | 2022-01-22 | 2022-03-03 | "12.14 NO ANS LEFT VM & TEXT. JC 12.14 SPOKE WITH LUPE SHE SAID OK BUT PLEASE CALL IN ADVANCE. SHE WANTS TO BE ON SITE DURING DEBRIS REMOVAL. NO PROPANE TANK. JC 01/21/22 NO ANS LEFT VM. JC" 01/22/22 NO ANS LEFT VM & TEXT. JC 01/22/22 LUPE GAVE CONSENT VIA TEXT. JC 03/03/22 NO ANS LEFT VM & TEXT. JC 03/03/22 HO GAVE CONSENT VIA TEXT. CALL 408 244-7828 JC |  |  |  | 2022-01-25 |  | 2022-01-26 | 2022-01-26 |  |  | 4 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-22 | Yes | 8 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-24 | 2022-03-25 | 8 | 2022-03-30 |  | 2022-03-26 | 2022-03-31 | 2022-03-31 | 2022-03-31 | MONTEZ ROBERT M & LUPE | 408-340-0216 , 408-244-7828 | montezcrew@@yahoo.com |  | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 503 | 38.6347 | -120.532 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
913 | 041-492-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6774 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4020.58 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-11 | 2021-10-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 4 |  |  | 2 | TRUE | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-14 | 2021-10-25 | 2022-01-14 | 10.25 Contacted James Kelly, acknowledged start of debris removal. 12.04 SPOKE WITH JAMES HE SAID OK. JC 01/14/22 NO ANS LEFT VM AND TEXT. JC 01/14/22 SPOKE WITH JAMES HE SAID OK. JC 01/26/22 SPOKE WITH JAMES HE SAID VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-10-27 |  | 2021-10-28 | 2021-10-28 |  |  | 7 | 2021-11-06 | 2021-11-12 | 5 | Approved | [12 empty] | 2021-11-16 | 2021-10-26 | Yes | 3 | 2022-01-17 |  | 2022-01-17 | 2022-01-17 |  | 2022-01-19 | 2022-01-20 | 3 | 2022-01-27 |  | 2022-01-22 | 2022-02-16 | 2022-02-16 | 2022-02-16 | JAMES & BARBARA KELLY | 916-206-3476 | jkelly@surewest.net |  | "Debris Crew Leader/Crew# Stefanie Fairlee/#502 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 502" | 38.641 | -120.5253 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 2
914 | 041-492-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4940 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4011.47 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-02-07 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-07 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 |  |  | 2022-02-22 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 SPOKE WITH JAMES HE SAID OK. JC | [27 empty] | 2021-12-18 | Yes | 6 | 2022-03-07 |  | 2022-03-07 | 2022-03-07 |  | 2022-03-09 | 2022-03-09 | 6 |  |  | 2022-03-10 |  | 2022-03-10 | 2022-03-10 | JAMES & BARBARA KELLY | 916-206-3476 | jkelly@surewest.net |  |  | 38.641 | -120.5249 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
915 | 041-492-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4924 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4007.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |  |  | 2 |  | Yes | Leave |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-10 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-08 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-17 |  |  | 11.17 PH# ON FILE OUT OF SERVICE. SENT EMAIL JC 11.19 PH# OUT OF SERVICE. JC GAVE TO RICHARD. 11.18 Called and texted number on insurance page of ROE. Left voicemails RCV 01/27/22 PHONE NOT IN SERVICE SENT EMAIL ABT PROPANE TANK. JC 02/10/22 PHONE NUMBER NOT IN SERVICE. SENT 2ND EMAIL ABOUT PROPANE TANK. JC"3.28 SENT TEXT. PF Called and # is no working. Emailed and it returned undeliverable.PF 3.28 approved by MP. PF" |  |  |  | 2021-11-19 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Soil Boring | 2022-01-17 | 2022-01-25 | Re-scrape | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2021-12-18 | Yes | 9 | [14 empty] | Paul Velebit | 602-318-6940 | paulvlbt@yahoo.com | Vehicles on site Septic | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 509 | 38.6416 | -120.5247 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
916 | 041-493-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6735 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4004.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2021-10-14 | Bio Monitoring Needed for Debris, not Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-25 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-10-14 | 2021-10-27 | 2022-02-28 | 10.25 Left a voicemail RCV 10.26 NO ANS. LEFT MESS PF 10.27 Left a voicemail RCV 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/27/22 HO WILL CHECK WITH VENDOR ABT PROPANE. JC 02/28/22 NO ANS LEFT VM & TEXT. JC 02/28/22 BEV C/B SHE SAID OK. JC | 3 | Kendall Wilson |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 |  |  | 10 | 2021-11-11 | 2021-11-18 | 6 | Re-scrape | 2022-01-26 | 2022-02-03 | Re-scrape | 2021-11-23 | 2021-12-03 | Soil Boring | 2022-02-09 | 2022-02-17 | Approved |  |  |  | 2022-02-19 | 2021-11-20 | Yes | 4 | 2022-03-07 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-08 | 2022-03-09 | 4 | 2022-03-10 |  | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-11 | SHELBY & BEVERLY FALLS | 530-295-7274 | BEVFALLS@GMAIL.COM |  | Debris Crew Leader/Crew# Curtis Henderson/#501 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 501 | 38.64 | -120.5248 | Caldor | DR-4619 | Residential | Yes | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 0
917 | 041-493-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6731 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4001.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-07 | Yes | 2021-10-08 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-19 | 2021-10-28 | 2022-01-14 | 10.25 Left a voicemail RCV 10.28 Spoke with Joe, acknowledged start of debris removal RCV 01/14/22 SPOKE WITH JOSEPH HE SAID OK. JC 01/26/22 NO ANS LEFT VM TEXT ABT PROPANE TANK. JC 01/26/22 HO C/B VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-10-29 |  | 2021-10-30 | 2021-10-30 |  |  | 5 | 2021-11-06 | 2021-11-12 | 5 | Approved | [12 empty] | 2021-11-16 | 2022-03-07 | Yes | 36 | 2022-01-17 |  | 2022-01-17 | 2022-01-17 |  | 2022-01-20 | 2022-01-22 | 36 | 2022-02-01 |  | 2022-01-25 | 2022-02-03 | 2022-02-03 | 2022-02-03 | JOSEPH HUTCHINSON & SANDRA RODRIGUEZ | 408-422-2535 | jhutchinsonsc1978@gmail.com |  | Debris Crew Leader/Crew# Curtis Henderson/#501 Debris Crew WO# Refer to IAP 10/27 to 10/30 Crew 501 | 38.6398 | -120.5247 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 3
918 | 041-494-002 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Planning Hold | Hold | 4933 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3999.55 |  |  |  |  | TRUE | New Owner |  | N/A | [5 empty] | Unk |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-20 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | Yes | 2022-03-02 | No |  | TRUE |  | No | None | FALSE | [13 empty] | "3.26 NO ANS. LEFT MESS AND SENT TEXT PF 3.28 HO TEXTED HE SOLD PROPERTY A FEW WEEKS AGO. HE ONLY GAVE THE AGENTS NAME ALEX 916-248-9209." (Parcel Sold) | [27 empty] | 2022-01-22 | Yes | 19 | [14 empty] | Richard & Emilia Harrington | 916-717-8787 | sierrawestrealty@yahoo.com |  |  | 38.6412 | -120.5242 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
919 | 041-494-003 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4941 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4000.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-20 | 2021-11-20 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-19 | Yes | 2021-11-19 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-24 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-08 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-06 | 2021-12-09 | 2022-03-16 | 12.07 NO ANS LEFT VM& EMAIL. JC 12.08 NO ANS LEFT VM. JC 12.09 SPOKE WITH NORA(CONSERVATOR FOR DEBRA) SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC Field staff attempted contact for 2 days, no answer. Voicemails left. approved by planning to proceed. 03/15/22 NO ANS LEFT VM & TEXT. PF 3.16 Spoke to her conservator (Nora) said ok to proceed. PF |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 2 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-28 | Yes | 41 | 2022-03-28 |  | 2022-03-29 | 2022-03-29 |  | 2022-04-01 | 2022-04-02 | 41 |  |  | 2022-04-05 |  |  |  | Debra Ayres | 530-621-6335 | nora.sharp@edcgov.us |  | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 510 | 38.6409 | -120.5243 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T15:56:36Z | FALSE | 3
920 | 041-494-004 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Felling in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Crew ELD 1 | 4949 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3994.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-16 | 2021-11-16 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 5 |  |  | 2 |  | Yes | Leave |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-22 | POSITIVE | 2021-11-24 | 2021-11-24 | 3 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-13 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-06 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-24 | 2021-11-10 | 2022-04-04 | 11.10 SPOKE TO TABITHA AND SHE SAID OK. PROPANE TANK HAS BEEN HANDLED BY VENDOR. PLEASE CALL BEFORE GOIING TO PROPERTY. PF 01/19/22 SPOKE WITH TABITHA SHE SAID OK. JC 04/04/22 SPOKE WITH TABITHA SHE HAS CONERNS ABOUT STATUS OF TREE REMOVAL AND WANTED TO KNOW IF WE CAN PRIORITIZE TREE REMOVAL. SENT EMAIL TO MELISSA FOR DIRECTION. JC 04/04/22 I contacted Tabitha to explain boundary lines issue, and informed that her parcel will move up list once issue is resolved. JC 04/04/22 Tabitha said ok for tree removal. JC 04/07/22 ﻿Jeff called to request a damage claim form. I emailed the damage claim form to email on file. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 4 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-17 | 2022-01-19 | Yes | 29 | 2022-03-31 | [6 empty] | 1 | [6 empty] | Jeff & Tabatha Walker | 916-872-3435, 530-957-3217 | jeffreywalker78@aol.com, tabatha.assist@gmail.com | Vehicles on site Septic | Debris Crew Leader/Crew# Cynthia Sanderson /#503 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 503 | 38.6406 | -120.5243 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T19:09:25Z | FALSE
921 | 041-494-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6746 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3985.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-02-12 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-31 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [12 empty] | 2022-03-26 | 02/21/22 NO ANS MAILBOX FULL SENT TEXT. JC 02/22/22 NO ANS MAILBOX FULL SENT EMAIL. JC 02/23/22 NO ANS MAILBOX FULL SENT 2ND EMAIL. JC 02/24/22 NO ANS MAILBOX FULL. SENT 3RD EMAIL. JC 02/24/22 PROCEED FOR TREE REMOVAL PER MELISSA PERRY. JC 3.26 NO ANS. MAILBOX IS FULL. SENT TEXT PF 3.26 Clear to proceed for trees as well following previous direction and new attempt per MP. PF | 4 | State planner: Melissa Perry | [25 empty] | 2021-12-07 | Yes | 51 | 2022-03-31 |  | 2022-04-01 | 2022-04-01 |  | 2022-04-04 | 2022-04-05 | 51 |  |  | 2022-04-06 |  | 2022-04-06 | 2022-04-07 | Ronald Hutchinson | 530-559-1243 | ronhutch22@gmail.com |  |  | 38.6404 | -120.5242 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T22:58:58Z | FALSE | 3
922 | 041-494-010 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7162 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3961.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [12 empty] | 2022-02-21 | 02/21/22 SPOKE WITH NORMAN HE SAID OK. JC | [27 empty] | 2022-01-21 | Yes | 12 | 2022-02-26 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-02 | 2022-03-04 | 12 |  |  | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | Norman & Rebecca Woehrman | 530-468-4262 | no email |  |  | 38.6404 | -120.5236 | Caldor | DR-4619 | Residential | No | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
923 | 041-494-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7156 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3975.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-11-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-15 | 2021-11-08 | 2022-02-16 | 1.8 SPOKE TO MIKE AND HE SAID OK. VENDOR IS TAKING CARE OF PROPANE TANK. PF 01/19/22 SPOKE WITH MICHAEL HE SAID OK. JC 02/16/22 MICHAEL SAID OK. JC |  |  |  | 2021-11-19 |  | 2021-11-19 | 2021-11-19 |  |  | 2 | 2021-11-22 | 2021-12-02 | 7 | Re-scrape |  |  |  | 2021-12-06 | 2021-12-14 | Approved | [6 empty] | 2021-12-15 | 2022-01-21 | Yes | 5 | 2022-02-21 |  | 2022-02-21 | 2022-02-21 |  | 2022-03-01 | 2022-03-02 | 5 | 2022-03-09 |  | 2022-03-03 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Michael Stinnett | 707-861-2231 | Michaelstinnett@hotmail.com | Septic | Debris Crew Leader/Crew# Sarah Mundt /#501 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 501 | 38.6407 | -120.5237 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 8
924 | 041-494-014 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7130 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3984.01 |  |  |  |  | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | Yes |  | TRUE | 2022-01-28 | 2021-12-11 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2022-01-15 | Yes | 2022-01-17 | 2022-01-20 | NEGATIVE |  |  |  | 2021-12-21 | No Bio Monitoring Needed for Debris or Trees | 2022-01-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-01 | Yes | 2022-03-04 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-20 | 2022-01-24 | 2022-03-25 | 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 NO ANS LEFT VM & EMAIL. JC 01/24/22 NO ANS LEFT VM. GAVE TO IMT. JC 01/24/22 sent email. per Mellissa clear for debris removal. jc 3.25 SPOKE TO JULIE SHE SAID OK PF |  |  |  | 2022-02-03 |  | 2022-02-03 | 2022-02-03 | FALSE |  | 4 | 2022-02-08 | 2022-02-16 | 7 | Approved | [12 empty] | 2022-02-17 | 2022-01-24 | Yes | 14 | [14 empty] | Stephen Wilcox | 925-784-6802 | juls.deane4@aol.com |  | Debris Crew Leader/Crew# Birdie Bell /#504 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 501 | 38.6415 | -120.5236 | Caldor | DR-4619 | Residential | Yes | 2021-12-09 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
925 | 041-495-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7143 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3963 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 6 | 0 | 0 | 2 | 0 | 1 | 0 | 9 |  |  | 9 |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-01 | No |  | TRUE |  | Class III | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-03 | 2021-12-06 | 2022-03-24 | 12.06 SPOKE WITH THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT REMOVE PROPANE TANK. JC 3.24 NO ANS. LEFT VM & TEXT PF 3.24 THOMAS C/B AND SAID OK PF |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 32 | 2022-01-22 | 2022-01-28 | 5 | Re-scrape |  |  |  | 2022-02-07 | 2022-02-15 | Approved | [6 empty] | 2022-02-16 | 2022-01-24 | Yes | 2 | [14 empty] | Thomas McQuerry, Jayme McQuerry | 916-224-3089 | mcquto@hotmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Cynthia Sanderson/#501 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 501 | 38.6411 | -120.5229 | Caldor | DR-4619 | Residential | Yes | 2021-11-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
926 | 041-501-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 6701 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3968.14 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 |  |  | 2 |  | Yes | Take | 2022-02-16 | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees | Yes |  |  |  |  | On Hold | Yes | 2022-03-03 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-03 | 2021-12-09 | 2022-04-05 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & SENT EMAIL. JC 12.09 NO ANS LEFT VM GAVE TO RICHARD. JC 12.09 SPOKE WITH MICHAEL HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 4.5 SPOKE TO BOTH AND THEY SAID OK PF |  |  |  | 2022-01-13 |  | 2022-01-13 | 2022-01-13 |  |  | 7 | 2022-01-21 | 2022-01-31 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2022-01-24 | Yes | 30 | [14 empty] | Anita & Mike Hibbard | 530-417-4286 , 530-391-8964 | anitahibbard@rocketmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre/#502 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 502 | 38.6389 | -120.5248 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-06T01:04:43Z | FALSE
927 | 041-501-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6715 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3986.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-20 | Yes | 2021-11-22 | 2021-11-24 | NEGATIVE |  |  |  | 2021-11-20 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-22 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-11 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-03 | 2021-12-08 | 2022-03-16 | 12.07 NO ANS LEFT VM &TEXT. JC 12.08 SPOKE WITH NICOLAS HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/16/22 SPOKE JENNIFER SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-13 |  | 2022-01-14 | 2022-01-14 |  |  | 5 | 2022-01-20 | 2022-01-28 | 7 | Re-scrape |  |  |  | 2022-02-07 | 2022-02-15 | Approved | [6 empty] | 2022-02-16 | 2022-01-24 | Yes | 9 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-26 | 2022-03-28 | 9 | 2022-04-05 |  | 2022-04-01 | 2022-04-06 | 2022-04-06 | 2022-04-06 | Jennifer & Nicolas Moore | 209-985-8460 , 209-486-1585 | jennymutley@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Tarrence Harrison /#502 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 502 | 38.6392 | -120.5247 | Caldor | DR-4619 | Residential | Yes | 2021-11-16 | ROE Verified | Central Division | 2022-04-06T21:24:02Z | FALSE | 4
928 | 041-502-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 6692 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3922.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-03-16 | Yes | 2022-03-18 | TRUE |  | No | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-18 | 2021-11-19 | 2022-03-18 | 11.19 SPOKE WITH PAMELA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 3.18 PAMELA C/B AND SAID OK pf |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-13 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2022-01-12 | Yes | 53 | 2022-03-21 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-26 | 2022-03-28 | 53 |  |  | 2022-03-30 |  |  |  | Pamela L Christiansen | 916-969-7864 | pamcaptain@comcast.net | Septic | Debris Crew Leader/Crew# Cynthia Sanderson /#503 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 503 | 38.6383 | -120.5245 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
929 | 041-502-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6700 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3940.2 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 3 | TRUE | Yes | Leave |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | No | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-05 | 2021-11-06 | 2022-01-19 | 11.6 NO ANS LEFT VM. JC 11.6 SPOKE WITH MATTHEW, HE SAID OK. PLEASE CALL IN ADVANCE. HE WILL CONTACT VENDOR ABT PROPANE TANK. JC 01/19/22 SPOKE WITH MATTHEW HE SAID OK. JC |  |  |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 |  |  | 4 | 2021-11-18 | 2021-11-30 | 7 | Re-scrape |  |  |  | 2021-12-04 | 2021-12-10 | Approved | [6 empty] | 2021-12-13 | 2022-01-19 | Yes | 63 | 2022-03-09 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-21 | 2022-03-22 | 63 | 2022-03-25 |  | 2022-03-23 | 2022-03-26 | 2022-03-26 | 2022-03-26 | MATTHEW TOFFEY & ROMAR CLARO | 925-800-9359 | homes@romarandmatt.com | Vehicle On Site Septic | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 503 | 38.6385 | -120.5242 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
930 | 041-502-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 6714 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3951.64 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-10 | 2021-11-10 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-09 | Yes | 2021-11-10 | 2021-11-15 | NEGATIVE |  |  |  | 2021-11-11 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-08 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-15 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-17 | 2021-11-18 | 2022-01-19 | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH MATTHEW HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE LAGE PROPANE TANK BUT PLEASE REMOVE SMALLER TANKS. JC 01/19/22 SPOKE WITH MATTHEW HE SAID OK. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 MATTHEW C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-11-22 |  | 2021-11-24 | 2021-11-24 |  |  | 3 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2022-01-21 | Yes | 43 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-22 | 2022-03-26 | 43 | 2022-03-30 |  | 2022-03-28 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Matthew Roe & Thomas Mikkelsen | 925-818-4100, 510-813-9500 | , tm2317@comcast.net | Septic | Debris Crew Leader/Crew# Terrence Harrison /#509 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 509 | 38.6392 | -120.5241 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 8
931 | 040-020-015 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 100 | 8N49 |  | Somerset | El Dorado |  | Residential | [5 empty] | 4037.98 |  | 2022-01-19 | No qualifying debris; not eligible for tree removal | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-11 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [42 empty] | Do Not Assess | 0 | [14 empty] | BORTHWICK, ROBERT | 530-642-8532 | RobertABorthwick@yahoo.com | Vehicles Onsite |  | 38.5751 | -120.4915 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
932 | 040-020-016 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Not Eligible for Haz Tree Removal | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 108 | 8N49 |  | SOMERSET | El Dorado |  | Residential | [5 empty] | 4315.1 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | "1777" | TRUE | Locked gate | Yes |  | TRUE | 2022-03-04 | 2022-03-04 | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No |  | FALSE | TRUE | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 6 | [7 empty] | 2022-03-04 | Yes | 2022-03-04 | 2022-03-09 | POSITIVE | 2022-03-16 | 2022-03-16 | 6 | 2022-03-17 | No Bio Monitoring Needed for Debris or Trees | 2022-03-25 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-05 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2022-03-25 | 2022-04-06 |  | 02/07/22 SPOKE WITH RICHARD HE SAID BURNED BUILDING ON SITE. JC 3.10 Spoke to Homeowner about key to the locked gate. He's in Cincinnati, wont be in town until the 21st. He will reach out to his brother and see if he can locate a key and call us back.PF 3.10 His Brother Robert called and he will get a combo lock on tomorrow and give us a call. ﻿PF Please note the signs "DO NOT REMOVE" Please don't ﻿take these things. PF﻿ 3.14@5:15 HO BROTHER ROBERT C/B AND GAVE GATE CODE"1777". HE ALSO STATED HE MARKED VEHICLES NOT TO REMOVE PLEASE LEAVE THEM. PF 03/28/22 SPOKE WITH RICHARD SAID HE WOULD LIKE TO PLACE ON HOLD UNTIL HE RETURNS FROM CINCINNATI ON APRIL 10TH.﻿ JC 04/06; Greg Lopez and Stehpanie Fairlee spoke with owner and he gave them instructions on what to look for. Including vehicles |  |  |  | 2022-04-06 |  | 2022-04-07 | 2022-04-07 | FALSE |  | 2 | [18 empty] | Do Not Assess | 0 | [14 empty] | Richard Borthwick | 513-319-9223 | drumfiredance@gmail.com |  |  | 38.577 | -120.4951 | Caldor | DR-4619 | Residential | No | 2021-12-10 | ROE Verified | Central Division | 2022-04-08T17:45:08Z | FALSE
933 | 040-020-019 | Full Program ROE (debris + trees) | Ready for Soil Sampling | Not Eligible for Haz Tree Removal | Next Step: N/A | Ready for Soil Sampling | NO ELIGIBLE TREES | 040-020-019 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 4246.8 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 02/02/022 SPOKE WITH GEORGE HE SAID HE CAN TAKE KEY TO THE COUNTY OFFICE ON FRIDAY. JC 02/03/22 NO ANS LEFT VM AND TEXT ABT GATE HAVING CODE OR KEY? 02/04/22 NO ANS LEFT VM. JC 02/08/22 HO C/B LOCK REQUIRES KEY. THE KEY IS AT THE COUNTY OFFICE. JC 3.14 @5:45 HO SAID He left his key at The ROE with someone name Alan. He said he'd told us this several times.PF | TRUE | Locked gate | Yes |  | TRUE | 2021-11-29 | 2021-11-29 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 |  |  |  |  | No |  |  | 2021-12-02 | Yes | 2021-12-02 | 2021-12-07 | POSITIVE | 2022-04-02 | 2022-04-02 | 83 | 2021-12-11 | No Bio Monitoring Needed for Debris or Trees | 2022-03-25 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-05 | No Activity/Nest Building Removed | [11 empty] | TRUE | [8 empty] | TRUE | 2022-04-14 | 2022-04-02 | 2022-03-14 |  | 02/01/22 NO ANS LEFT VM AND TEXT ABT GATE CODE. 02/02/022 SPOKE WITH GEORGE HE SAID HE CAN TAKE KEY TO THE COUNTY OFFICE ON FRIDAY. JC 3.14 @5:45 HO SAID He left his key at The ROE with someone name Alan. He said he'd told us this several times. I talked to him and explained that the keys may not be found. I also asked if we could cut the lock if it wasn't found. He said he rather we find the key but, if we can't find the key then please just cut the chain and save the lock. But it is ok to proceed. PF |  |  |  | 2022-04-07 |  | 2022-04-08 | 2022-04-08 |  |  | 1 | [18 empty] | Do Not Assess | 0 | [14 empty] | George Hettich | 707-876-9821 | gtheo@netscape.com |  |  | 38.5758 | -120.494 | Caldor | DR-4619 | Residential | No | 2021-11-19 | ROE Verified | Central Division | 2022-04-09T00:16:50Z | FALSE
934 | 040-070-044 | Full Program ROE (debris + trees) | Asbestos Abatement Needed | Not Eligible for Haz Tree Removal | Next Step: N/A | State - Debris Eligibility Review | NO ELIGIBLE TREES | 040-070-044 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 4144.78 |  |  |  |  | TRUE | Eligibility Determination, Standing Walls |  | N/A |  |  |  | TRUE |  | Yes |  | TRUE | 2022-03-04 | 2022-03-04 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No |  | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | [7 empty] | 2022-03-10 | Yes | 2022-03-10 | 2022-03-15 | POSITIVE |  |  | 19 | [18 empty] | FALSE | [8 empty] | TRUE | 2022-03-19 |  |  |  | 02/07/22 NO ANS LEFT VM AND TEXT ABT ELIGIBLE DEBRIS. JC 02/07/22 ﻿HO C/B HE SAID NO STRUCTURES ON PROPERTY. JC | [28 empty] | Do Not Assess | 0 | [14 empty] | ACEVEDO WILLIAM & BZIK SARA | 650-946-6015 | wacevedo678@gmail.com |  |  | 38.573 | -120.4632 | Caldor | DR-4619 | Residential | No | 2021-11-18 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
935 | 040-070-050 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | ELD 514 | NO ELIGIBLE TREES | 040-070-050 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 3778.04 |  |  |  |  | TRUE | Other - see comments |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 |  |  |  |  | No |  |  | 2021-11-22 | Yes | 2021-11-22 | 2021-11-23 | POSITIVE | 2021-12-02 | 2021-12-02 | 6 | 2021-12-10 | Bio Monitoring Needed for Debris, not Trees | 2021-11-13 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-07 | No Activity/Nest Building Removed | [9 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-19 | 2021-12-10 | 2022-04-06 |  | 12.11 NO ANS LEFT VM & TEXT. JC 12.11 SPOKE WITH DENNIS HE SAID OK BUT PLEASE CALL 530 409-6543 IN ADVANCE. NO PROPANE TANK. JC 01/21/22 SPOKE WITH DENNIS HE SAID GATE IS UNLOCKED AND OK. PLEASE CALL﻿ home first @530 626-3037 and cell if he cannot be reached on home phone @ 530 409-6543. JC 04/06/22 ﻿FOLLOW-UP CALL DENNIS SAID OK FOR DEBRIS REMOVAL. BUT PLEASE CALL IN ADVANCE. JC | [28 empty] | Do Not Assess | 0 | [14 empty] | Dennis, Jim & Kirk Theis | 530-626-3037 | dennis.sue.theis@gmail.com | SEPTIC |  | 38.5717 | -120.4701 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T23:02:34Z | FALSE
936 | 041-011-019 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 4650 | Cosumnes Mine Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3426.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-28 |  | FALSE | [5 empty] | No | Yes | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | [10 empty] | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2022-02-08 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-02 | Yes |  |  | Operational | Class I | Covered under suspension | FALSE | [8 empty] | TRUE | 2022-02-06 | [31 empty] | 2021-12-20 | Yes | 331 | [14 empty] | HARMER, CHRISTOPHER R & ANDREA | 415-827-0673 | chris@harmerschau.com | Other Septic Vehicles Onsite |  | 38.6665 | -120.538 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
937 | 041-021-027 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 2157 | Backwoods Trail |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4157.44 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | TRUE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-08 | Yes | 2021-11-10 | 2021-11-15 | POSITIVE | 2021-11-23 | 2021-11-23 | 7 | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-11-20 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [7 empty] | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-11-23 | 2021-11-23 |  | 11.23 SPOKE WITH CHRIS HE SAID OK BUT CALL IN ADVANCE. NO PROPANE TANK. JC |  |  |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 |  |  | 3 | 2021-12-07 | 2021-12-15 | 7 | Approved | [12 empty] | 2021-12-16 | 2021-11-16 | No | 0 | [8 empty] | 2022-03-23 |  |  | 2022-03-24 | 2022-03-24 | 2022-03-24 | CHRIS & JENNIFER PAPPAS | 208-789-0860 | CHRISPAPPAS24@GMAIL.COM | Vehicles on site Access issues (gate) | Debris Crew Leader/Crew# Max Patterson#506 Debris Crew WO# Refer to IAP 12/01 to 12/04 Crew 506 | 38.6468 | -120.5097 | Caldor | DR-4619 | Residential | No | 2021-10-23 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
938 | 041-021-029 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 8650 | Big Canyon Loop Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4277.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-12 | 2021-11-12 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-11-15 | Yes | 2021-11-15 | 2021-11-18 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-30 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-16 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-30 | 2022-01-21 |  | 11.19 SPOKE WITH OWNER. SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 SPOKE WITH MICHAEL HE SAID OK. BUT HE WANTS TO SAVE HIS RETAINING WALL AND HE WANTS TO SPEAK WITH A CREW LEADER BEFORE REMOVING DEBRIS. JC |  |  |  | 2022-02-03 |  | 2022-02-04 | 2022-02-04 |  |  | 4 | 2022-02-09 | 2022-02-17 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Re-scrape | 2022-03-18 | 2022-03-28 | Approved |  |  |  | 2022-03-30 | 2022-01-24 | No | 0 | [14 empty] | EMERY MICHAEL H | 530-903-9959 | michaelemery2008@yahoo.com | Septic | Debris Crew Leader/Crew# Carondlet Dunbar / #505 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 510 | 38.6502 | -120.5052 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
939 | 041-021-034 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 041-021-034 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4176 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-03 | 2021-11-03 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 |  |  | 1 |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | POSITIVE | 2021-11-23 | 2021-11-23 | 5 | 2021-11-09 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-04-01 | No |  | TRUE |  | No | None | FALSE | [10 empty] | 2021-11-23 | 2021-11-23 | 2022-04-05 | 11.23 SPOKE WITH STEVEN HE SAID OK BUT CALL IN ADVANCE. NO PROPANE. JC 04/05/22 SPOKE STEVEN HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-01 |  | 2021-12-02 | 2021-12-02 |  |  | 2 | 2021-12-04 | 2021-12-10 | 5 | Re-scrape |  |  |  | 2022-01-21 | 2022-01-31 | Re-scrape | 2022-02-08 | 2022-02-16 | Approved |  |  |  | 2022-02-17 | 2022-04-05 | Yes | 178 | [14 empty] | STEVEN R SWENSON | 408-390-3048 | stevenr.swensonlaw@yahoo.com | Other Vehicles Onsite | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 12/01 to 12/04Crew 506 | 38.6445 | -120.5113 | Caldor | DR-4619 | Residential | No | 2021-11-01 | ROE Verified | Central Division | 2022-04-06T01:18:18Z | FALSE
940 | 041-021-035 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7400 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4169.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-15 | 2021-11-15 | FALSE | No |  |  | No |  | No | Yes | Yes | Yes | No | No | FALSE | TRUE | 8 | 2 | 1 | 0 | 1 | 0 | 2 | 14 |  |  | 12 |  | Yes | Take | 2022-02-16 | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-05 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-03 | 2022-01-22 | 2022-03-28 | 12.4 NO ANS LEFT VM. JC 12.06 NO ANS MAILBOX FULL SENT TEXT. JC 12.06 ﻿SPOKE WITH DEAN TOMLIN HE SAID OK BUT PLEASE CALL IN ADVANCE. HE IS UNSURE IF THEY OWN THE PROPANE TANK BUT WILL CALL BACK TO LET US KNOW. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 RUTH GAVE CONSENT VIA TEXT. JC 01/28/22 HO SAID TO REMOVE PROPANE TANK JC 03/26/22 NO ANS LEFT VM &TEXT. JC 03/28/22 NO ANS LEFT VM & EMAIL FOR TREE REMOVAL. JC 03/28/22 MR. TOMLIN C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-04 |  | 2022-02-08 | 2022-02-08 |  |  | 4 | 2022-02-11 | 2022-02-21 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-01-27 | Yes | 182 | [14 empty] | Ruth Tomlin | 530-863-3161 | ruthptomlin@gmail.com | Keep Items Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Eric Rocha / #503 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 503 | 38.6445 | -120.5098 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
941 | 041-601-012 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7554 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4060.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | Yes |  | 2021-11-01 | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-23 | Yes | 2021-10-26 | 2021-10-29 | NEGATIVE |  |  |  | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-30 | 2021-11-03 | 2021-12-04 | 11.3 SPOKE WITH BECKY. SHE SAID OK. PLEASE CALL IN ADVANCE. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 CHRISTOPHER SAID OK TO PROCEED. JC |  |  |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 |  |  | 1 | 2021-11-13 | 2021-11-19 | 5 | Approved | [12 empty] | 2021-11-23 | 2021-11-04 | Yes | 16 | 2022-01-05 |  | 2022-01-06 | 2022-01-06 |  | 2022-01-08 | 2022-01-08 | 16 | 2022-01-31 |  | 2022-01-15 | 2022-02-05 | 2022-02-05 | 2022-02-07 | CHRISTOPHER & BECKY LAWRENCE | 209-566-5958 | beckyblawrence@gmail.com | Septic | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP -11/24- to -12/01- Crew 502 | 38.641 | -120.5078 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
942 | 041-602-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5128 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3976.37 |  |  |  |  | TRUE | Property Owner Issue |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 5 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | POSITIVE | 2021-12-10 | 2021-12-10 | 3 | 2021-12-02 | Bio Monitoring Needed for Debris AND Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-24 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-17 | 2021-12-11 | 2022-01-22 |  | 12.11 NO ANS LEFT VM & TEXT. JC 12.11 SPOKE WITH MICHAEL HE SAID OK BUT CALL BECAUSE HE WANTS TO BE ON SITE DURING THE DEBRIS REMOVAL. VENDOR HANDLING PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 SPOKE WITH MICHAEL HE SAID OK. JC 03/03/22 SPOKE WITH MICHAEL HE SAID OK FOR TREE REMOVAL. JC 3.25 NO ANS LEFT MESS AND SENT TEXT PF |  |  |  | 2022-01-26 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-17 | 2022-02-25 | Approved | [6 empty] | 2022-03-01 | 2021-12-04 | Yes | 18 | [14 empty] | Michael & Donna Figone | 530-391-7565 | dtmichaelfigone@gmail.com |  | Debris Crew Leader/Crew# Antonio Ruiz/ #510 Debris Crew WO# Refer to IAP 01/26 to 01/26 Crew 510 | 38.6413 | -120.5122 | Caldor | DR-4619 | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
943 | 041-602-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5134 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3989.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-02-01 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-01-13 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-14 |  |  | 2022-01-21 | 01/20/22 LINE BUSY SENT TEXT AND EMAIL. JC 01/21/22 PHONE NUMBER BUSY GAVE TO RICHARD. JC 01/21/22 per Melissa clear to proceed. jc | [27 empty] | 2021-11-29 | Yes | 17 | 2022-02-15 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-19 | 2022-02-21 | 17 |  |  | 2022-03-03 |  | 2022-03-03 | 2022-03-03 | Daniel Stevenson | 540-748-9038 | daclst@yahoo.com |  |  | 38.6415 | -120.5119 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
944 | 041-602-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5142 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4000.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Take | 2022-02-17 | 2021-11-17 | Yes | 2021-11-18 | 2021-11-23 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-14 | 2021-11-19 | 2021-11-29 | 2022-02-12 | 11.23 NO ANS NO VM. SENT EMAIL JC 11.24 TRIED CALLING BUT PHONE DID NOT ALLOW FOR MESS. ONLY BUSY TONE. JC 11.29 BUSY TONE. SENT EMAIL. JC 11.29 SPOKE WITH DANIEL HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK BUT UNSURE IF DAMAGED BY FIRE. JC 01/25/22 SPOKE WITH DANIEL HE SAID PLEASE REMOVE PROPANE TANK. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/11/22 NO ANS LEFT VM & EMAIL.JC 02/12/22 NO ANS LEFT VM & 2ND EMAIL. JC 02/12/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 |  |  | 32 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-11-23 | Yes | 5 | 2022-02-15 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-19 | 2022-02-21 | 5 | 2022-03-09 |  | 2022-03-01 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Daniel Stevenson | 530 748-9038 | daclst@yahoo.com | Septic | Debris Crew Leader/Crew# Matthew Dorenzo /#505 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 505 | 38.6418 | -120.5119 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 4
945 | 041-602-005 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7649 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4006.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 |  |  | 2022-02-02 | 02/01/22 PHONED SEVERAL TIMES BUT CONTINUE TO GET BUSY SIGNAL. SENT EMAIL. JC 02/02/22 PHONE IS STILL GIVING BUSY SIGNAL. SENT EMAIL. JC 02/02/22 TEXT CAME BACK UNDELIVERABLE. OK TO PROCEED PER MELISSA. JC | 3 | State Planner: Melissa Perry | [25 empty] | 2021-11-30 | Yes | 8 | 2022-02-15 |  | 2022-02-15 | 2022-02-15 |  | 2022-02-19 | 2022-02-21 | 8 |  |  | 2022-02-28 |  | 2022-02-28 | 2022-02-28 | Daniel Stevenson | 540-748-9038 | daclst@yahoo.com |  |  | 38.6418 | -120.5115 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
946 | 041-602-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 7641 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4019.62 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-23 | 2021-12-23 | FALSE | Yes |  | 2022-02-02 | No | TRUE | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  |  | No |  |  | 2022-01-25 | Yes | 2022-01-25 | 2022-01-28 | NEGATIVE |  | 2022-02-02 |  | 2021-12-04 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | No Arch Monitoring Needed for Debris or Trees | [6 empty] | No |  |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-02-02 | 2022-02-09 | 2022-03-31 | 02/09/22 SPOKE WITH HO THEY SAID OK. PLEASE CALL IN ADVANCE. NO PROPANE TANKS ON PROPERTY. JC 3.31 SPOKE TO CHU AND SHE SAID OK PF |  |  |  | 2022-02-10 |  | 2022-02-11 | 2022-02-11 |  |  | 2 | 2022-02-14 | 2022-02-22 | 7 | Approved | [12 empty] | 2022-02-24 | 2022-03-05 | Yes | 5 | [14 empty] | Chun Hao Zhu | 916-267-9005 | Jinchen1991@hotmail.com |  | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 02/12 To 02/16 Crew 504 | 38.6418 | -120.5111 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
947 | 041-602-008 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4914 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3999.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 |  | No |  |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes | 2022-04-02 | TRUE |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-01 | 2021-11-03 | 2022-04-04 | "11.3 NO ANS. LEFT MESS PF 11. SPOKE ANN AND SHE SAID OK PF" 04/04/22 NO ANS LEFT VM & TEXT. JC 04/04/22 ANN C/B SHE SAID OK FOR TREE REMOVAL AND NO NEED TO CALL IN ADVANCE. JC |  |  |  | 2021-11-06 |  | 2021-11-08 | 2021-11-08 |  |  | 4 | 2021-11-11 | 2021-11-19 | 7 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Approved | [6 empty] | 2021-12-07 | 2021-11-30 | Yes | 17 | [14 empty] | ANN DUFF | 530-409-9358 | mommaduff36@gmail.com |  | Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/06 To 11/10 Crew 507 | 38.6415 | -120.511 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-05T02:09:23Z | FALSE
948 | 041-602-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4934 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3983.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-30 | 2021-10-30 | FALSE | Yes |  | 2021-11-08 | No | TRUE | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-28 | Yes | 2021-10-29 | 2021-11-03 | POSITIVE | 2021-11-08 | 2021-11-08 | 4 | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-08 | 2021-11-10 |  | 11.10 NO ANS LEFT VM. JC 11.10 SPOKE WITH RUTH JACKSON SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 02/10/22 ﻿SPOKE WITH RUTH SHE SAID OK. JC |  |  |  | 2021-11-13 |  | 2021-11-15 | 2021-11-15 |  |  | 3 | 2021-11-17 | 2021-11-29 | 7 | Re-scrape |  |  |  | 2022-01-20 | 2022-01-28 | Approved | [6 empty] | 2022-02-01 | 2021-11-09 | Yes | 6 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-26 | 2022-02-28 | 6 | 2022-03-09 |  | 2022-03-01 | 2022-03-10 | 2022-03-10 | 2022-03-10 | RUTH JACKSON | 530-622-3095 |  |  | Debris Crew Leader/Crew# Stephanie Fairlee/#502 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 502 | 38.6411 | -120.5115 | Caldor | DR-4619 | Residential | Yes | 2021-09-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 7
949 | 041-602-011 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4944 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3967.13 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 5 |  |  |  |  | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-11 | Yes | 2022-03-14 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-04 | 2022-01-21 | 2022-03-18 | 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SENT EMAIL. JC 12.08 SPOKE WITH KYSTAL SHE SAID OK BUT PLEASE CALL IN ADVANCE. PROPANE TANK WAS NOT DAMAGED DO NOT REMOVE. JC 01/21/22 HO SAID OK. JC 03/15/22 NO ANS LEFT VM & TEXT. JC 03/16/22 NO ANS LEFT VM & EMAIL. JC 3.17 3.17 No ans. Left Mess PF. 03/18/22 SPOKE WITH KRYSTAL SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-24 |  | 2022-01-25 | 2022-01-25 |  |  | 5 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-25 | Yes | 1 | [14 empty] | Krystal pettit | 916-633-8219 | krystal_95628@yahoo.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 510 | 38.641 | -120.5119 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
950 | 041-603-004 | Full Program ROE (debris + trees) | Tree Operations in Progress | Hazard Trees Removed | Next Step: N/A | Ready for Tree Ops (Full Program) | Planning Hold | 7591 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4045.47 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | Yes |  | 2021-11-13 | No | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 2 |  | Yes | Leave |  | 2021-10-23 | Yes | 2021-10-26 | 2021-11-03 | POSITIVE | 2021-11-05 | 2021-11-05 | 3 | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | On Hold | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-17 | 2021-11-19 | 2022-01-11 | 11.18 NO ANS. UNABLE TO LEAVE VM. SENT EMAIL JC 11.18 EMAIL RETURNED DELIVERY FAILED. JC GAVE TO RCV. JC 11.19 Homeowner contact made, approved start of removal RCV﻿ 01.11 Homeowner gave permission for hazard tree removal to start RCV 01/26/22 SPOKE WITH PATRICIA SAID VENDOR WILL HANDLE PROPANE TANK. JC |  |  |  | 2021-11-29 |  | 2021-11-30 | 2021-11-30 |  |  | 4 | 2021-12-03 | 2021-12-10 | 6 | Approved | [12 empty] | 2021-12-13 | 2021-11-19 | Yes | 11 | 2022-01-11 |  | 2022-01-12 | 2022-01-12 |  | 2022-01-13 | 2022-01-14 | 11 | [6 empty] | PATRICIA SCHAMMA | 909-520-5078 | PATRICIASHAMMA@ATT.NET | Vehicle On Site | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 506 | 38.6416 | -120.5089 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
951 | 041-603-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7579 | Winding Way |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4050.74 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-30 | Yes | 2021-11-30 | 2021-12-03 | NEGATIVE |  |  |  | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-05 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-12-03 | 2022-01-22 | 2022-02-26 | 12.06 SPOKE WITH DON HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC 02/26/22 SPOKE WITH DON HE SAID OK FOR TREE REMOVAL. DON WANTS TO KNOW WHY THE PILE OF DIRT AND GRAVEL WAS LEFT BEHIND FROM THE DEBRIS REMOVAL. JC |  |  |  | 2022-01-31 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Approved | [12 empty] | 2022-02-16 | 2021-11-20 | Yes | 8 | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  | 2022-03-09 | 2022-03-10 | 8 | 2022-03-11 |  | 2022-03-11 | 2022-03-17 | 2022-03-17 | 2022-03-17 | Don & Donna Sutton | 209-402-5346 | dcsutton@yahoo.com | Vehicles on site Septic | Debris Crew Leader/Crew# Zara Armani/#511 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 511 | 38.6416 | -120.5085 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 0
952 | 041-603-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7584 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4035.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-23 | 2021-10-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-23 | Yes | 2021-10-26 | 2021-10-29 | POSITIVE | 2021-11-01 | 2021-11-01 | 2 | 2021-10-26 | No Bio Monitoring Needed for Debris or Trees | 2021-10-30 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-11-01 | 2021-11-03 | 2021-12-04 | 11.3 SPOKE WITH REBECCA SHE SAID OK. PLEASE CALL BEFORE IN ADVANCE 12-24 HOURS. OWNER CONTACTED VENDOR ABT. TANK. JC 12.4 SPOKE WITH REBECCA SHE SAID OK. JC |  |  |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 |  |  | 5 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-03 | Yes | 10 | 2022-01-06 |  | 2022-01-07 | 2022-01-07 |  | 2022-01-11 | 2022-01-14 | 10 | 2022-02-11 |  | 2022-02-05 | 2022-02-12 | 2022-02-12 | 2022-02-12 | REBECCA & KENNETH GREEN | 530-344-3109 | becky.hth@gmail.com | Septic | "Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP -- to -- Crew 507" | 38.641 | -120.5085 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
953 | 041-603-008 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7594 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4026.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-04 | 2021-11-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-11-05 | No | [6 empty] | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-01 | 2021-11-03 | 2021-12-06 | 11.3 NO ANS LEFT MESS PF 11.3 SPOKE TO JUDY THE VENDOR HAS TAKEN CARE OF THE TANK. OK TO PROCEED. PF 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.06 SPOKE WITH JUDITH SHE SAID OK BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-11-05 |  | 2021-11-05 | 2021-11-05 |  |  | 5 | 2021-11-11 | 2021-11-19 | 7 | Approved | [12 empty] | 2021-11-22 | 2021-11-08 | Yes | 27 | 2022-01-07 |  | 2022-01-10 | 2022-01-10 |  | 2022-01-11 | 2022-01-14 | 27 | 2022-02-01 |  | 2022-01-17 | 2022-02-02 | 2022-02-02 | 2022-02-02 | JUDITH CALZADA | 530-417-5948 | jude7565@att.net |  | "Debris Crew Leader/Crew# Adam Mattsson/#507 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 507" | 38.6411 | -120.5089 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 1
954 | 041-603-009 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7602 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4015.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 6 | 0 | 0 | 2 | 0 | 1 | 0 | 9 |  |  | 6 |  | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2022-01-13 | NEGATIVE |  |  |  | 2021-12-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-26 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  |  | No |  | No |  | TRUE |  | No | None | FALSE | [10 empty] | 2022-01-26 | 2022-02-01 | 2022-03-25 | 02/01/22 SPOKE WITH JOHN HE SAID OK . PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/17/22 CLEAR TO PROCEED FOR TREE REMOVAL PER MELISSA PERRY. JC 3.25 NO ANS LEFT MESS ON BOTH LINES. SENT TEXT PF "3.25 NO ANS LEFT MESS ON BOTH LINES. SENT TEXT PF 3.25 JOHN C/B AND SAID OK BUT HE'D LIKE TO KEEP A FEW OF THE TREES I EXPLAINED THE POLICY. HE SAID OH WELL OK PF" |  |  |  | 2022-02-11 |  | 2022-02-15 | 2022-02-15 |  |  | 2 | 2022-02-16 | 2022-02-24 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-01-25 | Yes | 39 | 2022-03-29 |  | 2022-03-31 | 2022-03-31 |  | 2022-04-01 | 2022-04-02 | 39 |  |  | 2022-04-05 |  |  |  | John King | 530-391-4068 530-391-6895 | johnnyjumpy1958@gmail.com, kjulie12260@gmail.com |  | Debris Crew Leader/Crew# Eric Rocha/ #503 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 503 | 38.6411 | -120.5093 | Caldor | DR-4619 | Residential | No | 2021-11-15 | ROE Verified | Central Division | 2022-04-06T16:02:13Z | FALSE | 1
955 | 041-603-010 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1a | 7610 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4012.4 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-24 | 2021-11-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2022-03-25 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-05 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-28 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-03 | 2021-12-21 | 2022-04-04 | 12.21 NO ANS LEFT VM & TEXT. JC 12.21 SPOKE WITH DAWN SHE SAID OK BUT PLEASE CALL IN ADVANCE, VENDOR HANDLING PROPANE. JC "4.04 NO ANS LEFT MESS SENT TEXT PF 4.4 DAWN C/B AND SAID OK. BUT PLEASE BE CAREFUL. SHE'S HAVING A NEW R/V DELIVERED TO HER PLACE. IT WILL NOT BE IN THE WAY OF THE TREE FELLING IT WILL BE IN THE DRIVEWAY. SHE WILL MENTION TO THE TFL AGAIN WHEN THEY CALL HER. PF" |  |  |  | 2022-01-15 |  | 2022-01-15 | 2022-01-15 |  |  | 6 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-18 | Yes | 16 | 2022-04-06 |  | 2022-04-07 | 2022-04-07 |  |  |  | 16 | [6 empty] | MARK & DAWN WUERTHNER | 530-317-8671 | NONE |  | Debris Crew Leader/Crew# Fernando Montealegre /#515 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 515 | 38.6411 | -120.5096 | Caldor | DR-4619 | Residential | Yes | 2021-11-19 | ROE Verified | Central Division | 2022-04-08T03:55:59Z | FALSE
956 | 041-603-011 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7618 | Forest Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4003.06 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-01 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-02-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 |  |  | 2022-02-10 | 02/10/22 NO ANS NO VOICEMAIL SENT TEXT. JC 02/10/22 SPOKE WITH ERIC SAID OK. | [27 empty] | 2021-11-24 | Yes | 30 | 2022-02-19 |  | 2022-02-26 | 2022-02-26 |  | 2022-03-02 | 2022-03-03 | 30 |  |  | 2022-03-04 |  | 2022-03-04 | 2022-03-07 | Eric Johnson | 530-388-6673 | fuzzy1tk2@gmail.com |  |  | 38.641 | -120.51 | Caldor | DR-4619 | Residential | No | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
957 | 041-603-012 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4911 | Meadow Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3999.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 2 | TRUE | Yes | Take | 2022-02-17 | 2021-11-19 | Yes | 2021-11-19 | 2021-11-24 | POSITIVE | 2021-12-01 | 2021-12-01 | 4 | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-02-16 | Yes |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-01 | 2021-11-30 | 2022-02-10 | 11.29 NO ANS LEFT VM. JC 11:30 SPOKE WITH ERIC HE SAID OK BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK AND PLEASE REMOVE. JC 02/10/22 NO ANS LEFT VM & TEXT. JC 02/10/22 ERIC SAID OK. JC |  |  |  | 2021-12-03 |  | 2021-12-04 | 2021-12-04 |  |  | 3 | 2021-12-08 | 2021-12-16 | 7 | Approved | [12 empty] | 2021-12-17 | 2021-11-20 | Yes | 21 | 2022-02-16 |  | 2022-02-17 | 2022-02-17 |  | 2022-02-28 | 2022-03-01 | 21 | 2022-03-09 |  | 2022-03-02 | 2022-03-10 | 2022-03-10 | 2022-03-10 | JOHNSON ERIC | 530-388-6673 | Fuzzy1tk2@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 506 | 38.6413 | -120.5103 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 11
958 | 042-222-410 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16586 | 5th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE |  |  | No |  |  | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | POSITIVE | 2022-01-17 | 2022-01-17 | 3 | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-17 | 2022-01-19 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 |  |  | 1 | 2022-01-22 | 2022-01-28 | 5 | Re-scrape |  |  |  | 2022-02-11 | 2022-02-21 | Approved | [6 empty] | 2022-02-24 | 2022-01-15 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-04 | 2022-03-04 | 2022-03-04 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean/ #202 Debris Crew WO# Refer to IAP ---- to --- Crew 202 | 38.9277 | -122.602 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-01T22:00:05Z | FALSE
959 | 042-222-500 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16537 | 6th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE |  |  | No |  |  | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | NEGATIVE |  |  |  | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-08 | 2022-01-19 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 3 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-12 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean / #202 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 202 | 38.928 | -122.6027 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-01T22:00:05Z | FALSE
960 | 042-222-600 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16576 | 5th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE |  |  | No |  |  | 2022-01-08 | No | [6 empty] | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-16 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-08 | 2022-01-19 |  | 1.13 warrant parcel, no contact required RCV |  |  |  | 2022-01-21 |  | 2022-01-21 | 2022-01-21 |  |  | 2 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-15 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-04 | 2022-03-04 | 2022-03-04 | ABATEMENT |  |  |  | Debris Crew Leader/Crew# Sahoi McLean / #202 Debris Crew WO# Refer to IAP --- to --- Crew 202 | 38.9277 | -122.6023 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-01T22:00:05Z | FALSE
961 | 042-223-370 | Tree Only ROE (no qualifying debris) | Ineligible | Not Eligible for Haz Tree Removal | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 16574 | 4th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1443.25 |  | 2021-12-16 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A |  | FALSE |  | FALSE |  | No |  | TRUE | 2021-12-15 |  | FALSE | No | FALSE |  | No | FALSE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE | [5 empty] | 2021-12-15 | No | [6 empty] | 2021-12-15 | No Bio Monitoring Needed for Debris or Trees | 2021-12-15 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | FALSE |  |  |  | 2021-12-17 | 12.16 NO ANS LEFT VM. JC 12.17 SPOKE WITH WENDY SHE ﻿SAID OK. JC | [7 empty] | FALSE | [19 empty] | 2021-12-16 | Do Not Assess | 0 | [14 empty] | Land Title LLC | (714) 602-4884 | Centuryland.manager@gmail.com |  |  | 38.927 | -122.6023 | Cache |  | Residential | No | 2021-12-14 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
962 | 042-231-550 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16583 | 4th Avenue |  | Clearlake | Lake |  | Residential | [5 empty] | 1367.36 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-08 | 2022-01-08 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | TRUE | 5 | TRUE | No |  |  | 2022-01-08 | Yes | 2022-01-10 | 2022-01-13 | NEGATIVE |  |  |  | 2022-01-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-08 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-13 | 2022-01-25 |  | ABATEMENT. NO CONTACT NEEDED. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 2 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-15 | No | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | ABATEMENT |  |  |  |  | 38.9267 | -122.6022 | Cache |  | Residential |  | 2022-01-05 | Abatement | Central Division | 2022-04-06T18:52:41Z | FALSE
963 | 042-233-030 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 16517 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1392.92 |  | 2022-03-09 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-08 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-08 | No | [6 empty] | 2022-03-08 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-08 | No Activity/Nest Building Removed | [53 empty] | 2022-03-07 | No | 0 | [14 empty] | Velma Loe/Diana Louise Tucker | (925)207-9643 | dltucker@tuckerfreochies.com |  |  | 38.9254 | -122.6035 | Cache |  | Residential | Yes | 2022-03-04 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
964 | 042-233-450 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16507 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1388.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-08 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-08 | No | [6 empty] | 2022-03-08 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-02 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-30 | Yes | 2022-03-31 | TRUE | [45 empty] | 2022-03-07 | Yes | 2 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 | 2 |  |  | 2022-04-05 |  | 2022-04-05 | 2022-04-05 | Velma Loe/Diana Louise Tucker | (925) 207-9643 | dltucker@tuckerfreochies.com |  |  | 38.9255 | -122.6036 | Cache |  | Residential | Yes | 2022-03-04 | ROE Verified | Central Division | 2022-04-05T18:35:21Z | FALSE | 0
965 | 042-233-460 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 16530 | Dam Road |  | Clearlake | Lake |  | Residential | [5 empty] | 1401.72 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-03-08 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-08 | No | [6 empty] | 2022-03-08 | No Bio Monitoring Needed for Debris or Trees | 2022-03-08 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-04-02 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-30 | Yes | 2022-03-31 | TRUE | [45 empty] | 2022-04-04 | Yes | 6 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 |  | 2022-04-04 | 2022-04-04 | 5 |  |  | 2022-04-05 |  | 2022-04-05 | 2022-04-05 | Velma Loe/Diana Louise Tucker | (925) 207-9643 | dltucker@tuckerfreochies.com |  |  | 38.9252 | -122.6028 | Cache |  | Residential | Yes | 2022-03-04 | ROE Verified | Central Division | 2022-04-05T18:31:58Z | FALSE | 0
966 | 041-200-020 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Complete | 041-200-020 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4049.27 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-08 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2022-01-14 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Survey Needed | Yes | 2022-03-02 | Yes |  |  |  | Class III | None | TRUE | [41 empty] | 2022-01-28 | Yes | 367 | [14 empty] | FRANKLIN & MICHAEL LUCAS | 530-677-2512 | lucus672@gmail.com |  |  | 38.6526 | -120.5234 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
967 | 041-250-013 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 041-250-013 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3774.58 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-26 | 2021-10-26 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-28 | No | [6 empty] | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No |  | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption |  |  | 2021-11-11 | 2021-12-21 | 2022-03-09 | 12.21 NO ANS LEFT VM & TEXT. JC 12.21 SPOKE WITH RODERICK HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/27/22 SPOKE WITH RODERICK HE SAID OK. VENDOR HANDLING PROPANE. JC 02/26/22 NO ANS LEFT VM & TEXT, JC 02/26/22 SPOKE WITH ROD HE SAID OK FOR TREE REMOVAL. JC﻿ 03/09/22 ROD SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 |  |  | 3 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-15 | 2021-11-15 | Yes | 2 | 2022-03-28 |  | 2022-03-28 | 2022-03-28 |  | 2022-03-29 | 2022-03-30 | 2 |  |  | 2022-03-31 |  |  |  | MACNEIL RODERICK W TR & R W REV TRUST 03/30/06 | 530-391-0128 | ADAMS.CATHIE2@GMAIL.COM |  | Debris Crew Leader/Crew# Eric Rocha/ #503 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 503 | 38.6369 | -120.5268 | Caldor | DR-4619 | Residential | No | 2021-09-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
968 | 041-250-014 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5083 | Sciaroni Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3918.94 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-07 | 2021-10-07 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-06 | Yes | 2021-10-07 | 2021-10-12 | NEGATIVE |  |  |  | 2022-01-17 | Bio Monitoring Needed for Trees, not Debris | 2021-10-14 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-14 | 2021-10-26 |  | 10.26 spoke to HO and he said ok but please call before going . PF 1.13.22 No Ans. Left Mess. PF 01/26/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 HO C/B VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2021-10-30 |  | 2021-11-01 | 2021-11-01 |  |  | 7 | 2021-11-09 | 2021-11-17 | 7 | Re-scrape |  |  |  | 2021-12-03 | 2021-12-13 | Approved | [6 empty] | 2021-12-14 | 2021-10-27 | Yes | 9 | 2022-01-17 |  | 2022-01-17 | 2022-01-17 |  | 2022-01-21 | 2022-01-22 | 9 | 2022-01-27 |  | 2022-01-25 | 2022-02-16 | 2022-02-16 | 2022-02-16 | RODERICK MACNEIL | 530-391-0128 | adams.cathie2@gmail.com |  | Debris Crew Leader/Crew# Sarah Mundt/#501 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 501 | 38.637 | -120.5268 | Caldor | DR-4619 | Residential | No | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 4
969 | 041-250-018 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10319 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3887.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-01 | 2021-11-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  |  | TRUE | No |  |  | 2021-10-30 | Yes | 2021-11-01 | 2021-11-04 | POSITIVE | 2021-11-08 | 2021-11-08 | 3 | 2021-11-09 | Bio Monitoring Needed for Debris AND Trees | 2021-11-15 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-11 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | Yes | 2022-02-17 |  |  | Class II | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-15 | 2021-11-19 | 2022-02-02 | 11.16 PHONE DISCONNECTED. JC 11.17 SENT EMAIL. JC 11.18 PHONE # ON FILE DISCONNECTED. GAVE TO RICHARD. JC 11.19 Reached out to the county for homeowner contact. 02/01/22 PHONE DISCONNECTED SENT EMAIL. JC 02/02/22 PHONE STILL DISCONNECTED EMAIL RETURNED. SENT TO IMT. JC 02/02/22 Clear to proceed per Melissa Perry | 2 | State Planner: Melissa Perry |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 5 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-02 | Yes | 16 | 2022-03-14 |  | 2022-03-15 | 2022-03-15 |  | 2022-03-22 | 2022-03-23 | 16 | 2022-03-30 |  | 2022-03-24 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Williard Bunyan | 925-370-9312 | bbunyan@mindspring.com | Septic Safety concern | Debris Crew Leader/Crew# Mathew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/20 to 11/24Crew 505 | 38.6371 | -120.5284 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 7
970 | 041-260-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 10405 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3799.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-02 | 2021-11-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 4 |  |  |  |  | No |  |  | 2021-11-03 | Yes | 2021-11-04 | 2022-03-08 | POSITIVE | 2021-11-30 | 2021-11-30 | -70 | 2021-11-08 | Bio Monitoring Needed for Debris AND Trees | 2021-11-23 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | Yes | 2022-02-26 | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-09 | 2021-11-30 | 2021-11-30 | 2022-03-22 | 11.29 NO ANS LEFT VM. JC 11:30 SPOKE WITH PATRICK HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. DO NOT TOUCH SEPTIC TANK. JC 03/22/22 SPOKE WITH PATRICK HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-07 |  | 2021-12-08 | 2021-12-08 |  |  | 42 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-18 | Yes | 89 | [14 empty] | Patrick or Donna Hamer | 925-360-1936 | homesculptor@yahoo.com | Vehicles on site Keep items Septic | Debris Crew Leader/Crew# Terrence Harrison/#509 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 509 | 38.636 | -120.5228 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-08T01:07:20Z | FALSE
971 | 041-950-004 | Full Program ROE (debris + trees) | Ready for Debris Removal | No Hazard Trees | Next Step: N/A | ELD Ready -Access Issues | NO ELIGIBLE TREES | 4720 | Blaze Trail |  | Somerset | El Dorado |  | Residential | [5 empty] | 3584.89 |  |  |  |  | TRUE | Access Issues |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-28 | 2021-10-28 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 10 | 1 | 3 | 0 | 1 | 5 | 3 | 23 |  |  |  |  | No |  |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | POSITIVE | 2021-10-30 | 2021-10-30 | 9 | 2021-11-01 | Bio Monitoring Needed for Debris AND Trees | 2021-11-18 | Arch Monitoring Needed for Debris AND Trees | [12 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-03-19 | 2021-11-18 | 2021-11-19 |  | 11.19 SPOKE WITH DANIEL HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC | [27 empty] | 2021-12-21 | No | 0 | [14 empty] | Daniel DeBoard | 530-957-2047 | 50magnum@sbcglobal.net |  |  | 38.6442 | -120.5414 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
972 | 041-950-008 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5901 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3861.07 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-18 | 2021-10-18 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No |  | TRUE | 5 | 2 | 2 | 0 | 2 | 0 | 0 | 11 |  |  | 5 | TRUE | Yes | Leave |  | 2021-10-18 | Yes | 2021-10-19 | 2021-10-28 | POSITIVE | 2021-10-29 | 2021-10-29 | 2 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-17 | 2021-11-18 |  | 11.18 NO ANS LEFT VM. JC 11.18 SPOKE WITH SUSAN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR IS HANDLING LARGE PROPANE TANK BUT PLEASE REMOVE SMALLER TANKS. JC |  |  |  | 2021-11-19 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-12-07 | No | 0 | [8 empty] | 2021-12-10 |  |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | Edwin and Susan Hatch | 530-503-7439 | mummset6@gmail.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 506 | 38.648 | -120.5375 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE
973 | 041-950-009 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5965 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3904.65 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-23 | Yes | 2021-12-23 | 2021-12-29 | POSITIVE | 2022-01-20 |  | 17 | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-14 | No Arch Monitoring Needed for Debris or Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-01-20 | 2022-01-21 |  | 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 SPOKE WITH DANNY HE SAID OK. PLEASE CALL BEFORE ENTERING PROPERTY. VENDOR HANDLING PROPANE. PLEASE DO NOT DAMAGE RETAINING WALL. HE WANTS TO SPEAK WITH THE CREW LEADER ABT CONCERNS OF RETAINING WALL. JC |  |  |  | 2022-01-24 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2021-12-18 | No | 0 | [8 empty] | 2022-02-21 |  |  | 2022-03-01 | 2022-03-01 | 2022-03-01 | Danny & Debra Rallens | 530-409-2260 , 916-213-9793 | drallens@att.net |  | Debris Crew Leader/Crew# Eric Rocha / #505 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 505 | 38.6502 | -120.5364 | Caldor | DR-4619 | Residential | Yes | 2021-11-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
974 | 041-950-010 | Tree Only ROE (no qualifying debris) | Ineligible | No Hazard Trees | Next Step: N/A | Ineligible/Withdrawn | Ineligible/Withdrawn | 3150 | Sunday Ridge Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3952.39 |  | 2022-01-29 | No qualifying debris; no hazard trees | State | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | TRUE | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | [15 empty] | 2021-11-16 | No Bio Monitoring Needed for Debris or Trees | [16 empty] | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  |  | 11.22 SPOKE WITH CHRIS HE SAID OK BUT WOULD LIKE TO A PHONE CALL BEFORE ANYONE GOING OUT TO HIS PROPERTY. HE WOULD LIKE TO BE THERE FOR DEBRIS REMOVAL. JC | [27 empty] | 2022-01-29 | No | 0 | [14 empty] | Christopher N Baker | 916-969-8089 | Cbakerinvestments@gmail.com | Keep Items Vehicles Onsite Well |  | 38.654 | -120.5358 | Caldor | DR-4619 | Residential | No | 2021-11-09 | ROE Verified | Central Division | 2022-04-05T17:56:48Z | FALSE
975 | 041-950-011 | Full Program ROE (debris + trees) | Ready for Erosion Control | No Hazard Trees | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 3134 | Sunday Ridge Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4062.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Take | 2022-03-08 | 2022-01-18 | Yes | 2022-01-18 | 2022-01-21 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-01-31 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-01-31 | 2022-02-02 |  | 02/01/22 NO ANS LEFT VM & TEXT. JC 02/02/22 NO ANS LEFT VM & EMAIL. JC 02/02/22 SPOKE WITH CHRISTIE SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC |  |  |  | 2022-02-10 |  | 2022-02-11 | 2022-02-11 |  |  | 2 | 2022-02-14 | 2022-02-22 | 7 | Approved | [12 empty] | 2022-03-17 | 2022-01-29 | No | 0 | [14 empty] | Vince & Christie Bizzini | 209-345-9879 , 209-404-2332 | vcbizzini@gmail.com |  | Debris Crew Leader/Crew# Zara Armani/ #507 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 507 | 38.6527 | -120.5389 | Caldor | DR-4619 | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
976 | 041-950-012 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | FSO Returned to County | FSO Returned to County | 3031 | Sunday Ridge Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3891.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2022-02-01 | Arch Monitoring Needed for Debris AND Trees | [14 empty] | FALSE | [8 empty] | TRUE | 2022-02-17 | 2022-02-01 | 2022-02-02 |  | 02/02/22 NO ANS LEFT VM & TEXT. JC 02/02/22 SPOKE WITH MARGARET SHE SAID OK. PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-02-07 |  | 2022-02-07 | 2022-02-07 |  |  | 4 | 2022-02-10 | 2022-02-18 | 7 | Soil Boring | 2022-02-25 | 2022-03-07 | Approved | [9 empty] | 2022-03-08 | 2022-01-29 | No | 0 | [8 empty] | 2022-03-17 |  |  | 2022-03-18 | 2022-03-18 | 2022-03-18 | margaret linzmeier C/O Shannon linzmeier linzmeier trust | 530-306-3778 | SLINZMEIER@LIVE.COM | Vehicles Onsite Well | Debris Crew Leader/Crew# Adam Mattssion/ #507 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew | 38.6549 | -120.538 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
977 | 041-950-013 | Full Program ROE (debris + trees) | Returned to County | Not Eligible for Haz Tree Removal | Next Step: N/A | FSO Returned to County | FSO Returned to County | 2992 | Sunday Ridge Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3829.37 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-10 | 2021-12-10 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 3 | 0 | 2 | 1 | 0 | 2 | 10 |  |  |  | TRUE | Yes | Leave |  | 2022-01-17 | Yes | 2022-01-17 | 2022-01-20 | NEGATIVE |  |  |  | 2021-12-06 | No Bio Monitoring Needed for Debris or Trees | 2022-02-02 | Arch Monitoring Needed for Debris AND Trees | Yes | [13 empty] | FALSE | [8 empty] | TRUE | 2022-02-16 | 2022-02-02 | 2022-02-03 |  | 02/03/22 NO ANS LEFT VM & TEXT. JC 02/03/22 MARGARET GAVE CONSENT VIA TEXT. JC 02/14/22 HO SAID TANK IS RENTED AND VENDOR WILL HANDLE TANK. JC |  |  |  | 2022-02-08 |  | 2022-02-10 | 2022-02-10 |  |  | 2 | 2022-02-12 | 2022-02-18 | 5 | Soil Boring | 2022-02-25 | 2022-03-07 | Approved | [9 empty] | 2022-03-08 |  | Do Not Assess | 0 | [8 empty] | 2022-03-17 |  |  | 2022-03-24 | 2022-03-24 | 2022-03-24 | margaret linzmeier C/O Shannon linzmeier linzmeier trust | 530-306-3778 | SLINZMEIER@LIVE.COM |  | Debris Crew Leader/Crew# Zara Armani/ #507 Debris Crew WO# Refer to IAP 02/09 to 02/12 Crew 507 | 38.657 | -120.5369 | Caldor | DR-4619 | Residential | No | 2021-11-16 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE
978 | 042-021-019 | Full Program ROE (debris + trees) | Re-scrape Needed | No Hazard Trees | Next Step: N/A | ELD Rescrape Needed | NO ELIGIBLE TREES | 042-021-019 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3996.88 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Gate code 3031 (first SPT gate) Gate 6054 code to actual property. SEE NOTES IN CONTACT AREA. |  |  | Yes |  | TRUE | 2022-02-19 | 2022-02-19 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes |  |  | 2022-03-03 | Yes | 2022-03-03 | 2022-03-08 | POSITIVE | 2022-03-09 | 2022-03-09 | 2 | 2022-02-19 | Bio Monitoring Needed for Debris AND Trees | 2022-03-08 | Arch Monitoring Needed for Debris, not Trees |  | 2022-03-26 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-03-19 | 2022-03-09 | 2022-03-11 |  | gate code 3031 number line up across the top line (first SPI gate) gate code 6054 to actual property. 01/28/22 I spoke with homeowner he said the 6054 is for the second gate and 3031 is code for first gate. He said the notified district manager from Sierra Pacific, and they are coming out next week to take care of the locked gate issue. jc 01/29/22 HO spoke with Matt from OES this morning. Matt informed him that there is too much snow. Please tell Lona combination lock for SPI at the top of the road code 3031number line up across the top line. and second gate code 6054 combination numbers go in the middle. 02/07/22 HO SAID BURNING STRUCTURES ON PROPERTY.JC 03/11/22 SPOKE WITH ROBERT HE SAID OK FOR DEBRIS REMOVAL. PLEASE CALL IN ADVANCE. JC |  |  |  | 2022-03-26 |  | 2022-03-26 | 2022-03-26 |  |  | 1 | 2022-03-28 | 2022-04-05 | 7 | Re-scrape | [13 empty] | 2022-02-03 | No | 0 | [14 empty] | Robert Crow | 510-506-8190 | rcrow94611@gmail.com | SEPTIC | Debris Crew Leader/Crew# Carondlet Dunbar/#519 Debris Crew WO# Refer to IAP 03/26/22 to 03/30/22 Crew 519 | 38.7316 | -120.4897 | Caldor | DR-4619 | Residential | No | 2021-10-28 | ROE Verified | Central Division | 2022-04-07T21:30:21Z | FALSE
979 | 042-030-070 | Full Program ROE (debris + trees) | Re-scrape Needed | Not Eligible for Haz Tree Removal | Next Step: N/A | ELD Rescrape Needed | NO ELIGIBLE TREES | 5580 | Ferrari Mill Road |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 3582.7 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Gate code is 1932 on first gate. Gate code is 5580 on second gate. | FALSE |  | Yes |  | TRUE | 2022-01-22 | 2022-01-22 | FALSE | No |  |  | No |  | No | Yes | No | No | Yes | Yes | FALSE | TRUE | 0 | 2 | 0 | 1 | 3 | 2 | 0 | 8 |  |  |  |  | Yes | Leave |  | 2021-12-03 | Yes | 2021-12-03 | 2021-12-08 | POSITIVE | 2022-01-24 | 2022-01-24 | 33 | 2022-01-22 | No Bio Monitoring Needed for Debris or Trees | 2022-01-22 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-16 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-03-18 | 2022-01-24 | 2022-01-26 |  | 12.17 NO ANS LEFT VM FOR GATE CODE, JC GATE code AT MORMAN INTERSECTION 1932. HOUSE GATE CODE 5580. HOMEOWNER WOULD LIKE TO BE CONTACTED BEFORE ANYONE ENTERS PROPERTY. JC ****Key lock on gate operates in conjunction with the combination lock. Once the code 1932 is entered the key lock will drop. **** Gate code is 1932 on first gate. Gate code is 5580 on second gate. 01/25/22 NO ANS LEFT VM & TEXT TANK. JC 01/26/22 TROY GAVE PRE CONSENT VIA TEXT FOR DEBRIS REMOVAL. THE PROPANE TANK IS IN WORKING CONDITION. DO NOT REMOVE. JC 01/31/22 HO CALLED TO INFORM US THAT HE MARKED OFF WITH CAUTION TAPE WHAT HE DOES NOT WANT REMOVED. PLEASE DO NOT REMOVE ITEMS MARKED WITH CAUTION TAPE! 02/16/22 TROY CALL FOR STATUS. JC |  |  |  | 2022-02-21 | 2022-03-17 | 2022-03-18 | 2022-03-18 |  |  | 4 | 2022-03-23 | 2022-03-31 | 7 | Re-scrape | [14 empty] | Do Not Assess | 0 | [14 empty] | Tim & Barbara Land & Troy Jacobs | 530 409-2827, 916-417-1705 | tland1953@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Fernando Montealegre / #519 Debris Crew WO# Refer to IAP 03/16 to 03/19 Crew 519 | 38.7108 | -120.5726 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-03T19:50:56Z | FALSE
980 | 042-040-047 | Full Program ROE (debris + trees) | Re-scrape Needed | No Hazard Trees | Next Step: N/A | ELD Rescrape Needed | NO ELIGIBLE TREES | 042-040-047 | No Address |  | Somerset | El Dorado |  | Residential | [5 empty] | 4368.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-31 | 2022-01-31 | FALSE | Yes |  | 2022-02-12 | No | TRUE | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2022-02-01 | Yes | 2022-02-01 | 2022-02-04 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2022-03-22 | Arch Monitoring Needed for Debris, not Trees |  | 2022-03-16 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-03-17 | 2022-02-12 | 2022-02-16 | 2022-02-16 | 02/14/22 NO ANS LEFT VM & TEXT. JC 02/15/22 NO ANS LEFT VM AND EMAIL. JC 02/15/22 Left message notifying them of upcoming crew mobilization﻿ - MP 02/16/22 NO ANS LEFT VM & 2ND EMAIL. JC 02/16/22 - Ok to proceed - MP | 6 | State Planner - Melissa Perry |  | 2022-03-21 |  | 2022-03-22 | 2022-03-22 | TRUE |  | 2 | 2022-03-23 | 2022-03-31 | 7 | Re-scrape | [13 empty] | 2022-02-03 | No | 0 | [14 empty] | Arlene Heggard | 415-304-8740 | adamsc21@gmail.com | Septic | Debris Crew Leader/Crew# Antonio Ruiz /#519 Debris Crew WO# Refer to IAP 03/19 to 03/22 Crew 519 | 38.703 | -120.5098 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-03T19:49:46Z | FALSE
981 | 042-090-032 | Full Program ROE (debris + trees) | Pending Soil Sample Results | No Hazard Trees | Next Step: N/A | Pending Soil Sampling Results | NO ELIGIBLE TREES | 042-090-032 | No Address |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 4515.16 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Gate Code: 6565 |  |  | Yes |  | TRUE | 2022-03-04 | 2022-03-04 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No |  | FALSE | TRUE | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | [7 empty] | 2022-03-03 | Yes | 2022-03-03 | 2022-03-08 | POSITIVE | 2022-03-10 | 2022-03-10 | 3 | 2022-02-19 | Bio Monitoring Needed for Debris AND Trees | 2022-03-09 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-26 | No Activity/Nest Building Removed | [11 empty] | FALSE | [8 empty] | TRUE | 2022-04-14 | 2022-03-10 | 2022-03-11 |  | 01/28/22 NO ANS LEFT VM & TEXT ABT GATE CODE. JC 01/31/22 HO C/B WITH GATE CODE 6565. HE SAID HE CANNOT MAKE IT TO PROPERTY TODAY BUT GAVE CONSENT FOR CREW TO ENTER PROPERTY. JC 01/31/22 HO TEXT TO INFORM THAT HE WANTS TO BE ON SITE DURING DEBRIS REMOVAL. JC 02/07/22 NO ANS LEFT VM AND TEXT ABT ELIGIBLE DEBRIS. JC 02/10/22 NO ANS LEFT VM & EMAIL ABT ELIGIBLE DEBRIS. JC 02/15/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/11/22 SPOKE WITH CHRIS. HE WANTS TO SPEAK WITH CREW LEADER BOFORE ANYONE ENTERS HIS PROPERTY. PLEASE CALL HOMEOWNER BEFORE ENTERING PROPERTY. JC |  |  |  | 2022-03-26 |  | 2022-04-02 | 2022-04-02 |  |  | 1 | 2022-04-04 |  | 5 | [14 empty] | 2022-02-03 | No | 0 | [14 empty] | Christopher Kingsley | 916-813-9044 | chrisk60@gmail.com |  |  | 38.7167 | -120.4748 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-08T07:02:33Z | FALSE
982 | 042-240-004 | Full Program ROE (debris + trees) | Ready for Erosion Control | Not Eligible for Haz Tree Removal | Next Step: N/A | Erosion Control | NO ELIGIBLE TREES | 4380 | Cosumnes Mine Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3142.9 |  |  |  |  | FALSE |  |  | N/A |  |  | key is at county office for gate. |  |  | Yes |  | TRUE | 2021-12-04 | 2021-12-04 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | Yes | Yes | No | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-10 | NEGATIVE |  |  |  | 2021-12-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-29 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-02 | No Activity/Nest Building Removed | [9 empty] | Class I |  | FALSE | [8 empty] | TRUE | 2022-02-04 | 2022-01-29 | 2022-02-01 |  | 02/01/22 NO ANS LEFT VM & TEXT. JC 02/01/22 SPOKE WITH KATHY SHE SAID OK. BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. KEY FOR GATE IS AT THE COUNTY OFFICE. JC |  |  |  | 2022-02-04 |  | 2022-02-08 | 2022-02-08 |  |  | 3 | 2022-02-10 | 2022-02-18 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 |  | Do Not Assess | 0 | [14 empty] | Kathy Vander Veen | 530-306-8312 | kvanderveen59@gmail.com | Safety Concerns Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar / #505 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 505 | 38.6696 | -120.5408 | Caldor | DR-4619 | Residential | Yes | 2021-11-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
983 | 041-733-001 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 041-733-001 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3721.58 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-06 | Bio Monitoring Needed for Trees, not Debris | 2022-01-21 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [12 empty] | 2022-02-01 | 02/01/22 SPOKE WITH TRACI SHE SAID OK. PLEASE REMOVE PROPANE TANK. JC | [27 empty] | 2022-01-18 | Yes | 47 | 2022-03-01 |  | 2022-03-02 | 2022-03-02 |  | 2022-03-08 | 2022-03-10 | 47 |  |  | 2022-03-11 |  | 2022-03-11 | 2022-03-11 | Traci Barsuglia | 916-349-1707 | processcomplete@netzero.net |  |  | 38.629 | -120.5359 | Caldor | DR-4619 | Residential | No | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
984 | 041-733-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5351 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3724.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-03 | 2021-12-03 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-13 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | Arch Monitoring Needed for Trees, not Debris |  | 2022-02-21 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 | 2022-01-14 | 2022-01-19 | 2022-02-16 | 12.16 NO ANS LEFT VM & TEXT. JC 12.16 HO GAVE CONSENT VIA TEXT. JC 01/19/22 NO ANS LEFT VM & TEXT. JC 01/19/22 HO GAVE CONSENT VIA TEXT FOR TREE REMOVAL. JC 02/16/22 HO SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 |  |  | 5 | 2022-01-27 | 2022-02-04 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-13 | Yes | 35 | 2022-02-25 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-04 | 35 | 2022-03-11 |  | 2022-03-08 | 2022-03-14 | 2022-03-14 | 2022-03-14 | LAWRENCE WATSON & ANN SEYMOUR | 916-765-5576 | larry.watson@comcast.net |  | Debris Crew Leader/Crew# Enedith Montiel / #501 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 501 Septic | 38.6287 | -120.5358 | Caldor | DR-4619 | Residential | Yes | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
985 | 041-733-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5359 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3707.05 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2022-02-04 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-21 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-02-11 | 02/10/22 NO ANS LEFT VM & TEXT. JC 02/11/22 HO GAVE CONSENT VIA TEXT. JC | [27 empty] | 2022-01-14 | Yes | 29 | 2022-02-21 |  | 2022-02-25 | 2022-02-25 |  | 2022-03-03 | 2022-03-04 | 29 |  |  | 2022-03-08 |  | 2022-03-08 | 2022-03-09 | LAWRENCE & ANN SEYMOUR | 916-765-5576 | larry.watson@comcast.net |  |  | 38.6285 | -120.5357 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 6
986 | 041-734-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5348 | Wood View Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3760.48 |  |  |  |  | TRUE | New Owner |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Yes | Leave |  | 2021-12-07 | Yes | 2021-12-07 | 2021-12-13 | NEGATIVE |  |  |  | 2021-11-12 | No Bio Monitoring Needed for Debris or Trees | 2021-12-11 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed |  |  | Survey Needed | Yes | 2022-02-25 | No |  | TRUE |  | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-13 | 2021-12-15 | 2022-03-24 | 12.14 NO ANS LEFT VM & TEXT. JC 12.15 NO ANS LEFT VM & EMAIL. JC 12.15 SPOKE WITH ANN SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 3.24 NO ANS. LEFT MESS - SENT TEXT PF 3.24 ANN C/B AND SAID OK TO PROCEED PF |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 5 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-02-01 | Yes | 46 | [14 empty] | Ann Thompson | 408-607-7077 | mssewnsew@gmail.com | Septic | Debris Crew Leader/Crew# Brandon Riley/ #501 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 501 | 38.6308 | -120.5335 | Caldor | DR-4619 | Residential | Yes | 2021-10-29 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
987 | 041-652-006 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5024 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3913.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 3 |  |  |  | TRUE | Yes | Leave |  | 2021-10-11 | Yes | 2021-10-12 | 2021-10-15 | NEGATIVE |  |  |  | 2021-12-10 | Bio Monitoring Needed for Trees, not Debris | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-20 | 2021-10-25 | 2021-12-04 | 10.25 Spoke with Jeffrey, acknowledged start of debris removal, does not need to be on site RCV 11.3 Jeff called and said his 2 tanks were marked. Please do not take. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.4 SPOKE WITH JEFF HE SAID OK. JC |  |  |  | 2021-11-03 |  | 2021-11-05 | 2021-11-05 |  |  | 4 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-01 | Yes | 74 | 2021-12-08 |  | 2021-12-11 | 2021-12-11 |  | 2021-12-17 | 2021-12-17 | 74 | 2022-01-31 |  | 2022-01-10 | 2022-02-02 | 2022-02-02 | 2022-02-02 | JEFFREY LEE LOESER | 925-285-4835 | styleprice@aol.com |  | "Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 11/03 to 11/03 Crew 504" | 38.6407 | -120.5333 | Caldor | DR-4619 | Residential | Yes | 2021-10-09 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
988 | 041-661-003 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | TREE ONLY ROEs | Grizzly Flats Ready | 5053 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3874.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-04 | Bio Monitoring Needed for Debris AND Trees | 2022-01-25 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No |  |  |  | TRUE |  | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption |  |  |  |  | 2022-03-19 | 02/10/22 SPOKE WITH DAVID'S assistant. She said ok and no propane tanks on the property. JC "03/09/22 NO ANS LEFT VM. JC 03/10/22 SPOKE WITH CO-WORKER, AND WAS ASKED TO CALL BACK AFTER 1 PM. JC 03/10/22 CALL BACK AND LEFT MESSAGE FOR DAVID TO RETURN CALL. JC" 03/16/22 NO ANS LEFT VM & EMAIL. JC 03/17/22 NO ANS LEFT VM & 2ND EMAIL. JC 03/19/22 CLEARED TO PROCEED PER MP | 4 | State Planner: Melissa Perry | [25 empty] | 2022-01-22 | Yes | 129 | [14 empty] | David Rabie | 714-602-4884 | centuryland.manager@gmail.com |  |  | 38.6396 | -120.5342 | Caldor | DR-4619 | Residential | No | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
989 | 041-661-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Hold | 5029 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3864.98 |  |  |  |  | TRUE | Boundary Line Issues, Safety Concerns, Other - see comments |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 5 |  |  |  |  | Yes | Leave |  | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | NEGATIVE |  |  |  | 2021-10-14 | No Bio Monitoring Needed for Debris or Trees | 2021-10-14 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-14 | 2021-11-03 | 2021-12-07 | 11.2 NO ANS LEFT MESS PF 11.3 NO ANS LEFT MESS. JC 11.3 SPOKE WITH DARLENE SHE SAID OK. THE VENDOR HAS BEEN CONTACTED ABT TANK. JC 12.4 NO ANS LEFT VM FOR TREE REMOVAL. JC 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH DARLENE SHE SAID OK. JC |  |  |  | 2021-11-05 |  | 2021-11-08 | 2021-11-08 |  |  | 3 | 2021-11-10 | 2021-11-19 | 8 | Approved | [12 empty] | 2021-11-22 | 2021-11-29 | Yes | 44 | [14 empty] | THEODORE & DARLENE NILES | 916-712-6098 | darniles@gmail.com |  | "Debris Crew Leader/Crew# Adam Hutcheson/504 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 504" | 38.6404 | -120.5342 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
990 | 041-662-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5034 | Rollingwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3915.42 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-08 | 2021-10-08 |  | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 4 |  |  |  | TRUE | Yes | Take | 2022-02-16 | 2021-10-08 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-22 | 2021-10-22 | 7 | 2021-10-14 | Bio Monitoring Needed for Debris AND Trees | 2021-10-20 | Arch Monitoring Needed for Debris AND Trees | Yes |  |  |  |  | Complete | No | [5 empty] | Class III | None | TRUE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-10-22 | 2021-10-27 | 2021-12-08 | 10.25 Left a voicemail RCV 10.26. NO ANS. PF 10.27 NO ANS. PF 12.08 SPOKE WITH STEVE ABT TREE REMOVAL HE SAID OK. PLEASE CALL IN ADVANCE. JC 01/25/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC 01/26/22 SPOKE WITH STEVE HE SAID REMOVE PROPANE TANK. JC | 3 | Kendall Wilson |  | 2021-10-30 |  | 2021-11-01 | 2021-11-01 |  |  | 7 | 2021-11-09 | 2021-11-17 | 7 | Re-scrape |  |  |  | 2021-11-23 | 2021-12-03 | Approved | [6 empty] | 2021-12-06 | 2021-11-06 | Yes | 67 | 2021-12-18 |  | 2021-12-22 | 2021-12-22 |  | 2021-12-23 | 2021-12-23 | 67 | 2022-01-28 |  | 2022-01-17 | 2022-03-02 | 2022-03-02 | 2022-03-02 | STEVE JURGENS & ANNA DUSDALL | 916-965-3936, 916-203-5385 | stevejurgens1@gmail.com |  | Debris Crew Leader/Crew# Adam Hutcheson/#504 Debris Crew WO# Refer to IAP 10/30 to 11/03 Crew 504 | 38.6401 | -120.5332 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 1
991 | 041-691-003 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5203 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3844.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 5 |  |  | 6 | TRUE | No |  |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | POSITIVE | 2021-12-10 | 2021-12-10 | 4 | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-15 | 2021-12-10 | 2022-01-21 | 2022-02-16 | "12.11 NO ANS LEFT VM & TEXT. JC 12.11 HO GAVE CONSENT VIA TEXT. JC 01/21/22 SANDRA SAID OK. JC" 02/16/22 NO ANS LEFT VM & TEXT. JC 02/16/22 SPOKE WITH SANDRA SHE OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-25 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-02-19 | Yes | 3 | 2022-02-19 |  | 2022-02-21 | 2022-02-21 |  | 2022-02-28 | 2022-03-04 | 3 | 2022-03-10 |  | 2022-03-05 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Sandra Mecham | 530-957-7423 | sandybear2009@hotmail.com | Vehicle on site Septic | Debris Crew Leader/Crew# Eric Rocha / #504 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 504 | 38.6335 | -120.5357 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
992 | 041-691-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5195 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3832.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Take | 2022-03-07 | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-02 | 2021-12-04 | 2022-02-16 | 12.03 Left voicemail RCV 12.4 NO ANS LEFT VM. JC 12.4 SPOKE WITH DANIEL HE SAID OK. BUT PLEASE CALL IN ADVANCE. HE OWNS PROPANE TANK AND PLEASE REMOVE. JC 02/16/22 HO SAID OK TO TREE REMOVAL. PLEASE CALL IN ADVANCE. JC |  |  |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 |  |  | 28 | 2022-01-18 | 2022-01-26 | 7 | Approved | [12 empty] | 2022-01-27 | 2022-01-20 | Yes | 8 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-02-28 | 2022-03-04 | 8 | 2022-03-10 |  | 2022-03-05 | 2022-03-11 | 2022-03-11 | 2022-03-11 | Daniel Macias Jr | 530-621-3170 |  | Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson /#507 Debris Crew WO# Refer to IAP 12/08 to 12/12 Crew 507 | 38.6337 | -120.5357 | Caldor | DR-4619 | Residential | Yes | 2021-11-03 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 9
993 | 041-691-005 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5187 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3821.12 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | No |  |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-21 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-12-03 | 2021-12-07 | 2022-03-18 | "12.06 NO ANS LEFT VM & TEXT . JC 12.06 SENT EMAIL JC 12.07 NO ANS LEFT VM & TEXT. JC 12.07 SPOKE WITH DONALD HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC" 3.17 No ans. left mess PF sent 2nd email PF 03/18/22 NO ANS LEFT. JC 03/18/22 CLEAR TO PROCEED PER MELISSA PEERY. JC | 3 | State Planner: Melissa Perry |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 3 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2022-01-19 | Yes | 6 | 2022-03-22 |  | 2022-03-22 | 2022-03-22 |  | 2022-03-24 | 2022-03-25 | 6 | 2022-03-30 |  | 2022-03-26 | 2022-04-01 | 2022-04-01 | 2022-04-01 | Donald & Debbi Scott | 530-409-8915 , 530-391-4352 | dscott719@sbcglobal.net | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Adam Mattsson/ #507 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 507 | 38.634 | -120.5357 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 2
994 | 041-691-006 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Ready for Tree Felling | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 5179 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3812.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 1 | 2 | 1 | 1 | 6 |  |  |  |  | No |  |  | 2021-12-03 | Yes | 2022-02-11 | 2022-02-16 | POSITIVE | 2022-03-08 | 2022-03-08 | 15 | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-02-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-17 | No | 2022-02-28 | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-04-13 | 2022-03-08 | 2022-03-14 |  | 03/11/22 NO ANS LEFT VM & TEXT. JC 3.14@9:00 No ANS. LEFT V/M ON BOTH #s INFORMING THEM OF THE CREW WOULD BE MOBILIZING AT LUNCH TODAY PER MP. PF 3.14@10:10 HO(MR SCOTT) C/B SAID OK BUT BE SURE TO GET A TRAILER SITTING IN THE BACK SIDE OF THEIR PROIPERTY. PF |  |  |  | 2022-03-14 |  | 2022-03-15 | 2022-03-15 |  |  | 3 | 2022-03-17 | 2022-03-25 | 7 | Re-scrape |  |  |  | 2022-03-31 | 2022-04-08 | [8 empty] | 2021-12-03 | Yes | 22 | [14 empty] | Donald & Debbi Scott | 530-409-8915 , 530-391-4352 | dscott719@sbcglobal.net | Other Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar /#514 Debris Crew WO# Refer to IAP 03/12 to 03/16 Crew 514 | 38.6343 | -120.5357 | Caldor | DR-4619 | Residential | No | 2021-11-10 | ROE Verified | Central Division | 2022-04-09T00:04:02Z | FALSE
995 | 041-692-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5180 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3798.25 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-22 | 2021-11-22 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-16 | No | [6 empty] | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-17 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-15 | No Activity/Nest Building Removed |  |  | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-04 | 2021-11-17 | 2021-11-19 | 2022-01-13 | 11.18 NO ANS LEFT VM. JC 11.19 SPOKE WITH SHAWN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 1.13.22 No Ans. Left Mess. PF 1.13.22 Sent Text.6:30 1.13.22 The Morgans c/b and said ok PF |  |  |  | 2021-11-23 |  | 2021-11-23 | 2021-11-23 |  |  | 4 | 2021-11-30 | 2021-12-08 | 7 | Approved | [12 empty] | 2021-12-09 | 2021-11-08 | Yes | 26 | 2022-03-18 |  | 2022-03-18 | 2022-03-18 |  | 2022-03-23 | 2022-03-25 | 26 | 2022-03-30 |  | 2022-03-26 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Shawn and Jolene Morgan | 530 391-3532 | jolene_morgan11@Yahoo.com |  | Debris Crew Leader/Crew# Adam Hutcheson /#504 Debris Crew WO# Refer to IAP 02/02 To 02/05 Crew 504 | 38.6342 | -120.535 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
996 | 041-692-004 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5206 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3818.31 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-03 | No | [6 empty] | 2021-12-03 | No Bio Monitoring Needed for Debris or Trees | 2022-02-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-02 | Yes | 2022-03-02 |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 |  |  | 2022-03-04 | 02/03/22 Ronald called for status. He gave pre approval for hazard tree removal. No propane tanks. jc 03/04/22 RONALD SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2021-12-07 | Yes | 27 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-19 | 2022-03-22 | 27 |  |  | 2022-03-25 |  | 2022-03-25 | 2022-03-24 | Ronald Myers | 530-313-3199 | myers.julie.c@gmail.com | Vehicles Onsite |  | 38.6334 | -120.5351 | Caldor | DR-4619 | Residential | No | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 5
997 | 041-692-005 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5214 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3820.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 17 | 3 | 0 | 1 | 0 | 3 | 0 | 24 |  |  | 2 |  | Yes | Take | 2022-02-16 | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-16 | 2022-01-21 | 2022-03-16 | 12.17 NO ANS LEFT VM & TEXT JC 12.18 NO ANS LEFT VM & EMAIL.JC 12.18 SPOKE RONALD HE SAID OK BUT PLEASE CALL IN ADVANCE﻿. OWNS PROPANE AND WANT REMOVED IF DAMAGED. JC 01/21/22 NO ANS LEFT VM & TEXT. JC 01/21/22 HO GAVE CONSENT VIA TEXT. JC 03/15/22 NO ANS LEFT VM & TEXT. JC 03/16/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-22 |  | 2022-01-25 | 2022-01-25 |  |  | 5 | 2022-01-31 | 2022-02-08 | 7 | Approved | [12 empty] | 2022-02-09 | 2022-01-18 | Yes | 17 | [14 empty] | Ronald Myers | 530-313-3199 | myers.julie.c@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell / # 504 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 504 | 38.6331 | -120.5351 | Caldor | DR-4619 | Residential | No | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
998 | 041-692-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 10149 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3797.71 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-02 | 2021-12-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 3 |  | Yes | Leave |  | 2021-12-04 | Yes | 2021-12-04 | 2021-12-08 | NEGATIVE |  |  |  | 2021-12-01 | No Bio Monitoring Needed for Debris or Trees | 2021-12-06 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | Yes | 2022-03-01 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-06 | 2021-12-09 | 2022-03-25 | 12.09 SPOKE WITH JEREMY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 03/03/22 SPOKE WITH JEREMY HE SAID OK. JC 03/25/22 FOLLOW UP CALL. SPOKE WITH JEREMY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-14 |  | 2022-01-15 | 2022-01-15 |  |  | 5 | 2022-01-22 | 2022-01-28 | 5 | Approved | [12 empty] | 2022-02-01 | 2022-01-07 | Yes | 3 | [14 empty] | Melissa Powell & Jeremy Nyberg | 530-644-4077 | fireindeedhot45@gmail.com | Vehicles Onsite | Debris Crew Leader/Crew# Eric Rocha/ #505 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 505 | 38.6336 | -120.5344 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
999 | 041-692-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5190 | Evergreen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3809.01 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 8 | 0 | 5 | 0 | 1 | 4 | 1 | 19 |  |  | 11 | TRUE | Yes | Leave |  | 2021-10-16 | Yes | 2021-10-18 | 2021-10-21 | POSITIVE | 2021-10-28 | 2021-10-28 | 6 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-10 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-16 | No |  |  |  | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-10 | 2021-11-11 | 2022-03-02 | 11.11 SPOKE WITH STEVEN HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE THE PROPANE TANK. JC 03/01/22 NO ANS LEFT VM & TEXT. JC 03/02/22 NO ANS LEFT VM & EMAIL JC 03/02/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-17 |  | 2021-11-20 | 2021-11-20 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2021-11-08 | Yes | 17 | 2022-03-14 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-21 | 2022-03-22 | 17 | 2022-03-24 |  | 2022-03-23 | 2022-03-25 | 2022-03-25 | 2022-03-25 | Steven Frazier | 530-903-6908 | frazier5190@gmail.com |  | Debris Crew Leader/Crew# Crystal Egan #508 Debris Crew WO# Refer to IAP 11/20 to 11/24 Crew 508 | 38.6337 | -120.5351 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
1000 | 041-693-001 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 5178 | Golden Aspen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3804.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-27 | 2021-10-27 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-10-26 | Yes | 2021-10-27 | 2021-11-01 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-06 | 2021-11-05 | 2021-11-09 |  | 11.8 PHONE NUMBER ON FILE NOT ACCEPTING MY CALL. SENT EMAIL. JC 11.9 SPOKE WITH JOHN HE SAID OK. NO CALL NECESSARY. NO PROPANE TANKS. PF |  |  |  | 2021-11-15 |  | 2021-11-16 | 2021-11-16 |  |  | 4 | 2021-11-19 | 2021-12-01 | 7 | Re-scrape |  |  |  | 2021-12-07 | 2021-12-15 | Approved | [6 empty] | 2021-12-16 | 2021-11-13 | Yes | 22 | 2022-01-13 |  | 2022-01-13 | 2022-01-13 |  | 2022-01-14 | 2022-01-19 | 22 | 2022-01-27 |  | 2022-01-25 | 2022-01-31 | 2022-01-31 | 2022-01-31 | JOHN HARWELL & ULRIKE DOBRICK | 916-726-2706 | herrjohn@hotmail.com | Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 505 | 38.6338 | -120.5326 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 1
1001 | 041-693-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 5227 | Wooded Glen Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3816.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-01 | 2021-12-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 3 |  |  | 2 |  | No |  |  | 2021-12-06 | Yes | 2021-12-06 | 2021-12-09 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-31 | No |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-06 | 2022-01-21 |  | 12.10 NO ANS LEFT VM & TEXT. JC 12.10 SPOKE WITH PATRICIA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/21/22 SPOKE WITH PATRICIA SHE SAID OK. JC |  |  |  | 2022-01-22 |  | 2022-01-24 | 2022-01-24 |  |  | 5 | 2022-01-29 | 2022-02-07 | 6 | Approved | [12 empty] | 2022-02-09 | 2022-01-20 | Yes | 18 | [14 empty] | KUNAKOV BRUCE & PATRICIA | 650-355-7210 , 255-8860 | pbk57@aol.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani/ #503 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 503 | 38.6339 | -120.5323 | Caldor | DR-4619 | Residential | Yes | 2021-11-08 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1002 | 041-695-001 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 10122 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3830.99 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-12-04 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No |  |  |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-07 |  | 12.07 SPOKE WITH TERRY HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLED PROPANE TANK. JC "03/15/22 NO ANS LEFT VM & TEXT. JC 03/15/22 SPOKE WITH TERRY HE SAID OK FOR TREE REMOVAL JC" |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 5 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-03 | 2022-01-07 | Yes | 30 | [14 empty] | Terry Collins | 530-919-7212 | t-collins2@sbcglobal.net | Other | Debris Crew Leader/Crew# Carondlet Dunbar/ #509 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 509 | 38.6323 | -120.5357 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1003 | 041-695-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10130 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3816.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | TRUE | Yes | Leave |  | 2021-12-01 | Yes | 2021-12-01 | 2021-12-07 | NEGATIVE |  |  |  | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-03 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-07 | 2021-12-09 | 2022-02-16 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM & SENT EMAIL. JC 12.09 NO ANS LEFT VM GAVE TO RICHARD. JC 12.09 HO GAVE CONSENT VIA TEXT. JC 01.21.22: TFL left multiple voicemails for parcel owner over tast three days RCV 02/14/22 HO TEXT BACK. VENDOR HANDLING PROPANE TANK. JC 02/16/22 NO ANS LEFT VM & TEXT ABT TREE REMOVAL. JC 02/16 SPOKE WITH DEBBIE SHE SAID OK TO TREE REMOVAL. JC |  |  |  | 2022-01-21 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-29 | 2022-02-04 | 5 | Approved | [12 empty] | 2022-02-08 | 2022-01-07 | Yes | 7 | 2022-02-19 |  | 2022-02-19 | 2022-02-19 |  | 2022-03-01 | 2022-03-02 | 7 | 2022-03-09 |  | 2022-03-03 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Deborah Goedeck | 530-417-1559 | debigoedeck@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Birdie Bell / #504 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 504 | 38.6325 | -120.5352 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 10
1004 | 041-695-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10144 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3799.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-29 | 2021-10-29 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 1 | TRUE | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-10-30 | No Bio Monitoring Needed for Debris or Trees | 2021-11-06 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-19 | No Activity/Nest Building Removed |  |  | Complete | [6 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-09 | 2021-11-06 | 2021-11-17 | 2022-01-20 | 11.12 TRIED CALL NUMBER ON FILE BUT THE PHONE IS NOT WORKING. GAVE TO RICHARD. JC 11.17 SPOKE WITH SOPHIA SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. RCV 01/20/22 SPOKE WITH SOPHIA SHE SAID OK. JC |  |  |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 |  |  | 2 | 2021-11-20 | 2021-12-01 | 6 | Approved | [12 empty] | 2021-12-03 | 2021-11-05 | Yes | 4 | 2022-02-19 |  | 2022-02-21 | 2022-02-21 |  | 2022-02-28 | 2022-03-02 | 4 | 2022-03-09 |  | 2022-03-03 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Sophia Zalot | 650-695-8815 | sophiazalot@icloud.com, szalot@mvwsd.org | Vehicle on site Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/17 to 11/20 Crew 505 | 38.6329 | -120.5343 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
1005 | 041-695-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Planning Hold | 10168 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3791.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-30 | 2021-10-30 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Yes | Leave |  | 2021-10-29 | Yes | 2021-10-30 | 2021-11-03 | NEGATIVE |  |  |  | 2021-11-08 | No Bio Monitoring Needed for Debris or Trees | 2021-11-05 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-09 | 2021-11-08 | 2021-11-13 | 2022-01-15 | 11.9 NO PHONE NUMBER ON FILE. GAVE TO RICHARD. JC 11.12 NO ANS LEFT VM.JC 11.12 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 01/14/22 NO ANS LEFT VM & TEXT. JC 01/15/22 SPOKE WITH GINA SHE SAID OK. JC |  |  |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 |  |  | 4 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-11-03 | Yes | 1 | [14 empty] | Robert W & Gina M Greene | (530) 414-0629 | Mtngal4us@yahoo.com | Septic | Debris Crew Leader/Crew# Matthew Dorenzo/#505 Debris Crew WO# Refer to IAP 11/10 To 11/13 Crew 505 | 38.6332 | -120.5334 | Caldor | DR-4619 | Residential | Yes | 2021-10-27 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1006 | 041-696-002 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 10196 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3806.82 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-30 | 2021-11-30 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 |  |  | 2 | TRUE | Yes | Take | 2022-02-16 | 2021-12-06 | Yes | 2021-12-06 | 2021-12-10 | NEGATIVE |  |  |  | 2021-11-17 | No Bio Monitoring Needed for Debris or Trees | 2021-12-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-10 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-12-10 | 2022-01-21 | 2022-02-26 | 12.20 NO ANS VOICEMAIL FULL SENT TEXT. JC 12.20 SPOKE WITH NOAH HE SAID OK BUT PLEASE CALL IN ADVANCE HE WANTS TO BE ON SITE DURING DEBRIS REMOVAL. ONWS PROPANE, PLEASE REMOVE. JC 01/21/22 NOAH WANTS TO BE ONSITE DURING REMOVAL. PLEASE CALL IN ADVANCE. JC 02/26/22 SPOKE WITH NOAH HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-22 |  | 2022-01-22 | 2022-01-22 |  |  | 5 | 2022-01-28 | 2022-02-07 | 7 | Approved | [12 empty] | 2022-02-08 | 2022-01-07 | Yes | 1 | 2022-03-11 |  | 2022-03-11 | 2022-03-11 |  | 2022-03-18 | 2022-03-19 | 1 | 2022-03-24 |  | 2022-03-22 | 2022-03-25 | 2022-03-25 | 2022-03-25 | STARKS NOAH | 530-903-6430 | nstarks2438@icloud.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Zara Armani / #503 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 503 | 38.6334 | -120.5322 | Caldor | DR-4619 | Residential | Yes | 2021-11-05 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 7
1007 | 041-511-004 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 7174 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4050.52 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-14 | 2021-10-14 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 3 |  |  | 1 | TRUE | No |  |  | 2021-10-13 | Yes | 2021-10-14 | 2021-10-19 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-20 | 2021-11-06 | 2022-01-20 | 11.6 SPOKE WITH KRYSTAL, SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANK. JC 01/20/22 SPOKE WITH KRYSTAL SHE SAID OK. JC |  |  |  | 2021-11-11 |  | 2021-11-11 | 2021-11-11 |  |  | 2 | 2021-11-12 | 2021-11-22 | 7 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Approved | [6 empty] | 2021-12-07 | 2021-11-03 | Yes | 65 | 2022-01-31 |  | 2022-02-02 | 2022-02-02 |  | 2022-02-08 | 2022-02-11 | 65 | 2022-02-18 |  | 2022-02-14 | 2022-02-19 | 2022-02-19 | 2022-02-19 | Krystal Olson | 916-813-3551 | olson5783@gmail.com |  | Debris Crew Leader/Crew# Max Patterson/#506 Debris Crew WO# Refer to IAP 11/10 to 11/13 Crew 506 | 38.6424 | -120.5199 | Caldor | DR-4619 | Residential | No | 2021-10-11 | ROE Verified | Central Division | 2022-04-06T18:52:41Z | FALSE | 6
1008 | 041-511-007 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 7200 | Capps Crossing Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4053.89 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-23 | 2021-11-23 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 2 | 4 | 3 | 10 |  |  |  |  | Yes | Leave |  | 2021-11-29 | Yes | 2021-11-29 | 2021-12-02 | POSITIVE | 2021-12-04 | 2021-12-04 | 2 | 2021-11-23 | No Bio Monitoring Needed for Debris or Trees | 2021-12-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-19 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-01 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-16 | 2021-12-04 | 2021-12-08 | 2022-03-03 | 12.07 NO ANS LEFT VM & TEXT. JC 12.08 NO ANS LEFT VM SENT EMAIL. JC 12.08 SPOKE THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK.JC 03/03/22 NO ANS LEFT VM & TEXT JC 03/03/22 THOMAS C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2021-12-11 |  | 2022-01-18 | 2022-01-18 |  |  | 7 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-21 | Yes | 75 | 2022-03-19 |  | 2022-03-21 | 2022-03-21 |  | 2022-03-25 | 2022-03-26 | 75 |  |  | 2022-03-28 |  |  |  | Thomas Horton | 530-240-5417 | tomhorton2017@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz / #510 Debris Crew WO# Refer to IAP 01/12 to 01/15 Crew 510 | 38.6426 | -120.519 | Caldor | DR-4619 | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
1009 | 041-513-001 | Full Program ROE (debris + trees) | Ready for Erosion Control | Passed Tree Completion Check | Next Step: N/A | Erosion Control | Ready for Erosion Control | 4909 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4026.04 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-02 | 2022-03-02 | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-02 | Yes | 2022-03-02 | 2022-03-07 | NEGATIVE |  |  |  | 2022-03-03 | No Bio Monitoring Needed for Debris or Trees | 2022-03-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-03-10 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-29 | 2022-03-07 | 2022-03-08 |  | Abatement Site - No contact Needed | 0 | Melissa Perry |  | 2022-03-09 |  | 2022-03-09 | 2022-03-09 |  |  | 2 | 2022-03-10 | 2022-03-18 | 7 | Approved | [12 empty] | 2022-03-21 | 2022-03-25 | Yes | 62 | 2022-03-25 |  | 2022-03-26 | 2022-03-26 |  | 2022-03-28 | 2022-03-29 | 62 |  |  | 2022-03-31 | [7 empty] | Debris Crew Leader/Crew# Stephanie Fairlee / #519 Debris Crew WO# Refer to IAP 03/09 to 03/12 Crew 519 | 38.6422 | -120.5212 | Caldor | DR-4619 | Residential |  | 2022-02-28 | Abatement | Central Division | 2022-04-01T22:00:05Z | FALSE | 2
1010 | 041-513-002 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 4921 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4016.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-18 | 2021-11-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 5 |  |  | 6 |  | Yes | Leave |  | 2021-11-17 | Yes | 2021-11-18 | 2021-11-22 | NEGATIVE |  |  |  | 2021-11-19 | No Bio Monitoring Needed for Debris or Trees | 2021-12-01 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | Yes |  |  |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2021-12-01 | 2021-12-02 |  | 12.02 Contacted homeowner, okayed debris removal RCV 02/14/22 NO ANS LEFT VM & TEXT ABT PROPANE TANK. JC |  |  |  | 2021-12-07 |  | 2021-12-07 | 2021-12-07 |  |  | 4 | 2021-12-11 | 2021-12-17 | 5 | Approved | [12 empty] | 2021-12-20 | 2021-12-22 | Yes | 21 | [14 empty] | Breanna Hartsock, Adam Iverson | 559-443-5374 | breannaleeiverson@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Antonio Ruiz Jr/#510 Debris Crew WO# Refer to IAP 12/04 to 12/08 Crew 510 | 38.6418 | -120.5214 | Caldor | DR-4619 | Residential | Yes | 2021-11-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1011 | 041-513-003 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4929 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4010.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2021-12-08 | No Bio Monitoring Needed for Debris or Trees | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [12 empty] | 2022-02-04 | 02/01/22 NO ANS LEFT VM & TEXT. JC 02/02/22 NO ANS LEFT VM NO EMAIL ON FILE. JC 02/03/22 NO ANS LEFT VM. JC 02/04/22 SPOKE WITH HO. THEY SAID OK BUT PLEASE CALL IN ADVANCE. HO said no propane tank. JC | [27 empty] | 2021-12-22 | Yes | 34 | 2022-02-09 |  | 2022-02-10 | 2022-02-10 |  | 2022-02-14 | 2022-02-15 | 34 |  |  | 2022-02-16 |  | 2022-02-16 | 2022-02-17 | LUNETTA KIMBERLY | 916-812-3860 | None |  |  | 38.6415 | -120.5215 | Caldor | DR-4619 | Residential | No | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE | 4
1012 | 041-513-004 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4941 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4007.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-13 | 2021-11-13 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No |  |  | 2021-11-12 | Yes | 2021-11-12 | 2021-11-17 | NEGATIVE |  |  |  | 2021-11-18 | No Bio Monitoring Needed for Debris or Trees | 2021-11-16 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-02-16 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-23 | 2021-11-18 | 2021-11-19 | 2022-03-01 | 11.19 SPOKE THOMAS HE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS.JC 03/01/22 SPOKE WITH RYAN HE SAID OK. JC |  |  |  | 2021-11-22 |  | 2021-11-22 | 2021-11-22 |  |  | 4 | 2021-11-29 | 2021-12-07 | 7 | Approved | [12 empty] | 2021-12-08 | 2022-03-19 | Yes | 50 | [14 empty] | THOMAS RYAN & KRISTA | 408-821-2154 | rmthomas2000@gmail.com | Septic | Debris Crew Leader/Crew# Adam Mattson /#507 Debris Crew WO# Refer to IAP 11/24 to 12/01 Crew 507 | 38.6413 | -120.5215 | Caldor | DR-4619 | Residential | Yes | 2021-11-04 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1013 | 041-513-007 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4981 | Edgewood Circle |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3994.75 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-16 | 2021-10-16 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  |  | TRUE | Yes | Leave |  | 2021-10-15 | Yes | 2021-10-16 | 2021-10-22 | NEGATIVE |  |  |  | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | N/A | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 |  | 2021-11-03 | 2021-12-04 | 11.3 SPOKE WITH KATIE. SHE SAID OK. PLEASE CALL IN ADVANCE. SHE WILL LIKE TO HAVE CREW LEARDER EXAMINE TANK. JC 12.4 SPOKE WITH KATIE SHE SAID OK. JC 01/14/22 HO SAID OK. JC 01/25/22 SPOKE WITH KATIE SHE SAID REMOVE PROPANE TANK IF DAMAGED﻿. JC 01/26/22 HO TEXT BACK. THEY CHANGED THEIR MIND ABT PROPANE TANK. PLEASE LEAVE PROPANE TANK. JC |  |  |  | 2021-11-05 |  | 2021-11-06 | 2021-11-06 |  |  | 3 | 2021-11-10 | 2021-11-18 | 7 | Approved | [12 empty] | 2021-11-19 | 2021-11-12 | Yes | 18 | 2022-01-11 |  | 2022-01-11 | 2022-01-11 |  | 2022-01-12 | 2022-01-17 | 18 | 2022-01-31 |  | 2022-01-18 | 2022-02-18 | 2022-02-18 | 2022-02-18 | Glen and Katie Thomas | 916-718-9069 | glenkatie12@gmail.com |  | Debris Crew Leader/Crew# Cynthia Sanderson/#503 Debris Crew WO# Refer to IAP 11/03 to 11/06 Crew 503 | 38.6408 | -120.5205 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 1
1014 | 041-513-009 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 4936 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4012.51 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-22 | 2022-01-22 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  |  | 1 |  | Yes | Leave |  | 2022-01-21 | Yes | 2022-01-21 | 2022-01-25 | NEGATIVE |  |  |  | 2021-12-09 | No Bio Monitoring Needed for Debris or Trees | 2022-01-28 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Survey Needed | Yes | 2022-03-07 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-02-06 | 2022-01-28 | 2022-01-29 | 2022-04-05 | 01/29/22 SPOKE WITH TRAVIS HE SAID OK. VENDOR HANDLING PROPANE TANK. JC 4.5 SPOKE TO TRAVIS AND HE SAID OK PF |  |  |  | 2022-02-01 |  | 2022-02-02 | 2022-02-02 |  |  | 4 | 2022-02-07 | 2022-02-15 | 7 | Re-scrape |  |  |  | 2022-02-19 | 2022-02-28 | Approved | [6 empty] | 2022-03-02 | 2022-02-07 | Yes | 12 | [14 empty] | Travis Taylor | 530-409-4689 | T.taylor333@yahoo.com |  | Debris Crew Leader/Crew# Eric Rocha / # 503 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 503 | 38.6412 | -120.5207 | Caldor | DR-4619 | Residential | Yes | 2021-12-03 | ROE Verified | Central Division | 2022-04-06T01:12:54Z | FALSE
1015 | 041-513-010 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Pending PO Notification | 4930 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4017.19 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-28 | 2022-01-28 | FALSE | No |  |  | No |  | No | Yes | No | Yes | No | No | FALSE | TRUE | 2 | 2 | 0 | 1 | 0 | 2 | 0 | 7 |  |  | 4 |  | Yes | Leave |  | 2022-01-22 | Yes | 2022-01-22 | 2022-01-27 | NEGATIVE |  |  |  | 2022-01-28 | No Bio Monitoring Needed for Debris or Trees | 2022-02-09 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-02 | No Activity/Nest Building Removed |  |  |  | Yes | 2022-03-31 | No |  | TRUE |  | No | None | FALSE | [8 empty] | TRUE | 2022-03-02 | 2022-02-09 | 2022-02-10 |  | 02/10/22 SPOKE WITH KIMBERLY SHE SAID OK. BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. PLEASE DO NOT REMOVE THE RETAINING WALL OR WINDMILL. JC 4.5.22 NO ANS. LEFT MESS AND SENT A TEXT PF 4.6 NO ANS. LEFT MESS AND SENT TEXT. NO EMAIL ON FILE. PF |  |  |  | 2022-02-14 |  | 2022-02-15 | 2022-02-15 |  |  | 2 | 2022-02-16 | 2022-02-24 | 7 | Re-scrape |  |  |  | 2022-03-02 | 2022-03-10 | Approved | [6 empty] | 2022-03-11 | 2022-01-31 | Yes | 25 | [14 empty] | Kimberly Lunetta | 916-812-3860 | NA | Keep Items Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 507 | 38.6415 | -120.5209 | Caldor | DR-4619 | Residential | Yes | 2022-01-19 | ROE Verified | Central Division | 2022-04-06T15:04:07Z | FALSE
1016 | 041-513-011 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | FSO Returned to County | FSO Returned to County | 4922 | Deerwood Drive |  | Grizzly Flats | El Dorado |  | Residential |  |  |  |  | 2: Public infrastructure OR Snow risk/high elevation | 4026.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | Yes | TRUE | No | No | No | No | No | No | FALSE | TRUE | 4 | 1 | 2 | 0 | 0 | 3 | 0 | 10 |  |  |  | TRUE | No |  |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-23 | 2021-10-23 | 7 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-10-20 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [5 empty] | No | None | FALSE | [6 empty] | ROW Exemption | ROW Exemption | TRUE | 2022-02-04 | 2021-10-23 | 2021-11-04 | 2022-01-20 | 10.28 NO ANS LEFT MESS PF 10.29 NO ANS. LEFT MESS PF 11.1 NO ANS LEFT MESS PF SENT TO RICHARD FOR IMT 11.04 Homeowner Approved, requires call before mobilization (no propane tank) RCV 01/20/22 NO ANS LEFT VM & TEXT. JC 01/20/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2021-11-08 |  | 2021-11-08 | 2021-11-08 |  |  | 4 | 2021-11-11 | 2021-11-18 | 6 | Re-scrape |  |  |  | 2021-11-24 | 2021-12-06 | Approved | [6 empty] | 2021-12-07 | 2022-02-08 | Yes | 35 | 2022-02-08 |  | 2022-02-09 | 2022-02-09 |  | 2022-02-15 | 2022-02-16 | 35 | 2022-03-09 |  | 2022-02-18 | 2022-03-17 | 2022-03-17 | 2022-03-17 | RICHARD ANDERSON & CATHERINE HUFFMAN | 530-409-3371 | chuffman1215@yahoo.com |  | "Debris Crew Leader/Crew# Max Patterson/506 Debris Crew WO# Refer to IAP 11/06 to 11/10 Crew 506" | 38.6419 | -120.5208 | Caldor | DR-4619 | Residential | Yes | 2021-10-12 | ROE Verified | Central Division | 2022-04-07T20:05:49Z | FALSE | 6
1017 | 041-950-006 | Full Program ROE (debris + trees) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Ready for Tree Ops (Full Program) | Tree Assessment Complete | 041-950-006 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3703.63 |  |  |  |  | FALSE |  |  | N/A |  | TRUE |  | TRUE | Locked gate | Yes |  | TRUE | 2021-12-11 | 2021-12-11 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 4 |  |  | 2 |  | Yes | Take |  | 2022-01-19 | Yes | 2022-01-19 | 2022-01-24 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2022-02-03 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | On Hold | Yes | 2022-04-01 | No |  | TRUE |  |  |  | TRUE | [10 empty] | 2022-02-03 | 2022-02-04 |  | 02/04/22 SPOKE WITH SAM HE SAID OK BUT DO NOT REMOVE THE ITEMS HE MARKED. PLEASE REMOVE PROPANE TANK. CALL IN ADVANCE. JC |  |  |  | 2022-02-10 |  | 2022-02-12 | 2022-02-12 |  |  | 4 | 2022-02-17 | 2022-02-25 | 7 | Approved | [12 empty] | 2022-03-01 | 2022-04-07 | Yes | 240 | [14 empty] | SAM DRUMGOOLE | 530-663-6108 | drumgoolesam@gmail.com |  | Debris Crew Leader/Crew# Carondlet Dunbar/ #505 Debris Crew WO# Refer to IAP 02/12 to 02/16 Crew 505 | 38.6463 | -120.5362 | Caldor | DR-4619 | Residential | No | 2021-09-30 | ROE Verified | Central Division | 2022-04-08T06:07:48Z | FALSE
1018 | 041-950-007 | Full Program ROE (debris + trees) | Ready for Tree Operations | Ready for Tree Felling | Next Step: N/A | Ready for Tree Ops (Full Program) | Grizzly Flats Ready | 5820 | Eagle Hill Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 3706.18 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-10-15 | 2021-10-15 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 7 | 0 | 3 | 0 | 0 | 1 | 2 | 13 |  |  | 7 |  | Yes | Leave |  | 2021-10-09 | Yes | 2021-10-11 | 2021-10-14 | POSITIVE | 2021-10-22 | 2021-10-22 | 7 | 2021-10-20 | No Bio Monitoring Needed for Debris or Trees | 2021-11-03 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | N/A | No |  | No |  | TRUE |  | Class III | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-04 | 2021-11-03 | 2021-11-05 | 2022-03-26 | 11.5 NO ANS. LEFT VM. JC 11.5 SPOKE WITH OWNER. SAID OK. PLEASE CALL IN ADVANCE. OWNER CONTACED VENDOR ABT. TANK. JC 02/21/22 NO ANS LEFT VM &TEXT. JC 02/22/22 HO GAVE CONSENT VIA TEXT. JC 03/25/22 FOLLOW UP CALL. NO ANS LEFT & TEXT. JC 03/26/22 SPOKE WITH MARK HE SAID OK FOR TREE REMOVAL. NO NEED TO CALL IN ADVANCE. JC 04/08/22 Spoke with Mark abt vehicles on site. He said to remove all. JC |  |  |  | 2021-11-13 |  | 2021-11-16 | 2021-11-16 |  |  | 5 | 2021-11-22 | 2021-12-02 | 7 | Approved | [12 empty] | 2021-12-03 | 2021-12-18 | Yes | 130 | [14 empty] | MARK & KATHLEEN CHITTY | 530-391-5737 | grizzlyflat5820@yahoo.com |  | Debris Crew Leader/Crew# Tony Ruiz/#510 Debris Crew WO# Refer to IAP 11/13 to 11/17 Crew 510 | 38.646 | -120.5382 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-08T19:33:09Z | FALSE
1019 | 042-040-025 | Full Program ROE (debris + trees) | Debris Removal in Progress | Haz Trees Present | Next Step: N/A | ELD 514 | Tree Assessment Complete | 96146 | Mormon Emigrant Trail |  | Pollock Pines | El Dorado |  | Residential | [5 empty] | 4421.13 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 6565 |  |  | Yes |  | TRUE | 2022-03-08 | 2022-03-08 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 2 | 7 | 0 | 2 | 11 | 1 | 23 | [7 empty] | 2022-03-04 | Yes | 2022-03-10 | 2022-03-15 | POSITIVE | 2022-03-29 | 2022-03-29 | 11 | 2022-02-19 | Bio Monitoring Needed for Debris AND Trees | 2022-03-21 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [11 empty] | TRUE | [8 empty] | TRUE | 2022-03-19 | 2022-03-29 | 2022-04-04 |  | 01/28/22 NO ANS LEFT VM & TEXT ABT GATE CODE. JC ﻿01/31/22 HO C/B WITH GATE CODE 6565. HE SAID HE CANNOT MAKE IT TO PROPERTY TODAY BUT GAVE CONSENT FOR CREW TO ENTER PROPERTY. JC 01/31/22 HO TEXT TO INFORM THAT HE WANTS TO BE ON SITE DURING DEBRIS REMOVAL. JC 04/04/22 SPOKE WITH CHRISTOPHER. HE SAID DEBRIS REMOVAL CREW HAS BEEN WORKING ON HIS PROPERTY FOR ABOUT A WEEK NOW. JC |  |  |  | 2022-04-06 | [23 empty] | 2022-02-04 | Yes | 51 | [14 empty] | Christopher Kingsley | 916-813-9044 | chrisk60@gmail.com |  |  | 38.7182 | -120.4806 | Caldor | DR-4619 | Residential | No | 2021-12-10 | ROE Verified | Central Division | 2022-04-08T15:02:38Z | FALSE
1020 | 042-260-002 | Full Program ROE (debris + trees) | Pending Soil Sample Results | Haz Trees Present | Next Step: N/A | Pending Soil Sampling Results | Tree Assessment Complete | 3105 | Sciaroni Road |  | Somerset | El Dorado |  | Residential | [5 empty] | 4121.89 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-02 | 2022-02-02 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 3 |  |  | 1 |  | Yes | Leave |  | 2022-02-02 | Yes | 2022-02-02 | 2022-02-07 | NEGATIVE |  |  |  | 2021-11-15 | No Bio Monitoring Needed for Debris or Trees | 2022-02-11 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-22 | No Activity/Nest Building Removed |  |  |  | Yes | [7 empty] | TRUE | [8 empty] | TRUE | 2022-03-17 | 2022-02-11 | 2022-02-12 |  | 02/12/22 SPOKE WITH MICKEY SHE SAID OF. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-03-22 |  | 2022-03-26 | 2022-03-26 |  |  | 4 | 2022-03-31 | 2022-04-08 | 7 | [14 empty] | 2022-04-02 | Yes | 46 | [14 empty] | MICKEY & FORREST VERNON | 530-391-2730 | mickey.vernon@protonmail.com | Other Vehicles on site Septic | Debris Crew Leader/Crew# Carondlet Dunbar/#519 Debris Crew WO# Refer to IAP 03/26/22 to 03/30/22 Crew 519 | 38.6817 | -120.5339 | Caldor | DR-4619 | Residential | Yes | 2021-10-05 | ROE Verified | Central Division | 2022-04-09T00:09:43Z | FALSE
1021 | 041-891-012 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 7336 | South View Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4158.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-19 | No Bio Monitoring Needed for Debris or Trees | 2022-03-18 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Shengjun Lu | (916) 622-5827 | Shengjun_lu0002@yahoo.com |  |  | 38.6459 | -120.5134 | Caldor | DR-4619 | Residential | No | 2022-02-02 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1022 | 041-472-009 | Tree Only ROE (no qualifying debris) | ROE Received | Needs Assessment | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 6950 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3964.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-17 | Bio Monitoring Needed for Debris AND Trees | 2022-03-18 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-17 | No Activity/Nest Building Removed | [54 empty] | Ok to Assess | [15 empty] | Amy & Richard Nugent | 925-820-5491 | richnugent@yahoo.com |  |  | 38.646 | -120.523 | Caldor | DR-4619 | Residential | No | 2022-03-10 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1023 | 041-861-002 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 5461 | Blue Mountain Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3911.3 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-19 | No Bio Monitoring Needed for Debris or Trees | 2022-03-18 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Douglas N. MacDonald Jr | 916-952-5705 | dmacd@att.net |  |  | 38.6288 | -120.5498 | Caldor | DR-4619 | Residential | Yes | 2022-03-14 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1024 | 041-551-001 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 5036 | Merrywood Court |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3908.41 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-29 | Bio Monitoring Needed for Trees, not Debris | 2022-03-29 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-29 | No Activity/Nest Building Removed | [70 empty] | Mary Allard | 916-320-0180 | maryallard@aol.com |  |  | 38.6375 | -120.525 | Caldor | DR-4619 | Residential | No | 2022-03-16 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1025 | 041-893-013 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-893-013 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4034.23 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-04-05 | Bio Monitoring Needed for Trees, not Debris | 2022-04-04 | Arch Monitoring Needed for Trees, not Debris | [73 empty] | Paul Allen Affron | 615-457-4711 | paulaffron@hotmail.com |  |  | 38.6427 | -120.5125 | Caldor | DR-4619 | Residential | No | 2022-02-04 | ROE Verified | Central Division | 2022-04-05T22:20:49Z | FALSE
1026 | 041-893-011 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-893-011 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 4035.88 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-31 | No Bio Monitoring Needed for Debris or Trees | 2022-03-29 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Paul Allen Affron | 615-457-4711 | paulaffron@hotmail.com |  |  | 38.6429 | -120.514 | Caldor | DR-4619 | Residential | No | 2022-01-28 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1027 | 041-471-017 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 7023 | Tyler Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3987.85 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-29 | No Bio Monitoring Needed for Debris or Trees | 2022-03-29 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-29 | No Activity/Nest Building Removed | [70 empty] | David Robinson, Teresa Robinson | 530-957-9733 | drobmapboy@gmail.com |  |  | 38.6447 | -120.5222 | Caldor | DR-4619 | Residential | No | 2022-03-07 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1028 | 041-200-023 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-200-023 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3823.96 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Maxine Tyler | 916-517-3267 | Grossma95662@gmail.com |  |  | 38.6606 | -120.5328 | Caldor | DR-4619 | Residential | Yes | 2022-02-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1029 | 041-290-008 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-290-008 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3920.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-03-31 | No Bio Monitoring Needed for Debris or Trees | 2022-04-01 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Maxine Tyler | 916-517-3268 | Grossma95662@gmail.com |  |  | 38.6606 | -120.5328 | Caldor | DR-4619 | Residential | Yes | 2022-02-03 | ROE Verified | Central Division | 2022-04-02T05:33:33Z | FALSE
1030 | 041-290-024 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-290-024 | No Address |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3995.53 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Maxine Tyler | 916-517-3269 | Grossma95662@gmail.com |  |  | 38.6606 | -120.5328 | Caldor | DR-4619 | Residential | Yes | 2022-02-03 | ROE Verified | Central Division | 2022-04-01T22:00:05Z | FALSE
1031 | 041-423-016 | Full Program ROE (debris + trees) | Tree Operations in Progress | Tree Removal in Progress | Next Step: N/A | Ready for Tree Ops (Full Program) | ELDT 1b | 4759 | Creekside Drive |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3815.28 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-11-19 | 2021-11-19 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | [7 empty] | 2021-11-23 | Yes | 2021-11-23 | 2021-11-29 | NEGATIVE |  |  |  | 2021-11-29 | No Bio Monitoring Needed for Debris or Trees | 2021-12-08 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-04 | Nest Building Not Removed |  |  | On Hold | Yes | 2022-03-21 | No |  | TRUE |  | No | None | [9 empty] | TRUE | 2022-02-16 | 2021-12-06 | 2021-12-07 | 2022-03-30 | 12.07 SPOKE WITH CINDY SHE SAID OK. CINDY LIVES OUT OF STATE AND WANTS TO BE CALLED BEFORE GOING TO HER PROPERTY BECAUSE SHE WOULD LIKE TO DISCUSS WITH CREW LEADER ITEMS SHE DOES NOT WANT REMOVED. NO PROPANE TANK. JC "3.25 NO ANS. LEFT MESS AND SENT TEXT. PF 3.26 NO ANS .LEFT MESS AND SENT EMAIL PF"03.26 SOKE TO CINDY AND VERIFIED ITS ONLY 2 TREES OF HER 47 COMING DOWN. SHE GAVE HER VERBAL APPROVAL AND WILL SEND AN EMAIL AS WELL PF.3.26 Spoke to Cindy and she wants a state re to call her before she gives her consent to proceed. PF (Pending Rep)3.30 @9:32AM Cindy sent an email after speaking to Dave and gave permission to proceed with Hazard Tree Removal. PF |  |  |  | 2022-01-15 |  | 2022-01-17 | 2022-01-17 |  |  | 4 | 2022-01-20 | 2022-01-28 | 7 | Approved | [12 empty] | 2022-02-01 | 2021-12-03 | Yes | 55 | 2022-04-04 |  | 2022-04-05 | 2022-04-05 |  |  |  | 55 | [6 empty] | Cindy Bandy | 530-391-6323 | cbandy110@gmail.com | Septic Vehicles Onsite | Debris Crew Leader/Crew# Brandon Riley / #501 Debris Crew WO# Refer to IAP 01/22 To 01/26 Crew 501 | 38.6369 | -120.5372 | Caldor | DR-4619 | Residential | Yes | 2021-11-15 | ROE Verified | Central Division | 2022-04-06T18:27:47Z | FALSE
1032 | 041-620-029 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-620-029 | Humbird Road |  | grizzly Flats | El Dorado |  | Residential | [10 empty] | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Margarito Deharo | 2093045530 | MargaritoDeharo@gmail.com | Other |  |  |  | Caldor | DR-4619 |  | No | 2022-03-30 | ROE Verified | Central Division | 2022-04-07T22:32:52Z | FALSE
1033 | 041-620-031 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-620-031 | Humbird Road |  | grizzly Flats | El Dorado |  | Residential | [10 empty] | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Margarito Deharo | 2093045530 | MargaritoDeharo@gmail.com | Other |  |  |  | Caldor | DR-4619 |  | No | 2022-03-30 | ROE Verified | Central Division | 2022-04-07T22:32:52Z | FALSE
1034 | 095-011-016 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 6835 | Slug Gulch Road |  | someerset | El Dorado |  | Residential | [10 empty] | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Thomas Herrington | 5306200304 | ThomasHerrington@yahoo.com | Other |  |  |  | Caldor | DR-4619 |  | No | 2022-04-04 | ROE Verified | Central Division | 2022-04-07T22:32:52Z | FALSE
1035 | 041-620-030 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 041-620-030 | Humbird Road |  | grizzly Flats | El Dorado |  | Residential | [10 empty] | FALSE |  |  | N/A | [5 empty] | No | [17 empty] | FALSE | [7 empty] | 0 | [92 empty] | Margarito Deharo | 2093045530 | MargaritoDeharo@gmail.com | Other |  |  |  | Caldor | DR-4619 |  | No | 2022-03-30 | ROE Verified | Central Division | 2022-04-07T22:32:52Z | FALSE
1036 | 041-541-019 | Tree Only ROE (no qualifying debris) | ROE Received |  | Next Step: N/A | TREE ONLY ROEs | Tree Assessment Needed | 5101 | Parkside Drive |  | grizzly flats | El Dorado |  | Residential | [10 empty] | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [92 empty] | Santiago & Maria Contreras | 831-210-5521 | santiago.contreras63@yahoo.com |  |  |  |  | Caldor | DR-4619 |  | No | 2022-03-27 | ROE Verified | Central Division | 2022-04-09T00:30:57Z | FALSE
1037 | 041-260-021 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Hazard Trees Removed | Next Step: N/A | TREE ONLY ROEs | Pending TISW | 10471 | Grizzly Flat Road |  | Grizzly Flats | El Dorado |  | Residential | [5 empty] | 3770.09 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | DEAD |  |  | No |  | TRUE | 2021-11-10 |  | FALSE | [5 empty] | No | No | No | No | No | No |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2021-12-08 | Bio Monitoring Needed for Trees, not Debris | 2022-02-07 | Arch Monitoring Needed for Trees, not Debris |  | 2022-04-07 | No Activity/Nest Building Removed |  |  | N/A | Yes | 2022-03-15 | No |  | TRUE |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-09 |  |  | 2022-02-21 | 02/21/22 SPOKE PATRICK HE SAID OK FOR TREE REMOVAL. GATE CODE IS: DEAD. JC | [27 empty] | 2022-01-17 | Yes | 14 | 2022-04-07 |  | 2022-04-07 | 2022-04-07 |  | 2022-04-08 |  | 14 | [6 empty] | Patrick or Donna Hamer | 925-360-1936 | homesculptor@yahoo.com | Well |  | 38.6342 | -120.5231 | Caldor | DR-4619 | Residential | No | 2021-10-27 | ROE Verified | Central Division | 2022-04-09T00:27:00Z | FALSE | 1
0 | 168-020-030 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5850 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 964.21 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-17 | 2021-12-17 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2 |  |  |  |  | 2021-12-16 | Yes | 2021-12-16 | 2021-12-20 | NEGATIVE |  |  |  | 2021-12-18 | Bio Monitoring Needed for Debris AND Trees | 2021-12-18 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-24 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-20 | 2022-01-11 | 2022-02-22 | 01/11/22 NO ANS LEFT VM AND TEXT. JC 01/11/22 HO GAVE CONSENT VIA TEXT. NO PROPANE TANK. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22﻿ NO ANS LEFT VM & EMAIL. JC 02/22/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-17 |  | 2022-01-18 | 2022-01-18 |  |  | 5 | 2022-01-24 | 2022-02-01 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-13 | Yes | 9 | 2022-02-25 |  | 2022-02-25 | 2022-02-25 |  | 2022-03-01 | 2022-03-01 | 9 | 2022-03-02 |  | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-03 | Scott Freeman, Sandra Freeman | 707-972-3087 | sfreeman@mlhrs.com | Keep Items Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adams /#601 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 601 | 39.2293 | -123.1877 | Hopkins Fire |  | Residential | Yes | 2021-12-06 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
1 | 168-020-040 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5870 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 965.55 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-31 | 2021-12-31 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | Yes | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 3 |  |  | 2 |  |  | Leave |  | 2021-12-31 | Yes | 2021-12-31 | 2022-01-06 | NEGATIVE |  |  |  | 2021-12-31 | Bio Monitoring Needed for Debris AND Trees | 2021-12-31 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-24 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-06 | 2022-01-11 | 2022-02-22 | 01/11/22 SPOKE WITH JOSEPH HE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE ALL PROPANE AND WATER TANKS. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 SPOKE WITH JOSEPH. HE SAID OF FOR TREE REMOVAL. JC |  |  |  | 2022-01-18 |  | 2022-01-19 | 2022-01-19 |  |  | 6 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-13 | Yes | 7 | 2022-02-25 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-01 | 2022-03-01 | 7 | 2022-03-02 |  | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-02 | Joseph Allsup | 707-758-3604 | Joe.Allsup@Yahoo.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adams / #601 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 601 | 39.2297 | -123.1877 | Hopkins Fire |  | Residential | Yes | 2021-12-21 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
2 | 168-020-150 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5895 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 964.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-16 | 2021-12-16 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | Yes | TRUE | TRUE | 1 | 0 | 0 | 0 | 1 | 2 | 3 | 7 |  |  | 1 |  |  | Leave |  | 2021-12-16 | Yes | 2021-12-16 | 2021-12-20 | POSITIVE | 2022-01-13 | 2022-01-13 | 18 | 2021-12-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-24 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-19 | No |  |  |  | No | None | [9 empty] | TRUE | 2022-02-23 | 2022-01-13 | 2022-01-17 | 2022-02-22 | 01/14/22 NO ANS LEFT VM & TEXT. JC 01/15/22 NO ANS VM FULL SENT EMAIL. JC 01/17/22 NO ANS GAVE TO RICHARD. JC 01/17/22 PETER CALLED BACK. HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/21 NO ANS LEFT VM & EMAIL. JC 02/22/22 SOKE WITH PETER HE SAID OK BUT PLEASE CALL IN ADVANCE. PETER WILL MOVE THE RV THIS SAT. JC |  |  |  | 2022-01-19 |  | 2022-01-22 | 2022-01-22 |  |  | 2 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-14 | Yes | 10 | 2022-02-24 |  | 2022-02-24 | 2022-02-24 |  | 2022-02-28 | 2022-02-28 | 10 | 2022-03-01 |  | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-03 | Peter D. Vindis | 415-246-2266 | pvindis@msn.com | Keep Items Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adams / #601 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 601 | 39.2308 | -123.1861 | Hopkins Fire |  | Residential | Yes | 2021-12-10 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
3 | 167-310-460 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 651 | Rubicon Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 785.49 |  |  |  |  | FALSE |  |  | N/A |  |  | Access code is #4321 |  |  | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-16 | Yes | 2021-12-16 | 2021-12-20 | NEGATIVE |  |  |  | 2021-12-18 | No Bio Monitoring Needed for Debris or Trees | 2021-12-17 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | N/A | No | [5 empty] | Class II | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2021-12-20 | 2022-01-11 | 2022-02-21 | 01/11/22 NO ANS LEFT VM AND TEXT. JC 01/11/22 HO GAVE CONSENT VIA TEXT. JC 02/21/22 NO AND LEFT VM & TEXT. JC 02/21/22 JEFFERY C/B HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-21 |  | 2022-01-24 | 2022-01-24 |  |  | 3 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-14 | Yes | 21 | 2022-02-22 |  | 2022-02-22 | 2022-02-22 |  | 2022-02-23 | 2022-02-23 | 21 | 2022-03-01 |  | 2022-02-25 | 2022-03-01 | 2022-03-01 | 2022-03-02 | Jeffery Adkins, Dana Adkins | 916-612-6528 | jadkins95630@gmail.com | Access Issues Safety Concerns Septic | Debris Crew Leader/Crew# Ashanti Broussard / #602 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 602 | 39.2322 | -123.1946 | Hopkins Fire |  | Residential | Yes | 2021-11-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
4 | 167-290-110 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6200 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 685.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-16 | 2021-12-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 8 | 0 | 0 | 0 | 0 | 1 | 0 | 9 | [5 empty] | Leave |  | 2021-12-16 | Yes | 2021-12-16 | 2021-12-21 | POSITIVE | 2022-01-12 | 2022-01-12 | 16 | 2021-12-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | Active Nest |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-13 | 2022-01-14 | 2022-03-24 | 01/14/22 SPOKE FRANCIS SHE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR HANDLING PROPANE. JC 01/31/22 SPOKE WITH FRANCIS SHE PRE APPROVED HAZARD TREE REMOVAL. JC 3.23 No ans left mess on both lines. JC 03/24/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-17 |  | 2022-01-19 | 2022-01-19 |  |  | 12 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Approved | [6 empty] | 2022-03-03 | 2022-01-13 | Yes | 2 | 2022-03-24 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 | 2 | 2022-04-04 |  | 2022-03-29 | 2022-04-05 | 2022-04-05 | 2022-04-05 | Francis Byers | 707-485-7434, 714-801-3884 | byers0704@gmail.com | Keep Items Vehicles Onsite | Debris Crew Leader/Crew# Ashanti Broussard/#602 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 602 | 39.2333 | -123.1998 | Hopkins Fire |  | Residential | Yes | 2021-11-15 | ROE Verified | Central Division | 2022-04-05T16:58:36Z | FALSE |  | Yes
5 | 167-310-030 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6040 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 684.02 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) |  |  |  |  | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No |  |  | Yes | TRUE | No | No | No | No | No | No | FALSE | TRUE | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 5 |  |  | 2 |  |  |  |  | 2021-12-15 | Yes | 2021-12-15 | 2021-12-27 | NEGATIVE |  |  |  | 2021-12-16 | No Bio Monitoring Needed for Debris or Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-25 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE |  | 2022-02-09 | Slope stabilzation and BMPs needed | [5 empty] | TRUE | 2022-02-23 | 2021-12-27 | 2022-01-11 | 2022-02-21 | 01/11/22 NO ANS LEFT VM AND TEXT. JC 01/11/22 SPOKE WITH HO SHE SAID OK BUT PLEASE CALL 24 HOURS PRIOR TO COMING TO PROPERTY BECAUSE OWNER WANTS TO BE THERE DURING THE DEBRIS REMOVAL PROCESS. NO PROPANE TANK. JC 02/21/22 SPOKE WIT JOLENE SHE SIAD OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-20 |  | 2022-01-21 | 2022-01-21 | TRUE | Steep slope disturbed, needs stabilization | 3 | 2022-01-25 | 2022-02-02 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-12 | Yes | 1 | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-02 | 2022-03-02 | 1 | 2022-03-10 |  | 2022-03-04 | 2022-03-10 | 2022-03-10 | 2022-03-11 | Jolene Shanahan, Mike Shanahan | 707-972-3317, 707-376-5497 | jojo42088@gmail.com |  | Debris Crew Leader/Crew# Ashanti Brousard / #602 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 602 | 39.2315 | -123.2005 | Hopkins Fire |  | Residential | Yes | 2021-12-06 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
6 | 167-310-230 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6060 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 683.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-11 | 2022-01-11 | 15 | 2021-12-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-12 | 2022-01-14 | 2022-02-22 | 01/14/22 NO ANS LEFT VM & TEXT. JC 01/14/22 JUDY GAVE CONSENT VIA TEXT. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 NO ANS LEFT VM & EMAIL. JC 02/22/22 SPOKE WITH JUDY SHE SAID OKM BUT PLEASE CALL IN ADVANCE. JC |  |  |  | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  |  | 3 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-13 | Yes | 4 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-03 | 4 | 2022-03-10 |  | 2022-03-04 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Judy Gatewood, Steve Csiklas | 510-849-1218, 510-283-8220 | hudygate@yahoo.com |  | Debris Crew Leader/Crew# Ashanti Broussard/ #602 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 602 | 39.2317 | -123.2005 | Hopkins Fire |  | Residential | Yes | 2021-12-01 | ROE Verified | Central Division | 2022-04-01T22:06:25Z | FALSE |  | No
7 | 167-310-240 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6195 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 682.76 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-24 | 2022-01-24 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 |  |  | 6 |  |  | Take | 2022-03-18 | 2022-01-24 | Yes | 2022-01-24 | 2022-01-27 | POSITIVE | 2022-02-01 | 2022-02-01 | 4 | 2022-01-25 | Bio Monitoring Needed for Debris AND Trees | 2022-01-24 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-28 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-19 | No |  |  |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-17 | 2022-02-01 | 2022-01-28 | 2022-02-21 | 01/28/22 SPOKE WITH MARIA SHE SAID OK BUT PLEASE CALL IN ADVANCE. PLEASE REMOVE PROPANE TANK. JC 02/21/22 SPOKE WITH MARIA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 2 | 2022-02-04 | 2022-02-14 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Approved | [6 empty] | 2022-03-03 | 2022-02-08 | Yes | 2 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-03 | 2 | 2022-04-04 |  | 2022-03-04 | 2022-04-05 | 2022-04-05 | 2022-04-05 | Maria Ortega, Cruz Ortega | 707-489-6279 | NA | Vehicles Onsite | Debris Crew Leader/Crew# Glenn Adams/ #601 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 601 | 39.233 | -123.1999 | Hopkins Fire |  | Residential | Yes | 2022-01-19 | ROE Verified | Central Division | 2022-04-05T17:03:21Z | FALSE |  | Yes
8 | 168-020-140 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Ready for FSO | No Eligible Trees | 5797 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 920.87 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-16 | 2021-12-16 | FALSE | Yes |  | 2022-01-14 | No | TRUE | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 1 |  |  |  |  | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-13 | 2022-01-13 | 17 | 2021-12-16 | No Bio Monitoring Needed for Debris or Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed | [20 empty] | TRUE | 2022-04-19 | 2022-01-14 | 2022-01-18 |  | 01/18/22 NO ANS LEFT VM & TEXT. JC 01/18/22 HO GAVE CONSENT VIA TEXT. JC |  |  |  | 2022-01-28 |  | 2022-01-29 | 2022-01-29 |  |  | 1 | 2022-01-31 | 2022-02-08 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Re-scrape | 2022-03-25 | 2022-04-04 | Approved |  |  |  | 2022-04-06 | 2022-01-13 | No | 0 | [8 empty] | 2022-04-04 | [5 empty] | Francis Shaw | 707-508-8770, 707-234-9119 | leeandrarachel@yahoo.com | Access Issues Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adams / #601 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 601 | 39.2281 | -123.1853 | Hopkins Fire |  | Residential | Yes | 2021-11-17 | ROE Verified | Central Division | 2022-04-08T16:50:11Z | FALSE |  | No
9 | 168-020-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5790 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 968.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-01-10 | Yes | 2022-01-11 | 2022-01-17 | NEGATIVE |  |  |  | 2022-01-08 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-23 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-19 | No |  |  |  | No | None | [9 empty] | TRUE | 2022-02-08 | 2022-01-17 | 2022-01-18 | 2022-02-21 | 01/18/22 SPOKE WITH ROBERT HE SAID OK BUT PLEASE CALL ADVANCE. NO PROPANE TANK. JC 02/21/22 SPOKE WITH MRS HUNT SHE ASKED THAT I CALL BACK IN AN HOUR TO SPEAK WITH MR HUNT. JC 02/21/22 SPOKE WITH ROBERT HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-27 |  | 2022-01-28 | 2022-01-28 |  |  | 3 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-01-14 | Yes | 20 | 2022-02-24 |  | 2022-02-25 | 2022-02-25 |  | 2022-03-01 | 2022-03-01 | 20 | 2022-03-02 |  | 2022-03-01 | 2022-03-04 | 2022-03-04 | 2022-03-04 | Robert Hunt, Feithlinn Hunt | 707-696-9896, 707-292-2927 | hunt4faye@gmail.com |  | Debris Crew Leader/Crew# Glenn Adam / #601 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 601 | 39.2284 | -123.188 | Hopkins Fire |  | Residential | Yes | 2022-01-03 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
10 | 167-310-180 | Full Program ROE (debris + trees) | Ready for Final Sign-off | Passed Tree Completion Check | Next Step: N/A | Punch List | Hold | 6180 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 695 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2021-12-16 | 2021-12-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-12 | 2022-01-12 | 16 | 2021-12-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-19 | No |  |  |  | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-12 | 2022-01-14 | 2022-03-23 | 01/14/22 SPOKE WITH SHARON AND JOLENE THEY SAID OK BUT PLEASE CALL JOLENE IN ADVANCE. VENDOR HANDLING PROPANE TANK. JC 707-972-3317 (Jolene) 3.23 Spoke w/friend of Sharon, Jolene and said ok for tree removal. JC 03/26/22 Sharon c/b she said ok. JC 03/28/22 HO GAVE CONSENT AGAIN VIA TEXT. JC |  |  |  | 2022-01-19 |  | 2022-01-20 | 2022-01-20 |  |  | 4 | 2022-01-25 | 2022-02-02 | 7 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-03-15 | 2022-01-13 | Yes | 1 | 2022-03-24 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 | 1 | 2022-04-04 |  | 2022-03-29 |  |  |  | Sharon Green | 707-254-9680/ CALL 707 513-0187 ALSO JOLENE 707 972-3317 | lucindamosna@yahoo.com |  | Debris Crew Leader/Crew# Ashanti Broussard/ #602 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 602 | 39.2325 | -123.2 | Hopkins Fire |  | Residential | Yes | 2021-11-28 | ROE Verified | Central Division | 2022-04-05T17:23:33Z | FALSE |  | No
11 | 167-310-210 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6100 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 686.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-31 | 2021-12-31 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 4 |  |  | 5 |  |  | Leave |  | 2021-12-31 | Yes | 2021-12-31 | 2022-01-06 | POSITIVE | 2022-01-12 | 2022-01-12 | 5 | 2021-12-31 | Bio Monitoring Needed for Debris AND Trees | 2021-12-31 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-12 | 2022-01-14 | 2022-02-22 | 01/14/22 LEFT MESSAGE FOR ANTONIO. JC 01/14/22 SPOKE WITH ANTONIO HE SAID OK BUT PLEASE CALL IN ADVANCE. VENDOR WILL HANDLE PROPANE TANK. JC 02/21/22 LEFT MESSAGE FOR ANTONIO. WILL CALL BACK IN AM. JC 02/22/22 SPOKE WITH ANTONIO HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-17 |  | 2022-01-17 | 2022-01-17 |  |  | 5 | 2022-01-22 | 2022-01-28 | 5 | Re-scrape |  |  |  | 2022-02-08 | 2022-02-16 | Approved | [6 empty] | 2022-02-17 | 2022-02-28 | Yes | 4 | 2022-02-28 |  | 2022-02-28 | 2022-02-28 |  | 2022-03-03 | 2022-03-03 | 4 | 2022-03-10 |  | 2022-03-04 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Antonio Moreno Rocha | 707-468-8464 | t.michoacan@yahoo.com | Other Vehicles Onsite | Debris Crew Leader/Crew# Ashland Broussard/#602 Debris Crew WO# Refer to IAP 01/15 to 01/19 Crew 602 | 39.2321 | -123.2002 | Hopkins Fire |  | Residential | No | 2021-12-22 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
12 | 167-310-220 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 6080 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 682.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-16 | 2021-12-16 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-11 | 2022-01-11 | 15 | 2021-12-16 | Bio Monitoring Needed for Debris AND Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-26 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class I | Covered under suspension | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-12 | 2022-01-14 | 2022-02-22 | 01/14/22 SPOKE JUANA SHE SAID OK BUT PLEASE CALL IN ADVANCE. NO PROPANE TANKS. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/22/22 SPOKE WITH JUANA SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-19 |  | 2022-01-19 | 2022-01-19 |  |  | 3 | 2022-01-21 | 2022-01-31 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-13 | Yes | 2 | 2022-03-01 |  | 2022-03-01 | 2022-03-01 |  | 2022-03-03 | 2022-03-03 | 2 | 2022-03-10 |  | 2022-03-04 | 2022-03-10 | 2022-03-10 | 2022-03-10 | Juana Becerra | 707-972-1229 | jade36.jb@gmail.com |  | Debris Crew Leader/Crew# Ashanti Broussard / #602 Debris Crew WO# Refer to IAP 01/19 to 01/22 Crew 602 | 39.2319 | -123.2003 | Hopkins Fire |  | Residential | Yes | 2021-11-29 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
13 | 168-020-080 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5851 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 974.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-15 | 2021-12-15 | FALSE | No |  |  | Yes | TRUE | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | [5 empty] | Take | 2022-03-18 | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-12 | 2022-01-12 | 16 | 2021-12-16 | Bio Monitoring Needed for Trees, not Debris | 2021-12-17 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-23 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | Class III | None | TRUE | [8 empty] | TRUE | 2022-02-23 | 2022-01-12 | 2022-01-14 | 2022-02-21 | 01/14/22 SPOKE WITH KAREN SHE SAID OK BUT PLEASE CALL IN ADVANCE. IF PROPANE TANK IS DAMAGED, PLEASE REMOVE. JC 02/21/22 NO ANS LEFT VM & TEXT. JC ﻿02/21/22 KAREN C/B SHE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-01-22 |  | 2022-01-24 | 2022-01-24 |  |  | 3 | 2022-01-26 | 2022-02-03 | 7 | Approved | [12 empty] | 2022-02-04 | 2022-01-13 | Yes | 12 | 2022-02-23 |  | 2022-02-23 | 2022-02-23 |  | 2022-02-28 | 2022-02-28 | 12 | 2022-03-10 |  | 2022-03-05 | 2022-03-18 | 2022-03-18 | 2022-03-18 | Knoles Family Trust | 415-517-0321 | fidres@gmail.com | Other Septic Vehicles Onsite | Debris Crew Leader/Crew# Gleen Adams / #601 Debris Crew WO# Refer to IAP 01/22 to 01/26 Crew 601 | 39.2292 | -123.1865 | Hopkins Fire |  | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
14 | 168-020-100 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 5801 | Lake Ridge Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 979.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2021-12-16 | 2021-12-16 | FALSE | Yes |  | 2022-01-14 | Yes | TRUE | Yes | No | Yes | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 3 |  |  | 2 |  |  | Take | 2022-03-18 | 2021-12-15 | Yes | 2021-12-15 | 2021-12-21 | POSITIVE | 2022-01-13 | 2022-01-13 | 17 | 2021-12-16 | No Bio Monitoring Needed for Debris or Trees | 2021-12-16 | No Arch Monitoring Needed for Debris or Trees |  | 2022-02-23 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | [9 empty] | TRUE | 2022-02-23 | 2022-01-14 | 2022-01-14 | 2022-02-21 | 01/14/22 SPOKE WITH KAREN SHE SAID OK BUT PLEASE CALL IN ADVANCE. IF PROPANE TANK IS DAMAGED, PLEASE REMOVE. JC 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 ﻿KAREN CB SHE SAID OK. JC |  |  |  | 2022-01-24 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Approved | [12 empty] | 2022-02-10 | 2022-01-13 | Yes | 6 | 2022-02-24 |  | 2022-02-24 | 2022-02-24 |  | 2022-02-28 | 2022-02-28 | 6 | 2022-03-02 |  | 2022-03-01 | 2022-03-19 | 2022-03-19 | 2022-03-19 | Knoles Family Trust | 415-517-0321 | fidres@gmail.com | Other Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adam / #601 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 601 | 39.2286 | -123.1869 | Hopkins Fire |  | Residential | Yes | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
15 | 168-020-170 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 168-020-170 | No Address |  | Ukiah | Mendocino |  | Residential | [5 empty] | 914.02 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2021-12-15 | 2021-12-18 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2021-12-15 | No | [6 empty] | 2021-12-16 | Bio Monitoring Needed for Trees, not Debris | 2021-12-16 | Arch Monitoring Needed for Debris AND Trees |  | 2022-02-23 | No Activity/Nest Building Removed |  |  | N/A | No | [5 empty] | No | None | [9 empty] | TRUE | 2022-02-23 |  |  | 2022-02-21 | 02/21/22 NO ANS LEFT VM & TEXT. JC 02/21/22 KAREN CB SHE SAID OK FOR TREE REMOVAL. JC | [27 empty] | 2022-01-13 | Yes | 7 | 2022-02-23 |  | 2022-02-23 | 2022-02-23 |  | 2022-03-03 | 2022-03-03 | 7 |  |  | 2022-03-04 |  | 2022-03-04 | 2022-03-04 | Knoles Family Trust | 415-517-0321 | fidres@gmail.com |  |  | 39.2299 | -123.1866 | Hopkins Fire |  | Residential | No | 2021-11-22 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE
16 | 167-300-140 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 951 | Rubicon Court |  | Ukiah | Mendocino |  | Residential | [5 empty] | 947.34 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-01-10 | Yes | 2022-01-11 | 2022-01-17 | NEGATIVE |  |  |  | 2022-02-01 | No Bio Monitoring Needed for Debris or Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-02-08 | 2022-01-17 | 2022-01-18 |  | 01/18/22 SPOKE WITH PAUL HE SAID OK BUT PLEASE CALL ADVANCE. NO PROPANE TANK. JC |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 |  |  | 2 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-14 | No | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-14 | 2022-03-14 | 2022-03-14 | Paul Kobetz, Joyce Kobetz | 707-972-7726, 707-972-7725 | Pkobetz@gmail.com | Septic | Debris Crew Leader/Crew# Glenn Adams/ #601 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 601 | 39.2329 | -123.1899 | Hopkins Fire |  | Residential | Yes | 2022-01-03 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
17 | 167-300-150 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 851 | Rubicon Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 932.51 |  |  |  |  | FALSE |  |  | N/A | Wall Remnants (JFO Approval) | TRUE | #4321 |  |  | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | Yes | TRUE | No | No | No | Yes | Yes | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-01-10 | Yes | 2022-01-11 | 2022-01-17 | NEGATIVE |  |  |  | 2022-01-08 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-02-08 | 2022-01-17 | 2022-01-18 |  | 01/18/22 SPOKE WITH PAUL HE SAID OK BUT PLEASE CALL ADVANCE. NO PROPANE TANK. JC |  |  |  | 2022-01-24 |  | 2022-01-26 | 2022-01-26 |  |  | 2 | 2022-01-27 | 2022-02-04 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Approved | [6 empty] | 2022-03-03 | 2022-01-14 | No | 0 | [8 empty] | 2022-03-10 |  |  | 2022-03-10 | 2022-03-10 | 2022-03-10 | Paul Kobetz, Joyce Kobetz | 707-972-7726, 707-972-7725 | Pkobetz@gmail.com | Keep Items Other Septic | Debris Crew Leader/Crew# Ashanti Broussard / #602 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 602 | 39.233 | -123.1924 | Hopkins Fire |  | Residential | Yes | 2022-01-03 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
18 | 167-310-200 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 6140 | Eastside Calpella Road |  | Ukiah | Mendocino |  | Residential | [5 empty] | 686.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-24 | 2022-01-24 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-01-24 | Yes | 2022-01-24 | 2022-01-27 | NEGATIVE |  |  |  | 2022-01-25 | Bio Monitoring Needed for Debris, not Trees | 2022-01-24 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class I | Covered under suspension | [9 empty] | TRUE | 2022-02-17 | 2022-01-27 | 2022-01-28 |  | 01/28/22 SPOKE WITH LUCILLE SHE ASKED THAT WE CALL HER SON BILL707 485-8021. BILL IS HANDLING PROPERTY. 01/28/22 SPOKE WITH BILL. HE SAID OK BUT PLEASE CALL IN ADVANCE. DO NOT KNOW IF PROPANE ON PROPERTY BUT HE SAID IF THERE IS A PROPANE TANK, DO NOT REMOVE. JC |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 1 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-02-08 | No | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-14 | 2022-03-14 | 2022-03-14 | Lucille Neese | 707-485-8458 / CALL HO SON BILL 707 485-8021 | NA | Septic | Debris Crew Leader/Crew# Glenn Adams/ #601 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 601 | 39.2321 | -123.2001 | Hopkins Fire |  | Residential | No | 2022-01-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
19 | 168-010-040 | Full Program ROE (debris + trees) | Ready for Final Sign-off | No Hazard Trees | Next Step: N/A | Punch List | Hold | 1091 | Marina Drive |  | Ukiah | Mendocino |  | Residential | [5 empty] | 846.63 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes | Hg Site | TRUE | 2022-01-26 | 2022-01-26 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | Yes | FALSE | TRUE | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 |  |  | 4 |  |  | Leave |  | 2022-01-26 | Yes | 2022-01-26 | 2022-02-01 | POSITIVE | 2022-02-01 | 2022-02-01 | 1 | 2022-01-25 | No Bio Monitoring Needed for Debris or Trees | 2022-01-25 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-02-22 | 2022-02-01 | 2022-01-28 |  | 01/28/22 SPOKE WITH MS. WILLIAMS SHE SAID OK. PLEASE CALL IN ADVANCE. DO NOT REMOVE PROPANE TANK. JC |  |  |  | 2022-02-03 |  | 2022-02-07 | 2022-02-07 |  |  | 3 | 2022-02-09 | 2022-02-17 | 7 | Approved | [12 empty] | 2022-03-16 | 2022-02-08 | No | 0 | [8 empty] | 2022-04-04 | [5 empty] | TDW Real Estate Investments | 707-584-7744, 707-303-6478 | deidre@allstatetanklines.com | Septic Vehicles Onsite Well | Debris Crew Leader/Crew# Glenn Adams / #601 Debris Crew WO# Refer to IAP 02/05 to 02/09 Crew 601 | 39.2336 | -123.1851 | Hopkins Fire |  | Residential | Yes | 2022-01-24 | ROE Verified | Central Division | 2022-04-06T00:02:59Z | FALSE |  | Yes
20 | 056-020-037 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 056-020-037 | No Address |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1703.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-12 | 2022-01-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE | [5 empty] | 2022-01-12 | Yes | 2022-01-13 | 2022-01-18 | NEGATIVE |  |  |  | 2022-01-10 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-28 | Yes | 2022-03-03 |  |  | Class III | Covered under suspension | [9 empty] | TRUE | 2022-02-08 | 2022-01-18 | 2022-01-20 | 2022-03-03 | 01/19/22 NO ANS LEFT & TEXT.JC 01/20/22 SPOKE WITH GWEN (OFFICE MANAGER) SHE SAID OK AND WILL GIVE HIM MESSAGE. JC 03/03/22 HO SAID OF FOR TREE REMOVAL. SPOKE WITH GWEN. JC |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 3 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-02-28 | Yes | 58 | 2022-03-11 |  | 2022-03-14 | 2022-03-14 |  | 2022-03-15 | 2022-03-15 | 58 | 2022-03-18 |  | 2022-03-15 | 2022-03-21 | 2022-03-21 | 2022-03-21 | Stewart Hatler | (209) 532-7695 | granddarlings@ATT.net | Septic | Debris Crew Leader/Crew# Ashanti Brousard/ #702 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 702 | 37.9687 | -120.3955 | Washington Fire |  | Industrial | No | 2021-12-13 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
21 | 059-550-005 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 059-550-005 | No Address |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1749.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-12 | 2022-01-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE | 2 |  |  | Leave |  | 2022-01-10 | Yes | 2022-01-11 | 2022-01-14 | POSITIVE | 2022-01-21 | 2022-01-21 | 6 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-03 | No Activity/Nest Building Removed |  |  | Complete | No |  | Yes | 2022-03-02 |  |  | Class III | Covered under suspension | [9 empty] | TRUE | 2022-02-08 | 2022-01-21 | 2022-01-21 | 2022-03-03 | 01/21/22 SPOKE WITH JEREMY HE SAID OK. VENDOR HANDLING PROPANE TANK. JC 03/03/22 SPOKE WITH JEREMY HE SAID OK FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-02 | 2022-02-02 |  |  | 2 | 2022-02-03 | 2022-02-11 | 7 | Approved | [12 empty] | 2022-02-14 | 2022-01-29 | No | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-25 | 2022-03-25 | 2022-03-25 | Jeremy Caswell | (209) 694-9313 | jercaswell0118@gmail.com | Septic | Debris Crew Leader/Crew# Joseph Richmond / #701 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 701 | 37.9654 | -120.3977 | Washington Fire |  | Residential | No | 2021-12-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
22 | 059-550-018 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 11387 | Silver Pine Drive |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1802.43 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-14 | 2022-01-14 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 7 | 0 | 0 | 0 | 3 | 5 | 0 | 15 |  | TRUE | 19 |  |  | Leave |  | 2022-01-12 | Yes | 2022-01-13 | 2022-01-18 | POSITIVE | 2022-01-21 | 2022-01-21 | 4 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | Yes | 2022-03-02 | [13 empty] | TRUE | 2022-02-08 | 2022-01-21 | 2022-01-21 |  | 01/21/22 SPOKE WITH JEREMY HE SAID OK. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-29 |  | 2022-02-01 | 2022-02-01 |  |  | 3 | 2022-02-03 | 2022-02-11 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Approved | [6 empty] | 2022-03-03 | 2022-01-28 | No | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-21 | 2022-03-21 | 2022-03-21 | Jeremy Caswell | (209) 694-9313 | jercaswell0118@gmail.com | Septic | Debris Crew Leader/Crew# Ashanti Broussard/ #702 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 702 | 37.9693 | -120.3972 | Washington Fire |  | Residential | No | 2021-12-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
23 | 056-590-002 | Full Program ROE (debris + trees) | Asbestos Abatement Needed | Haz Trees Present | Next Step: N/A | Tuolumne 701 | No Eligible Trees | 056-590-002 | No Address |  | Sonora | Tuolumne |  | Commercial | Yes | 2022-03-03 | 2022-03-21 | A1-1: CalHaz and RCRA B1-1: CalHaz (see email attachment) |  | 1749.91 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-04 | 2022-02-04 | FALSE | Yes |  |  | No | TRUE | No | Yes | No | No | No |  | TRUE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | [7 empty] | 2022-02-04 | Yes | 2022-02-23 | 2022-03-01 | POSITIVE |  |  | 29 | 2022-02-24 | Bio Monitoring Needed for Debris AND Trees | 2022-02-24 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No | [16 empty] | TRUE | 2022-05-02 | [31 empty] | 2022-04-04 | Yes | 107 | [19 empty] | 37.9687 | -120.3883 | Washington Fire |  | Commercial |  | 2022-02-18 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE |  | Yes
24 | 059-350-010 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 18885 | Golden Dove Lane |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1666.29 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No | No | FALSE | TRUE | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 4 |  | TRUE | 4 |  |  | Leave |  | 2022-01-10 | Yes | 2022-01-11 | 2022-01-14 | POSITIVE | 2022-01-20 | 2022-01-20 | 5 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | Yes | 2022-02-26 | Yes | 2022-03-02 |  |  | Class III | Covered under suspension | [9 empty] | TRUE | 2022-02-08 | 2022-01-20 | 2022-01-24 |  | 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 NO ANS LEFT VM & EMAIL. JC 01/24/22 SPOKE SANDRA SHE SAID OK.VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-27 |  | 2022-01-29 | 2022-01-29 |  |  | 2 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Re-scrape | 2022-03-10 | 2022-03-18 | Approved |  |  |  | 2022-03-21 | 2022-01-29 | Yes | 18 | 2022-03-10 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-11 | 2022-03-11 | 18 | 2022-04-05 |  | 2022-03-11 | 2022-04-06 | 2022-04-06 | 2022-04-07 | Michael and Sandra Sturzenacker | (209 559-2115 | sandrasturz@gmail.com | Other Septic | Debris Crew Leader/Crew# Sahoi McLean/ #701 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 701 | 37.9646 | -120.3979 | Washington Fire |  | Residential | Yes | 2021-12-28 | ROE Verified | Central Division | 2022-04-07T15:00:43Z | FALSE |  | Yes
25 | 059-350-017 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 11310 | McKibbon Drive |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1625.69 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | TRUE | 1 |  |  |  |  | 2022-01-10 | Yes | 2022-01-11 | 2022-01-14 | POSITIVE | 2022-01-21 | 2022-01-21 | 6 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | Arch Monitoring Needed for Trees, not Debris |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | Yes | 2022-03-02 |  |  | Class III | Covered under suspension | [9 empty] | TRUE | 2022-02-08 | 2022-01-21 | 2022-01-24 | 2022-03-03 | 01/24/22 SPOKE WITH GWEN SHE SAID OK. NO PROPANE TANKS. JC 03/03/22 HO SAID OF FOR TREE REMOVAL. JC |  |  |  | 2022-02-02 |  | 2022-02-03 | 2022-02-03 |  |  | 2 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-29 | Yes | 56 | 2022-03-08 |  | 2022-03-10 | 2022-03-10 |  | 2022-03-14 | 2022-03-14 | 56 | 2022-03-18 |  | 2022-03-14 | 2022-03-21 | 2022-03-21 | 2022-03-21 | Stewart Hatler | (209) 694-5734 | granddarlings@ATT.net | Septic | Debris Crew Leader/Crew# Joseph Richmond/ 701 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 701 | 37.964 | -120.3989 | Washington Fire |  | Residential | No | 2021-12-13 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
26 | 059-550-002 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 11201 | Silver Pine Drive |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1957.26 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-12 | 2022-01-12 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 2 | 1 | 0 | 0 | 2 | 0 | 0 | 5 |  | TRUE | 5 |  |  | Leave |  | 2022-01-12 | Yes | 2022-01-13 | 2022-01-18 | POSITIVE | 2022-01-21 | 2022-01-21 | 4 | 2022-01-11 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | Yes | 2022-03-02 |  |  | Class III | Covered under suspension | [9 empty] | TRUE | 2022-02-08 | 2022-01-21 | 2022-01-22 |  | 01/21/22 NO ANS LEFT VM & TEXT. JC 01/22/22 NO ANS LEFT VM & EMAIL. JC 01/22/22 HO GAVE CONSENT VIA TEXT. JC 01/24/22﻿ RICHARD CALLED BACK HE SAID PROPANE IS STILL WORKING SO DO NOT REMOVE. JC 02/02/22 LEFT MESSAGE FOR HO ABT HOSTILE ACCESS ON PROPERTY THIS MORNING. ﻿JC |  |  |  | 2022-02-01 |  | 2022-02-03 | 2022-02-03 |  |  | 2 | 2022-02-04 | 2022-02-14 | 7 | Approved | [12 empty] | 2022-02-15 | 2022-01-27 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-05 | 2022-03-05 | 2022-03-06 | Richard and Carrie Edmon | (909) 904-2102 | rich818dubs@yahoo.com | Septic | Debris Crew Leader/Crew# Ashanti Broussard/ #702 Debris Crew WO# Refer to IAP 02/02 to 02/06 Crew 702 | 37.9679 | -120.3986 | Washington Fire |  | Residential | No | 2021-12-23 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
27 | 059-550-021 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 19125 | Golden Dove Lane |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1734.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-11 | 2022-01-11 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 2 | 0 | 4 |  | TRUE | 4 |  |  |  |  | 2022-01-11 | Yes | 2022-01-12 | 2022-01-19 | POSITIVE | 2022-01-20 | 2022-01-20 | 2 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No | [16 empty] | TRUE | 2022-02-08 | 2022-01-20 | 2022-01-21 |  | 01/21/22 SPOKE WITH JEREMY HE SAID OK. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-27 |  | 2022-01-27 | 2022-01-27 |  |  | 4 | 2022-02-01 | 2022-02-09 | 7 | Soil Boring | 2022-02-14 | 2022-02-22 | Approved | [9 empty] | 2022-02-24 | 2022-01-28 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-22 | 2022-03-22 | 2022-03-22 | Jeremy Caswell | (209) 694-9313 | jercaswell0118@gmail.com | Septic | Debris Crew Leader/Crew# Ashanti Broussard / #702 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 702 | 37.967 | -120.3962 | Washington Fire |  | Residential | No | 2021-12-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
28 | 059-550-019 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 19115 | Golden Dove Lane |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1838.59 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-11 | 2022-01-11 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | TRUE | 2 |  |  |  |  | 2022-01-11 | Yes | 2022-01-12 | 2022-01-19 | POSITIVE | 2022-01-20 | 2022-01-20 | 2 | 2022-01-10 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | Arch Monitoring Needed for Debris AND Trees | [5 empty] | Complete | No |  | Yes | 2022-03-02 |  |  | No | None | [9 empty] | TRUE | 2022-02-08 | 2022-01-20 | 2022-01-20 |  | 01/19/22 NO ANS LEFT & TEXT.JC 01/20/22 SPOKE WITH GWEN (OFFICE MANAGER) SHE SAID OK AND WILL GIVE HIM MESSAGE. JC |  |  |  | 2022-01-29 |  | 2022-01-31 | 2022-01-31 |  |  | 3 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-28 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-05 | 2022-03-05 | 2022-03-05 | Stewart Hatler | (209) 694-5734 | granddarlings@ATT.net | Septic | Debris Crew Leader/Crew# Sahoi McLean/ 701 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 701 | 37.9676 | -120.3973 | Washington Fire |  | Residential | No | 2021-12-13 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
29 | 059-550-020 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 11399 | Silver Pine Drive |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1752.35 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-11 | 2022-01-11 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 1 | 0 | 0 | 8 | 0 | 4 | 3 | 16 |  | TRUE | 16 |  |  | Leave |  | 2022-01-11 | Yes | 2022-01-12 | 2022-01-19 | POSITIVE | 2022-01-20 | 2022-01-20 | 2 | 2022-01-10 | No Bio Monitoring Needed for Debris or Trees | 2022-01-11 | No Arch Monitoring Needed for Debris or Trees | [5 empty] | Complete | No |  | Yes | 2022-03-02 |  |  | Class III | None | [9 empty] | TRUE | 2022-02-08 | 2022-01-20 | 2022-01-21 |  | 01/21/22 SPOKE WITH JEREMY HE SAID OK. VENDOR HANDLING PROPANE TANK. JC |  |  |  | 2022-01-27 |  | 2022-01-29 | 2022-01-29 |  |  | 2 | 2022-02-01 | 2022-02-09 | 7 | Re-scrape |  |  |  | 2022-02-22 | 2022-03-02 | Approved | [6 empty] | 2022-03-03 | 2022-01-28 | No | 0 | [8 empty] | 2022-03-18 |  |  | 2022-03-21 | 2022-03-21 | 2022-03-21 | Jeremy Caswell | (209) 694-9313 | jercaswell0118@gmail.com | Keep Items Septic Vehicles Onsite | Debris Crew Leader/Crew# Ashanti Brassard / #702 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 702 | 37.9683 | -120.3966 | Washington Fire |  | Residential | No | 2021-12-23 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
30 | 059-550-022 | Full Program ROE (debris + trees) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 18887 | Golden Dove Lane |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1692.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-10 | 2022-01-10 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRUE | [5 empty] | 2022-01-10 | Yes | 2022-01-11 | 2022-01-14 | NEGATIVE |  |  |  | 2022-01-10 | No Bio Monitoring Needed for Debris or Trees | 2022-01-10 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | Yes | 2022-03-02 |  |  | No | None | [9 empty] | TRUE | 2022-02-08 | 2022-01-14 | 2022-01-20 |  | 01/19/22 NO ANS LEFT & TEXT.JC 01/20/22 SPOKE WITH GWEN (OFFICE MANAGER) SHE SAID OK AND WILL GIVE HIM MESSAGE. JC |  |  |  | 2022-01-27 |  | 2022-01-27 | 2022-01-27 |  |  | 3 | 2022-01-31 | 2022-02-08 | 7 | Soil Boring | 2022-02-11 | 2022-02-21 | Approved | [9 empty] | 2022-02-24 | 2022-01-29 | Yes | 6 | 2022-03-08 |  | 2022-03-08 | 2022-03-08 |  | 2022-03-08 | 2022-03-08 | 6 | 2022-03-18 |  | 2022-03-08 | 2022-03-21 | 2022-03-21 | 2022-03-21 | Stewart Hatler | (209) 694-5734 | granddarlings@ATT.net | Septic | Debris Crew Leader/Crew# Sahoi McLean/ #701 Debris Crew WO# Refer to IAP 01/26 to 01/29 Crew 701 | 37.9648 | -120.3973 | Washington Fire |  | Residential | No | 2021-12-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | No
31 | 059-550-004 | Full Program ROE (debris + trees) | Returned to County | No Hazard Trees | Next Step: N/A | Returned to County | Returned to County | 059-550-004 | No Address |  | Sonora | Tuolumne |  | Residential | [5 empty] | 1800.46 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-01-11 | 2022-01-11 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 4 |  | TRUE | 1 |  |  | Leave |  | 2022-01-11 | Yes | 2022-01-12 | 2022-03-08 | POSITIVE | 2022-01-21 | 2022-01-21 | -33 | 2022-01-10 | Bio Monitoring Needed for Debris AND Trees | 2022-01-10 | Arch Monitoring Needed for Trees, not Debris | [5 empty] | Complete | No | [16 empty] | TRUE | 2022-02-08 | 2022-01-21 | 2022-01-21 |  | 01/21/22 SPOKE WITH JEREMY HE SAID OK. NO PROPANE TANK. JC |  |  |  | 2022-01-31 |  | 2022-02-01 | 2022-02-01 |  |  | 2 | 2022-02-02 | 2022-02-10 | 7 | Approved | [12 empty] | 2022-02-11 | 2022-01-28 | No | 0 | [8 empty] | 2022-03-03 |  |  | 2022-03-22 | 2022-03-22 | 2022-03-22 | Jeremy Caswell | (209) 694-9313 | jercaswell0118@gmail.com | Septic | Debris Crew Leader/Crew# Sahoi McLean / #701 Debris Crew WO# Refer to IAP 01/29 to 02/02 Crew 701 | 37.966 | -120.397 | Washington Fire |  | Residential | No | 2021-12-20 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
32 | 056-020-043 | Tree Only ROE (no qualifying debris) | Returned to County | Passed Tree Completion Check | Next Step: N/A | Returned to County | Returned to County | 056-020-043 | No Address |  | Sonora | Tuolumne |  | Commercial | No |  |  |  |  | 1830.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-02-24 | 2022-02-24 | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-25 | No | [6 empty] | 2022-02-24 | No Bio Monitoring Needed for Debris or Trees | 2022-02-24 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-07 | No Activity/Nest Building Removed |  |  | Complete | No |  | Yes | 2022-03-04 | [46 empty] | 2022-03-04 | Yes | 75 | 2022-03-14 |  | 2022-03-16 | 2022-03-16 |  | 2022-03-17 | 2022-03-17 | 75 |  |  | 2022-03-17 |  | 2022-03-17 | 2022-03-18 | [5 empty] | 37.9679 | -120.3925 | Washington Fire |  | Commercial |  | 2022-02-18 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE
33 | 053-040-218 | Tree Only ROE (no qualifying debris) | No Asbestos Detected |  | Next Step: N/A | TREE ONLY ROEs | Needs Haz Tree Assessment | 949 | Alta Sierra Rd |  | Wofford Heights | Kern |  | Residential | [5 empty] | 5878.71 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Gate Code: #1269 |  |  | Yes |  | TRUE | 2022-03-01 |  | FALSE | No |  |  | No |  | No | Yes | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-01 | No | [6 empty] | 2022-03-02 | Bio Monitoring Needed for Trees, not Debris | 2022-03-01 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-03-31 | [48 empty] | Danny and Li Yang Mullinax | 7707132754 | dan.mullinax@yahoo.com |  |  | 35.7361 | -118.5431 | French Fire |  | Residential | Yes | 2022-02-25 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
34 | 062-020-029 | Full Program ROE (debris + trees) | ROE Received | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 062-020-029 | Alder Creek Road |  |  | Kern |  | Camp | [5 empty] | 3422.14 |  |  |  |  | TRUE | EHP (non-bridge/access) |  | N/A |  | TRUE | #0701 | TRUE | Weather-related | Yes |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [37 empty] | Yes | [9 empty] | 4.7 Spoke to Mike Nouric. He said Ted Cooper is the local contact and will let the crew in whenever they needed. Ted's #661-387-5127 and is expecting a call and will corporate. Ted Cooper c/b and gave the gate code #0701. PF | [28 empty] | Do Not Assess | [15 empty] | Celere Inc /Michael Nourie Ted Cooper - Local Contact | 6508679451 (Ted Cooper-661-387-5127) | mikenourie@gmail.com |  | Call Ted for Access he lives next to parcel. He will let you in per Michael Nourie. | 38.9906 | -120.7462 | French Fire |  | Other | No | 2022-01-12 | ROE Verified | Central Division | 2022-04-07T23:35:59Z | FALSE
35 | 062-285-069 | Full Program ROE (debris + trees) | Ready for Debris Removal | No Hazard Trees | Next Step: N/A | Kern Pending | No Eligible Trees | 810 | Sawmill Road |  | Lake Isabella | Kern |  | Residential | [5 empty] | 3812.81 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-24 | 2022-02-24 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No |  | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 |  | TRUE | [5 empty] | 2022-02-24 | Yes | 2022-02-24 | 2022-03-01 | POSITIVE | 2022-03-15 | 2022-03-15 | 11 | 2022-02-22 | Bio Monitoring Needed for Debris, not Trees | 2022-03-02 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-15 | [30 empty] | 2022-02-24 | No | 0 | [14 empty] | Andy Alvarez | 7605493110 | mudstamper@icloud.com |  |  | 35.6774 | -118.4964 | French Fire |  | Residential | No | 2022-01-06 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
36 | 062-285-275 | Full Program ROE (debris + trees) | Ready for Debris Removal | Ready for Tree Felling | Next Step: N/A | Kern Pending | Survey Complete | 1864 | Sawmill Road |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3858.39 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-22 | 2022-02-22 | FALSE | No |  |  | No |  | No | No | Yes | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-24 | Yes | 2022-02-24 | 2022-03-01 | NEGATIVE |  |  |  | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees | [12 empty] | Class III | None | [9 empty] | TRUE | 2022-04-08 | 2022-03-01 | [30 empty] | 2022-02-24 | Yes | 12 | [14 empty] | Elizabeth Carde-Leipnik | 7605499054 | elizabethcarde6@gmail.com |  |  | 35.6757 | -118.5012 | French Fire |  | Residential | No | 2021-12-17 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | No
37 | 062-285-317 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 1181 | H Street |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3911.86 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-22 | 2022-02-22 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-22 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-15 | 2022-03-15 | 12 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-15 | [31 empty] | Do Not Assess | [15 empty] | Michael Conrad | 8054164254 | mconrad@amgen.com |  |  | 35.6756 | -118.4983 | French Fire |  | Residential | No | 2021-12-17 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
38 | 062-285-416 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 4 | Avenue H |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3886.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-24 | 2022-02-24 | FALSE | No |  |  | No |  | No | Yes | Yes | No | No |  | FALSE | TRUE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | TRUE | [5 empty] | 2022-02-21 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-17 | 2022-03-17 | 14 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-03-02 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-17 | [31 empty] | Do Not Assess | [15 empty] | Don Tonty | 3108502305 | deton1@outlook.com |  |  | 35.6744 | -118.4963 | French Fire |  | Residential | No | 2021-12-21 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
39 | 053-332-128 | Full Program ROE (debris + trees) | No Asbestos Detected | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 127 | Arnold Springs Drive |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3793.2 |  |  |  |  | TRUE | Boundary Line Issues |  | N/A | [5 empty] | No |  | TRUE | 2022-02-23 |  | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-22 | No | [6 empty] | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-22 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-05 | [32 empty] | Do Not Assess | [15 empty] | Connie Shepard | 6614351004 | shepard622@gmail.com |  |  | 35.7186 | -118.4977 | French Fire |  | Residential | No | 2022-01-12 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE
40 | 062-182-142 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 6301 | Jacobs Lane |  | Lake Isabella | Kern |  | Residential | [5 empty] | 4512.63 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1st gate combo lock: 14-20-14 2nd gate combo lock: 22-4-26 3rd gate combo lock: 13-30-13 |  |  | No |  | TRUE | 2022-02-21 | 2022-02-21 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-22 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-15 | 2022-03-15 | 12 | 2022-02-22 | Bio Monitoring Needed for Debris, not Trees | 2022-03-02 | Arch Monitoring Needed for Debris AND Trees | Yes | [22 empty] | TRUE | 2022-04-08 | 2022-03-15 | [31 empty] | Do Not Assess | [15 empty] | Ralph Yep | 3104871374 | yepralph@gmail.com |  |  | 35.6658 | -118.5416 | French Fire |  | Residential | No | 2021-12-21 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
41 | 062-285-143 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 7076 | 12th Street |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3821.54 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-21 | 2022-02-21 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | TRUE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  | TRUE | [5 empty] | 2022-02-21 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-15 | 2022-03-15 | 12 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-03-02 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-15 | [31 empty] | Do Not Assess | [15 empty] | Ralph and Marianne Owen | 4244777372 | rustydoughnut@gmail.com |  |  | 35.6756 | -118.4963 | French Fire |  | Residential | No | 2022-01-03 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
42 | 062-285-242 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 7042 | 15th Street |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3883.84 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-22 | 2022-02-22 | FALSE | No |  |  | No |  | No | No | No | No | No |  | FALSE | TRUE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | TRUE | [5 empty] | 2022-02-22 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-16 | 2022-03-16 | 13 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-16 | [31 empty] | Do Not Assess | [15 empty] | David Turajski | 3238993013 | turajskibk@gmail.com |  |  | 35.6748 | -118.4992 | French Fire |  | Residential | No | 2022-02-08 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE
43 | 053-040-234 | Tree Only ROE (no qualifying debris) | Withdrawn | Not Eligible for Haz Tree Removal | Next Step: N/A | Withdrawn | Withdrawn/Ineligible | 962 | Alta Sierra Road |  | Wofford Heights | Kern |  | Residential | [5 empty] | 5748.16 | 2022-03-07 |  |  |  | FALSE |  |  | N/A |  | TRUE | Code = #1269 |  |  | Yes |  | TRUE | 2022-02-28 | 2022-02-28 | FALSE | No |  |  | No |  | No | Yes | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-28 | Yes | 2022-03-02 | 2022-03-07 | NEGATIVE |  |  |  | 2022-02-22 | Bio Monitoring Needed for Debris AND Trees | 2022-02-22 | No Arch Monitoring Needed for Debris or Trees | [57 empty] | Do Not Assess | [15 empty] | Tom Rowe | 6613327072 | tmrowe49@gmail.com |  |  | 35.7352 | -118.5408 | French Fire |  | Residential | No | 2021-12-09 | ROE Verified | Central Division | 2022-04-01T22:04:14Z | FALSE |  | Yes
44 | 053-040-242 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 945 | Alta Sierra Road |  | Wofford Heights | Kern |  | Residential | [5 empty] | 5891.45 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | Code = #1269 |  |  | Yes |  | TRUE | 2022-03-01 | 2022-03-01 | FALSE | No |  |  | No |  | No | Yes | No | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-01 | Yes | 2022-03-02 | 2022-03-07 | NEGATIVE |  |  |  | 2022-02-22 | Bio Monitoring Needed for Trees, not Debris | 2022-02-22 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-07 | [31 empty] | Do Not Assess | [15 empty] | Anglin Family Trust | 8057946741 | Jake_zimmerman@yahoo.com |  |  | 35.7352 | -118.5431 | French Fire |  | Residential | No | 2022-02-07 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE |  | Yes
45 | 062-285-259 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 7061 | 15th Street |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3866.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-22 | 2022-02-22 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | TRUE | 1 | 0 | 0 | 0 | 1 | 0 | 2 | 4 |  | TRUE | [5 empty] | 2022-02-22 | Yes | 2022-02-23 | 2022-02-28 | POSITIVE | 2022-03-16 | 2022-03-16 | 13 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-16 | [31 empty] | Do Not Assess | [15 empty] | William and Barbara Heizer | 7603796452 | pineswb@icloud.com |  |  | 35.6748 | -118.5002 | French Fire |  | Residential | No | 2022-02-07 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE
46 | 062-285-283 | Full Program ROE (debris + trees) | Ready for Debris Removal | Not Eligible for Haz Tree Removal | Next Step: N/A | Kern Pending | No Eligible Trees | 7073 | 15th Street |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3878.7 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-02-22 | 2022-02-22 | FALSE | No |  |  | No |  | No | No | Yes | No | No |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-02-22 | Yes | 2022-02-23 | 2022-03-03 | POSITIVE | 2022-03-16 | 2022-03-16 | 10 | 2022-02-22 | No Bio Monitoring Needed for Debris or Trees | 2022-02-21 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | 2022-03-16 | [31 empty] | Do Not Assess | [15 empty] | William and Barbara Heizer | 7603796452 | pineswb@icloud.com |  |  | 35.6757 | -118.5002 | French Fire |  | Residential | No | 2022-02-07 | ROE Verified | Central Division | 2022-04-05T01:52:55Z | FALSE
47 | 009-060-041 | Full Program ROE (debris + trees) | Pending Asbestos Results | No Hazard Trees | Next Step: N/A | Program Eligibility Pending | No Eligible Trees | 009-060-041 | No Address |  | Badger | Tulare |  | Residential | [5 empty] | 5012.03 |  |  |  |  | TRUE | Inclusion Approval |  | N/A | Pending |  |  |  |  | No | Phase 1 Revisit | TRUE | 2022-04-02 | 2022-04-02 | FALSE | Yes |  |  | Yes |  | No | Yes | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-02 | Yes | 2022-04-04 | [5 empty] | 2022-04-07 | Bio Monitoring Needed for Debris AND Trees | 2022-04-06 | Arch Monitoring Needed for Trees, not Debris |  | 2022-04-02 | No Activity/Nest Building Removed | [53 empty] | 2022-02-01 | No | 0 | [14 empty] | Deeds, Don/Cardonie Laurie/Richards, Carol/Twaddle, Deborah/Twaddle, Deborah/Twaddle Deborah | 559-309-2685 | eshom@hotmail.com | Septic Well |  | 36.6373 | -118.9434 | KNP |  | Agricultural | No | 2022-01-19 | ROE Verified | Central Division | 2022-04-09T00:25:23Z | FALSE
48 | 144-060-010 | Full Program ROE (debris + trees) | Pending Asbestos Results |  | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 144-060-010 | 326-110-017 |  | Springville | Tulare |  | Residential | [5 empty] | 5515.94 |  |  |  |  | FALSE |  |  | N/A |  | TRUE | 1ST GATE CODE 1935; 2ND GATE IS UNLOCKED |  |  | No |  | TRUE | 2022-04-05 | 2022-04-05 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-05 | Yes | 2022-04-06 | [5 empty] | 2022-04-01 | Bio Monitoring Needed for Debris AND Trees | 2022-03-31 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [25 empty] | 03/31/22 CALLED FOR GATE CODE. NO ANS LEFT VM & TEXT. JC 03/31/22 HO TEXT BACK SAYING IT IS A KEY LOCK AND ASKED THAT WE CONTACT VERN BITNEY. I AM WAITING FOR HO TO SEND ME CONTACT INFORMATION FOR VERN BITNEY. JC 04/01/22 SPOKE WITH JOHN RAIBLEY HE ASKED THAT WE SPEAK WITH VERN TO GET ACCESS. SPOKE WITH VERN. HE SAID HE NEEDS TO FIND GATE CODE AND WILL CALL BACK. ﻿JC 04/01/22 VERN C/B WITH GATE CODE. 1ST GATE CODE 1935; 2ND GATE IS UNLOCKED 4.4.22 PER MP SPOKE TO PO AND THE NEIGHBOR "VERN BITNEY" FOR CODE AND ADDITIONAL INFO ON GATES LOCKED & CONTACT #. 1ST GATE CODE IS 1935. THE 2ND GATE HAS A DUMMY LOCK(BUT OPENED). PF (MR BITNEY CONTACT INFO IS 559-750-7410) | [44 empty] | John & Barbara Raibley | 559-303-3066 | barbara.raibley@outlook.com | Access Issues |  | 36.2518 | -118.7252 | Windy |  |  | No | 2021-12-13 | ROE Verified | Central Division | 2022-04-08T00:46:48Z | FALSE
49 | 144-080-003 | Full Program ROE (debris + trees) | Pending Asbestos Results | Haz Trees Present | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 144-080-003 | Balch Park Road and Rancheria Creek (east) |  | Springville | Tulare |  | Residential | [5 empty] | 5555.66 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-04 | 2022-04-04 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-04 | Yes | 2022-04-05 | 2022-04-08 |  |  |  |  | 2022-04-01 | Bio Monitoring Needed for Debris AND Trees | 2022-03-31 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [53 empty] | 2022-03-28 | Yes | 34 | [14 empty] | John Stewart | 559-539-3975 | johnstewartjd@icloud.com | Septic Vehicles Onsite |  | 36.2452 | -118.7139 | Windy |  |  | No | 2021-12-10 | ROE Verified | Central Division | 2022-04-08T22:02:40Z | FALSE
50 | 220-057-003 | Full Program ROE (debris + trees) | Pending Asbestos Results | No Hazard Trees | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 54443 | Hossack Drive |  | Sequoia Crest | Tulare |  | Residential | [5 empty] | 6728.48 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-04-05 | 2022-04-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-05 | Yes | 2022-04-06 | [5 empty] | 2022-04-01 | No Bio Monitoring Needed for Debris or Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [53 empty] | 2022-03-29 | No | 0 | [14 empty] | David C Perez | 805-423-9495 | djdcp@charter.net |  |  | 36.1794 | -118.6305 | SQF |  |  | Yes | 2022-02-11 | ROE Verified | Central Division | 2022-04-07T03:02:44Z | FALSE
51 | 326-062-005 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-062-005 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 5926.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | POSITIVE |  |  | 2 | 2022-04-02 | No Bio Monitoring Needed for Debris or Trees | 2022-04-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [70 empty] | Daniel Johnson | 661-972-5914 | johnsondan5914@gmail.com / CPicco81@yahoo.com | Access Issues Other |  | 35.8387 | -118.6041 | Windy |  | Agricultural | No | 2022-01-12 | ROE Verified | Central Division | 2022-04-09T00:25:04Z | FALSE
52 | 326-110-002 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 48507 | Old Lodge Road |  | Posey | Tulare |  | Residential | [5 empty] | 5829.33 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | NEGATIVE |  |  |  | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Allen, Jeanne Trustee | 661-303-0986 | retd2quilt@yahoocom | Septic |  | 35.8398 | -118.6041 | Windy |  | Agricultural | No | 2022-01-06 | ROE Verified | Central Division | 2022-04-07T20:15:03Z | FALSE
53 | 326-050-042 | Full Program ROE (debris + trees) | Ready for Debris Removal | No Hazard Trees | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-050-042 | No Address |  | Posey | Tulare |  | Mobile Home Park | [5 empty] | 5860.68 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | NEGATIVE |  |  |  | 2022-03-31 | No Bio Monitoring Needed for Debris or Trees | 2022-03-30 | Arch Monitoring Needed for Debris AND Trees |  | 2022-03-31 | No Activity/Nest Building Removed | [22 empty] | 2022-04-06 | [30 empty] | 2022-03-30 | No | 0 | [14 empty] | Todd Thoroddsson (passed) | 805-934-5194 | peterthor60@yahoo.com | Septic |  | 35.8381 | -118.6062 | Windy |  | Agricultural | No | 2021-12-14 | ROE Verified | Central Division | 2022-04-07T17:47:20Z | FALSE
54 | 326-062-004 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-062-004 | No Address |  | Sugarloaf | Tulare |  | Residential | [5 empty] | 5931.98 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No | Phase 1 Revisit | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | NEGATIVE |  |  |  | 2022-03-31 | No Bio Monitoring Needed for Debris or Trees | 2022-04-04 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Johnson, Daniel L (Johnson Trust 1) | 661-972-5914 | johnsondan5914@gmail.com | Access Issues |  | 35.8385 | -118.6041 | Windy |  | Agricultural | No | 2021-12-14 | ROE Verified | Central Division | 2022-04-07T18:51:47Z | FALSE
55 | 220-272-019 | Tree Only ROE (no qualifying debris) | Ready for Tree Operations | Haz Trees Present | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 53122 | Pine View Drive |  | Springville | Tulare |  | Residential | [5 empty] | 6369.45 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-04-07 | No Bio Monitoring Needed for Debris or Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  |  | Yes | [49 empty] | 2022-03-29 | Yes | 27 | [14 empty] | Marius & Nicoleta Alecse | 310-228-7902 | alecsem@yahoo.com |  |  | 36.1593 | -118.6086 | Windy |  |  | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-08T03:18:49Z | FALSE
56 | 220-310-016 | Tree Only ROE (no qualifying debris) | ROE Received | No Hazard Trees | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 53009 | Pine View Drive |  | Camp Nelson | Tulare |  | Residential | [5 empty] | 6509.5 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | [15 empty] | FALSE | [7 empty] | 0 | [15 empty] | 2022-04-07 | No Bio Monitoring Needed for Debris or Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-07 | No Activity/Nest Building Removed |  |  |  | Yes | [49 empty] | 2022-03-29 | No | 0 | [14 empty] | Douglas & Jody Mead | 559-310-2232 | zantetowncal@gmail.com |  |  | 36.1608 | -118.6066 | Windy |  |  | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-08T03:19:07Z | FALSE
57 | 326-110-005 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-005 | No Address |  | Sugarloaf | Tulare |  | Residential | [5 empty] | 5852.97 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-01 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-02 | No | [8 empty] | 2022-04-04 | Arch Monitoring Needed for Trees, not Debris | [73 empty] | Burrows, Walter & Bonita | 661-322-4487 | waltburrows@att.net | Septic Well |  | 35.8398 | -118.6023 | Windy |  | Agricultural | No | 2021-12-23 | ROE Verified | Central Division | 2022-04-05T01:19:07Z | FALSE
58 | 326-110-006 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-006 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 6006.03 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No | Phase 1 Revisit | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | Yes | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-02 | Yes | 2022-04-04 | 2022-04-07 | NEGATIVE |  |  |  | 2022-04-02 | Bio Monitoring Needed for Debris AND Trees | 2022-04-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [70 empty] | Burrows, Walter & Bonita | 661-322-4487 | waltburrows@ATT.NET | Septic Well |  | 35.8391 | -118.6016 | Windy |  | Agricultural | No | 2022-01-12 | ROE Verified | Central Division | 2022-04-07T18:55:37Z | FALSE
59 | 326-110-008 | Full Program ROE (debris + trees) | Ready for Debris Removal |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-008 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 5700.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | NEGATIVE |  |  |  | 2022-03-31 | No Bio Monitoring Needed for Debris or Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [22 empty] | 2022-04-06 | [47 empty] | Dodson, Phillip C & Jean | 661-665-9422 | pipestring2@gmail.com | Other |  | 35.8402 | -118.6055 | Windy |  | Agricultural | Yes | 2022-01-12 | ROE Verified | Central Division | 2022-04-07T17:47:20Z | FALSE
60 | 326-110-007 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-007 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 6081.61 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No | Phase 1 Revisit | TRUE | 2022-04-01 |  | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-02 | No | [8 empty] | 2022-04-04 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Burrows, Walter & Bonita | 661-322-4487 | waltburrows@att.net | Septic Well |  | 35.8385 | -118.6018 | Windy |  | Agricultural | No | 2022-01-12 | ROE Verified | Central Division | 2022-04-05T03:16:31Z | FALSE
61 | 326-110-019 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 48491 | Redwood Circle |  | Posey | Tulare |  | Residential | [5 empty] | 5730.57 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | Yes |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | POSITIVE |  |  | 3 | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | Arch Monitoring Needed for Debris AND Trees | Yes | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Hirst, Paul Succesor Trustee | 661-578-0124 | paulhirst23@gmail.com | Access Issues Keep Items Septic Well |  | 35.8396 | -118.606 | Windy |  | Agricultural | No | 2021-12-30 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE
62 | 326-110-004 | Full Program ROE (debris + trees) | No Asbestos Detected | No Hazard Trees | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-004 | No Address |  | Sugarloaf | Tulare |  | Residential | [5 empty] | 5915.32 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | TRUE | 0 | 3 | 0 | 1 | 1 | 1 | 0 | 6 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | NEGATIVE |  |  |  | 2022-04-02 | Bio Monitoring Needed for Debris AND Trees | 2022-04-04 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [53 empty] | 2022-03-30 | No | 0 | [14 empty] | Crawford, Ivan | 661-110-004 | ivan3847@gmail.com | Other Septic Vehicles Onsite Well |  | 35.8392 | -118.6036 | Windy |  | Agricultural | Yes | 2022-01-13 | ROE Verified | Central Division | 2022-04-07T18:46:34Z | FALSE
63 | 326-110-003 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-003 | No Address |  | Sugarloaf | Tulare |  | Residential | [5 empty] | 5866.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No | Phase 1 Revisit | TRUE | 2022-04-01 | 2022-04-01 | FALSE | No |  |  | No |  | No | No | No | Yes | No | Yes | FALSE | TRUE | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 6 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | POSITIVE |  |  | 2 | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Van Allen Douglas, Jeffery Holding, Jerry Holding | 661-549-5013 | douglasvanallen@gmail.com | Keep Items Other Septic Vehicles Onsite |  | 35.8395 | -118.604 | Windy |  | Agricultural | No | 2021-12-29 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE
64 | 326-110-009 | Full Program ROE (debris + trees) | Ready for Debris Removal |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 48477 | Redwood Circle |  | Posey | Tulare |  | Residential | [5 empty] | 5798.37 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | NEGATIVE |  |  |  | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [22 empty] | 2022-04-06 | [47 empty] | Yetman, Kathy L & Macklin, Brian K & Karen D | 559-434-5441 or 559-289-7086 | klyetman@gmail.com/kdmacklin@gmail.com | Septic |  | 35.8394 | -118.6054 | Windy |  | Agricultural | Yes | 2022-01-12 | ROE Verified | Central Division | 2022-04-07T17:47:20Z | FALSE
65 | 326-110-013 | Full Program ROE (debris + trees) | Ready for Debris Removal |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-013 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 5841.9 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | NEGATIVE |  |  |  | 2022-04-02 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | Arch Monitoring Needed for Debris AND Trees |  | 2022-04-02 | No Activity/Nest Building Removed | [22 empty] | 2022-04-06 | [47 empty] | Frantz, Thomas & Aletha | 661-910-7734 | tom.frantz49@gmail.com | Septic Well |  | 35.8389 | -118.6055 | Windy |  | Agricultural | Yes | 2021-12-20 | ROE Verified | Central Division | 2022-04-07T17:47:20Z | FALSE
66 | 326-110-016 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 48512 | Redwood Circle |  | Posey | Tulare |  | Residential | [5 empty] | 5651.1 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | Yes |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-31 | Yes | 2022-03-31 | 2022-04-06 | POSITIVE |  |  | 3 | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Dodson, Phillip C & Jean | 661-665-9422 | pipestring2@gmail.com | Other |  | 35.8404 | -118.6059 | Windy |  | Agricultural | Yes | 2022-01-12 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE
67 | 220-080-006 | Full Program ROE (debris + trees) | Pending Asbestos Results | Haz Trees Present | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 41928 | Pine Way - 29 |  | Camp Nelson | Tulare |  | Residential | [5 empty] | 5852.93 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-04-04 | 2022-04-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-04 | Yes | 2022-04-05 | 2022-04-08 |  |  |  |  | 2022-04-01 | No Bio Monitoring Needed for Debris or Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed |  |  |  | Yes | [49 empty] | 2022-03-29 | Yes | 5 | [14 empty] | Michael Kilpatrick | 661-444-5544 | mikescessna@yahoo.com | Septic |  | 36.1457 | -118.5776 | Windy |  |  | Yes | 2021-12-10 | ROE Verified | Central Division | 2022-04-08T22:02:59Z | FALSE
68 | 220-090-001 | Full Program ROE (debris + trees) | Pending Asbestos Results |  | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 220-090-001 | No Address |  | Cedar Slope | Tulare |  | Residential | [5 empty] | 5638.22 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-04-05 | 2022-04-05 | FALSE | Yes |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-05 | Yes | 2022-04-06 | [5 empty] | 2022-04-01 | Bio Monitoring Needed for Debris AND Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [70 empty] | Bruce Smith, Gregory Smith, Gary Smith, Dale Smith | 559-690-0408 | pargrs@gmail.com |  |  | 36.1473 | -118.5837 | SQF |  |  | Yes | 2022-02-11 | ROE Verified | Central Division | 2022-04-07T03:02:22Z | FALSE
69 | 220-120-012 | Full Program ROE (debris + trees) | Pending Asbestos Results | No Hazard Trees | Next Step: N/A | Tulare 2020 | Needs Haz Tree Assessment | 52388 | Redwood Drive |  | Springville | Tulare |  | Residential | [5 empty] | 5552.17 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-04-05 | 2022-04-05 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-04 | Yes | 2022-04-05 | 2022-04-08 |  |  |  |  | 2022-04-01 | Bio Monitoring Needed for Debris AND Trees | 2022-04-01 | No Arch Monitoring Needed for Debris or Trees |  | 2022-04-01 | No Activity/Nest Building Removed | [53 empty] | 2022-04-01 | No | 0 | [14 empty] | Chris Shea | 805-901-6972 | chrisshea@charter.net |  |  | 36.1421 | -118.5782 | Windy |  |  | Yes | 2021-12-13 | ROE Verified | Central Division | 2022-04-09T00:00:55Z | FALSE
70 | 326-110-017 | Full Program ROE (debris + trees) | No Asbestos Detected |  | Next Step: N/A | Tulare 2021 | Needs Haz Tree Assessment | 326-110-017 | No Address |  | Posey | Tulare |  | Residential | [5 empty] | 5763.15 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | Yes |  | TRUE | 2022-03-31 | 2022-03-31 | FALSE | No |  |  | No |  | No | No | No | Yes | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-04-01 | Yes | 2022-04-04 | 2022-04-07 | NEGATIVE |  |  |  | 2022-03-31 | Bio Monitoring Needed for Debris AND Trees | 2022-04-02 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-31 | No Activity/Nest Building Removed | [70 empty] | Tietjen, Alex & Elisabeth | 559-909-2794 | atietjen@gmail.com | Septic Well |  | 35.84 | -118.6048 | Windy |  | Agricultural | Yes | 2022-01-05 | ROE Verified | Central Division | 2022-04-08T01:02:01Z | FALSE
71 | 062-285-200 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Kern Pending | Needs Haz Tree Assessment | 1589 | H Street | Lot 8 | Wofford Heights | Kern |  | Residential | [5 empty] | 3817.28 |  |  |  |  | FALSE | [8 empty] | No |  | TRUE | 2022-03-30 | 2022-03-30 | FALSE | No |  |  | No |  | No | Yes | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-30 | Yes | 2022-03-31 | 2022-04-06 | POSITIVE |  |  | 3 |  |  | 2022-04-06 | No Arch Monitoring Needed for Debris or Trees | [23 empty] | TRUE | 2022-04-08 | [48 empty] | Ralph and Marianne Owen | 4244777372 | rustydoughnut@gmail.com |  |  | 35.675 | -118.4957 | French Fire |  | Residential | No | 2022-03-04 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE
72 | 167-310-25-00 | Full Program ROE (debris + trees) | Tree Operations in Progress | Passed Tree Completion Check | Next Step: N/A | Mendocino Rescrapes | TFSW Complete (Soils) | 6190 | East Side Capella Road |  | Calpella | Mendocino |  | Residential | [5 empty] | 682.03 |  |  |  |  | TRUE | DTSC Attn |  | N/A | [5 empty] | No |  | TRUE | 2022-03-15 | 2022-03-15 | FALSE | No |  |  | No |  | No | No | No | No | No | No | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2022-03-15 | Yes | 2022-03-15 | 2022-03-18 | POSITIVE | 2022-03-23 | 2022-03-23 | 4 | 2022-03-15 | Bio Monitoring Needed for Debris AND Trees | 2022-03-15 | No Arch Monitoring Needed for Debris or Trees |  | 2022-03-24 | No Activity/Nest Building Removed | [20 empty] | TRUE | 2022-04-13 | 2022-03-23 |  |  | 3.23 NO PHONE NUMBER THIS IS A WARRANT LETTER. |  |  |  | 2022-03-24 |  | 2022-03-24 | 2022-03-24 |  |  | 2 | 2022-03-25 | 2022-04-04 | 7 | Re-scrape | [13 empty] | 2022-03-16 | Yes | 3 | 2022-03-24 |  | 2022-03-24 | 2022-03-24 |  | 2022-03-25 | 2022-03-25 |  |  |  | 2022-03-29 |  |  |  | Clifford Inong |  |  |  | Debris Crew Leader/Crew# Stephanie Fairlee / #602 Debris Crew WO# Refer to IAP 03/23 to 03/26 Crew 6012 | 39.2329 | -123.1999 | Hopkins Fire |  |  |  | 2022-03-15 | Abatement | Central Division | 2022-04-06T18:24:40Z | FALSE
73 | 053-332-110 | Full Program ROE (debris + trees) | Asbestos Abatement Needed |  | Next Step: N/A | Kern Pending | Needs Haz Tree Assessment | 227 | Tillie Creek Road |  | Wofford Heights | Kern |  | Residential | [5 empty] | 3755.73 |  |  |  |  | FALSE |  |  | N/A | [5 empty] | No |  | TRUE | 2022-04-04 | 2022-04-04 | FALSE | No |  |  | No |  | No | Yes | No | No | No | Yes | FALSE | TRUE | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | [7 empty] | 2022-03-30 | Yes | 2022-03-31 | 2022-04-06 | POSITIVE |  |  | 3 |  |  | 2022-04-06 | No Arch Monitoring Needed for Debris or Trees | [73 empty] | Tom Petrus | 3109729553 | tom@cobraracing.com |  |  | 35.719 | -118.4974 | French Fire |  | Residential | No | 2022-03-15 | ROE Verified | Central Division | 2022-04-08T07:16:06Z | FALSE
74 | 053-302-25 |  | ROE Received |  | Next Step: N/A |  |  | 2643 | Evans Road |  | Wofford Heights | Kern | [12 empty] | FALSE |  |  | N/A | [23 empty] | FALSE | [7 empty] | 0 | [92 empty] | STANFORD ROBERT J & THELMA LIV TR | [6 empty] | French Fire |  |  |  | 2022-04-08 | ROE Verified | Central Division | 2022-04-08T23:15:42Z | FALSE
75 | 062-285-26 |  | ROE Received |  | Next Step: N/A |  |  | 950 | Sawmill Road |  | Wofford Heights | Kern | [12 empty] | FALSE |  |  | N/A | [23 empty] | FALSE | [7 empty] | 0 | [92 empty] | BOWHAN MARJORIE R | [6 empty] | French Fire |  |  |  | 2022-04-08 | ROE Verified | Central Division | 2022-04-08T23:15:42Z | FALSE
76 | 053-450-21 |  | ROE Received |  | Next Step: N/A |  |  | 8301 | Old State Road |  | Alta Sierra | Kern | [12 empty] | FALSE |  |  | N/A | [23 empty] | FALSE | [7 empty] | 0 | [92 empty] | MONDS KENNETH R & JANET L | [6 empty] | French Fire |  |  |  | 2022-04-08 | ROE Verified | Central Division | 2022-04-08T23:23:30Z | FALSE
77 | 062-171-15 |  | ROE Received |  | Next Step: N/A |  |  | 6760 | Wagy Flat Road |  |  | Kern | [12 empty] | FALSE |  |  | N/A | [23 empty] | FALSE | [7 empty] | 0 | [92 empty] | HARRIS DAVID GUY | [6 empty] | French Fire |  |  |  | 2022-04-08 | ROE Verified | Central Division | 2022-04-08T23:29:04Z | FALSE